## 2026 vm lidar
2026 VM LiDAR
2026 VM LiDAR - Transmission
Name | Circuit ID | Scope ID | Region | Scope Day | Scope Year | Scope Date | KV | State Plane Projection | Scope Month | ACQPKG to QC Contract Date | ACQPKG QC Contract Date | PROCPKG to QC Contract Date | PROCPKG QC Contract Date | Targeted Flight Start | Targeted Flight End | SLA - Flight Start | SLA - Flight End | Contracting Status: | Contracting Delay Impact: | T/D | CWA - Total Mileage | CWA - HFRA Mileage | OH HFRA % | Scope Name | Acquisition CWA | Acquisition CWA Signature Date | Processing and Analysis CWA | Processing and Analysis CWA Signature Date | ACQ QC CWA | ACQ QC CWA Date | PROC QC CWA | PROC QC CWA Date | Exceptions to Processing and Analysis CWA | ACQ Delay | PROC Delay | ACQ Delay Responsibility | PROC Delay Responsibility | ACQ Delay Cause | PROC Delay Cause | ACQ Delay Cause Tags | ACQ Delay Notes and Description | PROC Delay Cause Tags | ACQ Delay Cause Confirmation | PROC Delay Cause Confirmation | ACQ Delay Impact (Calendar Days) | PROC Delay Impact (Calendar Days) | Stakeholder | Circuit Map Status | GCP Status | Line Loading Status | Line Load - Tasked | Line Load Due Date | Line Load Actual Date | Acquisition Package SLA Date - Data Acquisition Report, Ground Survey Report, Raw Weather, Calibrated LiDAR | Data Acquisition Status | Data Acquisition Actual Date | Acquisition Input Completion Date | Acquisition Package Completion Date | PROC Delay Notes and Description | Acquisition Package Deliverable ID | Ground Survey Package Deliverable ID | Ground Survey Package Status | Ground Survey Deliverable ID | Ground Survey Actual Date | Ground Survey Status | Ground Survey Report Deliverable ID | Ground Survey Report Actual Date | Ground Survey Report Status | Data Acquisition Deliverable ID | Acquisition Package Status | Data Acquisition Report Deliverable ID | Data Acquisition Report Actual Date | Data Acquisition Report Status | Raw Weather Report Deliverable ID | Raw Weather Data Status | Raw Weather Actual Date | Calibrated LiDAR Deliverable ID | Calibrated LiDAR Actual Date | Calibrated LiDAR Status | Calibrated LiDAR QC SLA Date | Calibrated LiDAR QC End Date | Calibrated LiDAR Reject Count | Processing Package Deliverable ID | Processing Package Status | ACQ Responsibility - Status | Weather Report Deliverable ID | Weather Report Actual Date | Processing Package SLA Date - Weather Report, Classified LiDAR, Vector Model, Vegetation Encroachment Report | Weather Report Status | Weather Report QC SLA Date | Weather Report QC End Date | Weather Report Reject Count | Vegetation Feature Classified LiDAR Deliverable ID | Vegetation Feature Classified LiDAR Actual Date | Vegetation Feature Classified LiDAR Status | Vegetation Feature Classified LiDAR QC SLA Date | Vegetation Feature Classified LiDAR QC End Date | Vegetation Feature Classified LiDAR Reject Count | Vegetation Vector Model Deliverable ID | Vegetation Vector Model Actual Date | Vegetation Vector Model Status | PROC Model Option | Vegetation Vector Model QC SLA Date | Vegetation Vector Model QC End Date | Vegetation Vector Model Reject Count | Vegetation P1 Report Deliverable ID | Vegetation P1 Report Actual Date | Vegetation P1 Status | Vegetation P1 SLA Date | Vegetation P1 QC SLA Date | Vegetation P1 Count Submitted | Vegetation P1 Report QC End Date | Vegetation P1 Report Reject Count | Vegetation P1 Count Validated | Vegetation Encroachment Report Deliverable ID | Vegetation Encroachment Report Actual Date | Vegetation Encroachment Report Status | Vegetation Encroachment Report QC SLA Date | Vegetation Encroachment Report QC End Date | Vegetation Encroachment Report Reject Count | Notes | OLD_Pilot Circuit | Canopy Sense Status | Revised Pilot Circuit List | Processing Evaluation Program Tracking | Acquisition Evaluation Program Tracking | Acquisition Deliverables Evaluation Program Tracking | GCP Folder Name | Engineering - GIS Processed | People | FERC/WECC | Time Flown | ACQ Platform Option | District | District Number | ACQ Mode | Laz Time Range | P1 Report Date | Encroachment Report Date | Weather Report Rejection Criteria | Calibrated LiDAR Rejection Criteria | Classified LiDAR Rejection Criteria | Potential P1 Rejection Criteria | Vegetation Encroachment Report Rejection Criteria | Vector Model Rejection Criteria | Calibrated LiDAR in GCP | ACQ QC Delay | PROC QC Delay | ACQ QC Delay Responsibility | PROC QC Delay Responsibility | ACQ QC Delay Cause | PROC QC Delay Cause | ACQ QC Delay Cause Tags | PROC QC Delay Cause Tags | ACQ QC Delay Notes and Description | PROC QC Delay Notes and Description | ACQ QC Delay Cause Confirmation | PROC QC Delay Cause Confirmation | ACQ QC Delay Impact (Calendar Days) | PROC QC Delay Impact (Calendar Days) | Calibrated LiDAR Missed Rejection Count | Weather Report Missed Rejection Count | Vegetation Feature Classified LiDAR Missed Rejection Count | Vegetation Vector Model Missed Rejection Count | Vegetation P1 Report Missed Rejection Count | Vegetation Encroachment Report Missed Rejection Count
PARDEE-SANTA CLARA | ET-00776 | 2026_ET-00776 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 39.7761 | 39.7761 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-28 | 01-04-2026 | 12-15-2025 |  | 2026_ET-00776_ACQPKG | 2026_ET-00776_GSPKG | Submitted | 2026_ET-00776_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00776_GCPR | 2025-12-08 | Historical | 2026_ET-00776_ACQ | QC Accepted | 2026_ET-00776_FR | 2025-12-01 | Submitted | 2026_ET-00776_RWR | Submitted | 2025-12-01 | 2026_ET-00776_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00776_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00776_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00776_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00776_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00776_RR | 2026-03-18 | No Violations | 02-13-2026 |  | 30 | 2026-03-27 | 0 | 0 | 2026_ET-00776_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PARDEE-SANTA CLARA_ET-00776 |  |  | Yes | 22:16 & 21:10 & 16:16 | Helicopter | VENTURA | 39 | HC | 2025-10-25 14:21 PDT ¦ 2025-10-29 10:38 PDT | 102825 | 20251029 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-RED BLUFF NO.1 | ET-00943 | 2026_ET-00943 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 31.5645 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-16 | 01-04-2026 | 12-15-2025 |  | 2026_ET-00943_ACQPKG | 2026_ET-00943_GSPKG | Submitted | 2026_ET-00943_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00943_GCPR | 2025-12-08 | Historical | 2026_ET-00943_ACQ | QC Accepted | 2026_ET-00943_FR | 2025-11-23 | Submitted | 2026_ET-00943_RWR | Submitted | 2025-11-20 | 2026_ET-00943_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00943_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00943_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00943_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00943_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00943_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00943_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLORADO RIVER-RED BLUFF NO.1_ET-00943 |  |  | Yes | 15:52 | Helicopter | BLYTHE | 87 | HC | 2025-10-16 09:41 PDT ¦ 2025-10-16 10:34 PDT | 101625 | 20251016 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
COLORADO RIVER-RED BLUFF NO.2 | ET-00959 | 2026_ET-00959 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 31.5502 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-16 | 01-04-2026 | 12-15-2025 |  | 2026_ET-00959_ACQPKG | 2026_ET-00959_GSPKG | Submitted | 2026_ET-00959_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00959_GCPR | 2025-12-08 | Historical | 2026_ET-00959_ACQ | QC Accepted | 2026_ET-00959_FR | 2025-11-23 | Submitted | 2026_ET-00959_RWR | Submitted | 2025-11-20 | 2026_ET-00959_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00959_PROCPKG | In Progress | All Good - Complete | 2026_ET-00959_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00959_VMLAZ | 2026-02-01 | QC Accepted |  | 2026-02-12 | 0 | 2026_ET-00959_VMM1 | 2026-02-01 | QC Accepted |  |  | 2026-02-12 | 0 | 2026_ET-00959_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00959_VER | 2026-04-17 | QC Rejected |  | 2026-05-01 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLORADO RIVER-RED BLUFF NO.2_ET-00959 |  |  | Yes | 15:52 | Helicopter | BLYTHE | 87 | HC | 2025-10-16 09:41 PDT ¦ 2025-10-16 10:34 PDT | 101625 | 20251016 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELLIS-JOHANNA | ET-00972 | 2026_ET-00972 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.3461 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-11-05 | 01-04-2026 | 12-15-2025 |  | 2026_ET-00972_ACQPKG | 2026_ET-00972_GSPKG | Submitted | 2026_ET-00972_GS | 2025-11-08 | Field Complete | 2026_ET-00972_GCPR | 2025-11-23 | Submitted | 2026_ET-00972_ACQ | QC Accepted | 2026_ET-00972_FR | 2025-11-23 | Submitted | 2026_ET-00972_RWR | Submitted | 2025-11-23 | 2026_ET-00972_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00972_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00972_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00972_VMLAZ | 2026-02-01 | QC Accepted | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00972_VMM1 | 2026-02-01 | QC Accepted |  | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00972_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00972_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-JOHANNA_ET-00972 |  |  | Yes | 18:32 & 14:08 | Helicopter | SANTA ANA | 29 | HC | 2025-11-04 10:53 PST ¦ 2025-11-05 06:54 PST | 110525 | 20251105 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELLIS-SANTIAGO | ET-00974 | 2026_ET-00974 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 14.682 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-11-05 | 01-04-2026 | 12-15-2025 |  | 2026_ET-00974_ACQPKG | 2026_ET-00974_GSPKG | Submitted | 2026_ET-00974_GS | 2025-11-08 | Field Complete | 2026_ET-00974_GCPR | 2025-11-23 | Submitted | 2026_ET-00974_ACQ | QC Accepted | 2026_ET-00974_FR | 2025-11-23 | Submitted | 2026_ET-00974_RWR | Submitted | 2025-11-23 | 2026_ET-00974_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00974_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00974_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-00974_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-00974_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-00974_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-00974_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-SANTIAGO_ET-00974 |  |  | Yes | 18:32 & 14:08 | Helicopter | SADDLEBACK | 43 | HC | 2025-10-17 09:34 PDT ¦ 2025-11-05 07:11 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELLIS-HUNTINGTON BEACH NO.3 | ET-01074 | 2026_ET-01074 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.1892 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-11-04 | 01-04-2026 | 12-11-2025 |  | 2026_ET-01074_ACQPKG | 2026_ET-01074_GSPKG | Submitted | 2026_ET-01074_GS | 2025-11-08 | Field Complete | 2026_ET-01074_GCPR | 2025-11-23 | Submitted | 2026_ET-01074_ACQ | QC Accepted | 2026_ET-01074_FR | 2025-11-23 | Submitted | 2026_ET-01074_RWR | Submitted | 2025-11-23 | 2026_ET-01074_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01074_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01074_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01074_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01074_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01074_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01074_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-HUNTINGTON BEACH NO.3_ET-01074 |  |  | Yes | 18:23 | Helicopter | HUNTINGTON BEACH | 33 | HC | 2025-11-04 10:58 PST ¦ 2025-11-04 11:08 PST | 110425 | 20251104 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ARCOGEN-HINSON NO. 1 | ET-01433 | 2026_ET-01433 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.4868 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-18 | 01-04-2026 | 12-08-2025 |  | 2026_ET-01433_ACQPKG | 2026_ET-01433_GSPKG | Submitted | 2026_ET-01433_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01433_GCPR | 2025-12-08 | Historical | 2026_ET-01433_ACQ | QC Accepted | 2026_ET-01433_FR | 2025-12-01 | Submitted | 2026_ET-01433_RWR | Submitted | 2025-12-01 | 2026_ET-01433_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-08 | 0 | 2026_ET-01433_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01433_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01433_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01433_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01433_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01433_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ARCOGEN-HINSON NO. 1_ET-01433 | Done |  | Yes | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 11:07 PDT ¦ 2025-11-05 08:23 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ARCOGEN-HINSON NO. 2 | ET-01434 | 2026_ET-01434 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.4822 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-18 | 01-04-2026 | 12-08-2025 |  | 2026_ET-01434_ACQPKG | 2026_ET-01434_GSPKG | Submitted | 2026_ET-01434_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01434_GCPR | 2025-12-08 | Historical | 2026_ET-01434_ACQ | QC Accepted | 2026_ET-01434_FR | 2025-12-01 | Submitted | 2026_ET-01434_RWR | Submitted | 2025-12-01 | 2026_ET-01434_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-08 | 0 | 2026_ET-01434_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01434_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01434_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01434_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01434_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01434_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ARCOGEN-HINSON NO. 2_ET-01434 | Done |  | Yes | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 11:07 PDT ¦ 2025-11-05 08:23 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
EL NIDO-EL SEGUNDO | ET-01618 | 2026_ET-01618 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.908 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2026-01-13 | 01-04-2026 | 12-09-2025 |  | 2026_ET-01618_ACQPKG | 2026_ET-01618_GSPKG | Submitted | 2026_ET-01618_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01618_GCPR | 2025-12-08 | Historical | 2026_ET-01618_ACQ | QC Accepted | 2026_ET-01618_FR | 2025-12-01 | Submitted | 2026_ET-01618_RWR | Submitted | 2025-12-01 | 2026_ET-01618_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-09 | 0 | 2026_ET-01618_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01618_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01618_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01618_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01618_RR | 2026-03-18 | Violations QC Confirmed | 02-12-2026 | 03-19-2026 | 1 | 2026-03-19 | 0 | 1 | 2026_ET-01618_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-EL SEGUNDO_ET-01618 |  |  | Yes | 11:58 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:51 PDT ¦ 2025-11-05 12:16 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
PARDEE-VINCENT NO. 1 | ET-01925 | 2026_ET-01925 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 31.7833 | 31.7833 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-25 | 01-04-2026 | 12-12-2025 |  | 2026_ET-01925_ACQPKG | 2026_ET-01925_GSPKG | Submitted | 2026_ET-01925_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01925_GCPR | 2025-12-08 | Historical | 2026_ET-01925_ACQ | QC Accepted | 2026_ET-01925_FR | 2025-12-01 | Submitted | 2026_ET-01925_RWR | Submitted | 2025-12-01 | 2026_ET-01925_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-01925_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01925_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01925_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01925_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01925_RR | 2026-03-18 | Violations QC Confirmed | 02-12-2026 | 03-19-2026 | 2 | 2026-03-19 | 0 | 2 | 2026_ET-01925_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PARDEE-VINCENT NO. 1_ET-01925 |  |  | Yes | 18:56 - 22:16 | Helicopter | VALENCIA | 59 | HC | 2025-10-25 12:47 PDT ¦ 2025-10-25 15:59 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELLIS-HUNTINGTON BEACH NO.1 | ET-02994 | 2026_ET-02994 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.1879 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-11-04 | 01-04-2026 | 12-12-2025 |  | 2026_ET-02994_ACQPKG | 2026_ET-02994_GSPKG | Submitted | 2026_ET-02994_GS | 2025-11-08 | Field Complete | 2026_ET-02994_GCPR | 2025-11-23 | Submitted | 2026_ET-02994_ACQ | QC Accepted | 2026_ET-02994_FR | 2025-11-23 | Submitted | 2026_ET-02994_RWR | Submitted | 2025-11-23 | 2026_ET-02994_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-02994_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02994_WR | 2026-02-01 | 02-03-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02994_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02994_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02994_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02994_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-HUNTINGTON BEACH NO.1_ET-02994 |  |  | Yes | 18:23 | Helicopter | HUNTINGTON BEACH | 33 | HC | 2025-11-04 10:53 PST ¦ 2025-11-04 11:11 PST | 110425 | 20251104 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
SANTA CLARA-VINCENT | ET-00770 | 2026_ET-00770 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 69.8888 | 69.8888 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-28 | 01-05-2026 | 12-15-2025 |  | 2026_ET-00770_ACQPKG | 2026_ET-00770_GSPKG | Submitted | 2026_ET-00770_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00770_GCPR | 2025-12-08 | Historical | 2026_ET-00770_ACQ | QC Accepted | 2026_ET-00770_FR | 2025-12-01 | Submitted | 2026_ET-00770_RWR | Submitted | 2025-12-01 | 2026_ET-00770_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00770_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00770_WR | 2026-02-01 | 02-04-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00770_VMLAZ | 2026-02-01 | QC Accepted | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00770_VMM1 | 2026-02-01 | QC Accepted |  | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00770_RR | 2026-03-18 | No Violations | 02-13-2026 |  | 11 | 2026-03-27 | 0 | 0 | 2026_ET-00770_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-20 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-VINCENT_ET-00770 |  |  | Yes | 18:56 & 21:10 & 16:16 | Helicopter | VALENCIA | 59 | HC | 2025-10-25 12:50 PDT ¦ 2025-10-29 10:38 PDT | 102825 | 20251029 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
DEL AMO-LAGUNA BELL | ET-01062 | 2026_ET-01062 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 18.9911 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-18 | 01-05-2026 | 12-11-2025 |  | 2026_ET-01062_ACQPKG | 2026_ET-01062_GSPKG | Submitted | 2026_ET-01062_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01062_GCPR | 2025-12-08 | Historical | 2026_ET-01062_ACQ | QC Accepted | 2026_ET-01062_FR | 2025-12-01 | Submitted | 2026_ET-01062_RWR | Submitted | 2025-12-01 | 2026_ET-01062_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01062_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01062_WR | 2026-02-01 | 02-04-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01062_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01062_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01062_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01062_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-LAGUNA BELL_ET-01062 |  |  | Yes | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 09:57 PDT ¦ 2025-11-05 10:32 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
COACHELLA VALLEY-MIRAGE | ET-01483 | 2026_ET-01483 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.83564 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-15 | 01-05-2026 | 12-11-2025 |  | 2026_ET-01483_ACQPKG | 2026_ET-01483_GSPKG | Submitted | 2026_ET-01483_GS | 2025-11-08 | Field Complete | 2026_ET-01483_GCPR | 2025-11-20 | Submitted | 2026_ET-01483_ACQ | QC Accepted | 2026_ET-01483_FR | 2025-11-23 | Submitted | 2026_ET-01483_RWR | Submitted | 2025-11-20 | 2026_ET-01483_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01483_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01483_WR | 2026-02-01 | 02-04-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01483_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01483_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01483_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01483_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COACHELLA VALLEY-MIRAGE_ET-01483 |  |  | Yes | 20:25 | Helicopter |  |  | HC | 2025-10-15 16:12 PDT ¦ 2025-10-15 16:16 PDT | 101525 | 20251015 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CENTIPEDE-COLORADO RIVER | ET-01947 | 2026_ET-01947 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.098209 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-16 | 01-05-2026 | 12-09-2025 |  | 2026_ET-01947_ACQPKG | 2026_ET-01947_GSPKG | Submitted | 2026_ET-01947_GS | 2025-11-08 | Field Complete | 2026_ET-01947_GCPR | 2025-11-20 | Submitted | 2026_ET-01947_ACQ | QC Accepted | 2026_ET-01947_FR | 2025-11-23 | Submitted | 2026_ET-01947_RWR | Submitted | 2025-11-20 | 2026_ET-01947_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-09 | 0 | 2026_ET-01947_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01947_WR | 2026-02-01 | 02-04-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01947_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01947_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01947_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01947_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTIPEDE-COLORADO RIVER_ET-01947 |  |  | Yes | 15:52 | Helicopter | BLYTHE | 87 | HC | 2025-10-16 09:42 PDT ¦ 2025-10-16 09:53 PDT | 101625 | 20251016 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
EL CASCO-SAN BERNARDINO | ET-00515 | 2026_ET-00515 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 13.7518 | 11.2173 | 82 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-22 | 01-07-2026 | 12-15-2025 |  | 2026_ET-00515_ACQPKG | 2026_ET-00515_GSPKG | Submitted | 2026_ET-00515_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00515_GCPR | 2025-12-08 | Historical | 2026_ET-00515_ACQ | QC Accepted | 2026_ET-00515_FR | 2025-11-23 | Submitted | 2026_ET-00515_RWR | Submitted | 2025-11-23 | 2026_ET-00515_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00515_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00515_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00515_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-00515_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00515_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00515_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL CASCO-SAN BERNARDINO_ET-00515 |  |  | Yes | 19:43 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 09:38 PDT ¦ 2025-10-22 13:31 PDT | 102225 | 20251022 |  |  |  |  | Attribute - Survey Date |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-NAROD NO.2 | ET-00736 | 2026_ET-00736 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.5036 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-15-2025 |  | 2026_ET-00736_ACQPKG | 2026_ET-00736_GSPKG | Submitted | 2026_ET-00736_GS | 2025-11-08 | Field Complete | 2026_ET-00736_GCPR | 2025-11-29 | Submitted | 2026_ET-00736_ACQ | QC Accepted | 2026_ET-00736_FR | 2025-11-29 | Submitted | 2026_ET-00736_RWR | Submitted | 2025-11-29 | 2026_ET-00736_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00736_PROCPKG | In Progress | All Good - Complete | 2026_ET-00736_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00736_VMLAZ | 2026-02-01 | QC Accepted |  | 2026-02-12 | 0 | 2026_ET-00736_VMM1 | 2026-02-01 | QC Accepted |  |  | 2026-02-12 | 0 | 2026_ET-00736_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00736_VER | 2026-04-29 | QC Rejected |  | 2026-05-13 | 5 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-NAROD NO.2_ET-00736 |  |  | No | 18:59 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:53 PDT ¦ 2025-10-25 13:42 PDT | 101725 | 20251025 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-LA FRESA | ET-01038 | 2026_ET-01038 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 14.0755 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-11-05 | 01-07-2026 | 12-09-2025 |  | 2026_ET-01038_ACQPKG | 2026_ET-01038_GSPKG | Submitted | 2026_ET-01038_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01038_GCPR | 2025-12-08 | Historical | 2026_ET-01038_ACQ | QC Accepted | 2026_ET-01038_FR | 2025-12-01 | Submitted | 2026_ET-01038_RWR | Submitted | 2025-12-01 | 2026_ET-01038_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-09 | 0 | 2026_ET-01038_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01038_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01038_VMLAZ | 2026-03-05 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01038_VMM1 | 2026-03-20 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01038_RR | 2026-03-20 | Violations QC Confirmed | 02-12-2026 | 03-21-2026 | 0 | 2026-03-19 | 23 | 37 | 2026_ET-01038_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HINSON-LA FRESA_ET-01038 |  |  | Yes | 14:08 - 18:01 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 10:54 PDT ¦ 2025-11-05 12:23 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
HINSON-LIGHTHIPE | ET-01050 | 2026_ET-01050 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.3441 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-18 | 01-07-2026 | 12-08-2025 |  | 2026_ET-01050_ACQPKG | 2026_ET-01050_GSPKG | Submitted | 2026_ET-01050_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01050_GCPR | 2025-12-08 | Historical | 2026_ET-01050_ACQ | QC Accepted | 2026_ET-01050_FR | 2025-12-01 | Submitted | 2026_ET-01050_RWR | Submitted | 2025-12-01 | 2026_ET-01050_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-08 | 0 | 2026_ET-01050_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01050_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01050_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01050_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 1 | 2026_ET-01050_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01050_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HINSON-LIGHTHIPE_ET-01050 |  |  | Yes | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 10:53 PDT ¦ 2025-11-05 10:30 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CHINO-NAROD NO.1 | ET-01057 | 2026_ET-01057 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.3958 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-09-2025 |  | 2026_ET-01057_ACQPKG | 2026_ET-01057_GSPKG | Submitted | 2026_ET-01057_GS | 2025-11-08 | Field Complete | 2026_ET-01057_GCPR | 2025-11-29 | Submitted | 2026_ET-01057_ACQ | QC Accepted | 2026_ET-01057_FR | 2025-11-29 | Submitted | 2026_ET-01057_RWR | Submitted | 2025-11-29 | 2026_ET-01057_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-09 | 0 | 2026_ET-01057_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01057_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01057_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01057_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01057_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01057_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-NAROD NO.1_ET-01057 |  |  | No | 18:59 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:54 PDT ¦ 2025-10-25 13:43 PDT | 101725 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CHINO-GANESHA-PEYTON NO. 2 | ET-01159 | 2026_ET-01159 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.3815 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01159_ACQPKG | 2026_ET-01159_GSPKG | Submitted | 2026_ET-01159_GS | 2025-11-08 | Field Complete | 2026_ET-01159_GCPR | 2025-11-29 | Submitted | 2026_ET-01159_ACQ | QC Accepted | 2026_ET-01159_FR | 2025-11-29 | Submitted | 2026_ET-01159_RWR | Submitted | 2025-11-29 | 2026_ET-01159_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01159_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01159_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01159_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01159_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01159_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01159_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-GANESHA-PEYTON NO. 2_ET-01159 |  |  | No | 15:48 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:47 PDT ¦ 2025-10-23 10:29 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CHINO-BROCKWAY-GLASS-FRANCIS | ET-01228 | 2026_ET-01228 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.82248 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01228_ACQPKG | 2026_ET-01228_GSPKG | Submitted | 2026_ET-01228_GS | 2025-11-08 | Field Complete | 2026_ET-01228_GCPR | 2025-11-28 | Submitted | 2026_ET-01228_ACQ | QC Accepted | 2026_ET-01228_FR | 2025-11-28 | Submitted | 2026_ET-01228_RWR | Submitted | 2025-11-28 | 2026_ET-01228_CLAZ | 2025-11-28 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01228_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01228_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01228_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01228_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01228_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01228_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-BROCKWAY-GLASS-FRANCIS_ET-01228 |  |  | No | 15:48 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 11:06 PDT ¦ 2025-10-17 11:10 PDT | 101725 | 20251017 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CORONA-FIREHOUSE | ET-01425 | 2026_ET-01425 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.69897 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-21 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01425_ACQPKG | 2026_ET-01425_GSPKG | Submitted | 2026_ET-01425_GS | 2025-11-08 | Field Complete | 2026_ET-01425_GCPR | 2025-11-29 | Submitted | 2026_ET-01425_ACQ | QC Accepted | 2026_ET-01425_FR | 2025-11-29 | Submitted | 2026_ET-01425_RWR | Submitted | 2025-11-29 | 2026_ET-01425_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01425_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01425_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01425_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01425_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01425_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01425_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CORONA-FIREHOUSE_ET-01425 |  |  | No | 15:48 | Helicopter | ONTARIO | 34 | HC | 2025-10-21 09:01 PDT ¦ 2025-10-23 10:49 PDT | 102125 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE BRYAN-MODENA-TUSTIN | ET-01441 | 2026_ET-01441 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.584 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown |  | 01-07-2026 | 12-15-2025 |  | 2026_ET-01441_ACQPKG | 2026_ET-01441_GSPKG | Submitted | 2026_ET-01441_GS | 2025-11-08 | Field Complete | 2026_ET-01441_GCPR | 2025-11-23 | Submitted | 2026_ET-01441_ACQ | QC Accepted | 2026_ET-01441_FR | 2025-11-23 | Submitted | 2026_ET-01441_RWR | Submitted | 2025-11-23 | 2026_ET-01441_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-01441_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01441_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01441_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01441_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01441_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01441_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE BRYAN-MODENA-TUSTIN_ET-01441 |  |  | No | 15:48 | Helicopter | SANTA ANA | 29 | HC | 2025-10-17 10:09 PDT ¦ 2025-11-05 07:23 PST | 101725 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CHINO-FRANCIS | ET-01693 | 2026_ET-01693 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 5.3584 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01693_ACQPKG | 2026_ET-01693_GSPKG | Submitted | 2026_ET-01693_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01693_GCPR | 2025-12-08 | Historical | 2026_ET-01693_ACQ | QC Accepted | 2026_ET-01693_FR | 2025-11-29 | Submitted | 2026_ET-01693_RWR | Submitted | 2025-11-29 | 2026_ET-01693_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01693_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01693_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01693_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01693_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 2 | 2026_ET-01693_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01693_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-FRANCIS_ET-01693 |  |  | No | 15:48 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:53 PDT ¦ 2025-10-25 13:42 PDT | 101725 | 20251025 | [5 empty] | Missing subject conductors. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE ELLIS-OCEANVIEW | ET-01733 | 2026_ET-01733 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.61213 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-24 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01733_ACQPKG | 2026_ET-01733_GSPKG | Submitted | 2026_ET-01733_GS | 2025-11-08 | Field Complete | 2026_ET-01733_GCPR | 2025-11-23 | Submitted | 2026_ET-01733_ACQ | QC Accepted | 2026_ET-01733_FR | 2025-11-23 | Submitted | 2026_ET-01733_RWR | Submitted | 2025-11-23 | 2026_ET-01733_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01733_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01733_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01733_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01733_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01733_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01733_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ELLIS-OCEANVIEW_ET-01733 |  |  | No | 19:56 | Helicopter | HUNTINGTON BEACH | 33 | HC | 2025-10-24 14:09 PDT ¦ 2025-11-03 15:57 PST | 102425 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CHINO-FIREHOUSE NO. 1 | ET-01767 | 2026_ET-01767 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.1324 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01767_ACQPKG | 2026_ET-01767_GSPKG | Submitted | 2026_ET-01767_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01767_GCPR | 2025-12-08 | Historical | 2026_ET-01767_ACQ | QC Accepted | 2026_ET-01767_FR | 2025-11-29 | Submitted | 2026_ET-01767_RWR | Submitted | 2025-11-29 | 2026_ET-01767_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01767_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01767_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01767_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01767_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01767_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01767_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-FIREHOUSE NO. 1_ET-01767 |  |  | No | 18:59 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:54 PDT ¦ 2025-10-25 13:43 PDT | 101725 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CHINO-FIREHOUSE NO. 2 | ET-01771 | 2026_ET-01771 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.1731 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-17 | 01-07-2026 | 12-11-2025 |  | 2026_ET-01771_ACQPKG | 2026_ET-01771_GSPKG | Submitted | 2026_ET-01771_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01771_GCPR | 2025-12-08 | Historical | 2026_ET-01771_ACQ | QC Accepted | 2026_ET-01771_FR | 2025-11-29 | Submitted | 2026_ET-01771_RWR | Submitted | 2025-11-29 | 2026_ET-01771_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01771_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01771_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01771_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01771_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01771_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01771_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-FIREHOUSE NO. 2_ET-01771 |  |  | No | 18:59 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:53 PDT ¦ 2025-10-25 13:44 PDT | 101725 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CHINO-LIGHTHIPE | ET-01938 | 2026_ET-01938 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.54579 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-26 | 01-07-2026 | 12-15-2025 |  | 2026_ET-01938_ACQPKG | 2026_ET-01938_GSPKG | Submitted | 2026_ET-01938_GS | 2025-11-08 | Field Complete | 2026_ET-01938_GCPR | 2025-11-29 | Submitted | 2026_ET-01938_ACQ | QC Accepted | 2026_ET-01938_FR | 2025-11-29 | Submitted | 2026_ET-01938_RWR | Submitted | 2025-11-29 | 2026_ET-01938_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-01938_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01938_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01938_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01938_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01938_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01938_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-LIGHTHIPE_ET-01938 |  |  | No | 20:14 | Helicopter | WHITTIER | 47 | HC | 2025-10-26 14:26 PDT ¦ 2025-10-26 14:28 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CENTER-DEL AMO | ET-02023 | 2026_ET-02023 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.13077 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-18 | 01-07-2026 | 12-12-2025 |  | 2026_ET-02023_ACQPKG | 2026_ET-02023_GSPKG | Submitted | 2026_ET-02023_GS | 2025-11-08 | Field Complete | 2026_ET-02023_GCPR | 2025-12-01 | Submitted | 2026_ET-02023_ACQ | QC Accepted | 2026_ET-02023_FR | 2025-12-01 | Submitted | 2026_ET-02023_RWR | Submitted | 2025-12-01 | 2026_ET-02023_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-02023_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02023_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02023_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02023_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02023_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02023_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CENTER-DEL AMO_ET-02023 |  |  | No | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 10:38 PDT ¦ 2025-10-18 10:43 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE LIGHTHIPE-IMPERIAL B | ET-02082 | 2026_ET-02082 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.55731 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-18 | 01-07-2026 | 12-31-2025 |  | 2026_ET-02082_ACQPKG | 2026_ET-02082_GSPKG | Submitted | 2026_ET-02082_GS | 2025-11-08 | Field Complete | 2026_ET-02082_GCPR | 2025-12-01 | Submitted | 2026_ET-02082_ACQ | QC Accepted | 2026_ET-02082_FR | 2025-12-01 | Submitted | 2026_ET-02082_RWR | Submitted | 2025-12-01 | 2026_ET-02082_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-31 | 0 | 2026_ET-02082_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02082_WR | 2026-03-17 | 02-06-2026 | QC Accepted | 03-31-2026 | 2026-03-20 | 0 | 2026_ET-02082_VMLAZ | 2026-02-02 | QC Accepted | 05-15-2026 | 2026-02-20 | 0 | 2026_ET-02082_VMM1 | 2026-02-03 | QC Accepted |  | 05-15-2026 | 2026-02-20 | 0 | 2026_ET-02082_RR | 2026-02-03 | No Violations | 02-21-2026 |  | 0 |  |  |  | 2026_ET-02082_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LIGHTHIPE-IMPERIAL B_ET-02082 |  |  | No | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 10:17 PDT ¦ 2025-10-18 10:18 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE LAGUNA BELL-GOODRICH-WEST | ET-02086 | 2026_ET-02086 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.38844 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-26 | 01-07-2026 | 12-31-2025 |  | 2026_ET-02086_ACQPKG | 2026_ET-02086_GSPKG | Submitted | 2026_ET-02086_GS | 2025-11-08 | Field Complete | 2026_ET-02086_GCPR | 2025-12-01 | Submitted | 2026_ET-02086_ACQ | QC Accepted | 2026_ET-02086_FR | 2025-12-01 | Submitted | 2026_ET-02086_RWR | Submitted | 2025-12-01 | 2026_ET-02086_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-31 | 0 | 2026_ET-02086_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02086_WR | 2026-03-17 | 02-06-2026 | QC Accepted | 03-31-2026 | 2026-03-20 | 0 | 2026_ET-02086_VMLAZ | 2026-02-02 | QC Accepted | 05-15-2026 | 2026-02-20 | 0 | 2026_ET-02086_VMM1 | 2026-02-03 | QC Accepted |  | 05-15-2026 | 2026-02-20 | 0 | 2026_ET-02086_RR | 2026-02-03 | No Violations | 02-21-2026 |  | 0 |  |  |  | 2026_ET-02086_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LAGUNA BELL-GOODRICH-WEST_ET-02086 |  |  | No | 20:14 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 09:09 PDT ¦ 2025-10-26 13:44 PDT | 101825 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE GOLETA-GAVIOTA | ET-02492 | 2026_ET-02492 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.92908 | 0.92908 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-28 | 01-07-2026 | 12-12-2025 |  | 2026_ET-02492_ACQPKG | 2026_ET-02492_GSPKG | Submitted | 2026_ET-02492_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02492_GCPR | 2025-12-08 | Historical | 2026_ET-02492_ACQ | QC Accepted | 2026_ET-02492_FR | 2025-11-29 | Submitted | 2026_ET-02492_RWR | Submitted | 2025-11-29 | 2026_ET-02492_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-02492_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02492_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02492_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02492_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02492_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02492_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE GOLETA-GAVIOTA_ET-02492 |  |  | No | 20:04 | Helicopter | SANTA BARBARA | 49 | HC | 2025-10-28 14:13 PDT ¦ 2025-10-28 14:49 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LIGHTHIPE-MESA | ET-04540 | 2026_ET-04540 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 12.2438 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-18 | 01-07-2026 | 12-12-2025 |  | 2026_ET-04540_ACQPKG | 2026_ET-04540_GSPKG | Submitted | 2026_ET-04540_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04540_GCPR | 2025-12-08 | Historical | 2026_ET-04540_ACQ | QC Accepted | 2026_ET-04540_FR | 2025-12-01 | Submitted | 2026_ET-04540_RWR | Submitted | 2025-12-01 | 2026_ET-04540_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-04540_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04540_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-04540_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-04540_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-04540_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-04540_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-MESA_ET-04540 |  |  | Yes | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 08:58 PDT ¦ 2025-11-05 10:31 PST | 102625 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE SANTA BARBARA-SAN MARCOS-VEGAS | ET-06969 | 2026_ET-06969 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.0514 | 2.0514 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-28 | 01-07-2026 | 12-12-2025 |  | 2026_ET-06969_ACQPKG | 2026_ET-06969_GSPKG | Submitted | 2026_ET-06969_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06969_GCPR | 2025-12-08 | Historical | 2026_ET-06969_ACQ | QC Accepted | 2026_ET-06969_FR | 2025-11-29 | Submitted | 2026_ET-06969_RWR | Submitted | 2025-11-29 | 2026_ET-06969_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-06969_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06969_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-06969_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-06969_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-06969_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 |  |  |  | 2026_ET-06969_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE SANTA BARBARA-SAN MARCOS-VEGAS_ET-06969 |  |  | No | 20:04 | Helicopter | SANTA BARBARA | 49 | HC | 2025-10-28 13:50 PDT ¦ 2025-10-28 15:02 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE SANTA CLARA-P.S. 11 | ET-07052 | 2026_ET-07052 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 25.0153 | 24.8561 | 99 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-27 | 01-07-2026 | 12-12-2025 |  | 2026_ET-07052_ACQPKG | 2026_ET-07052_GSPKG | Submitted | 2026_ET-07052_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07052_GCPR | 2025-12-08 | Historical | 2026_ET-07052_ACQ | QC Accepted | 2026_ET-07052_FR | 2025-12-01 | Submitted | 2026_ET-07052_RWR | Submitted | 2025-12-01 | 2026_ET-07052_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-07052_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-07052_WR | 2026-02-01 | 02-06-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-07052_VMLAZ | 2026-02-01 | QC Accepted | 03-12-2026 | 2026-02-11 | 0 | 2026_ET-07052_VMM1 | 2026-02-01 | QC Accepted |  | 03-12-2026 | 2026-02-11 | 0 | 2026_ET-07052_RR | 2026-03-18 | Violations QC Confirmed | 02-12-2026 | 03-19-2026 | 25 | 2026-03-19 | 10 | 15 | 2026_ET-07052_VER | 2026-02-26 | Uploaded to S123 | 03-12-2026 | 2026-03-12 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE SANTA CLARA-P.S. 11_ET-07052 |  |  | No | 21:10 | Helicopter | VENTURA | 39 | HC | 2025-10-27 15:03 PDT ¦ 2025-10-29 10:31 PDT | 102725 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CIMA-ELDORADO-PISGAH NO.1 | ET-00096 | 2026_ET-00096 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 109.1388 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-18 | 12-11-2025 | Flown | 2025-10-29 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00096_ACQPKG | 2026_ET-00096_GSPKG | Submitted | 2026_ET-00096_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00096_GCPR | 2025-12-08 | Historical | 2026_ET-00096_ACQ | QC Accepted | 2026_ET-00096_FR | 2025-11-18 | Submitted | 2026_ET-00096_RWR | Submitted | 2025-11-18 | 2026_ET-00096_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00096_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00096_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00096_VMLAZ | 2026-02-05 | QC Accepted | 03-15-2026 | 2026-02-19 | 0 | 2026_ET-00096_VMM1 | 2026-02-05 | QC Accepted |  | 03-15-2026 | 2026-02-17 | 0 | 2026_ET-00096_RR | 2026-03-18 | No Violations | 02-18-2026 |  | 39 | 2026-02-18 | 0 | 5 | 2026_ET-00096_VER | 2026-03-01 | Uploaded to S123 | 03-15-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CIMA-ELDORADO-PISGAH NO.1_ET-00096 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-10-29 09:37 PDT ¦ 2025-10-30 11:40 PDT | 103025 | 20251030 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VINCENT NO.2 | ET-00104 | 2026_ET-00104 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 46.9291 | 18.5664 | 40 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-28 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00104_ACQPKG | 2026_ET-00104_GSPKG | Submitted | 2026_ET-00104_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00104_GCPR | 2025-12-08 | Historical | 2026_ET-00104_ACQ | QC Accepted | 2026_ET-00104_FR | 2025-11-18 | Submitted | 2026_ET-00104_RWR | Submitted | 2025-11-18 | 2026_ET-00104_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00104_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00104_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00104_VMLAZ | 2026-02-05 | QC Accepted | 05-01-2026 | 2026-02-19 | 0 | 2026_ET-00104_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00104_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00104_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VINCENT NO.2_ET-00104 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-19 12:34 PDT ¦ 2025-10-28 11:23 PDT | 102825 | 20251028 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-LUGO | ET-00106 | 2026_ET-00106 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 176.8957 | 18.3811 | 10 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-28 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00106_ACQPKG | 2026_ET-00106_GSPKG | Submitted | 2026_ET-00106_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00106_GCPR | 2025-12-08 | Historical | 2026_ET-00106_ACQ | QC Accepted | 2026_ET-00106_FR | 2025-11-18 | Submitted | 2026_ET-00106_RWR | Submitted | 2025-11-18 | 2026_ET-00106_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00106_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00106_WR | 2026-03-24 | 02-07-2026 | QC Accepted | 04-07-2026 | 2026-04-15 | 2 | 2026_ET-00106_VMLAZ | 2026-03-16 | QC Accepted | 05-01-2026 | 2026-03-19 | 0 | 2026_ET-00106_VMM1 | 2026-03-09 | QC Accepted |  | 05-01-2026 | 2026-03-19 | 0 | 2026_ET-00106_RR | 2026-03-10 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00106_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-LUGO_ET-00106 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-10-28 11:15 PDT ¦ 2025-10-30 11:40 PDT | 103025 | 20251030 | Attribute - Air Temp | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A | [7 empty] | 1
LUGO-VINCENT NO.1 | ET-00112 | 2026_ET-00112 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 46.8972 | 18.7737 | 40 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-28 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00112_ACQPKG | 2026_ET-00112_GSPKG | Submitted | 2026_ET-00112_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00112_GCPR | 2025-12-08 | Historical | 2026_ET-00112_ACQ | QC Accepted | 2026_ET-00112_FR | 2025-11-18 | Submitted | 2026_ET-00112_RWR | Submitted | 2025-11-18 | 2026_ET-00112_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00112_PROCPKG | In Progress | All Good - Complete | 2026_ET-00112_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00112_VMLAZ | 2026-02-05 | QC Accepted |  | 2026-02-19 | 0 | 2026_ET-00112_VMM1 | 2026-02-05 | QC Rejected |  |  | 2026-02-18 | 1 | 2026_ET-00112_RR | 2026-02-05 | No Violations |  |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00112_VER | 2026-05-07 | QC Rejected |  | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VINCENT NO.1_ET-00112 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-19 12:34 PDT ¦ 2025-10-28 11:21 PDT | 102825 | 20251028 |  |  |  |  | Analysis Error - False Negative Vegetation Point | Subject conductors strung incorrectly. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MIDWAY-VINCENT NO.1 | ET-00126 | 2026_ET-00126 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 112.4913 | 64.5994 | 57 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-18 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00126_ACQPKG | 2026_ET-00126_GSPKG | Submitted | 2026_ET-00126_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00126_GCPR | 2025-12-08 | Historical | 2026_ET-00126_ACQ | QC Accepted | 2026_ET-00126_FR | 2025-11-18 | Submitted | 2026_ET-00126_RWR | Submitted | 2025-11-18 | 2026_ET-00126_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00126_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00126_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00126_VMLAZ | 2026-02-05 | QC Accepted | 05-21-2026 | 2026-02-19 | 0 | 2026_ET-00126_VMM1 | 2026-02-05 | QC Accepted |  | 05-21-2026 | 2026-02-17 | 0 | 2026_ET-00126_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00126_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIDWAY-VINCENT NO.1_ET-00126 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-18 13:53 PDT ¦ 2025-10-19 14:07 PDT | 101925 | 20251019 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELDORADO-IVANPAH | ET-00185 | 2026_ET-00185 |  | 11 | 2026 | Mar 11, 2026 | 220 | NV_E | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 34.3862 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-30 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00185_ACQPKG | 2026_ET-00185_GSPKG | Submitted | 2026_ET-00185_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00185_GCPR | 2025-12-08 | Historical | 2026_ET-00185_ACQ | QC Accepted | 2026_ET-00185_FR | 2025-11-18 | Submitted | 2026_ET-00185_RWR | Submitted | 2025-11-18 | 2026_ET-00185_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00185_PROCPKG | In Progress | All Good - Complete | 2026_ET-00185_WR | 2026-02-06 | 02-07-2026 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00185_VMLAZ | 2026-03-02 | QC Accepted |  | 2026-03-12 | 1 | 2026_ET-00185_VMM1 | 2026-02-06 | QC Accepted |  |  | 2026-02-17 | 0 | 2026_ET-00185_RR | 2026-02-06 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00185_VER | 2026-04-17 | QC Rejected |  | 2026-05-01 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-IVANPAH_ET-00185 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-10-29 11:45 PDT ¦ 2025-10-30 15:22 PDT | 103025 | 20251030 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
PRIMM-SILVER STATE | ET-00186 | 2026_ET-00186 |  | 11 | 2026 | Mar 11, 2026 | 220 | NV_E | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.071887 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-30 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00186_ACQPKG | 2026_ET-00186_GSPKG | Submitted | 2026_ET-00186_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00186_GCPR | 2025-12-08 | Historical | 2026_ET-00186_ACQ | QC Accepted | 2026_ET-00186_FR | 2025-11-18 | Submitted | 2026_ET-00186_RWR | Submitted | 2025-11-18 | 2026_ET-00186_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00186_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00186_WR | 2026-02-06 | 02-07-2026 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00186_VMLAZ | 2026-02-06 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00186_VMM1 | 2026-02-06 | QC Accepted |  | 02-20-2026 | 2026-02-17 | 0 | 2026_ET-00186_RR | 2026-02-06 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00186_VER | 2026-02-06 | Uploaded to S123 | 02-20-2026 | 2026-02-18 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PRIMM-SILVER STATE_ET-00186 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-30 15:05 PDT ¦ 2025-10-30 15:09 PDT | 103025 | 20251030 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-PRIMM | ET-00187 | 2026_ET-00187 |  | 11 | 2026 | Mar 11, 2026 | 220 | NV_E | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 24.9124 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-30 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00187_ACQPKG | 2026_ET-00187_GSPKG | Submitted | 2026_ET-00187_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00187_GCPR | 2025-12-08 | Historical | 2026_ET-00187_ACQ | QC Accepted | 2026_ET-00187_FR | 2025-11-18 | Submitted | 2026_ET-00187_RWR | Submitted | 2025-11-18 | 2026_ET-00187_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00187_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00187_WR | 2026-02-06 | 02-07-2026 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00187_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-00187_VMM1 | 2026-02-06 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00187_RR | 2026-02-06 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00187_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-PRIMM_ET-00187 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-30 15:09 PDT | 103025 | 20251030 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IVANPAH-PRIMM | ET-00188 | 2026_ET-00188 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 9.6389 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-30 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00188_ACQPKG | 2026_ET-00188_GSPKG | Submitted | 2026_ET-00188_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00188_GCPR | 2025-12-08 | Historical | 2026_ET-00188_ACQ | QC Accepted | 2026_ET-00188_FR | 2025-11-18 | Submitted | 2026_ET-00188_RWR | Submitted | 2025-11-18 | 2026_ET-00188_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00188_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00188_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00188_VMLAZ | 2026-02-05 | QC Accepted | 04-29-2026 | 2026-02-19 | 0 | 2026_ET-00188_VMM1 | 2026-02-05 | QC Accepted |  | 04-29-2026 | 2026-02-18 | 0 | 2026_ET-00188_RR | 2026-02-05 | No Violations | 02-19-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00188_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IVANPAH-PRIMM_ET-00188 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-10-30 15:05 PDT ¦ 2025-10-30 15:22 PDT | 103025 | 20251030 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-REDONDO NO.1 | ET-00216 | 2026_ET-00216 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.5112 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Does Not exist | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-18 | 01-08-2026 | 12-15-2025 |  | 2026_ET-00216_ACQPKG | 2026_ET-00216_GSPKG | Submitted | 2026_ET-00216_GS | 2025-11-08 | Field Complete | 2026_ET-00216_GCPR | 2025-12-01 | Submitted | 2026_ET-00216_ACQ | QC Accepted | 2026_ET-00216_FR | 2025-12-01 | Submitted | 2026_ET-00216_RWR | Submitted | 2025-12-01 | 2026_ET-00216_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00216_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00216_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00216_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00216_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00216_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00216_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-REDONDO NO.1_ET-00216 |  |  | No | 19:28 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:17 PDT ¦ 2025-11-05 11:08 PST | 101825 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-REDONDO NO.2 | ET-00217 | 2026_ET-00217 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.5149 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Does Not exist | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-18 | 01-08-2026 | 12-15-2025 |  | 2026_ET-00217_ACQPKG | 2026_ET-00217_GSPKG | Submitted | 2026_ET-00217_GS | 2025-11-08 | Field Complete | 2026_ET-00217_GCPR | 2025-12-01 | Submitted | 2026_ET-00217_ACQ | QC Accepted | 2026_ET-00217_FR | 2025-12-01 | Submitted | 2026_ET-00217_RWR | Submitted | 2025-12-01 | 2026_ET-00217_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00217_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00217_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00217_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00217_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00217_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00217_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-REDONDO NO.2_ET-00217 |  |  | No | 19:28 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:17 PDT ¦ 2025-11-05 11:08 PST | 101825 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-BEVERLY | ET-00368 | 2026_ET-00368 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 16.0938 | 4.9933 | 31 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-24 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00368_ACQPKG | 2026_ET-00368_GSPKG | Submitted | 2026_ET-00368_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00368_GCPR | 2025-12-08 | Historical | 2026_ET-00368_ACQ | QC Accepted | 2026_ET-00368_FR | 2025-11-13 | Submitted | 2026_ET-00368_RWR | Submitted | 2025-11-13 | 2026_ET-00368_CLAZ | 2025-11-13 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00368_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00368_WR | 2026-02-04 | 02-07-2026 | QC Accepted | 02-18-2026 | 2026-02-13 | 0 | 2026_ET-00368_VMLAZ | 2026-02-02 | QC Accepted | 05-21-2026 | 2026-03-04 | 1 | 2026_ET-00368_VMM1 | 2026-02-04 | QC Accepted |  | 05-21-2026 | 2026-02-13 | 0 | 2026_ET-00368_RR | 2026-03-18 | No Violations | 02-14-2026 |  | 4 | 2026-03-27 | 0 | 0 | 2026_ET-00368_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EAGLE ROCK-BEVERLY_ET-00368 |  |  | No |  | Helicopter | SANTA MONICA | 42 | HC | 2025-10-23 11:00 PDT ¦ 2025-10-24 12:47 PDT | 102425 | 20251024 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MAGUNDEN-OMAR | ET-00491 | 2026_ET-00491 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 9.398 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-13 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00491_ACQPKG | 2026_ET-00491_GSPKG | Submitted | 2026_ET-00491_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00491_GCPR | 2025-12-08 | Historical | 2026_ET-00491_ACQ | QC Accepted | 2026_ET-00491_FR | 2025-11-13 | Submitted | 2026_ET-00491_RWR | Submitted | 2025-11-13 | 2026_ET-00491_CLAZ | 2025-11-13 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00491_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00491_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00491_VMLAZ | 2026-02-05 | QC Accepted | 05-21-2026 | 2026-02-19 | 0 | 2026_ET-00491_VMM1 | 2026-02-05 | QC Accepted |  | 05-21-2026 | 2026-02-17 | 0 | 2026_ET-00491_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00491_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MAGUNDEN-OMAR_ET-00491 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-13 12:29 PDT ¦ 2025-10-13 12:42 PDT | 101325 | 20251013 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
BIG CREEK 2-BIG CREEK 8 | ET-00545 | 2026_ET-00545 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_3 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.7197 | 1.7197 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-17 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00545_ACQPKG | 2026_ET-00545_GSPKG | Submitted | 2026_ET-00545_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00545_GCPR | 2025-12-08 | Historical | 2026_ET-00545_ACQ | QC Accepted | 2026_ET-00545_FR | 2025-11-13 | Submitted | 2026_ET-00545_RWR | Submitted | 2025-11-13 | 2026_ET-00545_CLAZ | 2025-11-13 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00545_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00545_WR | 2026-02-03 | 02-07-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00545_VMLAZ | 2026-03-16 | QC Accepted | 05-01-2026 | 2026-03-23 | 2 | 2026_ET-00545_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-00545_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00545_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BIG CREEK 2-BIG CREEK 8_ET-00545 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-10-17 12:02 PDT ¦ 2025-10-17 12:24 PDT | 101725 | 20251017 |  |  |  |  | Attribute - Clearance, Attribute - Height POI |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 3-BIG CREEK 4 | ET-00577 | 2026_ET-00577 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_3 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 5.6344 | 5.3872 | 96 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-17 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00577_ACQPKG | 2026_ET-00577_GSPKG | Submitted | 2026_ET-00577_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00577_GCPR | 2025-12-08 | Historical | 2026_ET-00577_ACQ | QC Accepted | 2026_ET-00577_FR | 2025-11-13 | Submitted | 2026_ET-00577_RWR | Submitted | 2025-11-13 | 2026_ET-00577_CLAZ | 2025-11-13 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00577_PROCPKG | In Progress | All Good - Complete | 2026_ET-00577_WR | 2026-02-03 | 02-07-2026 | QC Accepted | 02-17-2026 | 2026-04-01 | 1 | 2026_ET-00577_VMLAZ | 2026-03-16 | QC Accepted |  | 2026-03-24 | 2 | 2026_ET-00577_VMM1 | 2026-02-03 | QC Accepted |  |  | 2026-02-13 | 0 | 2026_ET-00577_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00577_VER | 2026-05-07 | QC Rejected |  | 2026-05-21 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BIG CREEK 3-BIG CREEK 4_ET-00577 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-10-17 11:40 PDT ¦ 2025-10-17 12:37 PDT | 101725 | 20251017 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 3-BIG CREEK 8 | ET-00609 | 2026_ET-00609 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_3 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.1026 | 7.1026 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-17 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00609_ACQPKG | 2026_ET-00609_GSPKG | Submitted | 2026_ET-00609_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00609_GCPR | 2025-12-08 | Historical | 2026_ET-00609_ACQ | QC Accepted | 2026_ET-00609_FR | 2025-11-13 | Submitted | 2026_ET-00609_RWR | Submitted | 2025-11-13 | 2026_ET-00609_CLAZ | 2025-11-13 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00609_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00609_WR | 2026-02-03 | 02-07-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00609_VMLAZ | 2026-03-16 | QC Accepted | 05-21-2026 | 2026-03-24 | 2 | 2026_ET-00609_VMM1 | 2026-02-03 | QC Accepted |  | 05-21-2026 | 2026-02-13 | 0 | 2026_ET-00609_RR | 2026-03-18 | No Violations | 02-14-2026 |  | 2 | 2026-03-23 | 0 | 0 | 2026_ET-00609_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BIG CREEK 3-BIG CREEK 8_ET-00609 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-10-17 11:51 PDT ¦ 2025-10-17 12:31 PDT | 101725 | 20251017 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOODRICH-MESA | ET-00637 | 2026_ET-00637 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.8534 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-23 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00637_ACQPKG | 2026_ET-00637_GSPKG | Submitted | 2026_ET-00637_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00637_GCPR | 2025-12-08 | Historical | 2026_ET-00637_ACQ | QC Accepted | 2026_ET-00637_FR | 2025-11-18 | Submitted | 2026_ET-00637_RWR | Submitted | 2025-11-18 | 2026_ET-00637_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00637_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00637_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00637_VMLAZ | 2026-02-05 | QC Accepted | 05-01-2026 | 2026-02-19 | 0 | 2026_ET-00637_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00637_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00637_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOODRICH-MESA_ET-00637 |  |  | Yes |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-21 11:17 PDT ¦ 2025-10-23 10:38 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BAILEY-PASTORIA | ET-00655 | 2026_ET-00655 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 12.4432 | 7.9296 | 64 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-20 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00655_ACQPKG | 2026_ET-00655_GSPKG | Submitted | 2026_ET-00655_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00655_GCPR | 2025-12-08 | Historical | 2026_ET-00655_ACQ | QC Accepted | 2026_ET-00655_FR | 2025-11-18 | Submitted | 2026_ET-00655_RWR | Submitted | 2025-11-18 | 2026_ET-00655_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00655_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00655_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00655_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-00655_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00655_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00655_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BAILEY-PASTORIA_ET-00655 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-19 09:15 PDT ¦ 2025-10-19 13:54 PDT | 101925 | 20251019 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
BAILEY-PARDEE | ET-00665 | 2026_ET-00665 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 26.8285 | 26.8285 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-20 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00665_ACQPKG | 2026_ET-00665_GSPKG | Submitted | 2026_ET-00665_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00665_GCPR | 2025-12-08 | Historical | 2026_ET-00665_ACQ | QC Accepted | 2026_ET-00665_FR | 2025-11-18 | Submitted | 2026_ET-00665_RWR | Submitted | 2025-11-18 | 2026_ET-00665_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00665_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00665_WR | 2026-02-05 | 02-07-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00665_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-00665_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00665_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00665_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BAILEY-PARDEE_ET-00665 | Done |  | Yes |  | Helicopter | VALENCIA | 59 | HC | 2025-10-19 09:36 PDT ¦ 2025-10-20 12:51 PDT | 102025 | 20251020 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
PARDEE-PASTORIA | ET-00667 | 2026_ET-00667 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 38.7405 | 34.2396 | 88 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-20 | 01-08-2026 | 01-08-2026 |  | 2026_ET-00667_ACQPKG | 2026_ET-00667_GSPKG | Submitted | 2026_ET-00667_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00667_GCPR | 2025-12-08 | Historical | 2026_ET-00667_ACQ | QC Accepted | 2026_ET-00667_FR | 2025-11-18 | Submitted | 2026_ET-00667_RWR | Submitted | 2025-11-18 | 2026_ET-00667_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00667_PROCPKG | In Progress | All Good - Complete | 2026_ET-00667_WR | 2026-02-04 | 02-07-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00667_VMLAZ | 2026-03-05 | QC Accepted |  | 2026-02-12 | 0 | 2026_ET-00667_VMM1 | 2026-02-04 | QC Rejected |  |  | 2026-02-18 | 1 | 2026_ET-00667_RR | 2026-02-04 | No Violations |  |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00667_VER | 2026-02-04 | QC Rejected |  | 2026-05-12 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PARDEE-PASTORIA_ET-00667 |  |  | Yes |  | Helicopter | VALENCIA | 59 | HC | 2025-10-19 09:15 PDT ¦ 2025-10-20 12:51 PDT | 102025 | 20251020 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-SANTIAGO | ET-00973 | 2026_ET-00973 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.3171 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-11-05 | 01-08-2026 | 12-11-2025 |  | 2026_ET-00973_ACQPKG | 2026_ET-00973_GSPKG | Submitted | 2026_ET-00973_GS | 2025-11-08 | Field Complete | 2026_ET-00973_GCPR | 2025-11-23 | Submitted | 2026_ET-00973_ACQ | QC Accepted | 2026_ET-00973_FR | 2025-11-23 | Submitted | 2026_ET-00973_RWR | Submitted | 2025-11-23 | 2026_ET-00973_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-00973_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00973_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-00973_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-00973_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-00973_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-00973_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | JOHANNA-SANTIAGO_ET-00973 |  |  | Yes | 15:48 & 14:08 | Helicopter | SADDLEBACK | 43 | HC | 2025-10-17 09:35 PDT ¦ 2025-11-05 07:11 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MOUNTAINVIEW-SAN BERNARDINO NO.3 | ET-01013 | 2026_ET-01013 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.23243 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-22 | 01-08-2026 | 12-11-2025 |  | 2026_ET-01013_ACQPKG | 2026_ET-01013_GSPKG | Submitted | 2026_ET-01013_GS | 2025-11-08 | Field Complete | 2026_ET-01013_GCPR | 2025-12-01 | Submitted | 2026_ET-01013_ACQ | QC Accepted | 2026_ET-01013_FR | 2025-12-01 | Submitted | 2026_ET-01013_RWR | Submitted | 2025-12-01 | 2026_ET-01013_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01013_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01013_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01013_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01013_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01013_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01013_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MOUNTAINVIEW-SAN BERNARDINO NO.3_ET-01013 |  |  | Yes | 16:04 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 09:42 PDT ¦ 2025-10-22 09:48 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MOUNTAINVIEW-SAN BERNARDINO NO.4 | ET-01018 | 2026_ET-01018 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.24603 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-22 | 01-08-2026 | 12-08-2025 |  | 2026_ET-01018_ACQPKG | 2026_ET-01018_GSPKG | Submitted | 2026_ET-01018_GS | 2025-11-08 | Field Complete | 2026_ET-01018_GCPR | 2025-12-01 | Submitted | 2026_ET-01018_ACQ | QC Accepted | 2026_ET-01018_FR | 2025-12-01 | Submitted | 2026_ET-01018_RWR | Submitted | 2025-12-01 | 2026_ET-01018_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-08 | 0 | 2026_ET-01018_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01018_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01018_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01018_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01018_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01018_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MOUNTAINVIEW-SAN BERNARDINO NO.4_ET-01018 |  |  | Yes | 16:04 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 09:41 PDT ¦ 2025-10-22 09:48 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
OLINDA-CAROLINA | ET-01450 | 2026_ET-01450 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 5.9917 | 0.79725 | 13 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-25 | 01-08-2026 | 12-11-2025 |  | 2026_ET-01450_ACQPKG | 2026_ET-01450_GSPKG | Submitted | 2026_ET-01450_GS | 2025-11-08 | Field Complete | 2026_ET-01450_GCPR | 2025-11-23 | Submitted | 2026_ET-01450_ACQ | QC Accepted | 2026_ET-01450_FR | 2025-11-23 | Submitted | 2026_ET-01450_RWR | Submitted | 2025-11-23 | 2026_ET-01450_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01450_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01450_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01450_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01450_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01450_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01450_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-CAROLINA_ET-01450 |  |  | No | 20:08 | Helicopter | FULLERTON | 48 | HC | 2025-10-25 14:41 PDT ¦ 2025-10-25 15:25 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
OLINDA-LA HABRA NO. 1 | ET-01605 | 2026_ET-01605 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.2338 | 0.79762 | 36 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-25 | 01-08-2026 | 12-11-2025 |  | 2026_ET-01605_ACQPKG | 2026_ET-01605_GSPKG | Submitted | 2026_ET-01605_GS | 2025-11-08 | Field Complete | 2026_ET-01605_GCPR | 2025-11-23 | Submitted | 2026_ET-01605_ACQ | QC Accepted | 2026_ET-01605_FR | 2025-11-23 | Submitted | 2026_ET-01605_RWR | Submitted | 2025-11-23 | 2026_ET-01605_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01605_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01605_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01605_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01605_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01605_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01605_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-LA HABRA NO. 1_ET-01605 |  |  | No | 20:08 | Helicopter | FULLERTON | 48 | HC | 2025-10-25 14:48 PDT ¦ 2025-10-25 15:10 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
OLINDA-LA HABRA NO. 2 | ET-01608 | 2026_ET-01608 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.3276 | 0.097542 | 4 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-25 | 01-08-2026 | 12-11-2025 |  | 2026_ET-01608_ACQPKG | 2026_ET-01608_GSPKG | Submitted | 2026_ET-01608_GS | 2025-11-08 | Field Complete | 2026_ET-01608_GCPR | 2025-11-23 | Submitted | 2026_ET-01608_ACQ | QC Accepted | 2026_ET-01608_FR | 2025-11-23 | Submitted | 2026_ET-01608_RWR | Submitted | 2025-11-23 | 2026_ET-01608_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01608_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01608_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01608_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01608_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01608_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01608_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-LA HABRA NO. 2_ET-01608 |  |  | No | 20:08 | Helicopter | FULLERTON | 48 | HC | 2025-10-25 14:48 PDT ¦ 2025-10-25 15:07 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
OBERON-RED BLUFF | ET-02091 | 2026_ET-02091 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.16452 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-16 | 01-08-2026 | 12-12-2025 |  | 2026_ET-02091_ACQPKG | 2026_ET-02091_GSPKG | Submitted | 2026_ET-02091_GS | 2025-11-08 | Field Complete | 2026_ET-02091_GCPR | 2025-11-20 | Submitted | 2026_ET-02091_ACQ | QC Accepted | 2026_ET-02091_FR | 2025-11-23 | Submitted | 2026_ET-02091_RWR | Submitted | 2025-11-20 | 2026_ET-02091_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-02091_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02091_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02091_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02091_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02091_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02091_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OBERON-RED BLUFF_ET-02091 |  |  | Yes | 15:52 | Helicopter | BLYTHE | 87 | HC | 2025-10-16 10:26 PDT ¦ 2025-10-16 10:35 PDT | 101625 | 20251016 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LA FRESA-VICTORIA NO. 1 | ET-04308 | 2026_ET-04308 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.125 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-18 | 01-08-2026 | 12-12-2025 |  | 2026_ET-04308_ACQPKG | 2026_ET-04308_GSPKG | Submitted | 2026_ET-04308_GS | 2025-11-08 | Field Complete | 2026_ET-04308_GCPR | 2025-12-01 | Submitted | 2026_ET-04308_ACQ | QC Accepted | 2026_ET-04308_FR | 2025-12-01 | Submitted | 2026_ET-04308_RWR | Submitted | 2025-12-01 | 2026_ET-04308_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-04308_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04308_WR | 2026-02-01 | 02-07-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-04308_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-04308_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-04308_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-04308_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-VICTORIA NO. 1_ET-04308 |  |  | No | 15:38 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:22 PDT ¦ 2025-11-05 12:18 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
BRYAN-IRVINE-LAS LOMAS | ET-00101 | 2026_ET-00101 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.4101 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-17 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00101_ACQPKG | 2026_ET-00101_GSPKG | Submitted | 2026_ET-00101_GS | 2025-11-08 | Field Complete | 2026_ET-00101_GCPR | 2025-11-23 | Submitted | 2026_ET-00101_ACQ | QC Accepted | 2026_ET-00101_FR | 2025-11-23 | Submitted | 2026_ET-00101_RWR | Submitted | 2025-11-23 | 2026_ET-00101_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00101_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00101_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00101_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00101_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00101_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00101_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BRYAN-IRVINE-LAS LOMAS_ET-00101 | Done |  | No | 15:48 | Helicopter | SANTA ANA | 29 | HC | 2025-10-17 09:05 PDT ¦ 2025-11-05 07:16 PST | 101725 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-PICO | ET-00583 | 2026_ET-00583 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.73 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-18 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00583_ACQPKG | 2026_ET-00583_GSPKG | Submitted | 2026_ET-00583_GS | 2025-11-08 | Field Complete | 2026_ET-00583_GCPR | 2025-12-01 | Submitted | 2026_ET-00583_ACQ | QC Accepted | 2026_ET-00583_FR | 2025-12-01 | Submitted | 2026_ET-00583_RWR | Submitted | 2025-12-01 | 2026_ET-00583_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00583_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00583_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00583_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00583_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00583_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00583_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HINSON-PICO_ET-00583 |  |  | No | 15:38 - 19:28 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 11:07 PDT ¦ 2025-11-05 08:23 PST | 102425 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARDIFF-DEL ROSA | ET-00722 | 2026_ET-00722 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.1643 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-22 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00722_ACQPKG | 2026_ET-00722_GSPKG | Submitted | 2026_ET-00722_GS | 2025-11-08 | Field Complete | 2026_ET-00722_GCPR | 2025-11-29 | Submitted | 2026_ET-00722_ACQ | QC Accepted | 2026_ET-00722_FR | 2025-11-29 | Submitted | 2026_ET-00722_RWR | Submitted | 2025-11-29 | 2026_ET-00722_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00722_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00722_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00722_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00722_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00722_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00722_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CARDIFF-DEL ROSA_ET-00722 | Done |  | No | 19:43 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 14:10 PDT ¦ 2025-10-22 14:18 PDT | 102225 | 20251022 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARMENITA-MURPHY-PIONEER-TELEGRAPH | ET-00765 | 2026_ET-00765 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 11.3258 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-26 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00765_ACQPKG | 2026_ET-00765_GSPKG | Submitted | 2026_ET-00765_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00765_GCPR | 2025-12-08 | Historical | 2026_ET-00765_ACQ | QC Accepted | 2026_ET-00765_FR | 2025-11-29 | Submitted | 2026_ET-00765_RWR | Submitted | 2025-11-29 | 2026_ET-00765_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00765_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00765_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00765_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00765_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00765_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00765_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CARMENITA-MURPHY-PIONEER-TELEGRAPH_ET-00765 | Done |  | No | 20:14 | Helicopter | WHITTIER | 47 | HC | 2025-10-25 15:14 PDT ¦ 2025-10-26 14:50 PDT | 102625 | 20251026 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN BERNARDINO-VISTA | ET-00785 | 2026_ET-00785 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.1418 | 5.5215 | 68 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-21 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00785_ACQPKG | 2026_ET-00785_GSPKG | Submitted | 2026_ET-00785_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00785_GCPR | 2025-12-08 | Historical | 2026_ET-00785_ACQ | QC Accepted | 2026_ET-00785_FR | 2025-12-08 | Submitted | 2026_ET-00785_RWR | Submitted | 2025-12-08 | 2026_ET-00785_CLAZ | 2025-12-08 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00785_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00785_WR | 2026-03-16 | 02-08-2026 | QC Accepted | 03-30-2026 | 2026-04-15 | 1 | 2026_ET-00785_VMLAZ | 2026-03-16 | QC Accepted | 05-01-2026 | 2026-03-23 | 0 | 2026_ET-00785_VMM1 | 2026-03-16 | QC Accepted |  | 05-01-2026 | 2026-04-02 |  | 2026_ET-00785_RR | 2026-03-10 | No Violations | 04-03-2026 |  | 0 |  |  |  | 2026_ET-00785_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SAN BERNARDINO-VISTA_ET-00785 |  |  | Yes | 16:04 | Helicopter | REDLANDS | 31 | HC | 2025-10-20 09:42 PDT ¦ 2025-11-21 13:44 PST | 102225 | 20251121 | Attribute - Air Temp |  |  |  | Attribute - Survey Date |  | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
HINSON-LOS CERRITOS | ET-00809 | 2026_ET-00809 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.5013 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-18 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00809_ACQPKG | 2026_ET-00809_GSPKG | Submitted | 2026_ET-00809_GS | 2025-11-08 | Field Complete | 2026_ET-00809_GCPR | 2025-12-01 | Submitted | 2026_ET-00809_ACQ | QC Accepted | 2026_ET-00809_FR | 2025-12-01 | Submitted | 2026_ET-00809_RWR | Submitted | 2025-12-01 | 2026_ET-00809_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00809_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00809_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00809_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00809_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00809_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00809_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HINSON-LOS CERRITOS_ET-00809 |  |  | No | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 11:07 PDT ¦ 2025-11-05 08:23 PST | 101825 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-LA MIRADA | ET-00817 | 2026_ET-00817 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.5557 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-03 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00817_ACQPKG | 2026_ET-00817_GSPKG | Submitted | 2026_ET-00817_GS | 2025-11-08 | Field Complete | 2026_ET-00817_GCPR | 2025-11-23 | Submitted | 2026_ET-00817_ACQ | QC Accepted | 2026_ET-00817_FR | 2025-11-23 | Submitted | 2026_ET-00817_RWR | Submitted | 2025-11-23 | 2026_ET-00817_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00817_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00817_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00817_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00817_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00817_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00817_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-LA MIRADA_ET-00817 |  |  | No | 20:14 & 22:41 | Helicopter | FULLERTON | 48 | HC | 2025-10-26 14:22 PDT ¦ 2025-11-03 15:35 PST | 110325 | 20251103 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-GALLATIN | ET-00848 | 2026_ET-00848 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.5544 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-26 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00848_ACQPKG | 2026_ET-00848_GSPKG | Submitted | 2026_ET-00848_GS | 2025-11-08 | Field Complete | 2026_ET-00848_GCPR | 2025-12-01 | Submitted | 2026_ET-00848_ACQ | QC Accepted | 2026_ET-00848_FR | 2025-12-01 | Submitted | 2026_ET-00848_RWR | Submitted | 2025-12-01 | 2026_ET-00848_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00848_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00848_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00848_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00848_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00848_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00848_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-GALLATIN_ET-00848 |  |  | No | 20:14 | Helicopter | WHITTIER | 47 | HC | 2025-10-18 10:22 PDT ¦ 2025-10-26 15:09 PDT | 102625 | 20251026 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-DOWNEYMED-STEWART | ET-00924 | 2026_ET-00924 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.217 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-18 | 01-09-2026 | 12-15-2025 |  | 2026_ET-00924_ACQPKG | 2026_ET-00924_GSPKG | Submitted | 2026_ET-00924_GS | 2025-11-08 | Field Complete | 2026_ET-00924_GCPR | 2025-12-01 | Submitted | 2026_ET-00924_ACQ | QC Accepted | 2026_ET-00924_FR | 2025-12-01 | Submitted | 2026_ET-00924_RWR | Submitted | 2025-12-01 | 2026_ET-00924_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00924_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00924_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00924_VMLAZ | 2026-02-01 | QC Accepted | 05-13-2026 | 2026-02-12 | 0 | 2026_ET-00924_VMM1 | 2026-02-01 | QC Accepted |  | 05-13-2026 | 2026-02-12 | 0 | 2026_ET-00924_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00924_VER | 2026-04-29 | Uploaded to S123 | 05-13-2026 | 2026-05-13 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-DOWNEYMED-STEWART_ET-00924 |  |  | No |  | Helicopter | WHITTIER | 47 | HC | 2025-10-18 10:12 PDT ¦ 2025-10-26 14:06 PDT | 101825 | 20251026 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BRYAN-MODENA | ET-01349 | 2026_ET-01349 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.9423 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-05 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01349_ACQPKG | 2026_ET-01349_GSPKG | Submitted | 2026_ET-01349_GS | 2025-11-08 | Field Complete | 2026_ET-01349_GCPR | 2025-11-23 | Submitted | 2026_ET-01349_ACQ | QC Accepted | 2026_ET-01349_FR | 2025-11-23 | Submitted | 2026_ET-01349_RWR | Submitted | 2025-11-23 | 2026_ET-01349_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01349_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01349_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01349_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01349_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01349_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01349_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BRYAN-MODENA_ET-01349 | Done |  | No | 15:48 & 14:08 | Helicopter | SANTA ANA | 29 | HC | 2025-10-17 10:03 PDT ¦ 2025-11-05 07:24 PST | 101725 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
EL NIDO-FELTON | ET-01366 | 2026_ET-01366 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.2034 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-18 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01366_ACQPKG | 2026_ET-01366_GSPKG | Submitted | 2026_ET-01366_GS | 2025-11-08 | Field Complete | 2026_ET-01366_GCPR | 2025-12-01 | Submitted | 2026_ET-01366_ACQ | QC Accepted | 2026_ET-01366_FR | 2025-12-01 | Submitted | 2026_ET-01366_RWR | Submitted | 2025-12-01 | 2026_ET-01366_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01366_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01366_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01366_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01366_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01366_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01366_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-FELTON_ET-01366 |  |  | No | 19:28 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:48 PDT ¦ 2025-11-05 12:16 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
COLTON-HUB | ET-01438 | 2026_ET-01438 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.035907 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-03 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01438_ACQPKG | 2026_ET-01438_GSPKG | Submitted | 2026_ET-01438_GS | 2025-11-08 | Field Complete | 2026_ET-01438_GCPR | 2025-11-29 | Submitted | 2026_ET-01438_ACQ | QC Accepted | 2026_ET-01438_FR | 2025-11-29 | Submitted | 2026_ET-01438_RWR | Submitted | 2025-11-29 | 2026_ET-01438_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01438_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01438_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01438_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01438_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01438_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01438_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLTON-HUB_ET-01438 |  |  | No | 18:02 | Helicopter |  |  | HC | 2025-11-06 10:17 PST ¦ 2025-11-06 10:19 PST | 110625 | 20251106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
COLTON-CENTURY | ET-01439 | 2026_ET-01439 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.017101 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-03 | 01-09-2026 | 12-15-2025 |  | 2026_ET-01439_ACQPKG | 2026_ET-01439_GSPKG | Submitted | 2026_ET-01439_GS | 2025-11-08 | Field Complete | 2026_ET-01439_GCPR | 2025-11-29 | Submitted | 2026_ET-01439_ACQ | QC Accepted | 2026_ET-01439_FR | 2025-11-29 | Submitted | 2026_ET-01439_RWR | Submitted | 2025-11-29 | 2026_ET-01439_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-01439_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01439_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01439_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01439_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01439_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01439_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLTON-CENTURY_ET-01439 |  |  | No | 18:02 | Helicopter |  |  | HC | 2025-11-06 10:17 PST ¦ 2025-11-06 10:19 PST | 110625 | 20251106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
DEL AMO-SOMERSET | ET-01445 | 2026_ET-01445 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.0509 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-18 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01445_ACQPKG | 2026_ET-01445_GSPKG | Submitted | 2026_ET-01445_GS | 2025-11-08 | Field Complete | 2026_ET-01445_GCPR | 2025-12-01 | Submitted | 2026_ET-01445_ACQ | QC Accepted | 2026_ET-01445_FR | 2025-12-01 | Submitted | 2026_ET-01445_RWR | Submitted | 2025-12-01 | 2026_ET-01445_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01445_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01445_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01445_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01445_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01445_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01445_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-SOMERSET_ET-01445 |  |  | No | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 10:38 PDT ¦ 2025-10-18 10:49 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CAMDEN-CHESTNUT-TALBERT | ET-01513 | 2026_ET-01513 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.8746 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-05 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01513_ACQPKG | 2026_ET-01513_GSPKG | Submitted | 2026_ET-01513_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01513_GCPR | 2025-12-08 | Historical | 2026_ET-01513_ACQ | QC Accepted | 2026_ET-01513_FR | 2025-11-23 | Submitted | 2026_ET-01513_RWR | Submitted | 2025-11-23 | 2026_ET-01513_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01513_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01513_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01513_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01513_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01513_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01513_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CAMDEN-CHESTNUT-TALBERT_ET-01513 | Done |  | No | 18:23 & 14:08 | Helicopter | SANTA ANA | 29 | HC | 2025-11-04 11:21 PST ¦ 2025-11-05 06:54 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CHANNEL ISLAND-LEHMAN-LEVY-OXGEN | ET-01645 | 2026_ET-01645 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.3437 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-29 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01645_ACQPKG | 2026_ET-01645_GSPKG | Submitted | 2026_ET-01645_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01645_GCPR | 2025-12-08 | Historical | 2026_ET-01645_ACQ | QC Accepted | 2026_ET-01645_FR | 2025-11-29 | Submitted | 2026_ET-01645_RWR | Submitted | 2025-11-29 | 2026_ET-01645_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01645_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01645_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-01645_VMLAZ | 2026-03-05 | QC Accepted | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-01645_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-01645_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 |  |  |  | 2026_ET-01645_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHANNEL ISLAND-LEHMAN-LEVY-OXGEN_ET-01645 |  |  | No | 16:29 - 20:43 | Helicopter | VENTURA | 39 | HC | 2025-10-29 11:46 PDT ¦ 2025-10-29 14:18 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ESTERO-MISSILE | ET-01686 | 2026_ET-01686 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.3283 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-29 | 01-09-2026 | 12-11-2025 |  | 2026_ET-01686_ACQPKG | 2026_ET-01686_GSPKG | Submitted | 2026_ET-01686_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01686_GCPR | 2025-12-08 | Historical | 2026_ET-01686_ACQ | QC Accepted | 2026_ET-01686_FR | 2025-11-29 | Submitted | 2026_ET-01686_RWR | Submitted | 2025-11-29 | 2026_ET-01686_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01686_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01686_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01686_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01686_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01686_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01686_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ESTERO-MISSILE_ET-01686 |  |  | No | 16:29 | Helicopter | VENTURA | 39 | HC | 2025-10-29 12:20 PDT ¦ 2025-10-29 12:22 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CRAFTON HILLS-MENTONE-ZANJA | ET-01832 | 2026_ET-01832 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 5.2785 | 4.1916 | 79 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-22 | 01-09-2026 | 12-12-2025 |  | 2026_ET-01832_ACQPKG | 2026_ET-01832_GSPKG | Submitted | 2026_ET-01832_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01832_GCPR | 2025-12-08 | Historical | 2026_ET-01832_ACQ | QC Accepted | 2026_ET-01832_FR | 2025-11-29 | Submitted | 2026_ET-01832_RWR | Submitted | 2025-11-29 | 2026_ET-01832_CLAZ | 2025-12-29 | QC Accepted | 01-12-2026 | 2025-12-12 | 0 | 2026_ET-01832_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01832_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01832_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01832_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01832_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01832_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | CRAFTON HILLS-MENTONE-ZANJA_ET-01832 |  |  | No | 19:43 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 13:36 PDT ¦ 2025-10-22 13:49 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
DECLEZ-NIAGARA-THRIVE | ET-01959 | 2026_ET-01959 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.7983 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-20 | 01-09-2026 | 12-12-2025 |  | 2026_ET-01959_ACQPKG | 2026_ET-01959_GSPKG | Submitted | 2026_ET-01959_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01959_GCPR | 2025-12-08 | Historical | 2026_ET-01959_ACQ | QC Accepted | 2026_ET-01959_FR | 2025-11-29 | Submitted | 2026_ET-01959_RWR | Submitted | 2025-11-29 | 2026_ET-01959_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-01959_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01959_WR | 2026-02-01 | 02-08-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01959_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01959_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01959_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01959_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DECLEZ-NIAGARA-THRIVE_ET-01959 |  |  | No | 19:31 | Helicopter | FOOTHILL | 30 | HC | 2025-10-20 14:37 PDT ¦ 2025-10-20 14:55 PDT | 102025 | 20251020 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MESA-REDONDO | ET-00213 | 2026_ET-00213 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 26.1883 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Does Not exist | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-11-05 | 01-13-2026 | 12-15-2025 |  | 2026_ET-00213_ACQPKG | 2026_ET-00213_GSPKG | Submitted | 2026_ET-00213_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00213_GCPR | 2025-12-08 | Historical | 2026_ET-00213_ACQ | QC Accepted | 2026_ET-00213_FR | 2025-12-01 | Submitted | 2026_ET-00213_RWR | Submitted | 2025-12-01 | 2026_ET-00213_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00213_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00213_WR | 2026-02-01 | 02-12-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00213_VMLAZ | 2026-02-01 | QC Accepted |  | 2026-02-12 | 0 | 2026_ET-00213_VMM1 | 2026-02-01 | QC Accepted |  |  | 2026-02-12 | 0 | 2026_ET-00213_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00213_VER | 2026-04-29 | QC Rejected |  | 2026-04-29 | 6 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-REDONDO_ET-00213 |  |  | No | 15:38 - 19:28 & 18:01 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 08:58 PDT ¦ 2025-11-05 12:23 PST | 110525 | 20251105 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-BASSETT-MERCED | ET-00305 | 2026_ET-00305 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.6719 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-24 | 01-13-2026 | 12-15-2025 |  | 2026_ET-00305_ACQPKG | 2026_ET-00305_GSPKG | Submitted | 2026_ET-00305_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00305_GCPR | 2025-12-08 | Historical | 2026_ET-00305_ACQ | QC Accepted | 2026_ET-00305_FR | 2025-11-29 | Submitted | 2026_ET-00305_RWR | Submitted | 2025-11-29 | 2026_ET-00305_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00305_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00305_WR | 2026-02-01 | 02-12-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00305_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00305_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00305_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00305_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WALNUT-BASSETT-MERCED_ET-00305 |  |  | No | 18:42 | Helicopter |  |  | HC | 2025-10-24 12:33 PDT ¦ 2025-10-24 13:18 PDT | 102425 | 20251024 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-PUENTE-RAILROAD-SANTEE | ET-00681 | 2026_ET-00681 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.2908 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-24 | 01-13-2026 | 12-15-2025 |  | 2026_ET-00681_ACQPKG | 2026_ET-00681_GSPKG | Submitted | 2026_ET-00681_GS | 2025-11-08 | Field Complete | 2026_ET-00681_GCPR | 2025-11-29 | Submitted | 2026_ET-00681_ACQ | QC Accepted | 2026_ET-00681_FR | 2025-11-29 | Submitted | 2026_ET-00681_RWR | Submitted | 2025-11-29 | 2026_ET-00681_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00681_PROCPKG | Submitted | All Good - Complete | 2026_ET-00681_WR | 2026-03-09 | 02-12-2026 | QC Accepted | 03-23-2026 | 2026-03-24 | 0 | 2026_ET-00681_VMLAZ | 2026-03-16 | QC Accepted | 03-30-2026 | 2026-03-23 | 0 | 2026_ET-00681_VMM1 | 2026-03-09 | QC Accepted |  | 03-30-2026 | 2026-03-23 | 0 | 2026_ET-00681_RR | 2026-03-10 | No Violations | 03-24-2026 |  | 0 |  |  |  | 2026_ET-00681_VER | 2026-03-10 | Contested | 03-30-2026 | 2026-05-11 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WALNUT-PUENTE-RAILROAD-SANTEE_ET-00681 |  |  | No | 18:42 | Helicopter |  |  | HC | 2025-10-24 12:42 PDT ¦ 2025-10-24 13:18 PDT | 102425 | 20251024 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-ORANGE NO. 1 | ET-01283 | 2026_ET-01283 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.3306 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-23 | 01-13-2026 | 12-11-2025 |  | 2026_ET-01283_ACQPKG | 2026_ET-01283_GSPKG | Submitted | 2026_ET-01283_GS | 2025-11-08 | Field Complete | 2026_ET-01283_GCPR | 2025-11-23 | Submitted | 2026_ET-01283_ACQ | QC Accepted | 2026_ET-01283_FR | 2025-11-23 | Submitted | 2026_ET-01283_RWR | Submitted | 2025-11-23 | 2026_ET-01283_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01283_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01283_WR | 2026-02-01 | 02-12-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01283_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01283_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01283_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01283_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VILLA PARK-ORANGE NO. 1_ET-01283 |  |  | No | 20:32 | Helicopter | SANTA ANA | 29 | HC | 2025-10-23 14:29 PDT ¦ 2025-10-23 14:55 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
VILLA PARK-ORANGE NO. 2 | ET-01284 | 2026_ET-01284 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.323 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-23 | 01-13-2026 | 12-11-2025 |  | 2026_ET-01284_ACQPKG | 2026_ET-01284_GSPKG | Submitted | 2026_ET-01284_GS | 2025-11-08 | Field Complete | 2026_ET-01284_GCPR | 2025-11-23 | Submitted | 2026_ET-01284_ACQ | QC Accepted | 2026_ET-01284_FR | 2025-11-23 | Submitted | 2026_ET-01284_RWR | Submitted | 2025-11-23 | 2026_ET-01284_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01284_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01284_WR | 2026-02-01 | 02-12-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01284_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01284_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01284_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01284_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VILLA PARK-ORANGE NO. 2_ET-01284 |  |  | No | 20:32 | Helicopter | SANTA ANA | 29 | HC | 2025-10-23 14:29 PDT ¦ 2025-10-23 14:55 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
VISTA-BLOOMINGTON-GLEN AVON | ET-02063 | 2026_ET-02063 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 16.8197 | 8.9541 | 53 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-20 | 01-13-2026 | 12-15-2025 |  | 2026_ET-02063_ACQPKG | 2026_ET-02063_GSPKG | Submitted | 2026_ET-02063_GS | 2025-11-08 | Field Complete | 2026_ET-02063_GCPR | 2025-11-23 | Submitted | 2026_ET-02063_ACQ | QC Accepted | 2026_ET-02063_FR | 2025-11-23 | Submitted | 2026_ET-02063_RWR | Submitted | 2025-11-23 | 2026_ET-02063_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-02063_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02063_WR | 2026-02-01 | 02-12-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02063_VMLAZ | 2026-03-05 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02063_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 1 | 2026_ET-02063_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02063_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VISTA-BLOOMINGTON-GLEN AVON_ET-02063 |  |  | No | 15:52 | Helicopter |  |  | HC | 2025-10-20 09:16 PDT ¦ 2025-10-22 09:29 PDT | 102025 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELLIS-GISLER-ORCOSAN | ET-00790 | 2026_ET-00790 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.8318 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-14 | 12-11-2025 | Flown | 2025-11-04 | 01-14-2026 | 12-15-2025 |  | 2026_ET-00790_ACQPKG | 2026_ET-00790_GSPKG | Submitted | 2026_ET-00790_GS | 2025-11-08 | Field Complete | 2026_ET-00790_GCPR | 2025-11-23 | Submitted | 2026_ET-00790_ACQ | QC Accepted | 2026_ET-00790_FR | 2025-11-23 | Submitted | 2026_ET-00790_RWR | Submitted | 2025-11-23 | 2026_ET-00790_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00790_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00790_WR | 2026-02-01 | 02-13-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00790_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00790_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00790_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00790_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-GISLER-ORCOSAN_ET-00790 |  |  | No | 18:23 | Helicopter | HUNTINGTON BEACH | 33 | HC | 2025-11-04 10:53 PST ¦ 2025-11-04 11:20 PST | 110425 | 20251104 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-FAIRVIEW-GISLER | ET-00801 | 2026_ET-00801 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.3237 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-14 | 12-11-2025 | Flown | 2025-11-04 | 01-14-2026 | 12-15-2025 |  | 2026_ET-00801_ACQPKG | 2026_ET-00801_GSPKG | Submitted | 2026_ET-00801_GS | 2025-11-08 | Field Complete | 2026_ET-00801_GCPR | 2025-11-23 | Submitted | 2026_ET-00801_ACQ | QC Accepted | 2026_ET-00801_FR | 2025-11-23 | Submitted | 2026_ET-00801_RWR | Submitted | 2025-11-23 | 2026_ET-00801_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00801_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00801_WR | 2026-02-01 | 02-13-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00801_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00801_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00801_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00801_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-FAIRVIEW-GISLER_ET-00801 |  |  | No | 18:23 | Helicopter | HUNTINGTON BEACH | 33 | HC | 2025-11-04 10:55 PST ¦ 2025-11-05 06:29 PST | 110425 | 20251105 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-ALDER-RANDALL | ET-01573 | 2026_ET-01573 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 9.9754 | 0.46388 | 5 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-14 | 12-11-2025 | Flown | 2025-10-21 | 01-14-2026 | 12-11-2025 |  | 2026_ET-01573_ACQPKG | 2026_ET-01573_GSPKG | Submitted | 2026_ET-01573_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01573_GCPR | 2025-12-08 | Historical | 2026_ET-01573_ACQ | QC Accepted | 2026_ET-01573_FR | 2025-11-29 | Submitted | 2026_ET-01573_RWR | Submitted | 2025-11-29 | 2026_ET-01573_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01573_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01573_WR | 2026-02-01 | 02-13-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01573_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01573_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01573_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01573_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-ALDER-RANDALL_ET-01573 |  |  | No | 19:31 & 15:48 | Helicopter | FOOTHILL | 30 | HC | 2025-10-20 14:19 PDT ¦ 2025-10-21 10:14 PDT | 102125 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
EAGLE ROCK-MACNEIL NO.2 | ET-00440 | 2026_ET-00440 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 15.495 | 5.4023 | 35 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-24 | 01-15-2026 | 01-15-2026 |  | 2026_ET-00440_ACQPKG | 2026_ET-00440_GSPKG | Submitted | 2026_ET-00440_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00440_GCPR | 2025-12-08 | Historical | 2026_ET-00440_ACQ | QC Accepted | 2026_ET-00440_FR | 2025-11-13 | Submitted | 2026_ET-00440_RWR | Submitted | 2025-11-13 | 2026_ET-00440_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-00440_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00440_WR | 2026-02-03 | 02-14-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00440_VMLAZ | 2026-02-02 | QC Accepted | 05-21-2026 | 2026-03-04 | 1 | 2026_ET-00440_VMM1 | 2026-02-03 | QC Accepted |  | 05-21-2026 | 2026-02-13 | 0 | 2026_ET-00440_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00440_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EAGLE ROCK-MACNEIL NO.2_ET-00440 |  |  | No |  | Helicopter |  |  | HC | 2025-10-24 10:55 PDT ¦ 2025-10-24 11:27 PDT | 102425 | 20251024 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
STADLER-TENAJA | ET-00543 | 2026_ET-00543 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.6105 | 1.4736 | 32 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-16 | 01-15-2026 | 12-15-2025 |  | 2026_ET-00543_ACQPKG | 2026_ET-00543_GSPKG | Submitted | 2026_ET-00543_GS | 2025-11-08 | Field Complete | 2026_ET-00543_GCPR | 2025-11-20 | Submitted | 2026_ET-00543_ACQ | QC Accepted | 2026_ET-00543_FR | 2025-11-23 | Submitted | 2026_ET-00543_RWR | Submitted | 2025-11-20 | 2026_ET-00543_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00543_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00543_WR | 2026-02-01 | 02-14-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00543_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00543_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00543_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00543_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | STADLER-TENAJA_ET-00543 |  |  | No | 19:13 | Helicopter | WILDOMAR | 88 | HC | 2025-10-16 12:54 PDT ¦ 2025-10-16 13:06 PDT | 101625 | 20251016 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-ALHAMBRA NO. 2 | ET-00819 | 2026_ET-00819 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.9667 | 2.8473 | 41 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-23 | 01-15-2026 | 01-15-2026 |  | 2026_ET-00819_ACQPKG | 2026_ET-00819_GSPKG | Submitted | 2026_ET-00819_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00819_GCPR | 2025-12-08 | Historical | 2026_ET-00819_ACQ | QC Accepted | 2026_ET-00819_FR | 2025-11-18 | Submitted | 2026_ET-00819_RWR | Submitted | 2025-11-18 | 2026_ET-00819_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-00819_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00819_WR | 2026-02-03 | 02-14-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00819_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-00819_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-00819_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00819_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EAGLE ROCK-ALHAMBRA NO. 2_ET-00819 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 10:43 PDT ¦ 2025-10-23 11:17 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-FURNACE-ROLLING | ET-01127 | 2026_ET-01127 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.3959 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-21 | 01-15-2026 | 12-11-2025 |  | 2026_ET-01127_ACQPKG | 2026_ET-01127_GSPKG | Submitted | 2026_ET-01127_GS | 2025-11-08 | Field Complete | 2026_ET-01127_GCPR | 2025-11-29 | Submitted | 2026_ET-01127_ACQ | QC Accepted | 2026_ET-01127_FR | 2025-11-29 | Submitted | 2026_ET-01127_RWR | Submitted | 2025-11-29 | 2026_ET-01127_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01127_PROCPKG | In Progress | All Good - Complete | 2026_ET-01127_WR | 2026-02-01 | 02-14-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01127_VMLAZ | 2026-03-05 | QC Accepted |  | 2026-02-11 | 0 | 2026_ET-01127_VMM1 | 2026-03-10 | QC Rejected |  |  | 2026-02-11 | 3 | 2026_ET-01127_RR | 2026-02-01 | No Violations |  |  | 0 |  |  |  | 2026_ET-01127_VER | 2026-05-01 | Uploaded to S123 |  | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-FURNACE-ROLLING_ET-01127 |  |  | No | 19:31 & 15:48 | Helicopter | FOOTHILL | 30 | HC | 2025-10-20 14:50 PDT ¦ 2025-10-21 10:23 PDT | 102125 | 20251021 | [5 empty] | Missing subject conductors. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
COOLWATER-SEGS 2-TORTILLA | ET-01363 | 2026_ET-01363 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 13.3118 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-11-01 | 01-15-2026 | 01-15-2026 |  | 2026_ET-01363_ACQPKG | 2026_ET-01363_GSPKG | Submitted | 2026_ET-01363_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01363_GCPR | 2025-12-08 | Historical | 2026_ET-01363_ACQ | QC Accepted | 2026_ET-01363_FR | 2025-11-18 | Submitted | 2026_ET-01363_RWR | Submitted | 2025-11-18 | 2026_ET-01363_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-01363_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01363_WR | 2026-02-05 | 02-14-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-01363_VMLAZ | 2026-02-05 | QC Accepted | 05-01-2026 | 2026-02-19 | 0 | 2026_ET-01363_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-01363_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-01363_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COOLWATER-SEGS 2-TORTILLA_ET-01363 |  |  | No |  | Helicopter | BARSTOW | 72 | HC | 2025-11-01 10:51 PDT ¦ 2025-11-01 11:19 PDT | 110125 | 20251101 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
EAGLE ROCK-ALHAMBRA NO. 1 | ET-01553 | 2026_ET-01553 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.0201 | 4.6262 | 77 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-23 | 01-15-2026 | 01-15-2026 |  | 2026_ET-01553_ACQPKG | 2026_ET-01553_GSPKG | Submitted | 2026_ET-01553_GS | 2025-10-15 | Field Complete | 2026_ET-01553_GCPR | 2025-11-27 | Submitted | 2026_ET-01553_ACQ | QC Accepted | 2026_ET-01553_FR | 2025-11-18 | Submitted | 2026_ET-01553_RWR | Submitted | 2025-11-18 | 2026_ET-01553_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-01553_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01553_WR | 2026-02-03 | 02-14-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-01553_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-01553_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-01553_RR | 2026-03-18 | No Violations | 02-14-2026 |  | 3 | 2026-03-27 | 0 | 0 | 2026_ET-01553_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EAGLE ROCK-ALHAMBRA NO. 1_ET-01553 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 10:56 PDT ¦ 2025-10-23 11:17 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-MACNEIL NO. 1 | ET-01637 | 2026_ET-01637 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 15.2635 | 5.3951 | 35 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-24 | 01-15-2026 | 01-15-2026 |  | 2026_ET-01637_ACQPKG | 2026_ET-01637_GSPKG | Submitted | 2026_ET-01637_GS | 2025-10-15 | Field Complete | 2026_ET-01637_GCPR | 2025-11-27 | Submitted | 2026_ET-01637_ACQ | QC Accepted | 2026_ET-01637_FR | 2025-11-18 | Submitted | 2026_ET-01637_RWR | Submitted | 2025-11-18 | 2026_ET-01637_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-01637_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01637_WR | 2026-02-03 | 02-14-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-01637_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-01637_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-01637_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-01637_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EAGLE ROCK-MACNEIL NO. 1_ET-01637 |  |  | No |  | Helicopter |  |  | HC | 2025-10-24 10:52 PDT ¦ 2025-10-24 11:28 PDT | 102425 | 20251024 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-YBARRA | ET-01787 | 2026_ET-01787 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.6786 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-18 | 01-15-2026 | 12-12-2025 |  | 2026_ET-01787_ACQPKG | 2026_ET-01787_GSPKG | Submitted | 2026_ET-01787_GS | 2025-11-08 | Field Complete | 2026_ET-01787_GCPR | 2025-12-01 | Submitted | 2026_ET-01787_ACQ | QC Accepted | 2026_ET-01787_FR | 2025-12-01 | Submitted | 2026_ET-01787_RWR | Submitted | 2025-12-01 | 2026_ET-01787_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-01787_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01787_WR | 2026-02-01 | 02-14-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01787_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01787_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01787_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01787_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-YBARRA_ET-01787 |  |  | No | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 09:11 PDT ¦ 2025-10-26 13:53 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
CALDWELL-COLUSA-VICTOR | ET-02028 | 2026_ET-02028 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.6308 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-28 | 01-15-2026 | 01-15-2026 |  | 2026_ET-02028_ACQPKG | 2026_ET-02028_GSPKG | Submitted | 2026_ET-02028_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02028_GCPR | 2025-12-08 | Historical | 2026_ET-02028_ACQ | QC Accepted | 2026_ET-02028_FR | 2025-11-18 | Submitted | 2026_ET-02028_RWR | Submitted | 2025-11-18 | 2026_ET-02028_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-02028_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02028_WR | 2026-02-05 | 02-14-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-02028_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-02028_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-02028_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-02028_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CALDWELL-COLUSA-VICTOR_ET-02028 | Done |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 13:19 PDT ¦ 2025-10-28 14:00 PDT | 102825 | 20251028 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COOLWATER-SILVER SPRINGS | ET-02033 | 2026_ET-02033 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.073288 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-11-01 | 01-15-2026 | 01-15-2026 |  | 2026_ET-02033_ACQPKG | 2026_ET-02033_GSPKG | Submitted | 2026_ET-02033_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02033_GCPR | 2025-12-08 | Historical | 2026_ET-02033_ACQ | QC Accepted | 2026_ET-02033_FR | 2025-11-18 | Submitted | 2026_ET-02033_RWR | Submitted | 2025-11-18 | 2026_ET-02033_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-15 | 0 | 2026_ET-02033_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02033_WR | 2026-02-05 | 02-14-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-02033_VMLAZ | 2026-02-05 | QC Accepted | 02-19-2026 | 2026-02-19 | 0 | 2026_ET-02033_VMM1 | 2026-02-05 | QC Accepted |  | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-02033_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-02033_VER | 2026-02-05 | Uploaded to S123 | 02-19-2026 | 2026-02-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COOLWATER-SILVER SPRINGS_ET-02033 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-11-01 10:57 PDT ¦ 2025-11-01 11:00 PDT | 110125 | 20251101 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN MARCOS-VEGAS | ET-06985 | 2026_ET-06985 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.179 | 2.3997 | 75 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-28 | 01-15-2026 | 12-12-2025 |  | 2026_ET-06985_ACQPKG | 2026_ET-06985_GSPKG | Submitted | 2026_ET-06985_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06985_GCPR | 2025-12-08 | Historical | 2026_ET-06985_ACQ | QC Accepted | 2026_ET-06985_FR | 2025-11-29 | Submitted | 2026_ET-06985_RWR | Submitted | 2025-11-29 | 2026_ET-06985_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-06985_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06985_WR | 2026-02-01 | 02-14-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-06985_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-06985_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-06985_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-06985_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SAN MARCOS-VEGAS_ET-06985 |  |  | No | 20:04 | Helicopter | SANTA BARBARA | 49 | HC | 2025-10-28 13:45 PDT ¦ 2025-10-28 15:05 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ELDORADO-MCCULLOUGH | ET-00116 | 2026_ET-00116 |  | 11 | 2026 | Mar 11, 2026 | 500 | NV_E | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.11649 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-14 | 12-11-2025 | Flown | 2025-10-30 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00116_ACQPKG | 2026_ET-00116_GSPKG | Submitted | 2026_ET-00116_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00116_GCPR | 2025-12-08 | Historical | 2026_ET-00116_ACQ | QC Accepted | 2026_ET-00116_FR | 2025-11-13 | Submitted | 2026_ET-00116_RWR | Submitted | 2025-11-13 | 2026_ET-00116_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00116_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00116_WR | 2026-02-06 | 02-15-2026 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00116_VMLAZ | 2026-02-06 | QC Accepted | 02-20-2026 | 2026-02-19 | 0 | 2026_ET-00116_VMM1 | 2026-02-06 | QC Accepted |  | 02-20-2026 | 2026-02-17 | 0 | 2026_ET-00116_RR | 2026-02-06 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00116_VER | 2026-02-06 | Uploaded to S123 | 02-20-2026 | 2026-02-18 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-MCCULLOUGH_ET-00116 |  |  | No |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-29 11:52 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIDWAY-VINCENT NO.2 | ET-00127 | 2026_ET-00127 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 112.7233 | 64.8085 | 57 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-20 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00127_ACQPKG | 2026_ET-00127_GSPKG | Submitted | 2026_ET-00127_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00127_GCPR | 2025-12-08 | Historical | 2026_ET-00127_ACQ | QC Accepted | 2026_ET-00127_FR | 2025-11-18 | Submitted | 2026_ET-00127_RWR | Submitted | 2025-11-18 | 2026_ET-00127_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00127_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00127_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00127_VMLAZ | 2026-02-04 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00127_VMM1 | 2026-02-04 | QC Accepted |  | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00127_RR | 2026-03-18 | No Violations | 02-19-2026 |  | 28 | 2026-03-27 | 0 | 0 | 2026_ET-00127_VER | 2026-02-04 | Uploaded to S123 | 02-18-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIDWAY-VINCENT NO.2_ET-00127 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-18 13:53 PDT ¦ 2025-10-20 11:23 PDT | 102025 | 20251020 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-SAVAGE NO.3 | ET-00193 | 2026_ET-00193 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.0491 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-28 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00193_ACQPKG | 2026_ET-00193_GSPKG | Submitted | 2026_ET-00193_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00193_GCPR | 2025-12-08 | Historical | 2026_ET-00193_ACQ | QC Accepted | 2026_ET-00193_FR | 2025-11-18 | Submitted | 2026_ET-00193_RWR | Submitted | 2025-11-18 | 2026_ET-00193_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00193_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00193_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00193_VMLAZ | 2026-02-04 | QC Accepted | 05-21-2026 | 2026-02-23 | 0 | 2026_ET-00193_VMM1 | 2026-02-04 | QC Accepted |  | 05-21-2026 | 2026-02-20 | 0 | 2026_ET-00193_RR | 2026-03-18 | No Violations | 02-21-2026 |  | 1 | 2026-03-27 | 0 | 0 | 2026_ET-00193_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-SAVAGE NO.3_ET-00193 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 13:03 PDT ¦ 2025-10-28 13:25 PDT | 102825 | 20251028 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-ANITA NO.2 | ET-00371 | 2026_ET-00371 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.5055 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00371_ACQPKG | 2026_ET-00371_GSPKG | Submitted | 2026_ET-00371_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00371_GCPR | 2025-12-08 | Historical | 2026_ET-00371_ACQ | QC Accepted | 2026_ET-00371_FR | 2025-11-18 | Submitted | 2026_ET-00371_RWR | Submitted | 2025-11-18 | 2026_ET-00371_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00371_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00371_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00371_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-00371_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-00371_RR | 2026-03-18 | No Violations | 02-14-2026 |  | 3 | 2026-03-27 | 0 | 0 | 2026_ET-00371_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-ANITA NO.2_ET-00371 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 09:12 PDT ¦ 2025-10-23 09:58 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE MIRA LOMA-VINCENT | ET-00390 | 2026_ET-00390 |  | 11 | 2026 | Mar 11, 2026 | 500 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.050158 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_02 | 2026-01-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00390_ACQPKG | 2026_ET-00390_GSPKG | Submitted | 2026_ET-00390_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00390_GCPR | 2025-12-08 | Historical | 2026_ET-00390_ACQ | QC Accepted | 2026_ET-00390_FR | 2025-11-18 | Submitted | 2026_ET-00390_RWR | Submitted | 2025-11-18 | 2026_ET-00390_CLAZ | 2025-11-18 | QC Accepted | 01-16-2026 | 2026-01-16 | 0 | 2026_ET-00390_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00390_WR | 2026-02-05 | 02-15-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00390_VMLAZ | 2026-02-05 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00390_VMM1 | 2026-02-05 | QC Accepted |  | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-00390_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00390_VER | 2026-02-05 | Uploaded to S123 | 02-19-2026 | 2026-02-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE MIRA LOMA-VINCENT_ET-00390 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-23 12:57 PDT ¦ 2025-10-23 12:58 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CIMA-ELDORADO-PISGAH NO.2 | ET-00465 | 2026_ET-00465 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 109.4711 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-29 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00465_ACQPKG | 2026_ET-00465_GSPKG | Submitted | 2026_ET-00465_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00465_GCPR | 2025-12-08 | Historical | 2026_ET-00465_ACQ | QC Accepted | 2026_ET-00465_FR | 2025-11-18 | Submitted | 2026_ET-00465_RWR | Submitted | 2025-11-18 | 2026_ET-00465_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00465_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00465_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-17 | 0 | 2026_ET-00465_VMLAZ | 2026-03-02 | QC Accepted | 03-16-2026 | 2026-03-12 | 1 | 2026_ET-00465_VMM1 | 2026-02-04 | QC Accepted |  | 03-16-2026 | 2026-02-17 | 0 | 2026_ET-00465_RR | 2026-03-18 | No Violations | 02-18-2026 |  | 105 | 2026-03-27 | 0 | 0 | 2026_ET-00465_VER | 2026-03-01 | Uploaded to S123 | 03-16-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CIMA-ELDORADO-PISGAH NO.2_ET-00465 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-10-29 09:37 PDT ¦ 2025-11-01 10:34 PDT | 102925 | 20251101 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-PASTORIA-WARNE | ET-00624 | 2026_ET-00624 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 41.5828 | 37.0861 | 89 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-20 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00624_ACQPKG | 2026_ET-00624_GSPKG | Submitted | 2026_ET-00624_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00624_GCPR | 2025-12-08 | Historical | 2026_ET-00624_ACQ | QC Accepted | 2026_ET-00624_FR | 2025-11-18 | Submitted | 2026_ET-00624_RWR | Submitted | 2025-11-18 | 2026_ET-00624_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00624_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00624_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-00624_VMLAZ | 2026-02-04 | QC Accepted | 05-01-2026 | 2026-02-23 | 0 | 2026_ET-00624_VMM1 | 2026-02-04 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-00624_RR | 2026-02-04 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00624_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PARDEE-PASTORIA-WARNE_ET-00624 |  |  | Yes |  | Helicopter | VALENCIA | 59 | HC | 2025-10-19 09:15 PDT ¦ 2025-10-20 12:51 PDT | 102025 | 20251020 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-RUSH NO. 3 | ET-00656 | 2026_ET-00656 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.7148 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-13 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00656_ACQPKG | 2026_ET-00656_GSPKG | Submitted | 2026_ET-00656_GS | 2025-10-15 | Field Complete | 2026_ET-00656_GCPR | 2025-11-27 | Submitted | 2026_ET-00656_ACQ | QC Accepted | 2026_ET-00656_FR | 2025-11-18 | Submitted | 2026_ET-00656_RWR | Submitted | 2025-11-18 | 2026_ET-00656_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00656_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00656_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00656_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-00656_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-00656_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00656_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-RUSH NO. 3_ET-00656 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-21 11:18 PDT ¦ 2025-10-23 10:23 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-WALNUT | ET-00689 | 2026_ET-00689 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 13.9073 | 7.5622 | 54 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-00689_ACQPKG | 2026_ET-00689_GSPKG | Submitted | 2026_ET-00689_GS | 2025-10-15 | Field Complete | 2026_ET-00689_GCPR | 2025-11-27 | Submitted | 2026_ET-00689_ACQ | QC Accepted | 2026_ET-00689_FR | 2025-11-18 | Submitted | 2026_ET-00689_RWR | Submitted | 2025-11-18 | 2026_ET-00689_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00689_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00689_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-17 | 0 | 2026_ET-00689_VMLAZ | 2026-03-02 | QC Accepted | 05-21-2026 | 2026-03-12 | 1 | 2026_ET-00689_VMM1 | 2026-02-04 | QC Accepted |  | 05-21-2026 | 2026-02-17 | 0 | 2026_ET-00689_RR | 2026-02-04 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-00689_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-WALNUT_ET-00689 |  |  | Yes |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-21 11:18 PDT ¦ 2025-10-23 13:22 PDT | 102325 | 20251023 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
VICTOR-RIVERTEX | ET-01001 | 2026_ET-01001 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.6703 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-28 | 01-16-2026 | 01-16-2026 |  | 2026_ET-01001_ACQPKG | 2026_ET-01001_GSPKG | Submitted | 2026_ET-01001_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01001_GCPR | 2025-12-08 | Historical | 2026_ET-01001_ACQ | QC Accepted | 2026_ET-01001_FR | 2025-11-18 | Submitted | 2026_ET-01001_RWR | Submitted | 2025-11-18 | 2026_ET-01001_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-01001_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01001_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-01001_VMLAZ | 2026-02-04 | QC Accepted | 05-13-2026 | 2026-02-23 | 0 | 2026_ET-01001_VMM1 | 2026-02-04 | QC Accepted |  | 05-13-2026 | 2026-02-19 | 0 | 2026_ET-01001_RR | 2026-02-04 | No Violations | 02-20-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-01001_VER | 2026-04-29 | Uploaded to S123 | 05-13-2026 | 2026-05-06 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-RIVERTEX_ET-01001 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 13:18 PDT ¦ 2025-10-28 14:00 PDT | 102825 | 20251028 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-VINCENT NO. 1 | ET-01091 | 2026_ET-01091 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 35.9798 | 26.1882 | 73 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-21 | 01-16-2026 | 01-16-2026 |  | 2026_ET-01091_ACQPKG | 2026_ET-01091_GSPKG | Submitted | 2026_ET-01091_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01091_GCPR | 2025-12-08 | Historical | 2026_ET-01091_ACQ | QC Accepted | 2026_ET-01091_FR | 2025-11-18 | Submitted | 2026_ET-01091_RWR | Submitted | 2025-11-18 | 2026_ET-01091_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-01091_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01091_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-17 | 0 | 2026_ET-01091_VMLAZ | 2026-03-02 | QC Accepted | 05-21-2026 | 2026-03-12 | 1 | 2026_ET-01091_VMM1 | 2026-02-04 | QC Accepted |  | 05-21-2026 | 2026-02-17 | 0 | 2026_ET-01091_RR | 2026-03-18 | No Violations | 02-18-2026 |  | 2 | 2026-03-27 | 0 | 0 | 2026_ET-01091_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-VINCENT NO. 1_ET-01091 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | 2025-10-21 08:57 PDT ¦ 2025-10-21 11:38 PDT | 102125 | 20251021 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MESA-VINCENT NO. 2 | ET-01093 | 2026_ET-01093 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 36.3642 | 26.1866 | 72 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-21 | 01-16-2026 | 01-16-2026 |  | 2026_ET-01093_ACQPKG | 2026_ET-01093_GSPKG | Submitted | 2026_ET-01093_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01093_GCPR | 2025-12-08 | Historical | 2026_ET-01093_ACQ | QC Accepted | 2026_ET-01093_FR | 2025-11-18 | Submitted | 2026_ET-01093_RWR | Submitted | 2025-11-18 | 2026_ET-01093_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-01093_PROCPKG | Submitted | All Good - Complete | 2026_ET-01093_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-17 | 0 | 2026_ET-01093_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-01093_VMM1 | 2026-02-04 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-01093_RR | 2026-02-04 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-01093_VER | 2026-04-17 | Contested | 05-01-2026 | 2026-04-17 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-VINCENT NO. 2_ET-01093 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | 2025-10-19 12:34 PDT ¦ 2025-10-21 11:40 PDT | 102125 | 20251021 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RATTLESNAKE-WHIRLWIND | ET-01927 | 2026_ET-01927 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.63281 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-18 | 01-16-2026 | 01-16-2026 |  | 2026_ET-01927_ACQPKG | 2026_ET-01927_GSPKG | Submitted | 2026_ET-01927_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01927_GCPR | 2025-12-08 | Historical | 2026_ET-01927_ACQ | QC Accepted | 2026_ET-01927_FR | 2025-11-13 | Submitted | 2026_ET-01927_RWR | Submitted | 2025-11-13 | 2026_ET-01927_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-01927_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01927_WR | 2026-02-04 | 02-15-2026 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-01927_VMLAZ | 2026-02-04 | QC Accepted | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-01927_VMM1 | 2026-02-04 | QC Accepted |  | 02-18-2026 | 2026-02-18 | 0 | 2026_ET-01927_RR | 2026-02-04 | No Violations | 02-19-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-01927_VER | 2026-02-04 | Uploaded to S123 | 02-18-2026 | 2026-02-18 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RATTLESNAKE-WHIRLWIND_ET-01927 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-18 13:23 PDT ¦ 2025-10-18 13:34 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-RIO HONDO NO.1 | ET-01968 | 2026_ET-01968 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 10.9866 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-01968_ACQPKG | 2026_ET-01968_GSPKG | Submitted | 2026_ET-01968_GS | 2025-10-15 | Field Complete | 2026_ET-01968_GCPR | 2025-11-27 | Submitted | 2026_ET-01968_ACQ | QC Accepted | 2026_ET-01968_FR | 2025-11-18 | Submitted | 2026_ET-01968_RWR | Submitted | 2025-11-18 | 2026_ET-01968_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-01968_PROCPKG | Submitted | All Good - Complete | 2026_ET-01968_WR | 2026-02-05 | 02-15-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-01968_VMLAZ | 2026-03-05 | QC Accepted | 04-02-2026 | 2026-03-23 | 1 | 2026_ET-01968_VMM1 | 2026-03-19 | QC Accepted |  | 04-02-2026 | 2026-04-02 | 1 | 2026_ET-01968_RR | 2026-02-05 | No Violations | 04-03-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-01968_VER | 2026-03-01 | Contested | 04-02-2026 | 2026-02-18 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-RIO HONDO NO.1_ET-01968 |  |  | Yes |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-21 11:18 PDT ¦ 2025-10-23 10:22 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-LAGUNA BELL | ET-04320 | 2026_ET-04320 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 16.6902 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-07 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-04320_ACQPKG | 2026_ET-04320_GSPKG | Submitted | 2026_ET-04320_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04320_GCPR | 2025-12-08 | Historical | 2026_ET-04320_ACQ | QC Accepted | 2026_ET-04320_FR | 2025-11-18 | Submitted | 2026_ET-04320_RWR | Submitted | 2025-11-18 | 2026_ET-04320_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-04320_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04320_WR | 2026-02-05 | 02-15-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-04320_VMLAZ | 2026-03-02 | QC Accepted | 05-01-2026 | 2026-03-12 | 1 | 2026_ET-04320_VMM1 | 2026-02-05 | QC Accepted |  | 05-01-2026 | 2026-02-17 | 0 | 2026_ET-04320_RR | 2026-02-05 | No Violations | 02-18-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-04320_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-LAGUNA BELL_ET-04320 |  |  | Yes |  | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-23 12:07 PDT ¦ 2025-10-23 12:52 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-RIVERWAY | ET-06602 | 2026_ET-06602 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_4 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.4094 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-17 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06602_ACQPKG | 2026_ET-06602_GSPKG | Submitted | 2026_ET-06602_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06602_GCPR | 2025-12-08 | Historical | 2026_ET-06602_ACQ | QC Accepted | 2026_ET-06602_FR | 2025-11-13 | Submitted | 2026_ET-06602_RWR | Submitted | 2025-11-13 | 2026_ET-06602_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06602_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06602_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06602_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-06602_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-06602_RR | 2026-03-18 | No Violations | 02-14-2026 |  | 1 | 2026-03-27 | 0 | 0 | 2026_ET-06602_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RECTOR-RIVERWAY_ET-06602 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-10-17 14:16 PDT ¦ 2025-10-17 14:30 PDT | 101725 | 20251017 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-ANITA NO. 1 | ET-06801 | 2026_ET-06801 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.2146 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06801_ACQPKG | 2026_ET-06801_GSPKG | Submitted | 2026_ET-06801_GS | 2025-10-15 | Field Complete | 2026_ET-06801_GCPR | 2025-11-27 | Submitted | 2026_ET-06801_ACQ | QC Accepted | 2026_ET-06801_FR | 2025-11-18 | Submitted | 2026_ET-06801_RWR | Submitted | 2025-11-18 | 2026_ET-06801_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06801_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06801_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06801_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-06801_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-06801_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-06801_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-ANITA NO. 1_ET-06801 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 09:07 PDT ¦ 2025-10-23 09:57 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-AMADOR | ET-06802 | 2026_ET-06802 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.5769 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06802_ACQPKG | 2026_ET-06802_GSPKG | Submitted | 2026_ET-06802_GS | 2025-10-15 | Field Complete | 2026_ET-06802_GCPR | 2025-11-27 | Submitted | 2026_ET-06802_ACQ | QC Accepted | 2026_ET-06802_FR | 2025-11-18 | Submitted | 2026_ET-06802_RWR | Submitted | 2025-11-18 | 2026_ET-06802_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06802_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06802_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06802_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-06802_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-06802_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-06802_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-AMADOR_ET-06802 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-23 09:12 PDT ¦ 2025-10-23 09:58 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-ARCADIA | ET-06811 | 2026_ET-06811 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.6154 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06811_ACQPKG | 2026_ET-06811_GSPKG | Submitted | 2026_ET-06811_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06811_GCPR | 2025-12-08 | Historical | 2026_ET-06811_ACQ | QC Accepted | 2026_ET-06811_FR | 2025-11-18 | Submitted | 2026_ET-06811_RWR | Submitted | 2025-11-18 | 2026_ET-06811_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06811_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06811_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06811_VMLAZ | 2026-02-02 | QC Accepted | 04-29-2026 | 2026-03-04 | 1 | 2026_ET-06811_VMM1 | 2026-02-03 | QC Accepted |  | 04-29-2026 | 2026-02-13 | 0 | 2026_ET-06811_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-06811_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-ARCADIA_ET-06811 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 09:07 PDT ¦ 2025-10-23 09:57 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-BRADBURY | ET-06821 | 2026_ET-06821 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.6458 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-09 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06821_ACQPKG | 2026_ET-06821_GSPKG | Submitted | 2026_ET-06821_GS | 2025-10-15 | Field Complete | 2026_ET-06821_GCPR | 2025-11-27 | Submitted | 2026_ET-06821_ACQ | QC Accepted | 2026_ET-06821_FR | 2025-11-18 | Submitted | 2026_ET-06821_RWR | Submitted | 2025-11-18 | 2026_ET-06821_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06821_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06821_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06821_VMLAZ | 2026-02-02 | QC Accepted | 04-29-2026 | 2026-03-04 | 1 | 2026_ET-06821_VMM1 | 2026-02-03 | QC Accepted |  | 04-29-2026 | 2026-02-13 | 0 | 2026_ET-06821_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-06821_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-BRADBURY_ET-06821 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 09:06 PDT ¦ 2025-10-23 09:40 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RAVENDALE-ROSEMEAD | ET-06906 | 2026_ET-06906 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.0878 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 12-11-2025 | Flown | 2025-10-23 | 01-16-2026 | 01-16-2026 |  | 2026_ET-06906_ACQPKG | 2026_ET-06906_GSPKG | Submitted | 2026_ET-06906_GS | 2025-10-15 | Field Complete | 2026_ET-06906_GCPR | 2025-11-27 | Submitted | 2026_ET-06906_ACQ | QC Accepted | 2026_ET-06906_FR | 2025-11-18 | Submitted | 2026_ET-06906_RWR | Submitted | 2025-11-18 | 2026_ET-06906_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-06906_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06906_WR | 2026-02-03 | 02-15-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-06906_VMLAZ | 2026-02-02 | QC Accepted | 05-01-2026 | 2026-03-04 | 1 | 2026_ET-06906_VMM1 | 2026-02-03 | QC Accepted |  | 05-01-2026 | 2026-02-13 | 0 | 2026_ET-06906_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-06906_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RAVENDALE-ROSEMEAD_ET-06906 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-10-23 10:32 PDT ¦ 2025-10-23 10:33 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MAGUNDEN-VESTAL NO. 1 | ET-08214 | 2026_ET-08214 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 35.8002 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-15 | 01-16-2026 | 01-16-2026 |  | 2026_ET-08214_ACQPKG | 2026_ET-08214_GSPKG | Submitted | 2026_ET-08214_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08214_GCPR | 2025-12-08 | Historical | 2026_ET-08214_ACQ | QC Accepted | 2026_ET-08214_FR | 2025-11-13 | Submitted | 2026_ET-08214_RWR | Submitted | 2025-11-13 | 2026_ET-08214_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-08214_PROCPKG | Submitted | All Good - Complete | 2026_ET-08214_WR | 2026-02-05 | 02-15-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-08214_VMLAZ | 2026-03-05 | QC Accepted | 06-05-2026 | 2026-03-23 | 1 | 2026_ET-08214_VMM1 | 2026-03-19 | QC Accepted |  | 06-05-2026 | 2026-04-02 | 1 | 2026_ET-08214_RR | 2026-02-05 | No Violations | 04-03-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-08214_VER | 2026-05-22 | Ready for QC | 06-05-2026 | 2026-05-11 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MAGUNDEN-VESTAL NO. 1_ET-08214 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-15 10:02 PDT ¦ 2025-10-15 11:31 PDT | 101525 | 20251015 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MAGUNDEN-VESTAL NO. 2 | ET-08342 | 2026_ET-08342 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 35.7973 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-15 | 01-16-2026 | 01-16-2026 |  | 2026_ET-08342_ACQPKG | 2026_ET-08342_GSPKG | Submitted | 2026_ET-08342_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08342_GCPR | 2025-12-08 | Historical | 2026_ET-08342_ACQ | QC Accepted | 2026_ET-08342_FR | 2025-11-13 | Submitted | 2026_ET-08342_RWR | Submitted | 2025-11-13 | 2026_ET-08342_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-08342_PROCPKG | Submitted | All Good - Complete | 2026_ET-08342_WR | 2026-02-05 | 02-15-2026 | QC Accepted | 02-19-2026 | 2026-02-17 | 0 | 2026_ET-08342_VMLAZ | 2026-03-05 | QC Accepted | 06-05-2026 | 2026-03-23 | 1 | 2026_ET-08342_VMM1 | 2026-03-19 | QC Accepted |  | 06-05-2026 | 2026-04-02 | 1 | 2026_ET-08342_RR | 2026-02-05 | No Violations | 04-03-2026 |  | 0 | 2026-02-05 | 0 | 0 | 2026_ET-08342_VER | 2026-05-22 | Ready for QC | 06-05-2026 | 2026-05-11 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MAGUNDEN-VESTAL NO. 2_ET-08342 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-15 10:01 PDT ¦ 2025-10-15 11:31 PDT | 101525 | 20251015 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MAGNOLIA | ET-00178 | 2026_ET-00178 |  | 11 | 2026 | Mar 11, 2026 | 220 | NV_E | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.046473 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-14 | 12-11-2025 | Flown | 2025-10-30 | 01-21-2026 | 01-21-2026 |  | 2026_ET-00178_ACQPKG | 2026_ET-00178_GSPKG | Submitted | 2026_ET-00178_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00178_GCPR | 2025-12-08 | Historical | 2026_ET-00178_ACQ | QC Accepted | 2026_ET-00178_FR | 2025-11-13 | Submitted | 2026_ET-00178_RWR | Submitted | 2025-11-13 | 2026_ET-00178_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-21 | 0 | 2026_ET-00178_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00178_WR | 2026-02-09 | 02-20-2026 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-00178_VMLAZ | 2026-02-09 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-00178_VMM1 | 2026-02-09 | QC Accepted |  | 02-23-2026 | 2026-02-17 | 0 | 2026_ET-00178_RR | 2026-02-09 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00178_VER | 2026-02-09 | Uploaded to S123 | 02-23-2026 | 2026-02-18 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-MAGNOLIA_ET-00178 |  |  | No |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-29 11:52 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EDMONSTON-PASTORIA | ET-00684 | 2026_ET-00684 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.99193 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-18 | 01-21-2026 | 01-21-2026 |  | 2026_ET-00684_ACQPKG | 2026_ET-00684_GSPKG | Submitted | 2026_ET-00684_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00684_GCPR | 2025-12-08 | Historical | 2026_ET-00684_ACQ | QC Accepted | 2026_ET-00684_FR | 2025-11-18 | Submitted | 2026_ET-00684_RWR | Submitted | 2025-11-18 | 2026_ET-00684_CLAZ | 2025-11-18 | QC Accepted | 01-23-2026 | 2026-01-21 | 0 | 2026_ET-00684_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00684_WR | 2026-02-09 | 02-20-2026 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-00684_VMLAZ | 2026-02-09 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-00684_VMM1 | 2026-02-09 | QC Accepted |  | 02-23-2026 | 2026-02-17 | 0 | 2026_ET-00684_RR | 2026-02-09 | No Violations | 02-18-2026 |  | 0 | 2026-02-10 | 0 | 0 | 2026_ET-00684_VER | 2026-02-09 | Uploaded to S123 | 02-23-2026 | 2026-02-18 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EDMONSTON-PASTORIA_ET-00684 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-19 09:11 PDT ¦ 2025-10-19 11:10 PDT | 101925 | 20251019 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-VESTAL NO. 1 | ET-01083 | 2026_ET-01083 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_4 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 33.3721 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-18 | 01-21-2026 | 01-21-2026 |  | 2026_ET-01083_ACQPKG | 2026_ET-01083_GSPKG | Submitted | 2026_ET-01083_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01083_GCPR | 2025-12-08 | Historical | 2026_ET-01083_ACQ | QC Accepted | 2026_ET-01083_FR | 2025-11-13 | Submitted | 2026_ET-01083_RWR | Submitted | 2025-11-13 | 2026_ET-01083_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-21 | 0 | 2026_ET-01083_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01083_WR | 2026-02-09 | 02-20-2026 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-01083_VMLAZ | 2026-02-09 | QC Accepted | 05-21-2026 | 2026-02-19 | 0 | 2026_ET-01083_VMM1 | 2026-02-09 | QC Accepted |  | 05-21-2026 | 2026-02-17 | 0 | 2026_ET-01083_RR | 2026-03-18 | No Violations | 02-18-2026 |  | 152 | 2026-03-27 | 0 | 0 | 2026_ET-01083_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RECTOR-VESTAL NO. 1_ET-01083 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-15 10:41 PDT ¦ 2025-10-18 10:32 PDT | 101825 | 20251018 |  |  |  |  | Attribute - Clearance, Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-VESTAL NO. 2 | ET-06644 | 2026_ET-06644 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_4 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 33.3766 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 12-11-2025 | Flown | 2025-10-18 | 01-21-2026 | 01-21-2026 |  | 2026_ET-06644_ACQPKG | 2026_ET-06644_GSPKG | Submitted | 2026_ET-06644_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06644_GCPR | 2025-12-08 | Historical | 2026_ET-06644_ACQ | QC Accepted | 2026_ET-06644_FR | 2025-11-13 | Submitted | 2026_ET-06644_RWR | Submitted | 2025-11-13 | 2026_ET-06644_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-21 | 0 | 2026_ET-06644_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06644_WR | 2026-02-09 | 02-20-2026 | QC Accepted | 02-23-2026 | 2026-02-19 | 0 | 2026_ET-06644_VMLAZ | 2026-02-09 | QC Accepted | 03-15-2026 | 2026-02-19 | 0 | 2026_ET-06644_VMM1 | 2026-02-09 | QC Accepted |  | 03-15-2026 | 2026-02-17 | 0 | 2026_ET-06644_RR | 2026-03-18 | No Violations | 02-18-2026 |  | 117 | 2026-03-27 | 0 | 0 | 2026_ET-06644_VER | 2026-03-01 | Uploaded to S123 | 03-15-2026 | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RECTOR-VESTAL NO. 2_ET-06644 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-15 10:41 PDT ¦ 2025-10-18 10:32 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-ALUMAX-HUNTER | ET-01185 | 2026_ET-01185 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.6122 | 0.2993 | 11 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-01-22 | 12-11-2025 | Flown | 2025-11-03 | 01-22-2026 | 12-11-2025 |  | 2026_ET-01185_ACQPKG | 2026_ET-01185_GSPKG | Submitted | 2026_ET-01185_GS | 2025-11-08 | Field Complete | 2026_ET-01185_GCPR | 2025-12-01 | Submitted | 2026_ET-01185_ACQ | QC Accepted | 2026_ET-01185_FR | 2025-12-01 | Submitted | 2026_ET-01185_RWR | Submitted | 2025-12-01 | 2026_ET-01185_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01185_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01185_WR | 2026-02-01 | 02-21-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01185_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01185_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01185_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01185_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VISTA-ALUMAX-HUNTER_ET-01185 |  |  | No | 20:42 | Helicopter | REDLANDS | 31 | HC | 2025-10-20 09:41 PDT ¦ 2025-11-03 13:09 PST | 110325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
HUGHSAIRE-SEPULVEDA | ET-01288 | 2026_ET-01288 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.6489 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-22 | 12-11-2025 | Flown | 2026-01-13 | 01-22-2026 | 12-11-2025 |  | 2026_ET-01288_ACQPKG | 2026_ET-01288_GSPKG | Submitted | 2026_ET-01288_GS | 2025-11-08 | Field Complete | 2026_ET-01288_GCPR | 2025-12-01 | Submitted | 2026_ET-01288_ACQ | QC Accepted | 2026_ET-01288_FR | 2025-12-01 | Submitted | 2026_ET-01288_RWR | Submitted | 2025-12-01 | 2026_ET-01288_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01288_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01288_WR | 2026-02-01 | 02-21-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01288_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01288_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01288_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01288_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HUGHSAIRE-SEPULVEDA_ET-01288 |  |  | No | 11:58 | Helicopter | SOUTH BAY | 44 | HC | 2025-11-05 11:43 PST ¦ 2025-11-05 12:02 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LIGHTHIPE-CALDEN-FERNWOOD-SHRED | ET-01886 | 2026_ET-01886 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 14.3777 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-22 | 12-11-2025 | Flown | 2025-10-18 | 01-22-2026 | 12-15-2025 |  | 2026_ET-01886_ACQPKG | 2026_ET-01886_GSPKG | Submitted | 2026_ET-01886_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01886_GCPR | 2025-12-08 | Historical | 2026_ET-01886_ACQ | QC Accepted | 2026_ET-01886_FR | 2025-12-01 | Submitted | 2026_ET-01886_RWR | Submitted | 2025-12-01 | 2026_ET-01886_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-01886_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01886_WR | 2026-02-01 | 02-21-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-01886_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-01886_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-12 | 0 | 2026_ET-01886_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 |  |  |  | 2026_ET-01886_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-CALDEN-FERNWOOD-SHRED_ET-01886 |  |  | No | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 09:37 PDT ¦ 2025-11-05 10:31 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
HINSON-LONG BEACH-STATE STREET | ET-01007 | 2026_ET-01007 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 5.8301 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-10-18 | 01-27-2026 | 12-11-2025 |  | 2026_ET-01007_ACQPKG | 2026_ET-01007_GSPKG | Submitted | 2026_ET-01007_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01007_GCPR | 2025-12-08 | Historical | 2026_ET-01007_ACQ | QC Accepted | 2026_ET-01007_FR | 2025-12-01 | Submitted | 2026_ET-01007_RWR | Submitted | 2025-12-01 | 2026_ET-01007_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01007_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01007_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01007_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01007_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01007_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01007_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HINSON-LONG BEACH-STATE STREET_ET-01007 |  |  | No | 15:38 - 19:28 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 11:29 PDT ¦ 2025-11-05 08:15 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO1 | ET-01250 | 2026_ET-01250 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.8963 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-10-18 | 01-27-2026 | 12-12-2025 |  | 2026_ET-01250_ACQPKG | 2026_ET-01250_GSPKG | Submitted | 2026_ET-01250_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01250_GCPR | 2025-12-08 | Historical | 2026_ET-01250_ACQ | QC Accepted | 2026_ET-01250_FR | 2025-12-01 | Submitted | 2026_ET-01250_RWR | Submitted | 2025-12-01 | 2026_ET-01250_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-01250_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01250_WR | 2026-03-21 | 02-26-2026 | QC Accepted | 04-03-2026 | 2026-03-23 | 0 | 2026_ET-01250_VMLAZ | 2026-03-16 | QC Accepted | 05-15-2026 | 2026-03-23 | 0 | 2026_ET-01250_VMM1 | 2026-03-09 | QC Accepted |  | 05-15-2026 | 2026-03-23 | 0 | 2026_ET-01250_RR | 2026-03-10 | No Violations | 03-24-2026 |  | 0 |  |  |  | 2026_ET-01250_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO1_ET-01250 |  |  | No | 19:28 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:06 PDT ¦ 2025-11-05 11:08 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LAGUNA BELL-FEDERALGEN-FRUITLAND | ET-01289 | 2026_ET-01289 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.016 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-10-26 | 01-27-2026 | 12-11-2025 |  | 2026_ET-01289_ACQPKG | 2026_ET-01289_GSPKG | Submitted | 2026_ET-01289_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01289_GCPR | 2025-12-08 | Historical | 2026_ET-01289_ACQ | QC Accepted | 2026_ET-01289_FR | 2025-12-01 | Submitted | 2026_ET-01289_RWR | Submitted | 2025-12-01 | 2026_ET-01289_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01289_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01289_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01289_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01289_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01289_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01289_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-FEDERALGEN-FRUITLAND_ET-01289 |  |  | No | 15:38 & 20:14 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 09:11 PDT ¦ 2025-10-26 13:55 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
HUGHTRON-TORRANCE-WALTERIA | ET-01302 | 2026_ET-01302 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.1321 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-11-05 | 01-27-2026 | 12-11-2025 |  | 2026_ET-01302_ACQPKG | 2026_ET-01302_GSPKG | Submitted | 2026_ET-01302_GS | 2025-11-08 | Field Complete | 2026_ET-01302_GCPR | 2025-12-01 | Submitted | 2026_ET-01302_ACQ | QC Accepted | 2026_ET-01302_FR | 2025-12-01 | Submitted | 2026_ET-01302_RWR | Submitted | 2025-12-01 | 2026_ET-01302_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01302_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01302_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01302_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01302_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01302_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01302_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HUGHTRON-TORRANCE-WALTERIA_ET-01302 |  |  | No | 19:28 & 18:01 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 12:56 PDT ¦ 2025-11-05 11:12 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
VALLEY-ALESSANDRO-BUNKER | ET-01621 | 2026_ET-01621 |  | 11 | 2026 | Mar 11, 2026 | 115 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 15.4963 | 5.5962 | 36 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-10-16 | 01-27-2026 | 12-11-2025 |  | 2026_ET-01621_ACQPKG | 2026_ET-01621_GSPKG | Submitted | 2026_ET-01621_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01621_GCPR | 2025-12-08 | Historical | 2026_ET-01621_ACQ | QC Accepted | 2026_ET-01621_FR | 2025-11-23 | Submitted | 2026_ET-01621_RWR | Submitted | 2025-11-20 | 2026_ET-01621_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01621_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01621_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01621_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01621_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01621_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01621_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-ALESSANDRO-BUNKER_ET-01621 |  |  | No | 19:13 | Helicopter | MENIFEE | 77 | HC | 2025-10-16 13:20 PDT ¦ 2025-10-16 13:56 PDT | 101625 | 20251016 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
MIRA LOMA-CORONA-PEDLEY | ET-01740 | 2026_ET-01740 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 12.9589 | 3.1416 | 24 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-10-16 | 01-27-2026 | 12-11-2025 |  | 2026_ET-01740_ACQPKG | 2026_ET-01740_GSPKG | Submitted | 2026_ET-01740_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01740_GCPR | 2025-12-08 | Historical | 2026_ET-01740_ACQ | QC Accepted | 2026_ET-01740_FR | 2025-11-23 | Submitted | 2026_ET-01740_RWR | Submitted | 2025-11-23 | 2026_ET-01740_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01740_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01740_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01740_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01740_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01740_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01740_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-CORONA-PEDLEY_ET-01740 |  |  | No | 19:13 | Helicopter | ONTARIO | 34 | HC | 2025-10-16 14:16 PDT ¦ 2025-10-25 13:52 PDT | 101625 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
JOHANNA-CAMDEN-THADDEUS | ET-02007 | 2026_ET-02007 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.8598 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2025-11-05 | 01-27-2026 | 12-12-2025 |  | 2026_ET-02007_ACQPKG | 2026_ET-02007_GSPKG | Submitted | 2026_ET-02007_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02007_GCPR | 2025-12-08 | Historical | 2026_ET-02007_ACQ | QC Accepted | 2026_ET-02007_FR | 2025-11-23 | Submitted | 2026_ET-02007_RWR | Submitted | 2025-11-23 | 2026_ET-02007_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-12 | 0 | 2026_ET-02007_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02007_WR | 2026-02-01 | 02-26-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-02007_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02007_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-02007_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-02007_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | JOHANNA-CAMDEN-THADDEUS_ET-02007 |  |  | No | 18:23 & 14:08 | Helicopter | SANTA ANA | 29 | HC | 2025-11-04 11:25 PST ¦ 2025-11-05 06:54 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
RIO HONDO-VINCENT NO.2 | ET-00707 | 2026_ET-00707 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 32.2081 | 28.7579 | 89 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-04 | 01-29-2026 | 01-29-2026 |  | 2026_ET-00707_ACQPKG | 2026_ET-00707_GSPKG | Submitted | 2026_ET-00707_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00707_GCPR | 2025-12-08 | Historical | 2026_ET-00707_ACQ | QC Accepted | 2026_ET-00707_FR | 2025-11-27 | Submitted | 2026_ET-00707_RWR | Submitted | 2025-11-27 | 2026_ET-00707_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-29 |  | 2026_ET-00707_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00707_WR | 2026-03-24 | 02-28-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00707_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00707_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00707_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00707_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-VINCENT NO.2_ET-00707 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | 2025-10-23 08:58 PDT ¦ 2025-11-04 11:09 PST | 110325 | 20251104 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BAILEY-NEENACH-WESTPAC | ET-00827 | 2026_ET-00827 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 21.5195 | 15.5189 | 72 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-29 | 01-01-2026 | Flown | 2025-11-07 | 01-29-2026 | 01-24-2026 |  | 2026_ET-00827_ACQPKG | 2026_ET-00827_GSPKG | Submitted | 2026_ET-00827_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00827_GCPR | 2025-12-08 | Historical | 2026_ET-00827_ACQ | QC Accepted | 2026_ET-00827_FR | 2025-11-27 | Submitted | 2026_ET-00827_RWR | Submitted | 2025-11-27 | 2026_ET-00827_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-24 |  | 2026_ET-00827_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00827_WR | 2026-03-24 | 02-28-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00827_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00827_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00827_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00827_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BAILEY-NEENACH-WESTPAC_ET-00827 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-11-07 08:26 PST ¦ 2025-11-07 09:01 PST | 110725 | 20251107 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALESSANDRO-HIGHGROVE-MAXWELL | ET-01281 | 2026_ET-01281 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 13.2483 | 4.2101 | 32 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-29 | 01-01-2026 | Flown | 2025-10-23 | 01-29-2026 | 01-13-2026 |  | 2026_ET-01281_ACQPKG | 2026_ET-01281_GSPKG | Submitted | 2026_ET-01281_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01281_GCPR | 2025-12-08 | Historical | 2026_ET-01281_ACQ | QC Accepted | 2026_ET-01281_FR | 2026-01-01 | Submitted | 2026_ET-01281_RWR | Submitted | 2026-01-01 | 2026_ET-01281_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01281_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01281_WR | 2026-02-18 | 02-28-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01281_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01281_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01281_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01281_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ALESSANDRO-HIGHGROVE-MAXWELL_ET-01281 | Done |  | No | 15:40 |  | MENIFEE | 77 | UNK | 2025-10-16 13:52 PDT ¦ 2025-11-21 14:01 PST | 102325 | 20251121 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-VINCENT NO. 1 | ET-01905 | 2026_ET-01905 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 17.4365 | 15.1438 | 87 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-07 | 01-29-2026 | 01-29-2026 |  | 2026_ET-01905_ACQPKG | 2026_ET-01905_GSPKG | Submitted | 2026_ET-01905_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01905_GCPR | 2025-12-08 | Historical | 2026_ET-01905_ACQ | QC Accepted | 2026_ET-01905_FR | 2025-11-27 | Submitted | 2026_ET-01905_RWR | Submitted | 2025-11-27 | 2026_ET-01905_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-29 |  | 2026_ET-01905_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01905_WR | 2026-03-24 | 02-28-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01905_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01905_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01905_RR | 2026-03-22 | No Violations | 03-20-2026 |  | 3 | 2026-03-23 | 0 | 0 | 2026_ET-01905_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-VINCENT NO. 1_ET-01905 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-19 12:37 PDT ¦ 2025-11-07 13:08 PST | 110725 | 20251107 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BANDUCCI-CORRECTION-CUMMINGS | ET-02156 | 2026_ET-02156 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.5613 | 6.5613 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-29 | 01-01-2026 | Flown | 2025-11-02 | 01-29-2026 | 01-22-2026 |  | 2026_ET-02156_ACQPKG | 2026_ET-02156_GSPKG | Submitted | 2026_ET-02156_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02156_GCPR | 2025-12-08 | Historical | 2026_ET-02156_ACQ | QC Accepted | 2026_ET-02156_FR | 2025-11-27 | Submitted | 2026_ET-02156_RWR | Submitted | 2025-11-27 | 2026_ET-02156_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-22 |  | 2026_ET-02156_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02156_WR | 2026-03-24 | 02-28-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-02156_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02156_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02156_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-02156_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BANDUCCI-CORRECTION-CUMMINGS_ET-02156 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-11-02 10:54 PST ¦ 2025-11-02 11:07 PST | 110225 | 20251102 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MAGUNDEN-SPRINGVILLE NO. 1 | ET-07239 | 2026_ET-07239 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 52.0874 | 40.8426 | 78 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 12-11-2025 | Flown | 2025-10-13 | 01-29-2026 | 01-29-2026 |  | 2026_ET-07239_ACQPKG | 2026_ET-07239_GSPKG | Submitted | 2026_ET-07239_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07239_GCPR | 2025-12-08 | Historical | 2026_ET-07239_ACQ | QC Accepted | 2026_ET-07239_FR | 2025-11-13 | Submitted | 2026_ET-07239_RWR | Submitted | 2025-11-13 | 2026_ET-07239_CLAZ | 2026-01-27 | QC Accepted | 02-10-2026 | 2026-01-29 | 1 | 2026_ET-07239_PROCPKG | In Progress | All Good - Complete | 2026_ET-07239_WR | 2026-02-11 | 02-28-2026 | QC Accepted | 02-25-2026 | 2026-02-25 | 0 | 2026_ET-07239_VMLAZ | 2026-03-05 | QC Accepted |  | 2026-03-19 | 1 | 2026_ET-07239_VMM1 | 2026-02-11 | QC Rejected |  |  | 2026-03-04 | 1 | 2026_ET-07239_RR | 2026-03-18 | No Violations |  |  | 9 | 2026-03-27 | 0 |  | 2026_ET-07239_VER | 2026-02-11 | Contested |  | 2026-05-11 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | MAGUNDEN-SPRINGVILLE NO. 1_ET-07239 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-13 09:13 PDT ¦ 2025-10-13 12:08 PDT | 101325 | 20251013 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MAGUNDEN-SPRINGVILLE NO. 2 | ET-07240 | 2026_ET-07240 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 52.0903 | 40.8672 | 78 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-08 | 12-11-2025 | Flown | 2025-10-13 | 01-29-2026 | 01-29-2026 |  | 2026_ET-07240_ACQPKG | 2026_ET-07240_GSPKG | Submitted | 2026_ET-07240_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07240_GCPR | 2025-12-08 | Historical | 2026_ET-07240_ACQ | QC Accepted | 2026_ET-07240_FR | 2025-11-13 | Submitted | 2026_ET-07240_RWR | Submitted | 2025-11-13 | 2026_ET-07240_CLAZ | 2026-01-27 | QC Accepted | 02-10-2026 | 2026-01-29 | 1 | 2026_ET-07240_PROCPKG | In Progress | All Good - Complete | 2026_ET-07240_WR | 2026-02-11 | 02-28-2026 | QC Accepted | 02-25-2026 | 2026-02-25 | 0 | 2026_ET-07240_VMLAZ | 2026-03-16 | QC Accepted |  | 2026-03-23 | 0 | 2026_ET-07240_VMM1 | 2026-02-11 | QC Rejected |  |  | 2026-03-30 | 1 | 2026_ET-07240_RR | 2026-03-18 | No Violations |  |  | 1 | 2026-03-27 | 0 |  | 2026_ET-07240_VER | 2026-04-17 | Uploaded to S123 |  | 2026-04-27 | 2 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | MAGUNDEN-SPRINGVILLE NO. 2_ET-07240 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2025-10-13 09:13 PDT ¦ 2025-10-13 12:08 PDT | 101325 | 20251013 |  |  |  |  | Attribute - Latitude, Attribute - Longitude | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CLEMENTINE-MENTONE-PUREWATER | ET-00023 | 2026_ET-00023 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.0518 | 0.66325 | 13 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-22 | 01-30-2026 | 01-08-2026 |  | 2026_ET-00023_ACQPKG | 2026_ET-00023_GSPKG | Submitted | 2026_ET-00023_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00023_GCPR | 2025-12-08 | Historical | 2026_ET-00023_ACQ | QC Accepted | 2026_ET-00023_FR | 2026-01-01 | Submitted | 2026_ET-00023_RWR | Submitted | 2026-01-01 | 2026_ET-00023_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00023_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00023_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00023_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00023_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00023_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00023_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CLEMENTINE-MENTONE-PUREWATER_ET-00023 |  |  | No | 19:43 |  | REDLANDS | 31 | UNK | 2025-10-22 13:36 PDT ¦ 2025-10-22 13:56 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-SANTA FE SPRINGS-SIGGEN | ET-00028 | 2026_ET-00028 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.9594 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-03 | 01-30-2026 | 01-12-2026 |  | 2026_ET-00028_ACQPKG | 2026_ET-00028_GSPKG | Submitted | 2026_ET-00028_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00028_GCPR | 2025-12-08 | Historical | 2026_ET-00028_ACQ | QC Accepted | 2026_ET-00028_FR | 2026-01-01 | Submitted | 2026_ET-00028_RWR | Submitted | 2026-01-01 | 2026_ET-00028_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-00028_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00028_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00028_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00028_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00028_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00028_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-SANTA FE SPRINGS-SIGGEN_ET-00028 |  |  | No | 20:14 |  | WHITTIER | 47 | UNK | 2025-10-18 10:22 PDT ¦ 2025-11-03 15:08 PST | 110325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOLSA-OCEANVIEW-TRASK | ET-00457 | 2026_ET-00457 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.5912 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-24 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00457_ACQPKG | 2026_ET-00457_GSPKG | Submitted | 2026_ET-00457_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00457_GCPR | 2025-12-08 | Historical | 2026_ET-00457_ACQ | QC Accepted | 2026_ET-00457_FR | 2026-01-01 | Submitted | 2026_ET-00457_RWR | Submitted | 2026-01-01 | 2026_ET-00457_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00457_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00457_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00457_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00457_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00457_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00457_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BOLSA-OCEANVIEW-TRASK_ET-00457 | Done |  | No | 19:56 |  | HUNTINGTON BEACH | 33 | UNK | 2025-10-24 13:54 PDT ¦ 2025-11-03 15:53 PST | 102425 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE U.S. RUBBER-WHITEWALL | ET-00640 | 2026_ET-00640 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.66126 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-26 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00640_ACQPKG | 2026_ET-00640_GSPKG | Submitted | 2026_ET-00640_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00640_GCPR | 2025-12-08 | Historical | 2026_ET-00640_ACQ | QC Accepted | 2026_ET-00640_FR | 2026-01-01 | Submitted | 2026_ET-00640_RWR | Submitted | 2026-01-01 | 2026_ET-00640_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00640_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00640_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00640_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00640_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00640_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00640_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE U.S. RUBBER-WHITEWALL_ET-00640 |  |  | No | 20:14 |  | MONTEBELLO | 22 | UNK | 2025-10-18 09:07 PDT ¦ 2025-10-26 13:38 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CARMENITA-LA MIRADA | ET-00730 | 2026_ET-00730 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.44878 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-26 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00730_ACQPKG | 2026_ET-00730_GSPKG | Submitted | 2026_ET-00730_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00730_GCPR | 2025-12-08 | Historical | 2026_ET-00730_ACQ | QC Accepted | 2026_ET-00730_FR | 2026-01-01 | Submitted | 2026_ET-00730_RWR | Submitted | 2026-01-01 | 2026_ET-00730_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00730_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00730_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00730_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00730_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00730_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00730_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CARMENITA-LA MIRADA_ET-00730 |  |  | No | 20:14 |  | WHITTIER | 47 | UNK | 2025-10-26 14:29 PDT ¦ 2025-10-26 14:37 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LIGHTHIPE-ALON-STAUFFER | ET-00752 | 2026_ET-00752 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.302 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-05 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00752_ACQPKG | 2026_ET-00752_GSPKG | Submitted | 2026_ET-00752_GS | 2025-11-08 | Field Complete | 2026_ET-00752_GCPR | 2026-01-01 | Submitted | 2026_ET-00752_ACQ | QC Accepted | 2026_ET-00752_FR | 2026-01-01 | Submitted | 2026_ET-00752_RWR | Submitted | 2026-01-01 | 2026_ET-00752_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00752_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00752_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00752_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00752_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00752_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00752_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LIGHTHIPE-ALON-STAUFFER_ET-00752 |  |  | No | 21:40 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-10-18 11:14 PDT ¦ 2025-11-05 10:15 PST | 102425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BARRE-FULLERTON NO.2 | ET-00877 | 2026_ET-00877 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.36104 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00877_ACQPKG | 2026_ET-00877_GSPKG | Submitted | 2026_ET-00877_GS | 2025-11-08 | Field Complete | 2026_ET-00877_GCPR | 2026-01-01 | Submitted | 2026_ET-00877_ACQ | QC Accepted | 2026_ET-00877_FR | 2026-01-01 | Submitted | 2026_ET-00877_RWR | Submitted | 2026-01-01 | 2026_ET-00877_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00877_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00877_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00877_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00877_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00877_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00877_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE BARRE-FULLERTON NO.2_ET-00877 |  |  | No | 20:32 |  |  |  | UNK | 2025-10-23 14:32 PDT ¦ 2025-10-23 14:33 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BARRE-LAMPSON NO.2 | ET-00878 | 2026_ET-00878 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.2495 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-09-2026 |  | 2026_ET-00878_ACQPKG | 2026_ET-00878_GSPKG | Submitted | 2026_ET-00878_GS | 2025-11-08 | Field Complete | 2026_ET-00878_GCPR | 2026-01-01 | Submitted | 2026_ET-00878_ACQ | QC Accepted | 2026_ET-00878_FR | 2026-01-01 | Submitted | 2026_ET-00878_RWR | Submitted | 2026-01-01 | 2026_ET-00878_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00878_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00878_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00878_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00878_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00878_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00878_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE BARRE-LAMPSON NO.2_ET-00878 |  |  | No | 20:32 |  | SANTA ANA | 29 | UNK | 2025-10-23 14:29 PDT ¦ 2025-10-23 14:54 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-FILLMORE-SNTA CLRA-WAKEFIELD | ET-01098 | 2026_ET-01098 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 18.8676 | 9.8239 | 52 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-12-08 | 01-30-2026 | 01-09-2026 |  | 2026_ET-01098_ACQPKG | 2026_ET-01098_GSPKG | Submitted | 2026_ET-01098_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01098_GCPR | 2025-12-08 | Historical | 2026_ET-01098_ACQ | QC Accepted | 2026_ET-01098_FR | 2026-01-01 | Submitted | 2026_ET-01098_RWR | Submitted | 2026-01-01 | 2026_ET-01098_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01098_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01098_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01098_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01098_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01098_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 53 | 2026-03-23 | 33 | 20 | 2026_ET-01098_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-FILLMORE-SNTA CLRA-WAKEFIELD_ET-01098 |  |  | No | 21:10 & 17:13 |  | VENTURA | 39 | UNK | 2025-10-27 15:23 PDT ¦ 2025-10-29 10:31 PDT | 102725 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VILLA PARK-ORANGE NO. 1 | ET-01146 | 2026_ET-01146 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.11725 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-09-2026 |  | 2026_ET-01146_ACQPKG | 2026_ET-01146_GSPKG | Submitted | 2026_ET-01146_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01146_GCPR | 2025-12-08 | Historical | 2026_ET-01146_ACQ | QC Accepted | 2026_ET-01146_FR | 2026-01-01 | Submitted | 2026_ET-01146_RWR | Submitted | 2026-01-01 | 2026_ET-01146_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01146_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01146_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01146_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01146_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01146_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01146_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE VILLA PARK-ORANGE NO. 1_ET-01146 |  |  | No | 20:32 |  | SANTA ANA | 29 | UNK | 2025-10-23 14:29 PDT ¦ 2025-10-23 14:55 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VILLA PARK-CANYON-YORBA LINDA | ET-01147 | 2026_ET-01147 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.99769 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-09-2026 |  | 2026_ET-01147_ACQPKG | 2026_ET-01147_GSPKG | Submitted | 2026_ET-01147_GS | 2025-11-08 | Field Complete | 2026_ET-01147_GCPR | 2026-01-01 | Submitted | 2026_ET-01147_ACQ | QC Accepted | 2026_ET-01147_FR | 2026-01-01 | Submitted | 2026_ET-01147_RWR | Submitted | 2026-01-01 | 2026_ET-01147_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01147_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01147_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01147_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01147_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01147_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01147_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE VILLA PARK-CANYON-YORBA LINDA_ET-01147 |  |  | No | 20:32 |  | SANTA ANA | 29 | UNK | 2025-10-23 14:35 PDT ¦ 2025-10-25 14:26 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ASTRO-CERTIFIED-SIGNAL HILL-SUNNYSIDE | ET-01156 | 2026_ET-01156 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.1612 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-05 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01156_ACQPKG | 2026_ET-01156_GSPKG | Submitted | 2026_ET-01156_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01156_GCPR | 2025-12-08 | Historical | 2026_ET-01156_ACQ | QC Accepted | 2026_ET-01156_FR | 2026-01-01 | Submitted | 2026_ET-01156_RWR | Submitted | 2026-01-01 | 2026_ET-01156_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01156_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01156_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01156_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01156_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01156_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01156_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ASTRO-CERTIFIED-SIGNAL HILL-SUNNYSIDE_ET-01156 | Done |  | No | 14:08 |  | LONG BEACH | 46 | UNK | 2025-11-05 07:48 PST ¦ 2025-11-05 07:55 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ETIWANDA-BAIN-DECLEZ-REBAR | ET-01177 | 2026_ET-01177 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.35201 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-20 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01177_ACQPKG | 2026_ET-01177_GSPKG | Submitted | 2026_ET-01177_GS | 2025-11-08 | Field Complete | 2026_ET-01177_GCPR | 2026-01-01 | Submitted | 2026_ET-01177_ACQ | QC Accepted | 2026_ET-01177_FR | 2026-01-01 | Submitted | 2026_ET-01177_RWR | Submitted | 2026-01-01 | 2026_ET-01177_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01177_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01177_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01177_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01177_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01177_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01177_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ETIWANDA-BAIN-DECLEZ-REBAR_ET-01177 |  |  | No | 15:52 |  | FOOTHILL | 30 | UNK | 2025-10-20 09:55 PDT ¦ 2025-10-21 10:36 PDT | 102025 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOWL-LOS CERRITOS-SIGNAL HILL | ET-01233 | 2026_ET-01233 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.7291 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-05 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01233_ACQPKG | 2026_ET-01233_GSPKG | Submitted | 2026_ET-01233_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01233_GCPR | 2025-12-08 | Historical | 2026_ET-01233_ACQ | QC Accepted | 2026_ET-01233_FR | 2026-01-01 | Submitted | 2026_ET-01233_RWR | Submitted | 2026-01-01 | 2026_ET-01233_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01233_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01233_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01233_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01233_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01233_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01233_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BOWL-LOS CERRITOS-SIGNAL HILL_ET-01233 | Done |  | No | 14:08 |  | LONG BEACH | 46 | UNK | 2025-10-18 11:20 PDT ¦ 2025-11-05 07:54 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ALESSANDRO-AULD-CAJALCO-SKYLARK | ET-01321 | 2026_ET-01321 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.47057 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01321_ACQPKG | 2026_ET-01321_GSPKG | Submitted | 2026_ET-01321_GS | 2025-11-08 | Field Complete | 2026_ET-01321_GCPR | 2026-01-01 | Submitted | 2026_ET-01321_ACQ | QC Accepted | 2026_ET-01321_FR | 2026-01-01 | Submitted | 2026_ET-01321_RWR | Submitted | 2026-01-01 | 2026_ET-01321_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01321_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01321_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01321_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01321_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01321_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01321_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ALESSANDRO-AULD-CAJALCO-SKYLARK_ET-01321 |  |  | No | 15:40 |  | MENIFEE | 77 | UNK | 2025-10-23 10:51 PDT ¦ 2025-10-23 10:52 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VALLEY-AULD-SKYLARK | ET-01379 | 2026_ET-01379 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.54391 | 0.061567 | 11 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-23 | 01-30-2026 | 01-09-2026 |  | 2026_ET-01379_ACQPKG | 2026_ET-01379_GSPKG | Submitted | 2026_ET-01379_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01379_GCPR | 2025-12-08 | Historical | 2026_ET-01379_ACQ | QC Accepted | 2026_ET-01379_FR | 2026-01-01 | Submitted | 2026_ET-01379_RWR | Submitted | 2026-01-01 | 2026_ET-01379_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01379_PROCPKG | Submitted | All Good - Complete | 2026_ET-01379_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01379_VMLAZ | 2026-04-30 | QC Accepted | 05-14-2026 | 2026-05-07 | 3 | 2026_ET-01379_VMM1 | 2026-02-18 | QC Accepted |  | 05-14-2026 | 2026-03-04 | 0 | 2026_ET-01379_RR | 2026-03-10 | Violations Detected | 03-05-2026 | 03-11-2026 | 1 |  |  |  | 2026_ET-01379_VER | 2026-02-18 | Uploaded to S123 | 05-14-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE VALLEY-AULD-SKYLARK_ET-01379 |  |  | No | 20:21 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 101625 | 20251103 |  |  | Classification of vegetation or ground warrants rejection, impacting encroachment report. |  |  |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARSON-DOMHILL-NOLA-RALPHS | ET-01624 | 2026_ET-01624 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8434 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2026-01-09 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01624_ACQPKG | 2026_ET-01624_GSPKG | Submitted | 2026_ET-01624_GS | 2025-11-08 | Field Complete | 2026_ET-01624_GCPR | 2026-01-01 | Submitted | 2026_ET-01624_ACQ | QC Accepted | 2026_ET-01624_FR | 2026-01-01 | Submitted | 2026_ET-01624_RWR | Submitted | 2026-01-01 | 2026_ET-01624_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01624_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01624_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-17 | 0 | 2026_ET-01624_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01624_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01624_RR | 2026-03-09 | No Violations | 03-18-2026 |  | 0 |  |  |  | 2026_ET-01624_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CARSON-DOMHILL-NOLA-RALPHS_ET-01624 | Done |  | No | 18:01 & 21:40 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-10-24 10:13 PDT ¦ 2025-11-05 12:26 PST | 102425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ANTELOPE-CAL CEMENT | ET-01795 | 2026_ET-01795 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.5281 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-02 | 01-30-2026 | 01-28-2026 |  | 2026_ET-01795_ACQPKG | 2026_ET-01795_GSPKG | Submitted | 2026_ET-01795_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01795_GCPR | 2025-12-08 | Historical | 2026_ET-01795_ACQ | QC Accepted | 2026_ET-01795_FR | 2025-11-27 | Submitted | 2026_ET-01795_RWR | Submitted | 2025-11-27 | 2026_ET-01795_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-28 |  | 2026_ET-01795_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01795_WR | 2026-03-24 | 03-01-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01795_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01795_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01795_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01795_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ANTELOPE-CAL CEMENT_ET-01795 |  |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-11-02 11:41 PST ¦ 2025-11-02 11:43 PST | 110225 | 20251102 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-VINCENT NO. 2 | ET-01906 | 2026_ET-01906 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 17.4396 | 15.2257 | 87 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-07 | 01-30-2026 | 01-30-2026 |  | 2026_ET-01906_ACQPKG | 2026_ET-01906_GSPKG | Submitted | 2026_ET-01906_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01906_GCPR | 2025-12-08 | Historical | 2026_ET-01906_ACQ | QC Accepted | 2026_ET-01906_FR | 2025-11-27 | Submitted | 2026_ET-01906_RWR | Submitted | 2025-11-27 | 2026_ET-01906_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-30 |  | 2026_ET-01906_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01906_WR | 2026-03-24 | 03-01-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01906_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01906_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01906_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01906_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-VINCENT NO. 2_ET-01906 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-19 12:35 PDT ¦ 2025-11-07 13:07 PST | 110725 | 20251107 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LA FRESA - VICTORIA | ET-01924 | 2026_ET-01924 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.69717 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-18 | 01-30-2026 | 01-13-2026 |  | 2026_ET-01924_ACQPKG | 2026_ET-01924_GSPKG | Submitted | 2026_ET-01924_GS | 2025-11-08 | Field Complete | 2026_ET-01924_GCPR | 2026-01-01 | Submitted | 2026_ET-01924_ACQ | QC Accepted | 2026_ET-01924_FR | 2026-01-01 | Submitted | 2026_ET-01924_RWR | Submitted | 2026-01-01 | 2026_ET-01924_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01924_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01924_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01924_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01924_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01924_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01924_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LA FRESA - VICTORIA_ET-01924 |  |  | No | 19:28 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:25 PDT ¦ 2025-11-05 12:18 PST | 101825 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LUGO-MIRA LOMA (TEMP TAP LINE) | ET-01964 | 2026_ET-01964 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.2451 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-21 | 01-30-2026 | 01-09-2026 |  | 2026_ET-01964_ACQPKG | 2026_ET-01964_GSPKG | Submitted | 2026_ET-01964_GS | 2025-11-08 | Field Complete | 2026_ET-01964_GCPR | 2026-01-01 | Submitted | 2026_ET-01964_ACQ | QC Accepted | 2026_ET-01964_FR | 2026-01-01 | Submitted | 2026_ET-01964_RWR | Submitted | 2026-01-01 | 2026_ET-01964_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01964_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01964_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01964_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01964_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01964_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01964_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LUGO-MIRA LOMA (TEMP TAP LINE)_ET-01964 |  |  | No | 15:48 |  | FOOTHILL | 30 | UNK | 2025-10-21 10:02 PDT ¦ 2025-10-21 10:17 PDT | 102125 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEL AMO-LIGHTHIPE-CARMENITA | ET-02017 | 2026_ET-02017 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.4275 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-26 | 01-30-2026 | 01-13-2026 |  | 2026_ET-02017_ACQPKG | 2026_ET-02017_GSPKG | Submitted | 2026_ET-02017_GS | 2025-11-08 | Field Complete | 2026_ET-02017_GCPR | 2026-01-01 | Submitted | 2026_ET-02017_ACQ | QC Accepted | 2026_ET-02017_FR | 2026-01-01 | Submitted | 2026_ET-02017_RWR | Submitted | 2026-01-01 | 2026_ET-02017_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-02017_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02017_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-02017_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02017_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02017_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-02017_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE DEL AMO-LIGHTHIPE-CARMENITA_ET-02017 |  |  | No | 20:14 |  | LONG BEACH | 46 | UNK | 2025-10-18 10:33 PDT ¦ 2025-10-26 14:12 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE KERN RIVER 1-MACNEIL | ET-02042 | 2026_ET-02042 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.745 | 7.745 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-28 | 01-30-2026 | 01-13-2026 |  | 2026_ET-02042_ACQPKG | 2026_ET-02042_GSPKG | Submitted | 2026_ET-02042_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02042_GCPR | 2025-12-08 | Historical | 2026_ET-02042_ACQ | QC Accepted | 2026_ET-02042_FR | 2026-01-01 | Submitted | 2026_ET-02042_RWR | Submitted | 2026-01-01 | 2026_ET-02042_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-02042_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02042_WR | 2026-03-12 | 03-01-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-02042_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02042_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02042_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 12 | 2026-03-23 | 4 | 8 | 2026_ET-02042_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE KERN RIVER 1-MACNEIL_ET-02042 |  |  | No | 16:16 |  | VALENCIA | 59 | UNK | 2025-10-28 10:07 PDT ¦ 2025-10-28 10:43 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VICTOR-AQUEDUCT-PHELAN | ET-02100 | 2026_ET-02100 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.2847 | 4.39 | 60 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-31 | 01-30-2026 | 01-21-2026 |  | 2026_ET-02100_ACQPKG | 2026_ET-02100_GSPKG | Submitted | 2026_ET-02100_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02100_GCPR | 2025-12-08 | Historical | 2026_ET-02100_ACQ | QC Accepted | 2026_ET-02100_FR | 2025-11-27 | Submitted | 2026_ET-02100_RWR | Submitted | 2025-11-27 | 2026_ET-02100_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-21 |  | 2026_ET-02100_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02100_WR | 2026-03-24 | 03-01-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-02100_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02100_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02100_RR | 2026-03-18 | No Violations | 03-20-2026 |  | 4 | 2026-03-27 | 0 |  | 2026_ET-02100_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE VICTOR-AQUEDUCT-PHELAN_ET-02100 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 11:37 PDT ¦ 2025-10-31 12:18 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VICTOR-APPLE VALLEY-HESPERIA | ET-02148 | 2026_ET-02148 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.686 | 4.3232 | 56 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-31 | 01-30-2026 | 01-21-2026 |  | 2026_ET-02148_ACQPKG | 2026_ET-02148_GSPKG | Submitted | 2026_ET-02148_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02148_GCPR | 2025-12-08 | Historical | 2026_ET-02148_ACQ | QC Accepted | 2026_ET-02148_FR | 2025-11-27 | Submitted | 2026_ET-02148_RWR | Submitted | 2025-11-27 | 2026_ET-02148_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-21 |  | 2026_ET-02148_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02148_WR | 2026-03-24 | 03-01-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-02148_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02148_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02148_RR | 2026-03-18 | No Violations | 03-20-2026 |  | 13 | 2026-03-27 | 0 |  | 2026_ET-02148_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE VICTOR-APPLE VALLEY-HESPERIA_ET-02148 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 11:01 PDT ¦ 2025-10-31 12:18 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SPRINGVILLE-TULE RIVER | ET-02165 | 2026_ET-02165 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_4 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.2376 | 7.2376 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-12-13 | 01-30-2026 | 01-22-2026 |  | 2026_ET-02165_ACQPKG | 2026_ET-02165_GSPKG | Submitted | 2026_ET-02165_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02165_GCPR | 2025-12-08 | Historical | 2026_ET-02165_ACQ | QC Accepted | 2026_ET-02165_FR | 2026-01-09 | Submitted | 2026_ET-02165_RWR | Submitted | 2026-01-09 | 2026_ET-02165_CLAZ | 2026-01-09 | QC Accepted | 01-23-2026 | 2026-01-22 |  | 2026_ET-02165_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02165_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-02-25 | 0 | 2026_ET-02165_VMLAZ | 2026-02-18 | QC Accepted | 03-15-2026 | 2026-03-02 | 0 | 2026_ET-02165_VMM1 | 2026-02-18 | QC Accepted |  | 03-15-2026 | 2026-03-02 | 0 | 2026_ET-02165_RR | 2026-02-18 | No Violations | 03-03-2026 |  | 3 |  |  |  | 2026_ET-02165_VER | 2026-03-01 | Uploaded to S123 | 03-15-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed Late - Program | IDLE SPRINGVILLE-TULE RIVER_ET-02165 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-13 14:37 PST ¦ 2025-12-13 14:59 PST | 121325 | 20251213 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 3-MAMMOTH | ET-04870 | 2026_ET-04870 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_3 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.6665 | 6.6665 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-08 | 01-30-2026 | 01-30-2026 |  | 2026_ET-04870_ACQPKG | 2026_ET-04870_GSPKG | Submitted | 2026_ET-04870_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04870_GCPR | 2025-12-08 | Historical | 2026_ET-04870_ACQ | QC Accepted | 2026_ET-04870_FR | 2025-11-27 | Submitted | 2026_ET-04870_RWR | Submitted | 2025-11-27 | 2026_ET-04870_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-30 |  | 2026_ET-04870_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04870_WR | 2026-02-18 | 03-01-2026 | QC Accepted | 03-04-2026 | 2026-02-25 | 0 | 2026_ET-04870_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-02 | 0 | 2026_ET-04870_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-02 | 0 | 2026_ET-04870_RR | 2026-02-18 | No Violations | 03-03-2026 |  | 0 |  |  |  | 2026_ET-04870_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BIG CREEK 3-MAMMOTH_ET-04870 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-11-08 09:40 PST ¦ 2025-11-08 10:29 PST | 110825 | 20251108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAL CEMENT-WINDPARKS | ET-00058 | 2026_ET-00058 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.2134 | 5.7369 | 70 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-02 | 02-01-2026 | 01-21-2026 |  | 2026_ET-00058_ACQPKG | 2026_ET-00058_GSPKG | Submitted | 2026_ET-00058_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00058_GCPR | 2025-12-08 | Historical | 2026_ET-00058_ACQ | QC Accepted | 2026_ET-00058_FR | 2025-11-27 | Submitted | 2026_ET-00058_RWR | Submitted | 2025-11-27 | 2026_ET-00058_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-21 |  | 2026_ET-00058_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00058_WR | 2026-03-24 | 03-03-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00058_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00058_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00058_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00058_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CAL CEMENT-WINDPARKS_ET-00058 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-11-02 11:17 PST ¦ 2025-11-02 11:38 PST | 110225 | 20251102 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAKEVIEW-MOVAL | ET-00069 | 2026_ET-00069 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.9494 | 8.1821 | 75 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-23 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00069_ACQPKG | 2026_ET-00069_GSPKG | Submitted | 2026_ET-00069_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00069_GCPR | 2025-12-08 | Historical | 2026_ET-00069_ACQ | QC Accepted | 2026_ET-00069_FR | 2026-01-01 | Submitted | 2026_ET-00069_RWR | Submitted | 2026-01-01 | 2026_ET-00069_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00069_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00069_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00069_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00069_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00069_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00069_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAKEVIEW-MOVAL_ET-00069 |  |  | No | 15:40 - 19:23 |  | MENIFEE | 77 | UNK | 2025-10-23 10:31 PDT ¦ 2025-10-23 13:41 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-LAKEVIEW | ET-00070 | 2026_ET-00070 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.6657 | 6.0515 | 79 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-23 | 02-01-2026 | 01-14-2026 |  | 2026_ET-00070_ACQPKG | 2026_ET-00070_GSPKG | Submitted | 2026_ET-00070_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00070_GCPR | 2025-12-08 | Historical | 2026_ET-00070_ACQ | QC Accepted | 2026_ET-00070_FR | 2026-01-01 | Submitted | 2026_ET-00070_RWR | Submitted | 2026-01-01 | 2026_ET-00070_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-00070_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00070_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00070_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00070_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00070_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00070_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-LAKEVIEW_ET-00070 |  |  | No | 19:23 |  | MENIFEE | 77 | UNK | 2025-10-16 13:32 PDT ¦ 2025-10-23 13:15 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-ROADWAY | ET-00200 | 2026_ET-00200 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.2023 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-31 | 02-01-2026 | 01-22-2026 |  | 2026_ET-00200_ACQPKG | 2026_ET-00200_GSPKG | Submitted | 2026_ET-00200_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00200_GCPR | 2025-12-08 | Historical | 2026_ET-00200_ACQ | QC Accepted | 2026_ET-00200_FR | 2025-11-27 | Submitted | 2026_ET-00200_RWR | Submitted | 2025-11-27 | 2026_ET-00200_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-22 |  | 2026_ET-00200_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00200_WR | 2026-03-24 | 03-03-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00200_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00200_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00200_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00200_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-30 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-ROADWAY_ET-00200 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 10:08 PDT ¦ 2025-10-31 12:09 PDT | 103125 | 20251031 | Attribute - Air Temp |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-REDONDO | ET-00219 | 2026_ET-00219 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 14.1238 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Does Not exist | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-18 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00219_ACQPKG | 2026_ET-00219_GSPKG | Submitted | 2026_ET-00219_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00219_GCPR | 2025-12-08 | Historical | 2026_ET-00219_ACQ | QC Accepted | 2026_ET-00219_FR | 2026-01-01 | Submitted | 2026_ET-00219_RWR | Submitted | 2026-01-01 | 2026_ET-00219_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00219_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00219_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00219_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00219_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00219_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00219_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-REDONDO_ET-00219 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-10-18 10:53 PDT ¦ 2025-11-05 12:23 PST | 102425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOULD-LA CANADA | ET-00381 | 2026_ET-00381 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.0276 | 2.0276 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-04 | 02-01-2026 | 01-13-2026 |  | 2026_ET-00381_ACQPKG | 2026_ET-00381_GSPKG | Submitted | 2026_ET-00381_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00381_GCPR | 2025-12-08 | Historical | 2026_ET-00381_ACQ | QC Accepted | 2026_ET-00381_FR | 2025-11-27 | Submitted | 2026_ET-00381_RWR | Submitted | 2025-11-27 | 2026_ET-00381_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-13 |  | 2026_ET-00381_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00381_WR | 2026-03-24 | 03-03-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00381_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00381_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00381_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00381_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOULD-LA CANADA_ET-00381 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-11-04 14:11 PST ¦ 2025-11-04 14:17 PST | 110425 | 20251104 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-FREMONT-JERSEY | ET-00443 | 2026_ET-00443 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.6745 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-08-2026 |  | 2026_ET-00443_ACQPKG | 2026_ET-00443_GSPKG | Submitted | 2026_ET-00443_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00443_GCPR | 2025-12-08 | Historical | 2026_ET-00443_ACQ | QC Accepted | 2026_ET-00443_FR | 2026-01-01 | Submitted | 2026_ET-00443_RWR | Submitted | 2026-01-01 | 2026_ET-00443_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00443_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00443_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00443_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00443_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00443_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00443_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-FREMONT-JERSEY_ET-00443 |  |  | No | 18:01 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-10-18 10:54 PDT ¦ 2025-11-05 10:47 PST | 102425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-TALBERT NO. 1 | ET-00448 | 2026_ET-00448 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.9589 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-04 | 02-01-2026 | 01-08-2026 |  | 2026_ET-00448_ACQPKG | 2026_ET-00448_GSPKG | Submitted | 2026_ET-00448_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00448_GCPR | 2025-12-08 | Historical | 2026_ET-00448_ACQ | QC Accepted | 2026_ET-00448_FR | 2026-01-01 | Submitted | 2026_ET-00448_RWR | Submitted | 2026-01-01 | 2026_ET-00448_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00448_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00448_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00448_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00448_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00448_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00448_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-TALBERT NO. 1_ET-00448 |  |  | No | 18:23 |  | HUNTINGTON BEACH | 33 | UNK | 2025-11-04 10:53 PST ¦ 2025-11-04 11:39 PST | 110425 | 20251104 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ORANGE-WASHINGTON | ET-00524 | 2026_ET-00524 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.5625 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-23 | 02-01-2026 | 01-08-2026 |  | 2026_ET-00524_ACQPKG | 2026_ET-00524_GSPKG | Submitted | 2026_ET-00524_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00524_GCPR | 2025-12-08 | Historical | 2026_ET-00524_ACQ | QC Accepted | 2026_ET-00524_FR | 2026-01-01 | Submitted | 2026_ET-00524_RWR | Submitted | 2026-01-01 | 2026_ET-00524_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00524_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00524_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00524_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00524_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00524_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00524_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ORANGE-WASHINGTON_ET-00524 |  |  | No | 20:32 |  | SANTA ANA | 29 | UNK | 2025-10-23 14:42 PDT ¦ 2025-10-23 14:49 PDT | 102325 | 20251023 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOUGLAS-SERVER | ET-00612 | 2026_ET-00612 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.24743 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-12-2026 |  | 2026_ET-00612_ACQPKG | 2026_ET-00612_GSPKG | Submitted | 2026_ET-00612_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00612_GCPR | 2025-12-08 | Historical | 2026_ET-00612_ACQ | QC Accepted | 2026_ET-00612_FR | 2026-01-01 | Submitted | 2026_ET-00612_RWR | Submitted | 2026-01-01 | 2026_ET-00612_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-00612_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00612_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00612_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00612_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00612_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00612_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DOUGLAS-SERVER_ET-00612 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-11-05 11:44 PST ¦ 2025-11-05 11:53 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-HIGHGROVE NO. 2 | ET-00622 | 2026_ET-00622 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.1042 | 3.5243 | 43 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-23 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00622_ACQPKG | 2026_ET-00622_GSPKG | Submitted | 2026_ET-00622_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00622_GCPR | 2025-12-08 | Historical | 2026_ET-00622_ACQ | QC Accepted | 2026_ET-00622_FR | 2026-01-01 | Submitted | 2026_ET-00622_RWR | Submitted | 2026-01-01 | 2026_ET-00622_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00622_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00622_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00622_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00622_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00622_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 19 | 2026-03-23 | 0 | 19 | 2026_ET-00622_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CALECTRIC-HIGHGROVE NO. 2_ET-00622 | Done |  | No | 19:43 |  | REDLANDS | 31 | UNK | 2025-10-22 14:33 PDT ¦ 2025-11-03 13:05 PST | 102325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CYBER-SEPULVEDA-SERVER | ET-00628 | 2026_ET-00628 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.402 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00628_ACQPKG | 2026_ET-00628_GSPKG | Submitted | 2026_ET-00628_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00628_GCPR | 2025-12-08 | Historical | 2026_ET-00628_ACQ | QC Accepted | 2026_ET-00628_FR | 2026-01-01 | Submitted | 2026_ET-00628_RWR | Submitted | 2026-01-01 | 2026_ET-00628_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00628_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00628_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00628_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00628_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00628_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00628_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CYBER-SEPULVEDA-SERVER_ET-00628 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-11-05 11:43 PST ¦ 2025-11-05 12:01 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NORTH OAKS-SOLEMINT | ET-00688 | 2026_ET-00688 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.1227 | 3.1227 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-25 | 02-01-2026 | 01-06-2026 |  | 2026_ET-00688_ACQPKG | 2026_ET-00688_GSPKG | Submitted | 2026_ET-00688_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00688_GCPR | 2025-12-08 | Historical | 2026_ET-00688_ACQ | QC Accepted | 2026_ET-00688_FR | 2026-01-01 | Submitted | 2026_ET-00688_RWR | Submitted | 2026-01-01 | 2026_ET-00688_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00688_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00688_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00688_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00688_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00688_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00688_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | NORTH OAKS-SOLEMINT_ET-00688 |  |  | No | 22:16 |  | VALENCIA | 59 | UNK | 2025-10-25 15:31 PDT ¦ 2025-10-25 15:39 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NAROD-SAN ANTONIO-UPLAND | ET-00744 | 2026_ET-00744 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.6932 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-25 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00744_ACQPKG | 2026_ET-00744_GSPKG | Submitted | 2026_ET-00744_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00744_GCPR | 2025-12-08 | Historical | 2026_ET-00744_ACQ | QC Accepted | 2026_ET-00744_FR | 2026-01-01 | Submitted | 2026_ET-00744_RWR | Submitted | 2026-01-01 | 2026_ET-00744_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00744_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00744_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00744_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00744_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00744_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00744_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | NAROD-SAN ANTONIO-UPLAND_ET-00744 |  |  | No | 20:08 |  | ONTARIO | 34 | UNK | 2025-10-25 13:18 PDT ¦ 2025-10-25 13:30 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PICO-PIER-SEABRIGHT | ET-00774 | 2026_ET-00774 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.9631 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-24 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00774_ACQPKG | 2026_ET-00774_GSPKG | Submitted | 2026_ET-00774_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00774_GCPR | 2025-12-08 | Historical | 2026_ET-00774_ACQ | QC Accepted | 2026_ET-00774_FR | 2026-01-01 | Submitted | 2026_ET-00774_RWR | Submitted | 2026-01-01 | 2026_ET-00774_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00774_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00774_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00774_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00774_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00774_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00774_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PICO-PIER-SEABRIGHT_ET-00774 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2025-11-04 12:44 PST ¦ 2025-11-04 12:45 PST | 110425 | 20251104 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-ERIC NO. 1 | ET-00796 | 2026_ET-00796 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.6233 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-03 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00796_ACQPKG | 2026_ET-00796_GSPKG | Submitted | 2026_ET-00796_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00796_GCPR | 2025-12-08 | Historical | 2026_ET-00796_ACQ | QC Accepted | 2026_ET-00796_FR | 2026-01-01 | Submitted | 2026_ET-00796_RWR | Submitted | 2026-01-01 | 2026_ET-00796_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00796_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00796_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00796_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00796_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00796_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00796_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-ERIC NO. 1_ET-00796 |  |  | No | 20:14 & 22:41 |  | LONG BEACH | 46 | UNK | 2025-10-18 10:37 PDT ¦ 2025-10-26 14:13 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-RAVENDALE-RUSH | ET-00843 | 2026_ET-00843 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.2349 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-04 | 02-01-2026 | 01-23-2026 |  | 2026_ET-00843_ACQPKG | 2026_ET-00843_GSPKG | Submitted | 2026_ET-00843_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00843_GCPR | 2025-12-08 | Historical | 2026_ET-00843_ACQ | QC Accepted | 2026_ET-00843_FR | 2025-11-27 | Submitted | 2026_ET-00843_RWR | Submitted | 2025-11-27 | 2026_ET-00843_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-23 |  | 2026_ET-00843_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00843_WR | 2026-03-24 | 03-03-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00843_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00843_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00843_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00843_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-30 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-RAVENDALE-RUSH_ET-00843 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-11-04 11:30 PST ¦ 2025-11-04 13:47 PST | 110425 | 20251104 | Attribute - Air Temp |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELY-GILBERT | ET-00855 | 2026_ET-00855 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.3678 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-03 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00855_ACQPKG | 2026_ET-00855_GSPKG | Submitted | 2026_ET-00855_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00855_GCPR | 2025-12-08 | Historical | 2026_ET-00855_ACQ | QC Accepted | 2026_ET-00855_FR | 2026-01-01 | Submitted | 2026_ET-00855_RWR | Submitted | 2026-01-01 | 2026_ET-00855_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00855_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00855_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00855_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00855_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-00855_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-00855_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-ELY-GILBERT_ET-00855 | Done |  | No | 19:56 & 22:41 |  | FULLERTON | 48 | UNK | 2025-10-24 13:13 PDT ¦ 2025-11-03 15:36 PST | 110325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-BEVERLY-CULVER | ET-00987 | 2026_ET-00987 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8796 | 0.8952 | 23 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-19 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00987_ACQPKG | 2026_ET-00987_GSPKG | Submitted | 2026_ET-00987_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00987_GCPR | 2025-12-08 | Historical | 2026_ET-00987_ACQ | QC Accepted | 2026_ET-00987_FR | 2026-01-01 | Submitted | 2026_ET-00987_RWR | Submitted | 2026-01-01 | 2026_ET-00987_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00987_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00987_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00987_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00987_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00987_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00987_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA CIENEGA-BEVERLY-CULVER_ET-00987 |  |  | No | 15:54 |  | SOUTH BAY | 44 | UNK | 2025-10-19 09:57 PDT ¦ 2025-10-19 10:13 PDT | 101925 | 20251019 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-BEVERLY | ET-00996 | 2026_ET-00996 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.7924 | 2.1008 | 44 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-19 | 02-01-2026 | 01-09-2026 |  | 2026_ET-00996_ACQPKG | 2026_ET-00996_GSPKG | Submitted | 2026_ET-00996_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00996_GCPR | 2025-12-08 | Historical | 2026_ET-00996_ACQ | QC Accepted | 2026_ET-00996_FR | 2026-01-01 | Submitted | 2026_ET-00996_RWR | Submitted | 2026-01-01 | 2026_ET-00996_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00996_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00996_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00996_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00996_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00996_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00996_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA CIENEGA-BEVERLY_ET-00996 |  |  | No | 15:54 |  | SOUTH BAY | 44 | UNK | 2025-10-19 09:47 PDT ¦ 2025-10-19 10:00 PDT | 101925 | 20251019 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LONG BEACH-PICO | ET-01060 | 2026_ET-01060 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.5844 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-09-2026 |  | 2026_ET-01060_ACQPKG | 2026_ET-01060_GSPKG | Submitted | 2026_ET-01060_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01060_GCPR | 2025-12-08 | Historical | 2026_ET-01060_ACQ | QC Accepted | 2026_ET-01060_FR | 2026-01-01 | Submitted | 2026_ET-01060_RWR | Submitted | 2026-01-01 | 2026_ET-01060_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01060_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01060_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01060_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01060_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01060_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01060_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LONG BEACH-PICO_ET-01060 |  |  | No | 19:28 & 14:08 |  | LONG BEACH | 46 | UNK | 2025-10-18 12:43 PDT ¦ 2025-11-05 08:15 PST | 110425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-GALVANIZING-STRIP | ET-01106 | 2026_ET-01106 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8202 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-21 | 02-01-2026 | 01-09-2026 |  | 2026_ET-01106_ACQPKG | 2026_ET-01106_GSPKG | Submitted | 2026_ET-01106_GS | 2025-11-08 | Field Complete | 2026_ET-01106_GCPR | 2026-01-01 | Submitted | 2026_ET-01106_ACQ | QC Accepted | 2026_ET-01106_FR | 2026-01-01 | Submitted | 2026_ET-01106_RWR | Submitted | 2026-01-01 | 2026_ET-01106_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01106_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01106_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01106_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01106_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01106_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01106_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-GALVANIZING-STRIP_ET-01106 |  |  | No | 15:48 |  | FOOTHILL | 30 | UNK | 2025-10-20 14:50 PDT ¦ 2025-10-21 10:23 PDT | 102125 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NELSON-STETSON | ET-01141 | 2026_ET-01141 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8312 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-22 | 02-01-2026 | 01-12-2026 |  | 2026_ET-01141_ACQPKG | 2026_ET-01141_GSPKG | Submitted | 2026_ET-01141_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01141_GCPR | 2025-12-08 | Historical | 2026_ET-01141_ACQ | QC Accepted | 2026_ET-01141_FR | 2026-01-01 | Submitted | 2026_ET-01141_RWR | Submitted | 2026-01-01 | 2026_ET-01141_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-01141_PROCPKG | Submitted | All Good - Complete | 2026_ET-01141_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01141_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01141_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01141_RR | 2026-02-18 | Violations Detected | 03-05-2026 | 03-05-2026 | 2 |  |  |  | 2026_ET-01141_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | NELSON-STETSON_ET-01141 |  |  | No | 16:04 |  | MENIFEE | 77 | UNK | 2025-10-22 10:45 PDT ¦ 2025-10-22 11:08 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-ROLLING-STRIP | ET-01172 | 2026_ET-01172 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.6557 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-21 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01172_ACQPKG | 2026_ET-01172_GSPKG | Submitted | 2026_ET-01172_GS | 2025-11-08 | Field Complete | 2026_ET-01172_GCPR | 2026-01-01 | Submitted | 2026_ET-01172_ACQ | QC Accepted | 2026_ET-01172_FR | 2026-01-01 | Submitted | 2026_ET-01172_RWR | Submitted | 2026-01-01 | 2026_ET-01172_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01172_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01172_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01172_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01172_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01172_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01172_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-ROLLING-STRIP_ET-01172 |  |  | No | 15:48 |  | FOOTHILL | 30 | UNK | 2025-10-21 10:01 PDT ¦ 2025-10-21 10:25 PDT | 102125 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-GALAXY-SPACE | ET-01293 | 2026_ET-01293 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.2378 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-18 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01293_ACQPKG | 2026_ET-01293_GSPKG | Submitted | 2026_ET-01293_GS | 2025-11-08 | Field Complete | 2026_ET-01293_GCPR | 2026-01-01 | Submitted | 2026_ET-01293_ACQ | QC Accepted | 2026_ET-01293_FR | 2026-01-01 | Submitted | 2026_ET-01293_RWR | Submitted | 2026-01-01 | 2026_ET-01293_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01293_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01293_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01293_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01293_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01293_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01293_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-GALAXY-SPACE_ET-01293 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:51 PDT ¦ 2025-11-05 12:17 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-LEONIS-VERNON | ET-01373 | 2026_ET-01373 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.6534 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01373_ACQPKG | 2026_ET-01373_GSPKG | Submitted | 2026_ET-01373_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01373_GCPR | 2025-12-08 | Historical | 2026_ET-01373_ACQ | QC Accepted | 2026_ET-01373_FR | 2026-01-01 | Submitted | 2026_ET-01373_RWR | Submitted | 2026-01-01 | 2026_ET-01373_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01373_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01373_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01373_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01373_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01373_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01373_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-LEONIS-VERNON_ET-01373 |  |  | No | 20:14 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-10-18 09:14 PDT ¦ 2025-10-26 13:55 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CABRILLO-ESTRELLA | ET-01514 | 2026_ET-01514 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.3283 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-04 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01514_ACQPKG | 2026_ET-01514_GSPKG | Submitted | 2026_ET-01514_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01514_GCPR | 2025-12-08 | Historical | 2026_ET-01514_ACQ | QC Accepted | 2026_ET-01514_FR | 2026-01-01 | Submitted | 2026_ET-01514_RWR | Submitted | 2026-01-01 | 2026_ET-01514_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01514_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01514_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01514_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01514_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01514_RR | 2026-03-22 | Violations QC Confirmed | 03-05-2026 | 03-23-2026 | 0 | 2026-03-23 | 25 | 2 | 2026_ET-01514_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | JOHANNA-CABRILLO-ESTRELLA_ET-01514 |  |  | No | 18:23 |  | SADDLEBACK | 43 | UNK | 2025-10-23 13:52 PDT ¦ 2025-11-05 06:57 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CABRILLO | ET-01516 | 2026_ET-01516 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.2168 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-21-2026 |  | 2026_ET-01516_ACQPKG | 2026_ET-01516_GSPKG | Submitted | 2026_ET-01516_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01516_GCPR | 2025-12-08 | Historical | 2026_ET-01516_ACQ | QC Accepted | 2026_ET-01516_FR | 2026-01-01 | Submitted | 2026_ET-01516_RWR | Submitted | 2026-01-01 | 2026_ET-01516_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-21 | 1 | 2026_ET-01516_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01516_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01516_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-05 | 0 | 2026_ET-01516_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-05 | 0 | 2026_ET-01516_RR | 2026-02-18 | No Violations | 03-06-2026 |  | 0 |  |  |  | 2026_ET-01516_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | JOHANNA-CABRILLO_ET-01516 |  |  | No | 18:23 & 14:08 |  | SADDLEBACK | 43 | UNK | 2025-10-17 09:51 PDT ¦ 2025-11-05 06:43 PST | 110425 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-BANDINI | ET-01557 | 2026_ET-01557 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.6018 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-18 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01557_ACQPKG | 2026_ET-01557_GSPKG | Submitted | 2026_ET-01557_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01557_GCPR | 2025-12-08 | Historical | 2026_ET-01557_ACQ | QC Accepted | 2026_ET-01557_FR | 2026-01-01 | Submitted | 2026_ET-01557_RWR | Submitted | 2026-01-01 | 2026_ET-01557_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01557_PROCPKG | Submitted | All Good - Complete | 2026_ET-01557_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01557_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01557_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01557_RR | 2026-03-22 | Violations Detected | 03-17-2026 | 03-23-2026 | 1 | 2026-03-23 | 1 | 0 | 2026_ET-01557_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-BANDINI_ET-01557 |  |  | No | 20:14 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-10-18 09:14 PDT ¦ 2025-10-26 13:49 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-CAPITAN-GAVIOTA | ET-01575 | 2026_ET-01575 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 16.3362 | 16.3362 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-28 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01575_ACQPKG | 2026_ET-01575_GSPKG | Submitted | 2026_ET-01575_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01575_GCPR | 2025-12-08 | Historical | 2026_ET-01575_ACQ | QC Accepted | 2026_ET-01575_FR | 2026-01-01 | Submitted | 2026_ET-01575_RWR | Submitted | 2026-01-01 | 2026_ET-01575_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01575_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01575_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01575_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01575_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01575_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01575_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOLETA-CAPITAN-GAVIOTA_ET-01575 |  |  | No | 20:04 |  | SANTA BARBARA | 49 | UNK | 2025-10-28 14:13 PDT ¦ 2025-10-28 15:43 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-CAPITAN | ET-01576 | 2026_ET-01576 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.0337 | 7.0337 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-28 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01576_ACQPKG | 2026_ET-01576_GSPKG | Submitted | 2026_ET-01576_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01576_GCPR | 2025-12-08 | Historical | 2026_ET-01576_ACQ | QC Accepted | 2026_ET-01576_FR | 2026-01-01 | Submitted | 2026_ET-01576_RWR | Submitted | 2026-01-01 | 2026_ET-01576_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01576_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01576_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01576_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01576_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01576_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01576_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOLETA-CAPITAN_ET-01576 |  |  | No | 20:04 |  | SANTA BARBARA | 49 | UNK | 2025-10-28 14:13 PDT ¦ 2025-10-28 14:49 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELSINORE-SKYLARK | ET-01582 | 2026_ET-01582 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.6107 | 0.96769 | 21 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01582_ACQPKG | 2026_ET-01582_GSPKG | Submitted | 2026_ET-01582_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01582_GCPR | 2025-12-08 | Historical | 2026_ET-01582_ACQ | QC Accepted | 2026_ET-01582_FR | 2026-01-01 | Submitted | 2026_ET-01582_RWR | Submitted | 2026-01-01 | 2026_ET-01582_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01582_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01582_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-04 | 0 | 2026_ET-01582_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01582_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01582_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01582_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELSINORE-SKYLARK_ET-01582 |  |  | No | 20:21 |  | WILDOMAR | 88 | UNK | 2025-10-26 14:11 PDT ¦ 2025-10-27 14:06 PDT | 102725 | 20251027 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OLINDA-TELEGRAPH | ET-01611 | 2026_ET-01611 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.2267 | 0.097309 | 2 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-25 | 02-01-2026 | 01-12-2026 |  | 2026_ET-01611_ACQPKG | 2026_ET-01611_GSPKG | Submitted | 2026_ET-01611_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01611_GCPR | 2025-12-08 | Historical | 2026_ET-01611_ACQ | QC Accepted | 2026_ET-01611_FR | 2026-01-01 | Submitted | 2026_ET-01611_RWR | Submitted | 2026-01-01 | 2026_ET-01611_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-01611_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01611_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01611_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01611_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01611_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01611_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-TELEGRAPH_ET-01611 |  |  | No | 20:08 |  | FULLERTON | 48 | UNK | 2025-10-25 14:55 PDT ¦ 2025-10-26 14:43 PDT | 102525 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-BUNKER-CAJALCO | ET-01622 | 2026_ET-01622 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 18.3811 | 5.0185 | 27 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-23 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01622_ACQPKG | 2026_ET-01622_GSPKG | Submitted | 2026_ET-01622_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01622_GCPR | 2025-12-08 | Historical | 2026_ET-01622_ACQ | QC Accepted | 2026_ET-01622_FR | 2026-01-01 | Submitted | 2026_ET-01622_RWR | Submitted | 2026-01-01 | 2026_ET-01622_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01622_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01622_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01622_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01622_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01622_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01622_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-BUNKER-CAJALCO_ET-01622 |  |  | No | 15:40 - 19:23 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 102325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-CABRILLO-CHIP-MACARTHUR | ET-01644 | 2026_ET-01644 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.2104 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-12-28 | 02-01-2026 | 01-21-2026 |  | 2026_ET-01644_ACQPKG | 2026_ET-01644_GSPKG | Submitted | 2026_ET-01644_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01644_GCPR | 2025-12-08 | Historical | 2026_ET-01644_ACQ | QC Accepted | 2026_ET-01644_FR | 2026-01-01 | Submitted | 2026_ET-01644_RWR | Submitted | 2026-01-01 | 2026_ET-01644_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-21 | 1 | 2026_ET-01644_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01644_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01644_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01644_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01644_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01644_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTIAGO-CABRILLO-CHIP-MACARTHUR_ET-01644 |  |  | No | 18:23 & 20:17 - 21:56 |  | SADDLEBACK | 43 | UNK | 2025-10-17 09:34 PDT ¦ 2025-12-18 13:33 PST | 110425 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PASSONS-PROCAL-SANTA FE SPRINGS | ET-01659 | 2026_ET-01659 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.2862 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01659_ACQPKG | 2026_ET-01659_GSPKG | Submitted | 2026_ET-01659_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01659_GCPR | 2025-12-08 | Historical | 2026_ET-01659_ACQ | QC Accepted | 2026_ET-01659_FR | 2026-01-01 | Submitted | 2026_ET-01659_RWR | Submitted | 2026-01-01 | 2026_ET-01659_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01659_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01659_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01659_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01659_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01659_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01659_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PASSONS-PROCAL-SANTA FE SPRINGS_ET-01659 |  |  | No | 20:14 |  | WHITTIER | 47 | UNK | 2025-10-26 14:48 PDT ¦ 2025-10-26 15:16 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-SEPULVEDA-SPACE-WESBASIN | ET-01663 | 2026_ET-01663 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.0834 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01663_ACQPKG | 2026_ET-01663_GSPKG | Submitted | 2026_ET-01663_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01663_GCPR | 2025-12-08 | Historical | 2026_ET-01663_ACQ | QC Accepted | 2026_ET-01663_FR | 2026-01-01 | Submitted | 2026_ET-01663_RWR | Submitted | 2026-01-01 | 2026_ET-01663_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01663_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01663_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01663_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01663_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01663_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01663_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-SEPULVEDA-SPACE-WESBASIN_ET-01663 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:51 PDT ¦ 2025-11-05 12:17 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OLINDA-ATWOOD-BREA-CAROLINA | ET-01689 | 2026_ET-01689 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.9232 | 1.488 | 15 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-25 | 02-01-2026 | 01-21-2026 |  | 2026_ET-01689_ACQPKG | 2026_ET-01689_GSPKG | Submitted | 2026_ET-01689_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01689_GCPR | 2025-12-08 | Historical | 2026_ET-01689_ACQ | QC Accepted | 2026_ET-01689_FR | 2026-01-01 | Submitted | 2026_ET-01689_RWR | Submitted | 2026-01-01 | 2026_ET-01689_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-21 | 1 | 2026_ET-01689_PROCPKG | Submitted | All Good - Complete | 2026_ET-01689_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01689_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01689_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01689_RR | 2026-02-18 | Violations Detected | 03-05-2026 | 03-05-2026 | 1 |  |  |  | 2026_ET-01689_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-ATWOOD-BREA-CAROLINA_ET-01689 |  |  | No | 20:08 |  | FULLERTON | 48 | UNK | 2025-10-25 14:29 PDT ¦ 2025-10-25 15:25 PDT | 102525 | 20251025 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-SHANDIN | ET-01715 | 2026_ET-01715 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 11.0175 | 3.4148 | 31 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-22 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01715_ACQPKG | 2026_ET-01715_GSPKG | Submitted | 2026_ET-01715_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01715_GCPR | 2025-12-08 | Historical | 2026_ET-01715_ACQ | QC Accepted | 2026_ET-01715_FR | 2026-01-01 | Submitted | 2026_ET-01715_RWR | Submitted | 2026-01-01 | 2026_ET-01715_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01715_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01715_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01715_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01715_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01715_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 2 | 2026-03-23 | 0 | 2 | 2026_ET-01715_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CALECTRIC-SHANDIN_ET-01715 | Done |  | No | 18:01 |  | REDLANDS | 31 | UNK | 2025-10-22 14:27 PDT ¦ 2025-10-22 14:37 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-TORRANCE-VAPOR | ET-01713 | 2026_ET-01713 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.2557 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-09-2026 |  | 2026_ET-01713_ACQPKG | 2026_ET-01713_GSPKG | Submitted | 2026_ET-01713_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01713_GCPR | 2025-12-08 | Historical | 2026_ET-01713_ACQ | QC Accepted | 2026_ET-01713_FR | 2026-01-01 | Submitted | 2026_ET-01713_RWR | Submitted | 2026-01-01 | 2026_ET-01713_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-01713_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01713_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01713_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01713_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01713_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01713_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA FRESA-TORRANCE-VAPOR_ET-01713 |  |  | No | 19:43 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:30 PDT ¦ 2025-11-05 11:13 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARMENITA-LA MIRADA | ET-01748 | 2026_ET-01748 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8233 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01748_ACQPKG | 2026_ET-01748_GSPKG | Submitted | 2026_ET-01748_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01748_GCPR | 2025-12-08 | Historical | 2026_ET-01748_ACQ | QC Accepted | 2026_ET-01748_FR | 2026-01-01 | Submitted | 2026_ET-01748_RWR | Submitted | 2026-01-01 | 2026_ET-01748_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01748_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01748_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-17 | 0 | 2026_ET-01748_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01748_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01748_RR | 2026-03-09 | No Violations | 03-18-2026 |  | 0 |  |  |  | 2026_ET-01748_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CARMENITA-LA MIRADA_ET-01748 | Done |  | No | 20:14 |  | WHITTIER | 47 | UNK | 2025-10-26 14:22 PDT ¦ 2025-10-26 14:37 PDT | 102625 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-TALBERT NO.2 | ET-01760 | 2026_ET-01760 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.4733 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-04 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01760_ACQPKG | 2026_ET-01760_GSPKG | Submitted | 2026_ET-01760_GS | 2025-11-08 | Field Complete | 2026_ET-01760_GCPR | 2026-01-01 | Submitted | 2026_ET-01760_ACQ | QC Accepted | 2026_ET-01760_FR | 2026-01-01 | Submitted | 2026_ET-01760_RWR | Submitted | 2026-01-01 | 2026_ET-01760_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01760_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01760_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01760_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01760_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01760_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01760_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ELLIS-TALBERT NO.2_ET-01760 |  |  | No | 18:23 |  | HUNTINGTON BEACH | 33 | UNK | 2025-11-04 10:55 PST ¦ 2025-11-04 11:23 PST | 110425 | 20251104 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-COLEGIO-ISLA VISTA-VEGAS | ET-01800 | 2026_ET-01800 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.8304 | 6.1986 | 79 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-28 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01800_ACQPKG | 2026_ET-01800_GSPKG | Submitted | 2026_ET-01800_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01800_GCPR | 2025-12-08 | Historical | 2026_ET-01800_ACQ | QC Accepted | 2026_ET-01800_FR | 2026-01-01 | Submitted | 2026_ET-01800_RWR | Submitted | 2026-01-01 | 2026_ET-01800_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01800_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01800_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-17 | 0 | 2026_ET-01800_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01800_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01800_RR | 2026-03-22 | Violations QC Confirmed | 03-18-2026 | 03-23-2026 | 1 | 2026-03-23 | 0 | 1 | 2026_ET-01800_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOLETA-COLEGIO-ISLA VISTA-VEGAS_ET-01800 |  |  | No | 20:04 |  | SANTA BARBARA | 49 | UNK | 2025-10-28 14:02 PDT ¦ 2025-10-28 15:02 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-NEWCOMB | ET-01852 | 2026_ET-01852 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.4044 | 1.4695 | 23 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-15-2026 |  | 2026_ET-01852_ACQPKG | 2026_ET-01852_GSPKG | Submitted | 2026_ET-01852_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01852_GCPR | 2025-12-08 | Historical | 2026_ET-01852_ACQ | QC Accepted | 2026_ET-01852_FR | 2026-01-01 | Submitted | 2026_ET-01852_RWR | Submitted | 2026-01-01 | 2026_ET-01852_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-15 | 0 | 2026_ET-01852_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01852_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01852_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01852_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01852_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01852_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-NEWCOMB_ET-01852 |  |  | No | 20:21 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 102625 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-NEWCOMB-SKYLARK | ET-01856 | 2026_ET-01856 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 19.3044 | 8.9795 | 47 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-15-2026 |  | 2026_ET-01856_ACQPKG | 2026_ET-01856_GSPKG | Submitted | 2026_ET-01856_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01856_GCPR | 2025-12-08 | Historical | 2026_ET-01856_ACQ | QC Accepted | 2026_ET-01856_FR | 2026-01-01 | Submitted | 2026_ET-01856_RWR | Submitted | 2026-01-01 | 2026_ET-01856_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-15 | 0 | 2026_ET-01856_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01856_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01856_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01856_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01856_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01856_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-NEWCOMB-SKYLARK_ET-01856 |  |  | No | 20:21 |  | MENIFEE | 77 | UNK | 2025-10-26 14:21 PDT ¦ 2025-10-27 14:06 PDT | 102725 | 20251027 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-IVYGLEN | ET-01946 | 2026_ET-01946 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 19.3289 | 15.5418 | 80 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-26 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01946_ACQPKG | 2026_ET-01946_GSPKG | Submitted | 2026_ET-01946_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01946_GCPR | 2025-12-08 | Historical | 2026_ET-01946_ACQ | QC Accepted | 2026_ET-01946_FR | 2026-01-01 | Submitted | 2026_ET-01946_RWR | Submitted | 2026-01-01 | 2026_ET-01946_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01946_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01946_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01946_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01946_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01946_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01946_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-IVYGLEN_ET-01946 |  |  | No | 20:21 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 102625 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GALAXY-ROSECRANS | ET-01948 | 2026_ET-01948 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.521 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01948_ACQPKG | 2026_ET-01948_GSPKG | Submitted | 2026_ET-01948_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01948_GCPR | 2025-12-08 | Historical | 2026_ET-01948_ACQ | QC Accepted | 2026_ET-01948_FR | 2026-01-01 | Submitted | 2026_ET-01948_RWR | Submitted | 2026-01-01 | 2026_ET-01948_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01948_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01948_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01948_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01948_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01948_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01948_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GALAXY-ROSECRANS_ET-01948 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:51 PDT ¦ 2025-11-05 12:16 PST | 110525 | 20251105 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-CARPINTERIA-CASITAS | ET-01949 | 2026_ET-01949 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 23.8226 | 23.5168 | 99 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-29 | 02-01-2026 | 01-13-2026 |  | 2026_ET-01949_ACQPKG | 2026_ET-01949_GSPKG | Submitted | 2026_ET-01949_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01949_GCPR | 2025-12-08 | Historical | 2026_ET-01949_ACQ | QC Accepted | 2026_ET-01949_FR | 2026-01-01 | Submitted | 2026_ET-01949_RWR | Submitted | 2026-01-01 | 2026_ET-01949_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01949_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01949_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01949_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01949_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01949_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01949_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-CARPINTERIA-CASITAS_ET-01949 |  |  | No | 16:16 & 16:29 |  | VENTURA | 39 | UNK | 2025-10-28 11:10 PDT ¦ 2025-10-29 11:21 PDT | 102825 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-CARPINTERIA-GETTY | ET-01950 | 2026_ET-01950 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 24.147 | 22.6915 | 94 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-29 | 02-01-2026 | 01-14-2026 |  | 2026_ET-01950_ACQPKG | 2026_ET-01950_GSPKG | Submitted | 2026_ET-01950_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01950_GCPR | 2025-12-08 | Historical | 2026_ET-01950_ACQ | QC Accepted | 2026_ET-01950_FR | 2026-01-01 | Submitted | 2026_ET-01950_RWR | Submitted | 2026-01-01 | 2026_ET-01950_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01950_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01950_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-17 | 0 | 2026_ET-01950_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01950_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01950_RR | 2026-03-09 | No Violations | 03-18-2026 |  | 0 |  |  |  | 2026_ET-01950_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-CARPINTERIA-GETTY_ET-01950 |  |  | No | 16:16 & 16:29 |  | VENTURA | 39 | UNK | 2025-10-28 11:10 PDT ¦ 2025-10-29 11:32 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-VALDEZ | ET-01971 | 2026_ET-01971 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 24.8571 | 24.8571 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-29 | 02-01-2026 | 01-12-2026 |  | 2026_ET-01971_ACQPKG | 2026_ET-01971_GSPKG | Submitted | 2026_ET-01971_GS | 2025-11-08 | Field Complete | 2026_ET-01971_GCPR | 2026-01-01 | Submitted | 2026_ET-01971_ACQ | QC Accepted | 2026_ET-01971_FR | 2026-01-01 | Submitted | 2026_ET-01971_RWR | Submitted | 2026-01-01 | 2026_ET-01971_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-01971_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01971_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01971_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01971_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01971_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01971_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MOORPARK-VALDEZ_ET-01971 |  |  | No | 20:43 |  | THOUSAND OAKS | 35 | UNK | 2025-10-29 15:00 PDT ¦ 2025-11-06 08:26 PST | 102925 | 20251106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-TRITON | ET-02035 | 2026_ET-02035 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 13.9773 | 11.3009 | 81 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-22 | 02-01-2026 | 01-15-2026 |  | 2026_ET-02035_ACQPKG | 2026_ET-02035_GSPKG | Submitted | 2026_ET-02035_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02035_GCPR | 2025-12-08 | Historical | 2026_ET-02035_ACQ | QC Accepted | 2026_ET-02035_FR | 2026-01-01 | Submitted | 2026_ET-02035_RWR | Submitted | 2026-01-01 | 2026_ET-02035_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-15 | 0 | 2026_ET-02035_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02035_WR | 2026-02-18 | 03-03-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-02035_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-02035_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-02035_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-02035_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-TRITON_ET-02035 |  |  | No | 16:04 & 20:42 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 102325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHATSWORTH-THRUST | ET-02045 | 2026_ET-02045 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.74372 | 0.74372 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-31 | 02-01-2026 | 01-13-2026 |  | 2026_ET-02045_ACQPKG | 2026_ET-02045_GSPKG | Submitted | 2026_ET-02045_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02045_GCPR | 2025-12-08 | Historical | 2026_ET-02045_ACQ | QC Accepted | 2026_ET-02045_FR | 2026-01-01 | Submitted | 2026_ET-02045_RWR | Submitted | 2026-01-01 | 2026_ET-02045_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-02045_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02045_WR | 2026-03-12 | 03-03-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-02045_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02045_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-02045_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-02045_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHATSWORTH-THRUST_ET-02045 |  |  | No | 23:00 |  | THOUSAND OAKS | 35 | UNK | 2025-10-31 16:46 PDT ¦ 2025-11-06 08:36 PST | 103125 | 20251106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-BIG SKY | ET-00016 | 2026_ET-00016 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.18329 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-12-2026 |  | 2026_ET-00016_ACQPKG | 2026_ET-00016_GSPKG | Submitted | 2026_ET-00016_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00016_GCPR | 2025-12-08 | Historical | 2026_ET-00016_ACQ | QC Accepted | 2026_ET-00016_FR | 2025-11-27 | Submitted | 2026_ET-00016_RWR | Submitted | 2025-11-27 | 2026_ET-00016_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-12 |  | 2026_ET-00016_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00016_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00016_VMLAZ | 2026-02-21 | QC Accepted | 03-09-2026 | 2026-02-24 | 0 | 2026_ET-00016_VMM1 | 2026-02-23 | QC Accepted |  | 03-09-2026 | 2026-02-24 | 0 | 2026_ET-00016_RR | 2026-02-23 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00016_VER | 2026-02-23 | Uploaded to S123 | 03-09-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-BIG SKY_ET-00016 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-MIRA LOMA NO. 2 | ET-00083 | 2026_ET-00083 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 30.6253 | 20.9866 | 69 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00083_ACQPKG | 2026_ET-00083_GSPKG | Submitted | 2026_ET-00083_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00083_GCPR | 2025-12-08 | Historical | 2026_ET-00083_ACQ | QC Accepted | 2026_ET-00083_FR | 2026-01-01 | Submitted | 2026_ET-00083_RWR | Submitted | 2026-01-01 | 2026_ET-00083_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00083_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00083_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-03-13 | 0 | 2026_ET-00083_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-13 | 0 | 2026_ET-00083_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-13 | 0 | 2026_ET-00083_RR | 2026-03-02 | No Violations | 03-14-2026 | [5 empty] | 2026_ET-00083_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-13 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-MIRA LOMA NO. 2_ET-00083 |  |  | Yes | 15:52 - 19:31 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AVENUE-WHIRLWIND | ET-00103 | 2026_ET-00103 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.47769 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-15-2026 |  | 2026_ET-00103_ACQPKG | 2026_ET-00103_GSPKG | Submitted | 2026_ET-00103_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00103_GCPR | 2025-12-08 | Historical | 2026_ET-00103_ACQ | QC Accepted | 2026_ET-00103_FR | 2025-11-27 | Submitted | 2026_ET-00103_RWR | Submitted | 2025-11-27 | 2026_ET-00103_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-15 |  | 2026_ET-00103_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00103_WR | 2026-02-27 | 03-04-2026 | QC Accepted | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-00103_VMLAZ | 2026-02-21 | QC Accepted | 03-13-2026 | 2026-02-24 | 0 | 2026_ET-00103_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-00103_RR | 2026-02-27 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-00103_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | AVENUE-WHIRLWIND_ET-00103 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-MIRA LOMA NO.3 | ET-00129 | 2026_ET-00129 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 31.485 | 21.0883 | 67 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00129_ACQPKG | 2026_ET-00129_GSPKG | Submitted | 2026_ET-00129_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00129_GCPR | 2025-12-08 | Historical | 2026_ET-00129_ACQ | QC Accepted | 2026_ET-00129_FR | 2026-01-01 | Submitted | 2026_ET-00129_RWR | Submitted | 2026-01-01 | 2026_ET-00129_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00129_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00129_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00129_VMLAZ | 2026-02-25 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00129_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00129_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00129_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-MIRA LOMA NO.3_ET-00129 |  |  | Yes | 15:52 - 19:31 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALCREEK-WALNUT | ET-00139 | 2026_ET-00139 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.36531 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-24 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00139_ACQPKG | 2026_ET-00139_GSPKG | Submitted | 2026_ET-00139_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00139_GCPR | 2025-12-08 | Historical | 2026_ET-00139_ACQ | QC Accepted | 2026_ET-00139_FR | 2026-01-01 | Submitted | 2026_ET-00139_RWR | Submitted | 2026-01-01 | 2026_ET-00139_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00139_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00139_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00139_VMLAZ | 2026-02-21 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00139_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00139_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00139_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WALCREEK-WALNUT_ET-00139 |  |  | Yes | 18:42 |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHATSWORTH-NATURAL | ET-00149 | 2026_ET-00149 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.4142 | 8.4045 | 81 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-02 | 01-01-2026 | Flown | 2025-10-31 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00149_ACQPKG | 2026_ET-00149_GSPKG | Submitted | 2026_ET-00149_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00149_GCPR | 2025-12-08 | Historical | 2026_ET-00149_ACQ | QC Accepted | 2026_ET-00149_FR | 2026-01-01 | Submitted | 2026_ET-00149_RWR | Submitted | 2026-01-01 | 2026_ET-00149_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00149_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00149_WR | 2026-03-12 | 03-04-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00149_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00149_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00149_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 1 | 2026-03-23 | 0 | 1 | 2026_ET-00149_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHATSWORTH-NATURAL_ET-00149 |  |  | No | 23:00 |  | THOUSAND OAKS | 35 | UNK | 2025-10-31 16:46 PDT ¦ 2025-11-06 09:02 PST | 110625 | 20251106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELLIS NO 3 | ET-00174 | 2026_ET-00174 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.7408 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00174_ACQPKG | 2026_ET-00174_GSPKG | Submitted | 2026_ET-00174_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00174_GCPR | 2025-12-08 | Historical | 2026_ET-00174_ACQ | QC Accepted | 2026_ET-00174_FR | 2026-01-01 | Submitted | 2026_ET-00174_RWR | Submitted | 2026-01-01 | 2026_ET-00174_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00174_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00174_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00174_VMLAZ | 2026-02-27 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00174_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00174_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00174_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-ELLIS NO 3_ET-00174 | Done |  | Yes | 19:56 - 18:23 |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELLIS NO 4 | ET-00175 | 2026_ET-00175 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.7422 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00175_ACQPKG | 2026_ET-00175_GSPKG | Submitted | 2026_ET-00175_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00175_GCPR | 2025-12-08 | Historical | 2026_ET-00175_ACQ | QC Accepted | 2026_ET-00175_FR | 2026-01-01 | Submitted | 2026_ET-00175_RWR | Submitted | 2026-01-01 | 2026_ET-00175_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00175_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00175_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00175_VMLAZ | 2026-02-27 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00175_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00175_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00175_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-ELLIS NO 4_ET-00175 | Done |  | Yes | 19:56 - 18:23 |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLOSEUM 1-IVANPAH | ET-00181 | 2026_ET-00181 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.08515 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-10-30 | 02-02-2026 | 01-21-2026 |  | 2026_ET-00181_ACQPKG | 2026_ET-00181_GSPKG | Submitted | 2026_ET-00181_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00181_GCPR | 2025-12-08 | Historical | 2026_ET-00181_ACQ | QC Accepted | 2026_ET-00181_FR | 2025-11-27 | Submitted | 2026_ET-00181_RWR | Submitted | 2025-11-27 | 2026_ET-00181_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-21 |  | 2026_ET-00181_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00181_WR | 2026-03-04 | 03-04-2026 | QC Accepted | 03-18-2026 | 2026-03-04 | 0 | 2026_ET-00181_VMLAZ | 2026-02-21 | QC Accepted | 03-18-2026 | 2026-02-24 | 0 | 2026_ET-00181_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-04 | 0 | 2026_ET-00181_RR | 2026-03-04 | No Violations | 03-05-2026 | [5 empty] | 2026_ET-00181_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLOSEUM 1-IVANPAH_ET-00181 |  |  | No |  | Helicopter | BARSTOW | 72 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLOSEUM 2-IVANPAH | ET-00182 | 2026_ET-00182 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.20538 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-10-30 | 02-02-2026 | 01-20-2026 |  | 2026_ET-00182_ACQPKG | 2026_ET-00182_GSPKG | Submitted | 2026_ET-00182_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00182_GCPR | 2025-12-08 | Historical | 2026_ET-00182_ACQ | QC Accepted | 2026_ET-00182_FR | 2025-11-27 | Submitted | 2026_ET-00182_RWR | Submitted | 2025-11-27 | 2026_ET-00182_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-20 |  | 2026_ET-00182_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00182_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00182_VMLAZ | 2026-02-21 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-00182_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00182_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00182_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLOSEUM 2-IVANPAH_ET-00182 |  |  | No |  | Helicopter | BARSTOW | 72 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLOSEUM 3-IVANPAH | ET-00183 | 2026_ET-00183 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.20862 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-10-30 | 02-02-2026 | 01-22-2026 |  | 2026_ET-00183_ACQPKG | 2026_ET-00183_GSPKG | Submitted | 2026_ET-00183_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00183_GCPR | 2025-12-08 | Historical | 2026_ET-00183_ACQ | QC Accepted | 2026_ET-00183_FR | 2025-11-27 | Submitted | 2026_ET-00183_RWR | Submitted | 2025-11-27 | 2026_ET-00183_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-22 |  | 2026_ET-00183_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00183_WR | 2026-02-27 | 03-04-2026 | QC Accepted | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-00183_VMLAZ | 2026-02-21 | QC Accepted | 03-13-2026 | 2026-02-24 | 0 | 2026_ET-00183_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-00183_RR | 2026-02-27 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-00183_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLOSEUM 3-IVANPAH_ET-00183 |  |  | No |  | Helicopter | BARSTOW | 72 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DESERT STATELINE-IVANPAH | ET-00184 | 2026_ET-00184 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.070862 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-30 | 02-02-2026 | 01-15-2026 |  | 2026_ET-00184_ACQPKG | 2026_ET-00184_GSPKG | Submitted | 2026_ET-00184_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00184_GCPR | 2025-12-08 | Historical | 2026_ET-00184_ACQ | QC Accepted | 2026_ET-00184_FR | 2025-11-27 | Submitted | 2026_ET-00184_RWR | Submitted | 2025-11-27 | 2026_ET-00184_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-15 |  | 2026_ET-00184_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00184_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-00184_VMLAZ | 2026-02-23 | QC Accepted | 03-16-2026 | 2026-02-24 | 0 | 2026_ET-00184_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-00184_RR | 2026-03-02 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-00184_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DESERT STATELINE-IVANPAH_ET-00184 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELLIS NO 1 | ET-00195 | 2026_ET-00195 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.7477 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00195_ACQPKG | 2026_ET-00195_GSPKG | Submitted | 2026_ET-00195_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00195_GCPR | 2025-12-08 | Historical | 2026_ET-00195_ACQ | QC Accepted | 2026_ET-00195_FR | 2026-01-01 | Submitted | 2026_ET-00195_RWR | Submitted | 2026-01-01 | 2026_ET-00195_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00195_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00195_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00195_VMLAZ | 2026-02-24 | QC Accepted | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00195_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00195_RR | 2026-02-27 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00195_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-ELLIS NO 1_ET-00195 | Done |  | Yes | 19:56 - 18:23 |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELLIS NO 2 | ET-00196 | 2026_ET-00196 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.745 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00196_ACQPKG | 2026_ET-00196_GSPKG | Submitted | 2026_ET-00196_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00196_GCPR | 2025-12-08 | Historical | 2026_ET-00196_ACQ | QC Accepted | 2026_ET-00196_FR | 2026-01-01 | Submitted | 2026_ET-00196_RWR | Submitted | 2026-01-01 | 2026_ET-00196_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00196_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00196_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00196_VMLAZ | 2026-02-25 | QC Accepted | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00196_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00196_RR | 2026-02-27 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00196_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-ELLIS NO 2_ET-00196 | Done |  | Yes | 19:56 - 18:23 |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALPINE SOLAR-NEENACH | ET-00205 | 2026_ET-00205 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.049763 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-10-30 | 02-02-2026 | 01-12-2026 |  | 2026_ET-00205_ACQPKG | 2026_ET-00205_GSPKG | Submitted | 2026_ET-00205_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00205_GCPR | 2025-12-08 | Historical | 2026_ET-00205_ACQ | QC Accepted | 2026_ET-00205_FR | 2025-11-27 | Submitted | 2026_ET-00205_RWR | Submitted | 2025-11-27 | 2026_ET-00205_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-12 |  | 2026_ET-00205_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00205_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00205_VMLAZ | 2026-02-17 | QC Accepted | 03-09-2026 | 2026-02-17 | 0 | 2026_ET-00205_VMM1 | 2026-02-23 | QC Accepted |  | 03-09-2026 | 2026-02-24 | 0 | 2026_ET-00205_RR | 2026-02-23 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00205_VER | 2026-02-23 | Uploaded to S123 | 03-09-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ALPINE SOLAR-NEENACH_ET-00205 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-PISGAH NO.2 | ET-00289 | 2026_ET-00289 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 64.7144 | 1.504 | 2 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-01 | 02-02-2026 | 01-27-2026 |  | 2026_ET-00289_ACQPKG | 2026_ET-00289_GSPKG | Submitted | 2026_ET-00289_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00289_GCPR | 2025-12-08 | Historical | 2026_ET-00289_ACQ | QC Accepted | 2026_ET-00289_FR | 2025-11-27 | Submitted | 2026_ET-00289_RWR | Submitted | 2025-11-27 | 2026_ET-00289_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-27 |  | 2026_ET-00289_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00289_WR |  | 03-04-2026 | QC Accepted |  | 2026-02-26 | 0 | 2026_ET-00289_VMLAZ | 2026-02-21 | QC Accepted | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00289_VMM1 | 2026-02-24 | QC Accepted |  | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00289_RR | 2026-02-24 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00289_VER | 2026-02-24 | Uploaded to S123 | 03-10-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-PISGAH NO.2_ET-00289 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-BOVINE NO.1 | ET-00328 | 2026_ET-00328 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.8763 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-11-03 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00328_ACQPKG | 2026_ET-00328_GSPKG | Submitted | 2026_ET-00328_GS | 2025-11-08 | Field Complete | 2026_ET-00328_GCPR | 2026-01-01 | Submitted | 2026_ET-00328_ACQ | QC Accepted | 2026_ET-00328_FR | 2026-01-01 | Submitted | 2026_ET-00328_RWR | Submitted | 2026-01-01 | 2026_ET-00328_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00328_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00328_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00328_VMLAZ | 2026-02-25 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00328_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00328_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00328_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-BOVINE NO.1_ET-00328 |  |  | No | 22:41 |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-BOVINE NO.2 | ET-00329 | 2026_ET-00329 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.4262 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-11-03 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00329_ACQPKG | 2026_ET-00329_GSPKG | Submitted | 2026_ET-00329_GS | 2025-11-08 | Field Complete | 2026_ET-00329_GCPR | 2026-01-01 | Submitted | 2026_ET-00329_ACQ | QC Accepted | 2026_ET-00329_FR | 2026-01-01 | Submitted | 2026_ET-00329_RWR | Submitted | 2026-01-01 | 2026_ET-00329_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00329_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00329_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00329_VMLAZ | 2026-02-25 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00329_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00329_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00329_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEL AMO-BOVINE NO.2_ET-00329 |  |  | No | 22:41 |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-SERRANO | ET-00470 | 2026_ET-00470 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 24.6473 | 21.661 | 88 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00470_ACQPKG | 2026_ET-00470_GSPKG | Submitted | 2026_ET-00470_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00470_GCPR | 2025-12-08 | Historical | 2026_ET-00470_ACQ | QC Accepted | 2026_ET-00470_FR | 2026-01-01 | Submitted | 2026_ET-00470_RWR | Submitted | 2026-01-01 | 2026_ET-00470_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00470_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00470_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00470_VMLAZ | 2026-02-25 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00470_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00470_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00470_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-SERRANO_ET-00470 |  |  | Yes | 17:14 - 20:32 |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-FULLERTON | ET-00473 | 2026_ET-00473 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.582 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-10-24 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00473_ACQPKG | 2026_ET-00473_GSPKG | Submitted | 2026_ET-00473_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00473_GCPR | 2025-12-08 | Historical | 2026_ET-00473_ACQ | QC Accepted | 2026_ET-00473_FR | 2026-01-01 | Submitted | 2026_ET-00473_RWR | Submitted | 2026-01-01 | 2026_ET-00473_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00473_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00473_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00473_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00473_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00473_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00473_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-FULLERTON_ET-00473 | Done |  | No | 19:56 |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SERRANO-VILLA PARK NO.1 | ET-00474 | 2026_ET-00474 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.1844 | 2.1077 | 66 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00474_ACQPKG | 2026_ET-00474_GSPKG | Submitted | 2026_ET-00474_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00474_GCPR | 2025-12-08 | Historical | 2026_ET-00474_ACQ | QC Accepted | 2026_ET-00474_FR | 2026-01-01 | Submitted | 2026_ET-00474_RWR | Submitted | 2026-01-01 | 2026_ET-00474_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00474_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00474_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00474_VMLAZ | 2026-02-24 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00474_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00474_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00474_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SERRANO-VILLA PARK NO.1_ET-00474 |  |  | Yes | 20:32 |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 2-BIG CREEK 3 | ET-00513 | 2026_ET-00513 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_4 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.4446 | 7.4446 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-08 | 02-02-2026 | 01-27-2026 |  | 2026_ET-00513_ACQPKG | 2026_ET-00513_GSPKG | Submitted | 2026_ET-00513_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00513_GCPR | 2025-12-08 | Historical | 2026_ET-00513_ACQ | QC Accepted | 2026_ET-00513_FR | 2025-11-27 | Submitted | 2026_ET-00513_RWR | Submitted | 2025-11-27 | 2026_ET-00513_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-27 |  | 2026_ET-00513_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00513_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00513_VMLAZ | 2026-02-21 | QC Accepted | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00513_VMM1 | 2026-02-24 | QC Accepted |  | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00513_RR | 2026-02-24 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00513_VER | 2026-02-24 | Uploaded to S123 | 03-10-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BIG CREEK 2-BIG CREEK 3_ET-00513 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-EL CASCO | ET-00514 | 2026_ET-00514 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 29.3056 | 22.681 | 77 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00514_ACQPKG | 2026_ET-00514_GSPKG | Submitted | 2026_ET-00514_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00514_GCPR | 2025-12-08 | Historical | 2026_ET-00514_ACQ | QC Accepted | 2026_ET-00514_FR | 2026-01-01 | Submitted | 2026_ET-00514_RWR | Submitted | 2026-01-01 | 2026_ET-00514_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00514_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00514_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00514_VMLAZ | 2026-02-25 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00514_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00514_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00514_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEVERS-EL CASCO_ET-00514 |  |  | Yes | 19:27 & 15:40 |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-SAN BERNARDINO | ET-00526 | 2026_ET-00526 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 42.9139 | 33.7503 | 79 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00526_ACQPKG | 2026_ET-00526_GSPKG | Submitted | 2026_ET-00526_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00526_GCPR | 2025-12-08 | Historical | 2026_ET-00526_ACQ | QC Accepted | 2026_ET-00526_FR | 2026-01-01 | Submitted | 2026_ET-00526_RWR | Submitted | 2026-01-01 | 2026_ET-00526_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00526_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00526_WR |  | 03-04-2026 | QC Accepted |  | 2026-03-11 | 0 | 2026_ET-00526_VMLAZ | 2026-02-27 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00526_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00526_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00526_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEVERS-SAN BERNARDINO_ET-00526 |  |  | Yes | 19:27 & 16:04 & 15:40 |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-RITTER RANCH NO. 1 | ET-00553 | 2026_ET-00553 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.5829 | 7.487 | 78 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-28-2026 |  | 2026_ET-00553_ACQPKG | 2026_ET-00553_GSPKG | Submitted | 2026_ET-00553_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00553_GCPR | 2025-12-08 | Historical | 2026_ET-00553_ACQ | QC Accepted | 2026_ET-00553_FR | 2025-11-27 | Submitted | 2026_ET-00553_RWR | Submitted | 2025-11-27 | 2026_ET-00553_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-28 |  | 2026_ET-00553_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00553_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00553_VMLAZ | 2026-02-21 | QC Accepted | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00553_VMM1 | 2026-02-24 | QC Accepted |  | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00553_RR | 2026-02-24 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00553_VER | 2026-02-24 | Uploaded to S123 | 03-10-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-RITTER RANCH NO. 1_ET-00553 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-RITTER RANCH NO. 2 | ET-00556 | 2026_ET-00556 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.5843 | 7.4879 | 78 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-28-2026 |  | 2026_ET-00556_ACQPKG | 2026_ET-00556_GSPKG | Submitted | 2026_ET-00556_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00556_GCPR | 2025-12-08 | Historical | 2026_ET-00556_ACQ | QC Accepted | 2026_ET-00556_FR | 2025-11-27 | Submitted | 2026_ET-00556_RWR | Submitted | 2025-11-27 | 2026_ET-00556_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-28 |  | 2026_ET-00556_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00556_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00556_VMLAZ | 2026-02-23 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-00556_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00556_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00556_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-RITTER RANCH NO. 2_ET-00556 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-VISTA NO.1 | ET-00594 | 2026_ET-00594 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 15.5425 | 4.9398 | 32 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00594_ACQPKG | 2026_ET-00594_GSPKG | Submitted | 2026_ET-00594_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00594_GCPR | 2025-12-08 | Historical | 2026_ET-00594_ACQ | QC Accepted | 2026_ET-00594_FR | 2026-01-01 | Submitted | 2026_ET-00594_RWR | Submitted | 2026-01-01 | 2026_ET-00594_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00594_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00594_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00594_VMLAZ | 2026-02-26 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00594_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00594_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00594_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-VISTA NO.1_ET-00594 |  |  | Yes | 15:52 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-VISTA NO.2 | ET-00599 | 2026_ET-00599 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 15.3792 | 4.9392 | 32 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00599_ACQPKG | 2026_ET-00599_GSPKG | Submitted | 2026_ET-00599_GS | 2025-11-08 | Field Complete | 2026_ET-00599_GCPR | 2026-01-01 | Submitted | 2026_ET-00599_ACQ | QC Accepted | 2026_ET-00599_FR | 2026-01-01 | Submitted | 2026_ET-00599_RWR | Submitted | 2026-01-01 | 2026_ET-00599_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00599_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00599_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00599_VMLAZ | 2026-02-26 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00599_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00599_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00599_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-VISTA NO.2_ET-00599 |  |  | Yes | 15:52 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-MIRA LOMA NO.2 | ET-00601 | 2026_ET-00601 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.0733 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-25 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00601_ACQPKG | 2026_ET-00601_GSPKG | Submitted | 2026_ET-00601_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00601_GCPR | 2025-12-08 | Historical | 2026_ET-00601_ACQ | QC Accepted | 2026_ET-00601_FR | 2026-01-01 | Submitted | 2026_ET-00601_RWR | Submitted | 2026-01-01 | 2026_ET-00601_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00601_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00601_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00601_VMLAZ | 2026-02-24 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00601_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00601_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00601_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-MIRA LOMA NO.2_ET-00601 |  |  | Yes | 20:08 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-WALNUT (B) | ET-00602 | 2026_ET-00602 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 27.5549 | 18.5544 | 67 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-25 | 02-02-2026 | 01-08-2026 |  | 2026_ET-00602_ACQPKG | 2026_ET-00602_GSPKG | Submitted | 2026_ET-00602_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00602_GCPR | 2025-12-08 | Historical | 2026_ET-00602_ACQ | QC Accepted | 2026_ET-00602_FR | 2026-01-01 | Submitted | 2026_ET-00602_RWR | Submitted | 2026-01-01 | 2026_ET-00602_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-08 | 0 | 2026_ET-00602_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00602_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00602_VMLAZ | 2026-02-26 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00602_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00602_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00602_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-WALNUT (B)_ET-00602 |  |  | Yes | 18:42 & 20:08 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-VISTA | ET-00611 | 2026_ET-00611 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 15.255 | 3.9259 | 26 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00611_ACQPKG | 2026_ET-00611_GSPKG | Submitted | 2026_ET-00611_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00611_GCPR | 2025-12-08 | Historical | 2026_ET-00611_ACQ | QC Accepted | 2026_ET-00611_FR | 2026-01-01 | Submitted | 2026_ET-00611_RWR | Submitted | 2026-01-01 | 2026_ET-00611_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00611_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00611_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00611_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00611_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00611_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00611_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-VISTA_ET-00611 |  |  | Yes | 15:52 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOODRICH-GOULD | ET-00638 | 2026_ET-00638 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.6404 | 7.3048 | 85 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-27-2026 |  | 2026_ET-00638_ACQPKG | 2026_ET-00638_GSPKG | Submitted | 2026_ET-00638_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00638_GCPR | 2025-12-08 | Historical | 2026_ET-00638_ACQ | QC Accepted | 2026_ET-00638_FR | 2025-11-27 | Submitted | 2026_ET-00638_RWR | Submitted | 2025-11-27 | 2026_ET-00638_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-27 |  | 2026_ET-00638_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00638_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00638_VMLAZ | 2026-02-21 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-00638_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00638_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00638_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | GOODRICH-GOULD_ET-00638 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-OLINDA | ET-00690 | 2026_ET-00690 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 18.7221 | 10.5223 | 56 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-26 | 02-02-2026 | 01-09-2026 |  | 2026_ET-00690_ACQPKG | 2026_ET-00690_GSPKG | Submitted | 2026_ET-00690_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00690_GCPR | 2025-12-08 | Historical | 2026_ET-00690_ACQ | QC Accepted | 2026_ET-00690_FR | 2026-01-01 | Submitted | 2026_ET-00690_RWR | Submitted | 2026-01-01 | 2026_ET-00690_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00690_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00690_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00690_VMLAZ | 2026-02-26 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00690_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-00690_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00690_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-OLINDA_ET-00690 |  |  | Yes | 18:42 & 20:08 & 20:14 |  | MONTEBELLO | 22 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-VINCENT NO.1 | ET-00708 | 2026_ET-00708 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 32.5374 | 29.1045 | 89 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-28-2026 |  | 2026_ET-00708_ACQPKG | 2026_ET-00708_GSPKG | Submitted | 2026_ET-00708_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00708_GCPR | 2025-12-08 | Historical | 2026_ET-00708_ACQ | QC Accepted | 2026_ET-00708_FR | 2025-11-27 | Submitted | 2026_ET-00708_RWR | Submitted | 2025-11-27 | 2026_ET-00708_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-28 |  | 2026_ET-00708_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00708_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00708_VMLAZ | 2026-02-21 | QC Accepted | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00708_VMM1 | 2026-02-24 | QC Accepted |  | 03-10-2026 | 2026-02-24 | 0 | 2026_ET-00708_RR | 2026-02-24 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-00708_VER | 2026-02-24 | Uploaded to S123 | 03-10-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RIO HONDO-VINCENT NO.1_ET-00708 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTA CLARA-GETTY | ET-00723 | 2026_ET-00723 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.39 | 9.9102 | 95 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-10-24 | 02-02-2026 | 02-02-2026 |  | 2026_ET-00723_ACQPKG | 2026_ET-00723_GSPKG | Submitted | 2026_ET-00723_GS | 2025-10-15 | Field Complete | 2026_ET-00723_GCPR | 2025-12-08 | Submitted | 2026_ET-00723_ACQ | QC Accepted | 2026_ET-00723_FR | 2025-11-27 | Submitted | 2026_ET-00723_RWR | Submitted | 2025-11-27 | 2026_ET-00723_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-02 | 1 | 2026_ET-00723_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00723_WR | 2026-03-24 | 03-04-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00723_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00723_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00723_RR | 2026-03-18 | No Violations | 03-20-2026 |  | 8 | 2026-03-27 | 0 |  | 2026_ET-00723_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE SANTA CLARA-GETTY_ET-00723 |  |  | No |  | Helicopter | VENTURA | 39 | HC | 2025-10-24 09:44 PDT ¦ 2025-10-24 10:18 PDT | 102425 | 20251024 | Attribute - Wind Speed | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-OLINDA | ET-00763 | 2026_ET-00763 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 24.8895 | 17.3364 | 70 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-25 | 02-02-2026 | 01-06-2026 |  | 2026_ET-00763_ACQPKG | 2026_ET-00763_GSPKG | Submitted | 2026_ET-00763_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00763_GCPR | 2025-12-08 | Historical | 2026_ET-00763_ACQ | QC Accepted | 2026_ET-00763_FR | 2026-01-01 | Submitted | 2026_ET-00763_RWR | Submitted | 2026-01-01 | 2026_ET-00763_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-06 | 0 | 2026_ET-00763_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00763_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00763_VMLAZ | 2026-02-28 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00763_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-00763_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00763_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-OLINDA_ET-00763 |  |  | Yes | 18:42 & 20:08 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-VIEJO | ET-00880 | 2026_ET-00880 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 24.5813 | 21.5832 | 88 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-09-2026 |  | 2026_ET-00880_ACQPKG | 2026_ET-00880_GSPKG | Submitted | 2026_ET-00880_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00880_GCPR | 2025-12-08 | Historical | 2026_ET-00880_ACQ | QC Accepted | 2026_ET-00880_FR | 2026-01-01 | Submitted | 2026_ET-00880_RWR | Submitted | 2026-01-01 | 2026_ET-00880_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00880_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00880_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-13 | 0 | 2026_ET-00880_VMLAZ | 2026-03-09 | QC Accepted | 03-23-2026 | 2026-03-13 | 0 | 2026_ET-00880_VMM1 | 2026-03-02 | QC Accepted |  | 03-23-2026 | 2026-03-13 | 0 | 2026_ET-00880_RR | 2026-03-02 | No Violations | 03-14-2026 | [5 empty] | 2026_ET-00880_VER | 2026-03-02 | Uploaded to S123 | 03-23-2026 | 2026-03-13 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-VIEJO_ET-00880 |  |  | Yes | 17:14 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HIGHWIND-WINDHUB | ET-00920 | 2026_ET-00920 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.5448 | 6.0937 | 64 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-02 | 02-02-2026 | 01-27-2026 |  | 2026_ET-00920_ACQPKG | 2026_ET-00920_GSPKG | Submitted | 2026_ET-00920_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00920_GCPR | 2025-12-08 | Historical | 2026_ET-00920_ACQ | QC Accepted | 2026_ET-00920_FR | 2025-11-27 | Submitted | 2026_ET-00920_RWR | Submitted | 2025-11-27 | 2026_ET-00920_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-27 |  | 2026_ET-00920_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00920_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00920_VMLAZ | 2026-02-23 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-00920_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00920_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00920_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | HIGHWIND-WINDHUB_ET-00920 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MANZANA-WHIRLWIND | ET-00928 | 2026_ET-00928 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.3074 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-13-2026 |  | 2026_ET-00928_ACQPKG | 2026_ET-00928_GSPKG | Submitted | 2026_ET-00928_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00928_GCPR | 2025-12-08 | Historical | 2026_ET-00928_ACQ | QC Accepted | 2026_ET-00928_FR | 2025-11-27 | Submitted | 2026_ET-00928_RWR | Submitted | 2025-11-27 | 2026_ET-00928_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-13 |  | 2026_ET-00928_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00928_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00928_VMLAZ | 2026-02-23 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-00928_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00928_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00928_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MANZANA-WHIRLWIND_ET-00928 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-PARDEE | ET-00999 | 2026_ET-00999 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 26.5405 | 25.5207 | 96 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-25-2026 |  | 2026_ET-00999_ACQPKG | 2026_ET-00999_GSPKG | Submitted | 2026_ET-00999_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00999_GCPR | 2025-12-08 | Historical | 2026_ET-00999_ACQ | QC Accepted | 2026_ET-00999_FR | 2025-11-27 | Submitted | 2026_ET-00999_RWR | Submitted | 2025-11-27 | 2026_ET-00999_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-25 |  | 2026_ET-00999_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00999_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-00999_VMLAZ | 2026-02-17 | QC Accepted | 03-11-2026 | 2026-02-17 | 0 | 2026_ET-00999_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-00999_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-00999_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-PARDEE_ET-00999 | Done |  | Yes |  | Helicopter | VALENCIA | 59 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-VISTA NO.2 | ET-01108 | 2026_ET-01108 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 44.9596 | 37.8433 | 84 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-22 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01108_ACQPKG | 2026_ET-01108_GSPKG | Submitted | 2026_ET-01108_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01108_GCPR | 2025-12-08 | Historical | 2026_ET-01108_ACQ | QC Accepted | 2026_ET-01108_FR | 2026-01-01 | Submitted | 2026_ET-01108_RWR | Submitted | 2026-01-01 | 2026_ET-01108_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01108_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01108_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01108_VMLAZ | 2026-02-28 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01108_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01108_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01108_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEVERS-VISTA NO.2_ET-01108 |  |  | Yes | 15:48 - 19:27 & 16:04 - 19:43 |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-VISTA NO.1 | ET-01135 | 2026_ET-01135 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 44.9449 | 37.7981 | 84 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-22 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01135_ACQPKG | 2026_ET-01135_GSPKG | Submitted | 2026_ET-01135_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01135_GCPR | 2025-12-08 | Historical | 2026_ET-01135_ACQ | QC Accepted | 2026_ET-01135_FR | 2026-01-01 | Submitted | 2026_ET-01135_RWR | Submitted | 2026-01-01 | 2026_ET-01135_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01135_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01135_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01135_VMLAZ | 2026-02-28 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01135_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01135_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01135_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEVERS-VISTA NO.1_ET-01135 |  |  | Yes | 15:48 - 19:27 & 16:04 - 19:43 |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-MIRA LOMA NO.1 | ET-01277 | 2026_ET-01277 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.0716 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-25 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01277_ACQPKG | 2026_ET-01277_GSPKG | Submitted | 2026_ET-01277_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01277_GCPR | 2025-12-08 | Historical | 2026_ET-01277_ACQ | QC Accepted | 2026_ET-01277_FR | 2026-01-01 | Submitted | 2026_ET-01277_RWR | Submitted | 2026-01-01 | 2026_ET-01277_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01277_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01277_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01277_VMLAZ | 2026-02-24 | QC Accepted | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-01277_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-01277_RR | 2026-02-27 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01277_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-MIRA LOMA NO.1_ET-01277 |  |  | Yes | 20:08 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-COLLEGE | ET-00889 | 2026_ET-00889 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.2524 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-09-2026 |  | 2026_ET-00889_ACQPKG | 2026_ET-00889_GSPKG | Submitted | 2026_ET-00889_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00889_GCPR | 2025-12-08 | Historical | 2026_ET-00889_ACQ | QC Accepted | 2026_ET-00889_FR | 2026-01-01 | Submitted | 2026_ET-00889_RWR | Submitted | 2026-01-01 | 2026_ET-00889_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00889_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00889_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-00889_VMLAZ | 2026-02-23 | QC Accepted | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00889_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-00889_RR | 2026-02-27 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-00889_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ALAMITOS-COLLEGE_ET-00889 | Done |  | No | 18:23 |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-TEAM | ET-01392 | 2026_ET-01392 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.1445 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-26 | 01-01-2026 | Flown | 2025-10-24 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01392_ACQPKG | 2026_ET-01392_GSPKG | Submitted | 2026_ET-01392_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01392_GCPR | 2025-12-08 | Historical | 2026_ET-01392_ACQ | QC Accepted | 2026_ET-01392_FR | 2026-01-01 | Submitted | 2026_ET-01392_RWR | Submitted | 2026-01-01 | 2026_ET-01392_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01392_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01392_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01392_VMLAZ | 2026-02-27 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01392_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01392_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01392_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BARRE-TEAM_ET-01392 | Done |  | No | 19:56 |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-LA FRESA NO.3 | ET-01591 | 2026_ET-01591 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.8795 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2026-01-13 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01591_ACQPKG | 2026_ET-01591_GSPKG | Submitted | 2026_ET-01591_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01591_GCPR | 2025-12-08 | Historical | 2026_ET-01591_ACQ | QC Accepted | 2026_ET-01591_FR | 2026-01-01 | Submitted | 2026_ET-01591_RWR | Submitted | 2026-01-01 | 2026_ET-01591_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01591_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01591_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01591_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01591_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01591_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01591_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-LA FRESA NO.3_ET-01591 |  |  | Yes | 18:01 & 15:16 |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-LA FRESA NO.4 | ET-01594 | 2026_ET-01594 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 3.9974 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2026-01-13 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01594_ACQPKG | 2026_ET-01594_GSPKG | Submitted | 2026_ET-01594_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01594_GCPR | 2025-12-08 | Historical | 2026_ET-01594_ACQ | QC Accepted | 2026_ET-01594_FR | 2026-01-01 | Submitted | 2026_ET-01594_RWR | Submitted | 2026-01-01 | 2026_ET-01594_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01594_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01594_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01594_VMLAZ | 2026-02-25 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01594_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01594_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01594_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-LA FRESA NO.4_ET-01594 |  |  | Yes | 18:01 & 15:16 |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OLINDA-WALNUT | ET-01607 | 2026_ET-01607 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 6.2516 | 4.6898 | 75 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-25 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01607_ACQPKG | 2026_ET-01607_GSPKG | Submitted | 2026_ET-01607_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01607_GCPR | 2025-12-08 | Historical | 2026_ET-01607_ACQ | QC Accepted | 2026_ET-01607_FR | 2026-01-01 | Submitted | 2026_ET-01607_RWR | Submitted | 2026-01-01 | 2026_ET-01607_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01607_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01607_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01607_VMLAZ | 2026-02-24 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01607_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01607_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01607_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | OLINDA-WALNUT_ET-01607 |  |  | Yes | 18:42 & 20:08 |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-PHELAN | ET-01729 | 2026_ET-01729 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 15.2822 | 0.97743 | 6 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-10-31 | 02-02-2026 | 02-02-2026 |  | 2026_ET-01729_ACQPKG | 2026_ET-01729_GSPKG | Submitted | 2026_ET-01729_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01729_GCPR | 2025-12-08 | Historical | 2026_ET-01729_ACQ | QC Accepted | 2026_ET-01729_FR | 2025-11-27 | Submitted | 2026_ET-01729_RWR | Submitted | 2025-11-27 | 2026_ET-01729_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-02 |  | 2026_ET-01729_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01729_WR | 2026-03-24 | 03-04-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01729_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 |  | 2026_ET-01729_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01729_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01729_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-PHELAN_ET-01729 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 10:16 PDT ¦ 2025-10-31 12:09 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-RANCHO VISTA | ET-01896 | 2026_ET-01896 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.7535 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01896_ACQPKG | 2026_ET-01896_GSPKG | Submitted | 2026_ET-01896_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01896_GCPR | 2025-12-08 | Historical | 2026_ET-01896_ACQ | QC Accepted | 2026_ET-01896_FR | 2026-01-01 | Submitted | 2026_ET-01896_RWR | Submitted | 2026-01-01 | 2026_ET-01896_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01896_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01896_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01896_VMLAZ | 2026-02-26 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01896_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01896_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01896_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-RANCHO VISTA_ET-01896 |  |  | Yes | 15:48 |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-RANCHO VISTA NO. 1 | ET-01897 | 2026_ET-01897 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.0098 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-14-2026 |  | 2026_ET-01897_ACQPKG | 2026_ET-01897_GSPKG | Submitted | 2026_ET-01897_GS | 2025-11-08 | Field Complete | 2026_ET-01897_GCPR | 2026-01-01 | Submitted | 2026_ET-01897_ACQ | QC Accepted | 2026_ET-01897_FR | 2026-01-01 | Submitted | 2026_ET-01897_RWR | Submitted | 2026-01-01 | 2026_ET-01897_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01897_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01897_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01897_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01897_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01897_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01897_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-RANCHO VISTA NO. 1_ET-01897 |  |  | Yes | 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-RANCHO VISTA NO. 2 | ET-01898 | 2026_ET-01898 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.0043 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-14-2026 |  | 2026_ET-01898_ACQPKG | 2026_ET-01898_GSPKG | Submitted | 2026_ET-01898_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01898_GCPR | 2025-12-08 | Historical | 2026_ET-01898_ACQ | QC Accepted | 2026_ET-01898_FR | 2026-01-01 | Submitted | 2026_ET-01898_RWR | Submitted | 2026-01-01 | 2026_ET-01898_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01898_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01898_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01898_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01898_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01898_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01898_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-RANCHO VISTA NO. 2_ET-01898 |  |  | Yes | 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PADUA-RANCHO VISTA NO.1 | ET-01899 | 2026_ET-01899 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 14.5747 | 10.0328 | 69 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01899_ACQPKG | 2026_ET-01899_GSPKG | Submitted | 2026_ET-01899_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01899_GCPR | 2025-12-08 | Historical | 2026_ET-01899_ACQ | QC Accepted | 2026_ET-01899_FR | 2026-01-01 | Submitted | 2026_ET-01899_RWR | Submitted | 2026-01-01 | 2026_ET-01899_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01899_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01899_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01899_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01899_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01899_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01899_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PADUA-RANCHO VISTA NO.1_ET-01899 |  |  | Yes | 19:31 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PADUA-RANCHO VISTA NO.2 | ET-01900 | 2026_ET-01900 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 14.5117 | 9.9764 | 69 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01900_ACQPKG | 2026_ET-01900_GSPKG | Submitted | 2026_ET-01900_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01900_GCPR | 2025-12-08 | Historical | 2026_ET-01900_ACQ | QC Accepted | 2026_ET-01900_FR | 2026-01-01 | Submitted | 2026_ET-01900_RWR | Submitted | 2026-01-01 | 2026_ET-01900_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01900_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01900_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01900_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01900_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01900_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01900_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PADUA-RANCHO VISTA NO.2_ET-01900 |  |  | Yes | 19:31 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-RANCHO VISTA NO.1 | ET-01901 | 2026_ET-01901 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.45221 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01901_ACQPKG | 2026_ET-01901_GSPKG | Submitted | 2026_ET-01901_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01901_GCPR | 2025-12-08 | Historical | 2026_ET-01901_ACQ | QC Accepted | 2026_ET-01901_FR | 2026-01-01 | Submitted | 2026_ET-01901_RWR | Submitted | 2026-01-01 | 2026_ET-01901_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01901_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01901_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01901_VMLAZ | 2026-02-24 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01901_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01901_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01901_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-RANCHO VISTA NO.1_ET-01901 |  |  | Yes | 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-RANCHO VISTA NO.2 | ET-01903 | 2026_ET-01903 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.46865 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01903_ACQPKG | 2026_ET-01903_GSPKG | Submitted | 2026_ET-01903_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01903_GCPR | 2025-12-08 | Historical | 2026_ET-01903_ACQ | QC Accepted | 2026_ET-01903_FR | 2026-01-01 | Submitted | 2026_ET-01903_RWR | Submitted | 2026-01-01 | 2026_ET-01903_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01903_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01903_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01903_VMLAZ | 2026-02-24 | QC Accepted | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01903_VMM1 | 2026-02-28 | QC Accepted |  | 03-14-2026 | 2026-03-11 | 0 | 2026_ET-01903_RR | 2026-02-28 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01903_VER | 2026-02-28 | Uploaded to S123 | 03-14-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-RANCHO VISTA NO.2_ET-01903 |  |  | Yes | 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-WINDHUB | ET-01907 | 2026_ET-01907 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 25.6113 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-02 | 02-02-2026 | 01-27-2026 |  | 2026_ET-01907_ACQPKG | 2026_ET-01907_GSPKG | Submitted | 2026_ET-01907_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01907_GCPR | 2025-12-08 | Historical | 2026_ET-01907_ACQ | QC Accepted | 2026_ET-01907_FR | 2025-11-27 | Submitted | 2026_ET-01907_RWR | Submitted | 2025-11-27 | 2026_ET-01907_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-27 |  | 2026_ET-01907_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01907_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-01907_VMLAZ | 2026-02-17 | QC Accepted | 03-09-2026 | 2026-02-17 | 0 | 2026_ET-01907_VMM1 | 2026-02-23 | QC Accepted |  | 03-09-2026 | 2026-02-24 | 0 | 2026_ET-01907_RR | 2026-02-23 | No Violations | 02-25-2026 | [5 empty] | 2026_ET-01907_VER | 2026-02-23 | Uploaded to S123 | 03-09-2026 | 2026-02-24 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-WINDHUB_ET-01907 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-WHIRLWIND | ET-01908 | 2026_ET-01908 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 14.3278 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-23-2026 |  | 2026_ET-01908_ACQPKG | 2026_ET-01908_GSPKG | Submitted | 2026_ET-01908_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01908_GCPR | 2025-12-08 | Historical | 2026_ET-01908_ACQ | QC Accepted | 2026_ET-01908_FR | 2025-11-27 | Submitted | 2026_ET-01908_RWR | Submitted | 2025-11-27 | 2026_ET-01908_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-23 |  | 2026_ET-01908_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01908_WR | 2026-02-27 | 03-04-2026 | QC Accepted | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-01908_VMLAZ | 2026-02-23 | QC Accepted | 03-13-2026 | 2026-02-24 | 0 | 2026_ET-01908_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-01908_RR | 2026-02-27 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-01908_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ANTELOPE-WHIRLWIND_ET-01908 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WHIRLWIND-WINDHUB | ET-01910 | 2026_ET-01910 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 16.0527 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-02 | 02-02-2026 | 01-24-2026 |  | 2026_ET-01910_ACQPKG | 2026_ET-01910_GSPKG | Submitted | 2026_ET-01910_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01910_GCPR | 2025-12-08 | Historical | 2026_ET-01910_ACQ | QC Accepted | 2026_ET-01910_FR | 2025-11-27 | Submitted | 2026_ET-01910_RWR | Submitted | 2025-11-27 | 2026_ET-01910_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-24 |  | 2026_ET-01910_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01910_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-01910_VMLAZ | 2026-02-23 | QC Accepted | 03-16-2026 | 2026-02-24 | 0 | 2026_ET-01910_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-01910_RR | 2026-03-02 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-01910_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WHIRLWIND-WINDHUB_ET-01910 |  |  | Yes |  | Helicopter |  |  | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-RANCHO VISTA | ET-01895 | 2026_ET-01895 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 27.6871 | 21.5919 | 78 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-21 | 02-02-2026 | 01-14-2026 |  | 2026_ET-01895_ACQPKG | 2026_ET-01895_GSPKG | Submitted | 2026_ET-01895_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01895_GCPR | 2025-12-08 | Historical | 2026_ET-01895_ACQ | QC Accepted | 2026_ET-01895_FR | 2026-01-01 | Submitted | 2026_ET-01895_RWR | Submitted | 2026-01-01 | 2026_ET-01895_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01895_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01895_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-16 | 0 | 2026_ET-01895_VMLAZ | 2026-02-26 | QC Accepted | 03-16-2026 | 2026-03-16 | 0 | 2026_ET-01895_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-16 | 0 | 2026_ET-01895_RR | 2026-03-02 | No Violations | 03-17-2026 | [5 empty] | 2026_ET-01895_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-RANCHO VISTA_ET-01895 |  |  | Yes | 15:52 - 19:31 & 15:48 |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VINCENT-WHIRLWIND | ET-01914 | 2026_ET-01914 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 36.6365 | 21.3235 | 58 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-11-07 | 02-02-2026 | 01-25-2026 |  | 2026_ET-01914_ACQPKG | 2026_ET-01914_GSPKG | Submitted | 2026_ET-01914_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01914_GCPR | 2025-12-08 | Historical | 2026_ET-01914_ACQ | QC Accepted | 2026_ET-01914_FR | 2025-11-27 | Submitted | 2026_ET-01914_RWR | Submitted | 2025-11-27 | 2026_ET-01914_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-25 |  | 2026_ET-01914_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01914_WR | 2026-02-27 | 03-04-2026 | QC Accepted | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-01914_VMLAZ | 2026-02-23 | QC Accepted | 03-13-2026 | 2026-02-24 | 0 | 2026_ET-01914_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-02 | 0 | 2026_ET-01914_RR | 2026-02-27 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-01914_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VINCENT-WHIRLWIND_ET-01914 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-MIRA LOMA | ET-01966 | 2026_ET-01966 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 31.3909 | 17.0878 | 54 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-24 | 02-02-2026 | 01-21-2026 |  | 2026_ET-01966_ACQPKG | 2026_ET-01966_GSPKG | Submitted | 2026_ET-01966_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01966_GCPR | 2025-12-08 | Historical | 2026_ET-01966_ACQ | QC Accepted | 2026_ET-01966_FR | 2026-01-01 | Submitted | 2026_ET-01966_RWR | Submitted | 2026-01-01 | 2026_ET-01966_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-21 | 1 | 2026_ET-01966_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01966_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01966_VMLAZ | 2026-02-27 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01966_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-01966_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01966_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-MIRA LOMA_ET-01966 |  |  | Yes | 17:14 & 18:42 |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-VINCENT | ET-01967 | 2026_ET-01967 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 42.8688 | 28.7924 | 67 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-04 | 02-02-2026 | 01-25-2026 |  | 2026_ET-01967_ACQPKG | 2026_ET-01967_GSPKG | Submitted | 2026_ET-01967_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01967_GCPR | 2025-12-08 | Historical | 2026_ET-01967_ACQ | QC Accepted | 2026_ET-01967_FR | 2025-11-27 | Submitted | 2026_ET-01967_RWR | Submitted | 2025-11-27 | 2026_ET-01967_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-25 |  | 2026_ET-01967_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01967_WR | 2026-02-25 | 03-04-2026 | QC Accepted | 03-11-2026 | 2026-02-26 | 0 | 2026_ET-01967_VMLAZ | 2026-02-21 | QC Accepted | 03-11-2026 | 2026-02-24 | 0 | 2026_ET-01967_VMM1 | 2026-02-25 | QC Accepted |  | 03-11-2026 | 2026-02-25 | 0 | 2026_ET-01967_RR | 2026-02-25 | No Violations | 02-26-2026 | [5 empty] | 2026_ET-01967_VER | 2026-02-25 | Uploaded to S123 | 03-11-2026 | 2026-02-25 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MESA-VINCENT_ET-01967 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALESSANDRO-KARMA | ET-01986 | 2026_ET-01986 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.1198 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-10-23 | 02-02-2026 | 01-13-2026 |  | 2026_ET-01986_ACQPKG | 2026_ET-01986_GSPKG | Submitted | 2026_ET-01986_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01986_GCPR | 2025-12-08 | Historical | 2026_ET-01986_ACQ | QC Accepted | 2026_ET-01986_FR | 2026-01-01 | Submitted | 2026_ET-01986_RWR | Submitted | 2026-01-01 | 2026_ET-01986_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01986_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01986_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-01986_VMLAZ | 2026-02-23 | QC Accepted | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-01986_VMM1 | 2026-02-27 | QC Accepted |  | 03-13-2026 | 2026-03-11 | 0 | 2026_ET-01986_RR | 2026-02-27 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-01986_VER | 2026-02-27 | Uploaded to S123 | 03-13-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ALESSANDRO-KARMA_ET-01986 | Done |  | No | 15:40 |  | MENIFEE | 77 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-CRIMSON | ET-02031 | 2026_ET-02031 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.15797 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-10-16 | 02-02-2026 | 01-13-2026 |  | 2026_ET-02031_ACQPKG | 2026_ET-02031_GSPKG | Submitted | 2026_ET-02031_GS | 2025-11-08 | Field Complete | 2026_ET-02031_GCPR | 2026-01-01 | Submitted | 2026_ET-02031_ACQ | QC Accepted | 2026_ET-02031_FR | 2026-01-01 | Submitted | 2026_ET-02031_RWR | Submitted | 2026-01-01 | 2026_ET-02031_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-02031_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02031_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-02031_VMLAZ | 2026-02-21 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-02031_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-02031_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-02031_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | COLORADO RIVER-CRIMSON_ET-02031 |  |  | Yes | 15:52 |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SUNWARD-WINDHUB NO.1 | ET-02071 | 2026_ET-02071 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.35885 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-11-02 | 02-02-2026 | 01-16-2026 |  | 2026_ET-02071_ACQPKG | 2026_ET-02071_GSPKG | Submitted | 2026_ET-02071_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02071_GCPR | 2025-12-08 | Historical | 2026_ET-02071_ACQ | QC Accepted | 2026_ET-02071_FR | 2025-11-27 | Submitted | 2026_ET-02071_RWR | Submitted | 2025-11-27 | 2026_ET-02071_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-16 |  | 2026_ET-02071_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02071_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-02071_VMLAZ | 2026-02-23 | QC Accepted | 03-16-2026 | 2026-02-24 | 0 | 2026_ET-02071_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-02 | 0 | 2026_ET-02071_RR | 2026-03-02 | No Violations | 03-03-2026 | [5 empty] | 2026_ET-02071_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-02 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SUNWARD-WINDHUB NO.1_ET-02071 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RAMOLA-VALLEY | ET-02137 | 2026_ET-02137 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.86579 | 0.50809 | 59 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-26 | 02-02-2026 | 01-14-2026 |  | 2026_ET-02137_ACQPKG | 2026_ET-02137_GSPKG | Submitted | 2026_ET-02137_GS | 2025-11-08 | Field Complete | 2026_ET-02137_GCPR | 2026-01-01 | Submitted | 2026_ET-02137_ACQ | QC Accepted | 2026_ET-02137_FR | 2026-01-01 | Submitted | 2026_ET-02137_RWR | Submitted | 2026-01-01 | 2026_ET-02137_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-02137_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02137_WR | 2026-03-03 | 03-04-2026 | QC Accepted | 03-17-2026 | 2026-03-11 | 0 | 2026_ET-02137_VMLAZ | 2026-02-24 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-02137_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-02137_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-02137_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | RAMOLA-VALLEY_ET-02137 |  |  | Yes | 20:21 |  | MENIFEE | 77 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-VELASCO | ET-04406 | 2026_ET-04406 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.5025 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_SAM_CWA_02_r0 | 2026-02-02 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-18 | 02-02-2026 | 01-14-2026 |  | 2026_ET-04406_ACQPKG | 2026_ET-04406_GSPKG | Submitted | 2026_ET-04406_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04406_GCPR | 2025-12-08 | Historical | 2026_ET-04406_ACQ | QC Accepted | 2026_ET-04406_FR | 2026-01-01 | Submitted | 2026_ET-04406_RWR | Submitted | 2026-01-01 | 2026_ET-04406_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-04406_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04406_WR | 2026-03-02 | 03-04-2026 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-04406_VMLAZ | 2026-02-23 | QC Accepted | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-04406_VMM1 | 2026-03-02 | QC Accepted |  | 03-16-2026 | 2026-03-11 | 0 | 2026_ET-04406_RR | 2026-03-02 | No Violations | 03-12-2026 | [5 empty] | 2026_ET-04406_VER | 2026-03-02 | Uploaded to S123 | 03-16-2026 | 2026-03-11 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-VELASCO_ET-04406 |  |  | Yes | 15:38 |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WINDHUB-MONOLITH-WINDFARMS | ET-00158 | 2026_ET-00158 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 11.7785 | 8.2568 | 70 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-03 | 12-11-2025 | Flown | 2025-10-18 | 02-03-2026 | 01-16-2026 |  | 2026_ET-00158_ACQPKG | 2026_ET-00158_GSPKG | Submitted | 2026_ET-00158_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00158_GCPR | 2025-12-08 | Historical | 2026_ET-00158_ACQ | QC Accepted | 2026_ET-00158_FR | 2025-11-13 | Submitted | 2026_ET-00158_RWR | Submitted | 2025-11-13 | 2026_ET-00158_CLAZ | 2025-11-13 | QC Accepted | 01-23-2026 | 2026-01-16 | 0 | 2026_ET-00158_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00158_WR | 2026-02-03 | 03-05-2026 | QC Accepted | 02-17-2026 | 2026-02-13 | 0 | 2026_ET-00158_VMLAZ | 2026-02-02 | QC Accepted | 04-29-2026 | 2026-03-04 | 1 | 2026_ET-00158_VMM1 | 2026-02-03 | QC Accepted |  | 04-29-2026 | 2026-02-13 | 0 | 2026_ET-00158_RR | 2026-02-03 | No Violations | 02-14-2026 |  | 0 | 2026-02-04 | 0 | 0 | 2026_ET-00158_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WINDHUB-MONOLITH-WINDFARMS_ET-00158 |  |  | No |  | Helicopter |  |  | HC | 2025-10-18 11:34 PDT ¦ 2025-10-18 12:11 PDT | 101825 | 20251018 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-PISGAH NO.1 | ET-00290 | 2026_ET-00290 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 65.1977 | 1.5539 | 2 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-01 | 02-03-2026 | 02-03-2026 |  | 2026_ET-00290_ACQPKG | 2026_ET-00290_GSPKG | Submitted | 2026_ET-00290_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00290_GCPR | 2025-12-08 | Historical | 2026_ET-00290_ACQ | QC Accepted | 2026_ET-00290_FR | 2025-11-27 | Submitted | 2026_ET-00290_RWR | Submitted | 2025-11-27 | 2026_ET-00290_CLAZ | 2026-01-09 | QC Accepted | 01-23-2026 | 2026-02-03 |  | 2026_ET-00290_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00290_WR | 2026-03-24 | 03-05-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00290_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00290_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00290_RR | 2026-03-18 | No Violations | 03-20-2026 |  | 3 | 2026-03-27 | 0 |  | 2026_ET-00290_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | LUGO-PISGAH NO.1_ET-00290 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:15 PDT ¦ 2025-12-14 09:00 PST | 110125 | 20251214 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-CORTEZ-MERCED NO. 2 | ET-00897 | 2026_ET-00897 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.6667 | 0.013196 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-24 | 02-03-2026 | 01-12-2026 |  | 2026_ET-00897_ACQPKG | 2026_ET-00897_GSPKG | Submitted | 2026_ET-00897_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00897_GCPR | 2025-12-08 | Historical | 2026_ET-00897_ACQ | QC Accepted | 2026_ET-00897_FR | 2026-01-01 | Submitted | 2026_ET-00897_RWR | Submitted | 2026-01-01 | 2026_ET-00897_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-00897_PROCPKG | Submitted | All Good - Complete | 2026_ET-00897_WR | 2026-03-12 | 03-05-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00897_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00897_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00897_RR | 2026-03-22 | Violations Detected | 03-17-2026 | 03-23-2026 | 2 | 2026-03-23 | 2 | 0 | 2026_ET-00897_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WALNUT-CORTEZ-MERCED NO. 2_ET-00897 |  |  | No | 18:42 |  |  |  | UNK | 2025-10-24 12:24 PDT ¦ 2025-10-24 13:18 PDT | 102425 | 20251024 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-CORTEZ-MERCED NO. 1 | ET-00898 | 2026_ET-00898 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.6266 | 0.013136 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-24 | 02-03-2026 | 01-09-2026 |  | 2026_ET-00898_ACQPKG | 2026_ET-00898_GSPKG | Submitted | 2026_ET-00898_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00898_GCPR | 2025-12-08 | Historical | 2026_ET-00898_ACQ | QC Accepted | 2026_ET-00898_FR | 2026-01-01 | Submitted | 2026_ET-00898_RWR | Submitted | 2026-01-01 | 2026_ET-00898_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-09 | 0 | 2026_ET-00898_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00898_WR | 2026-03-12 | 03-05-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00898_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00898_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00898_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00898_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | WALNUT-CORTEZ-MERCED NO. 1_ET-00898 |  |  | No | 18:42 |  |  |  | UNK | 2025-10-24 12:24 PDT ¦ 2025-10-24 13:18 PDT | 102425 | 20251024 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA HABRA-MWD-TELEGRAPH | ET-01327 | 2026_ET-01327 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 4.5348 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-03 | 12-11-2025 | Flown | 2025-10-25 | 02-03-2026 | 12-11-2025 |  | 2026_ET-01327_ACQPKG | 2026_ET-01327_GSPKG | Submitted | 2026_ET-01327_GS | 2025-11-08 | Field Complete | 2026_ET-01327_GCPR | 2025-11-23 | Submitted | 2026_ET-01327_ACQ | QC Accepted | 2026_ET-01327_FR | 2025-11-23 | Submitted | 2026_ET-01327_RWR | Submitted | 2025-11-23 | 2026_ET-01327_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01327_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01327_WR | 2026-02-01 | 03-05-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01327_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01327_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01327_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01327_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LA HABRA-MWD-TELEGRAPH_ET-01327 |  |  | No | 20:08 | Helicopter | FULLERTON | 48 | HC | 2025-10-25 14:48 PDT ¦ 2025-10-26 14:43 PDT | 102525 | 20251026 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
ESTERO-LEVY-ORMOND BEACH-WASTEWATER-WILL | ET-01374 | 2026_ET-01374 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 12.6873 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-02-03 | 12-11-2025 | Flown | 2025-10-29 | 02-03-2026 | 12-11-2025 |  | 2026_ET-01374_ACQPKG | 2026_ET-01374_GSPKG | Submitted | 2026_ET-01374_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01374_GCPR | 2025-12-08 | Historical | 2026_ET-01374_ACQ | QC Accepted | 2026_ET-01374_FR | 2025-11-29 | Submitted | 2026_ET-01374_RWR | Submitted | 2025-11-29 | 2026_ET-01374_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01374_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01374_WR | 2026-02-01 | 03-05-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01374_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01374_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01374_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01374_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ESTERO-LEVY-ORMOND BEACH-WASTEWATER-WILL_ET-01374 |  |  | No | 16:29 - 20:43 | Helicopter | VENTURA | 39 | HC | 2025-10-15 11:26 PDT ¦ 2025-10-29 14:10 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
VICTOR-APPLE VALLEY-HESPERIA | ET-01430 | 2026_ET-01430 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 17.5359 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-31 | 02-03-2026 | 01-29-2026 |  | 2026_ET-01430_ACQPKG | 2026_ET-01430_GSPKG | Submitted | 2026_ET-01430_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01430_GCPR | 2025-12-08 | Historical | 2026_ET-01430_ACQ | QC Accepted | 2026_ET-01430_FR | 2025-11-27 | Submitted | 2026_ET-01430_RWR | Submitted | 2025-11-27 | 2026_ET-01430_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-29 |  | 2026_ET-01430_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01430_WR | 2026-03-24 | 03-05-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01430_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01430_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01430_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01430_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-APPLE VALLEY-HESPERIA_ET-01430 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 10:16 PDT ¦ 2025-10-31 12:16 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-MAYBERRY-MORENO-VISTA | ET-01471 | 2026_ET-01471 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 51.6538 | 36.2049 | 70 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-23 | 02-03-2026 | 01-16-2026 |  | 2026_ET-01471_ACQPKG | 2026_ET-01471_GSPKG | Submitted | 2026_ET-01471_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01471_GCPR | 2025-12-08 | Historical | 2026_ET-01471_ACQ | QC Accepted | 2026_ET-01471_FR | 2026-01-01 | Submitted | 2026_ET-01471_RWR | Submitted | 2026-01-01 | 2026_ET-01471_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-16 | 0 | 2026_ET-01471_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01471_WR | 2026-02-18 | 03-05-2026 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01471_VMLAZ | 2026-02-18 | QC Accepted | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01471_VMM1 | 2026-02-18 | QC Accepted |  | 04-01-2026 | 2026-03-04 | 0 | 2026_ET-01471_RR | 2026-03-18 | Violations QC Confirmed | 03-05-2026 | 03-19-2026 | 11 | 2026-03-19 | 4 | 7 | 2026_ET-01471_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-MAYBERRY-MORENO-VISTA_ET-01471 |  |  | No | 16:04 & 19:23 |  | MENIFEE | 77 | UNK | 2025-10-20 09:41 PDT ¦ 2025-10-22 13:27 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-ELIZABETH LAKE-MWD FOOTHILL | ET-01570 | 2026_ET-01570 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.9889 | 8.9889 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-28 | 02-03-2026 | 01-14-2026 |  | 2026_ET-01570_ACQPKG | 2026_ET-01570_GSPKG | Submitted | 2026_ET-01570_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01570_GCPR | 2025-12-08 | Historical | 2026_ET-01570_ACQ | QC Accepted | 2026_ET-01570_FR | 2026-01-01 | Submitted | 2026_ET-01570_RWR | Submitted | 2026-01-01 | 2026_ET-01570_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-14 | 0 | 2026_ET-01570_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01570_WR | 2026-03-12 | 03-05-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01570_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01570_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01570_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01570_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SAUGUS-ELIZABETH LAKE-MWD FOOTHILL_ET-01570 |  |  | No | 22:16 & 16:16 |  | VALENCIA | 59 | UNK | 2025-10-25 16:05 PDT ¦ 2025-10-28 10:43 PDT | 102825 | 20251028 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BEVERLY-STUDIO-UNIVERSAL | ET-01587 | 2026_ET-01587 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 5.5838 | 3.7003 | 66 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available |  |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-19 | 02-03-2026 | 01-13-2026 |  | 2026_ET-01587_ACQPKG | 2026_ET-01587_GSPKG | Submitted | 2026_ET-01587_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01587_GCPR | 2025-12-08 | Historical | 2026_ET-01587_ACQ | QC Accepted | 2026_ET-01587_FR | 2026-01-01 | Submitted | 2026_ET-01587_RWR | Submitted | 2026-01-01 | 2026_ET-01587_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-13 | 0 | 2026_ET-01587_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01587_WR | 2026-03-12 | 03-05-2026 | QC Accepted | 03-26-2026 | 2026-03-17 | 0 | 2026_ET-01587_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01587_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-01587_RR | 2026-03-22 | Violations QC Confirmed | 03-18-2026 | 03-23-2026 | 18 | 2026-03-23 | 6 | 12 | 2026_ET-01587_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | BEVERLY-STUDIO-UNIVERSAL_ET-01587 | Done |  | No | 15:54 |  | SANTA MONICA | 42 | UNK | 2025-10-19 09:23 PDT ¦ 2025-10-19 09:40 PDT | 101925 | 20251019 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-AQUEDUCT-HESPERIA | ET-01629 | 2026_ET-01629 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 11.6297 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-31 | 02-03-2026 | 01-29-2026 |  | 2026_ET-01629_ACQPKG | 2026_ET-01629_GSPKG | Submitted | 2026_ET-01629_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01629_GCPR | 2025-12-08 | Historical | 2026_ET-01629_ACQ | QC Accepted | 2026_ET-01629_FR | 2025-11-27 | Submitted | 2026_ET-01629_RWR | Submitted | 2025-11-27 | 2026_ET-01629_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-29 |  | 2026_ET-01629_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01629_WR | 2026-03-24 | 03-05-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01629_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01629_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01629_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01629_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-AQUEDUCT-HESPERIA_ET-01629 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 10:16 PDT ¦ 2025-10-31 12:16 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-AQUEDUCT-PHELAN | ET-01630 | 2026_ET-01630 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 19.1132 | 2.9197 | 15 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-10-31 | 02-03-2026 | 01-29-2026 |  | 2026_ET-01630_ACQPKG | 2026_ET-01630_GSPKG | Submitted | 2026_ET-01630_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01630_GCPR | 2025-12-08 | Historical | 2026_ET-01630_ACQ | QC Accepted | 2026_ET-01630_FR | 2025-11-27 | Submitted | 2026_ET-01630_RWR | Submitted | 2025-11-27 | 2026_ET-01630_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-01-29 |  | 2026_ET-01630_PROCPKG | In Progress | All Good - Complete | 2026_ET-01630_WR | 2026-03-24 | 03-05-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01630_VMLAZ | 2026-03-04 | QC Accepted |  | 2026-03-19 | 0 | 2026_ET-01630_VMM1 | 2026-03-04 | QC Rejected |  |  | 2026-03-19 | 1 | 2026_ET-01630_RR | 2026-03-09 | No Violations |  |  | 0 |  |  |  | 2026_ET-01630_VER | 2026-03-18 | Uploaded to S123 |  | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VICTOR-AQUEDUCT-PHELAN_ET-01630 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-31 10:16 PDT ¦ 2025-10-31 12:16 PDT | 103125 | 20251031 | Attribute - Air Temp |  |  |  |  | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-MWD-STETSON | ET-01784 | 2026_ET-01784 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 13.1105 | 10.3501 | 79 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-03 | 01-01-2026 | Flown | 2025-11-03 | 02-03-2026 | 01-16-2026 |  | 2026_ET-01784_ACQPKG | 2026_ET-01784_GSPKG | Submitted | 2026_ET-01784_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01784_GCPR | 2025-12-08 | Historical | 2026_ET-01784_ACQ | QC Accepted | 2026_ET-01784_FR | 2026-01-01 | Submitted | 2026_ET-01784_RWR | Submitted | 2026-01-01 | 2026_ET-01784_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-16 | 0 | 2026_ET-01784_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01784_WR | 2026-03-12 | 03-05-2026 | QC Accepted | 03-26-2026 | 2026-03-04 | 0 | 2026_ET-01784_VMLAZ | 2026-02-18 | QC Accepted | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01784_VMM1 | 2026-02-18 | QC Accepted |  | 03-04-2026 | 2026-03-04 | 0 | 2026_ET-01784_RR | 2026-02-18 | No Violations | 03-05-2026 |  | 0 |  |  |  | 2026_ET-01784_VER | 2026-02-18 | Uploaded to S123 | 03-04-2026 | 2026-03-04 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VALLEY-MWD-STETSON_ET-01784 |  |  | No | 16:04 & 19:23 |  | MENIFEE | 77 | UNK | 2025-10-16 13:16 PDT ¦ 2025-11-03 13:46 PST | 102325 | 20251103 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CAL CEMENT-MONOLITH-RSMOND-WNDFRMS | ET-01796 | 2026_ET-01796 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.92176 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-01-30 | 01-01-2026 | Flown | 2025-11-02 | 02-04-2026 | 02-04-2026 |  | 2026_ET-01796_ACQPKG | 2026_ET-01796_GSPKG | Submitted | 2026_ET-01796_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01796_GCPR | 2025-12-08 | Historical | 2026_ET-01796_ACQ | QC Accepted | 2026_ET-01796_FR | 2025-11-27 | Submitted | 2026_ET-01796_RWR | Submitted | 2025-11-27 | 2026_ET-01796_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-04 |  | 2026_ET-01796_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01796_WR | 2026-03-24 | 03-06-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01796_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01796_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01796_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-01796_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CAL CEMENT-MONOLITH-RSMOND-WNDFRMS_ET-01796 |  |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-11-02 11:36 PST ¦ 2025-11-02 11:38 PST | 110225 | 20251102 | Does not contain Latitude, Longitude, Probe Latitude, or Probe Longitude Values | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VALLEY-AULD-TRITON | ET-00067 | 2026_ET-00067 |  | 1 | 2026 | May 01, 2026 | 115 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.5471 | 1.1101 | 72 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-10 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00067_ACQPKG | 2026_ET-00067_GSPKG | Submitted | 2026_ET-00067_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00067_GCPR | 2025-12-08 | Historical | 2026_ET-00067_ACQ | QC Accepted | 2026_ET-00067_FR | 2026-01-31 | Submitted | 2026_ET-00067_RWR | Submitted | 2026-01-31 | 2026_ET-00067_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00067_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00067_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00067_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00067_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00067_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00067_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE VALLEY-AULD-TRITON_ET-00067 |  |  | No | 20:26 |  | WILDOMAR | 88 | UNK | 2025-12-10 10:24 PST ¦ 2025-12-10 13:12 PST | 121025 | 20251210 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-NEENACH | ET-00285 | 2026_ET-00285 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 16.6277 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-15 | 02-07-2026 | 01-30-2026 |  | 2026_ET-00285_ACQPKG | 2026_ET-00285_GSPKG | Submitted | 2026_ET-00285_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00285_GCPR | 2025-12-08 | Historical | 2026_ET-00285_ACQ | QC Accepted | 2026_ET-00285_FR | 2026-01-09 | Submitted | 2026_ET-00285_RWR | Submitted | 2026-01-09 | 2026_ET-00285_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-01-30 |  | 2026_ET-00285_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00285_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-29 |  | 2026_ET-00285_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00285_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00285_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00285_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ANTELOPE-NEENACH_ET-00285 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-15 08:50 PST ¦ 2025-12-15 09:27 PST | 121525 | 20251215 |  |  |  |  | Attribute - Project |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOVINE-LA MIRADA | ET-00334 | 2026_ET-00334 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 5.8483 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-21 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00334_ACQPKG | 2026_ET-00334_GSPKG | Submitted | 2026_ET-00334_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00334_GCPR | 2025-12-08 | Historical | 2026_ET-00334_ACQ | QC Accepted | 2026_ET-00334_FR | 2026-01-31 | Submitted | 2026_ET-00334_RWR | Submitted | 2026-01-31 | 2026_ET-00334_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00334_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00334_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00334_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00334_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00334_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00334_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BOVINE-LA MIRADA_ET-00334 | Done |  | No | 19:32 & 21:12 |  | FULLERTON | 48 | UNK | 2025-12-20 13:18 PST ¦ 2026-01-09 10:55 PST | 122125 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE GALLATIN-LAGUNA BELL-MERCURY-SPONGE | ET-00418 | 2026_ET-00418 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.11921 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-16 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00418_ACQPKG | 2026_ET-00418_GSPKG | Submitted | 2026_ET-00418_GS |  | Field Complete | 2026_ET-00418_GCPR | 2026-01-31 | Submitted | 2026_ET-00418_ACQ | QC Accepted | 2026_ET-00418_FR | 2026-01-31 | Submitted | 2026_ET-00418_RWR | Submitted | 2026-01-31 | 2026_ET-00418_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00418_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00418_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00418_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00418_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00418_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00418_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE GALLATIN-LAGUNA BELL-MERCURY-SPONGE_ET-00418 |  |  | No | 19:30 |  | WHITTIER | 47 | UNK | 2025-12-16 11:30 PST ¦ 2025-12-16 11:31 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-HINSON | ET-00464 | 2026_ET-00464 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 12.4985 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2026-01-09 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00464_ACQPKG | 2026_ET-00464_GSPKG | Submitted | 2026_ET-00464_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00464_GCPR | 2025-12-08 | Historical | 2026_ET-00464_ACQ | QC Accepted | 2026_ET-00464_FR | 2026-01-31 | Submitted | 2026_ET-00464_RWR | Submitted | 2026-01-31 | 2026_ET-00464_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00464_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00464_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00464_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00464_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00464_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00464_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | DEL AMO-HINSON_ET-00464 |  |  | Yes | 18:13 |  | LONG BEACH | 46 | UNK | 2025-12-16 13:48 PST ¦ 2026-01-09 14:45 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-LA PALMA NO. 2 | ET-00541 | 2026_ET-00541 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.7006 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-20 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00541_ACQPKG | 2026_ET-00541_GSPKG | Submitted | 2026_ET-00541_GS |  | Field Complete | 2026_ET-00541_GCPR | 2026-01-31 | Submitted | 2026_ET-00541_ACQ | QC Accepted | 2026_ET-00541_FR | 2026-01-31 | Submitted | 2026_ET-00541_RWR | Submitted | 2026-01-31 | 2026_ET-00541_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00541_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00541_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00541_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00541_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00541_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00541_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BARRE-LA PALMA NO. 2_ET-00541 | Done |  | No | 21:10 |  | FULLERTON | 48 | UNK | 2025-12-20 13:11 PST ¦ 2025-12-20 13:22 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE WALNUT-JOHNSTON-SAN DIMAS | ET-00691 | 2026_ET-00691 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.9951 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-14 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00691_ACQPKG | 2026_ET-00691_GSPKG | Submitted | 2026_ET-00691_GS |  | Field Complete | 2026_ET-00691_GCPR | 2026-01-31 | Submitted | 2026_ET-00691_ACQ | QC Accepted | 2026_ET-00691_FR | 2026-01-31 | Submitted | 2026_ET-00691_RWR | Submitted | 2026-01-31 | 2026_ET-00691_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00691_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00691_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00691_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00691_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00691_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00691_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE WALNUT-JOHNSTON-SAN DIMAS_ET-00691 |  |  | No | 21:41 |  | COVINA | 26 | UNK | 2025-12-14 13:36 PST ¦ 2025-12-14 13:42 PST | 121425 | 20251214 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AULD-SUN CITY | ET-00902 | 2026_ET-00902 |  | 1 | 2026 | May 01, 2026 | 115 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.6851 | 4.0503 | 53 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-10 | 02-07-2026 | 02-06-2026 |  | 2026_ET-00902_ACQPKG | 2026_ET-00902_GSPKG | Submitted | 2026_ET-00902_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00902_GCPR | 2025-12-08 | Historical | 2026_ET-00902_ACQ | QC Accepted | 2026_ET-00902_FR | 2026-01-31 | Submitted | 2026_ET-00902_RWR | Submitted | 2026-01-31 | 2026_ET-00902_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00902_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00902_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00902_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00902_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00902_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00902_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | AULD-SUN CITY_ET-00902 | Done |  | No | 19:01 - 20:56 |  | WILDOMAR | 88 | UNK | 2025-12-10 10:24 PST ¦ 2025-12-10 13:12 PST | 121025 | 20251210 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE INYOKERN-MCGEN-SEARLES | ET-02052 | 2026_ET-02052 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 5.0754 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-11-02 | 02-07-2026 | 01-28-2026 |  | 2026_ET-02052_ACQPKG | 2026_ET-02052_GSPKG | Submitted | 2026_ET-02052_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02052_GCPR | 2025-12-08 | Historical | 2026_ET-02052_ACQ | QC Accepted | 2026_ET-02052_FR | 2025-12-01 | Submitted | 2026_ET-02052_RWR | Submitted | 2025-12-01 | 2026_ET-02052_CLAZ | 2025-12-01 | QC Accepted | 02-15-2026 | 2026-01-28 |  | 2026_ET-02052_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02052_WR | 2026-03-12 | 03-09-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-02052_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-23 | 0 | 2026_ET-02052_VMM1 | 2026-04-15 | QC Accepted |  | 04-29-2026 | 2026-04-20 | 1 | 2026_ET-02052_RR |  | No Violations | 04-21-2026 | [5 empty] | 2026_ET-02052_VER | 2026-03-18 | Uploaded to S123 | 04-29-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE INYOKERN-MCGEN-SEARLES_ET-02052 |  |  | No |  | Helicopter | RIDGECREST | 86 | HC | 2025-11-02 13:46 PST ¦ 2025-11-02 13:59 PST | 110225 | 20251102 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-DEL SUR-GLOW | ET-00155 | 2026_ET-00155 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.7354 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-15 | 02-09-2026 | 02-09-2026 |  | 2026_ET-00155_ACQPKG | 2026_ET-00155_GSPKG | Submitted | 2026_ET-00155_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00155_GCPR | 2025-12-08 | Historical | 2026_ET-00155_ACQ | QC Accepted | 2026_ET-00155_FR | 2026-01-09 | Submitted | 2026_ET-00155_RWR | Submitted | 2026-01-09 | 2026_ET-00155_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-09 |  | 2026_ET-00155_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00155_WR | 2026-03-12 | 03-11-2026 | QC Accepted | 04-01-2026 | 2026-04-29 |  | 2026_ET-00155_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00155_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00155_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00155_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ANTELOPE-DEL SUR-GLOW_ET-00155 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-15 09:12 PST ¦ 2025-12-15 09:32 PST | 121525 | 20251215 |  |  |  |  | Attribute - Project |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARODEAN-HI DESERT | ET-00046 | 2026_ET-00046 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.9175 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-22 | 02-11-2026 | 02-06-2026 |  | 2026_ET-00046_ACQPKG | 2026_ET-00046_GSPKG | Submitted | 2026_ET-00046_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00046_GCPR | 2025-12-08 | Historical | 2026_ET-00046_ACQ | QC Accepted | 2026_ET-00046_FR | 2026-01-31 | Submitted | 2026_ET-00046_RWR | Submitted | 2026-01-31 | 2026_ET-00046_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00046_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00046_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00046_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00046_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00046_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00046_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CARODEAN-HI DESERT_ET-00046 | Done |  | No | 22:00 |  | YUCCA VALLEY | 84 | UNK | 2025-12-22 13:35 PST ¦ 2025-12-22 14:04 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MOHAVE | ET-00079 | 2026_ET-00079 |  | 1 | 2026 | May 01, 2026 | 500 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 59.561 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-17 | 02-11-2026 | 02-05-2026 |  | 2026_ET-00079_ACQPKG | 2026_ET-00079_GSPKG | Submitted | 2026_ET-00079_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00079_GCPR | 2025-12-08 | Historical | 2026_ET-00079_ACQ | QC Accepted | 2026_ET-00079_FR | 2026-01-09 | Submitted | 2026_ET-00079_RWR | Submitted | 2026-01-09 | 2026_ET-00079_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-05 |  | 2026_ET-00079_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00079_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-01 | 1 | 2026_ET-00079_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-23 | 0 | 2026_ET-00079_VMM1 | 2026-03-15 | QC Accepted |  | 04-29-2026 | 2026-03-19 | 0 | 2026_ET-00079_RR |  | No Violations | 03-20-2026 | [5 empty] | 2026_ET-00079_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MOHAVE_ET-00079 |  |  | Yes |  | Helicopter |  |  | HC | 2025-12-17 11:13 PST ¦ 2025-12-17 13:18 PST | 121725 | 20251217 | Does not contain Latitude, Longitude, Probe Latitude, or Probe Longitude Values |  |  |  | Attribute - Height POI |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KINGBIRD-WHIRLWIND | ET-00107 | 2026_ET-00107 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.52744 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-15 | 02-11-2026 | 02-05-2026 |  | 2026_ET-00107_ACQPKG | 2026_ET-00107_GSPKG | Submitted | 2026_ET-00107_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00107_GCPR | 2025-12-08 | Historical | 2026_ET-00107_ACQ | QC Accepted | 2026_ET-00107_FR | 2026-01-09 | Submitted | 2026_ET-00107_RWR | Submitted | 2026-01-09 | 2026_ET-00107_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-05 |  | 2026_ET-00107_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00107_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00107_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00107_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00107_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00107_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | KINGBIRD-WHIRLWIND_ET-00107 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-15 08:36 PST ¦ 2025-12-15 08:45 PST | 121525 | 20251215 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MOENKOPI | ET-00121 | 2026_ET-00121 |  | 1 | 2026 | May 01, 2026 | 500 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 28.0763 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-10-30 | 02-11-2026 | 01-27-2026 |  | 2026_ET-00121_ACQPKG | 2026_ET-00121_GSPKG | Submitted | 2026_ET-00121_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00121_GCPR | 2025-12-08 | Historical | 2026_ET-00121_ACQ | QC Accepted | 2026_ET-00121_FR | 2025-12-01 | Submitted | 2026_ET-00121_RWR | Submitted | 2025-12-01 | 2026_ET-00121_CLAZ | 2025-12-01 | QC Accepted | 02-15-2026 | 2026-01-27 |  | 2026_ET-00121_PROCPKG | In Progress | All Good - Complete | 2026_ET-00121_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-01 | 1 | 2026_ET-00121_VMLAZ | 2026-03-12 | QC Accepted |  | 2026-03-24 |  | 2026_ET-00121_VMM1 | 2026-04-28 | QC Rejected |  |  | 2026-05-04 | 2 | 2026_ET-00121_RR |  | No Violations | [6 empty] | 2026_ET-00121_VER | 2026-04-15 | Uploaded to S123 |  | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MOENKOPI_ET-00121 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:38 PDT ¦ 2025-10-30 14:21 PDT | 103025 | 20251030 | Does not contain Latitude, Longitude, Probe Latitude, or Probe Longitude Values |  |  |  |  | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-PEPPER | ET-00291 | 2026_ET-00291 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.1156 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-16 | 02-11-2026 | 02-06-2026 |  | 2026_ET-00291_ACQPKG | 2026_ET-00291_GSPKG | Submitted | 2026_ET-00291_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00291_GCPR | 2025-12-08 | Historical | 2026_ET-00291_ACQ | QC Accepted | 2026_ET-00291_FR | 2026-01-31 | Submitted | 2026_ET-00291_RWR | Submitted | 2026-01-31 | 2026_ET-00291_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00291_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00291_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00291_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00291_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00291_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00291_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CALECTRIC-PEPPER_ET-00291 | Done |  | No | 17:30 |  | REDLANDS | 31 | UNK | 2025-12-16 10:20 PST ¦ 2025-12-16 10:40 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MEAD NO.1 | ET-00517 | 2026_ET-00517 |  | 1 | 2026 | May 01, 2026 | 220 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 15.2506 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-10-30 | 02-11-2026 | 01-27-2026 |  | 2026_ET-00517_ACQPKG | 2026_ET-00517_GSPKG | Submitted | 2026_ET-00517_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00517_GCPR | 2025-12-08 | Historical | 2026_ET-00517_ACQ | QC Accepted | 2026_ET-00517_FR | 2025-12-01 | Submitted | 2026_ET-00517_RWR | Submitted | 2025-12-01 | 2026_ET-00517_CLAZ | 2025-12-01 | QC Accepted | 02-15-2026 | 2026-01-27 |  | 2026_ET-00517_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00517_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00517_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-19 | 1 | 2026_ET-00517_VMM1 | 2026-03-12 | QC Accepted |  | 04-29-2026 | 2026-03-19 | 0 | 2026_ET-00517_RR |  | No Violations | 03-20-2026 | [5 empty] | 2026_ET-00517_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MEAD NO.1_ET-00517 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-30 14:31 PDT | 103025 | 20251030 |  |  | Missing Epoch 2017.5 |  |  |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MEAD NO.2 | ET-00521 | 2026_ET-00521 |  | 1 | 2026 | May 01, 2026 | 220 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 15.2402 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-10-30 | 02-11-2026 | 01-28-2026 |  | 2026_ET-00521_ACQPKG | 2026_ET-00521_GSPKG | Submitted | 2026_ET-00521_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00521_GCPR | 2025-12-08 | Historical | 2026_ET-00521_ACQ | QC Accepted | 2026_ET-00521_FR | 2025-12-01 | Submitted | 2026_ET-00521_RWR | Submitted | 2025-12-01 | 2026_ET-00521_CLAZ | 2025-12-01 | QC Accepted | 02-15-2026 | 2026-01-28 |  | 2026_ET-00521_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00521_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00521_VMLAZ | 2026-03-12 | QC Accepted | 05-05-2026 | 2026-03-19 | 1 | 2026_ET-00521_VMM1 | 2026-04-21 | QC Accepted |  | 05-05-2026 | 2026-04-30 | 1 | 2026_ET-00521_RR |  | No Violations | 05-01-2026 | [5 empty] | 2026_ET-00521_VER | 2026-04-15 | Uploaded to S123 | 05-05-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MEAD NO.2_ET-00521 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:46 PDT ¦ 2025-10-30 14:31 PDT | 103025 | 20251030 |  |  | Missing Epoch 2017.5 |  |  |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-HIGHGROVE NO. 1 | ET-00623 | 2026_ET-00623 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.8969 | 3.5259 | 45 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-16 | 02-11-2026 | 02-06-2026 |  | 2026_ET-00623_ACQPKG | 2026_ET-00623_GSPKG | Submitted | 2026_ET-00623_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00623_GCPR | 2025-12-08 | Historical | 2026_ET-00623_ACQ | QC Accepted | 2026_ET-00623_FR | 2026-01-31 | Submitted | 2026_ET-00623_RWR | Submitted | 2026-01-31 | 2026_ET-00623_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00623_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00623_WR | 2026-03-12 | 03-13-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00623_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00623_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00623_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00623_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CALECTRIC-HIGHGROVE NO. 1_ET-00623 | Done |  | No | 17:30 |  | REDLANDS | 31 | UNK | 2025-12-16 10:07 PST ¦ 2025-12-16 10:44 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VICTOR NO. 3 | ET-00038 | 2026_ET-00038 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.7711 | 1.4968 | 14 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-31 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00038_ACQPKG | 2026_ET-00038_GSPKG | Submitted | 2026_ET-00038_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00038_GCPR | 2025-12-08 | Historical | 2026_ET-00038_ACQ | QC Accepted | 2026_ET-00038_FR | 2025-11-27 | Submitted | 2026_ET-00038_RWR | Submitted | 2025-11-27 | 2026_ET-00038_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-12 |  | 2026_ET-00038_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00038_WR | 2026-03-24 | 03-14-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00038_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00038_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00038_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00038_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VICTOR NO. 3_ET-00038 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:15 PDT ¦ 2025-10-31 12:10 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VICTOR NO. 4 | ET-00039 | 2026_ET-00039 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.7752 | 1.4998 | 14 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-31 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00039_ACQPKG | 2026_ET-00039_GSPKG | Submitted | 2026_ET-00039_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00039_GCPR | 2025-12-08 | Historical | 2026_ET-00039_ACQ | QC Accepted | 2026_ET-00039_FR | 2025-11-27 | Submitted | 2026_ET-00039_RWR | Submitted | 2025-11-27 | 2026_ET-00039_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-12 |  | 2026_ET-00039_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00039_WR | 2026-03-24 | 03-14-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00039_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00039_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00039_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00039_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VICTOR NO. 4_ET-00039 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:15 PDT ¦ 2025-10-31 12:11 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VICTORVILLE | ET-00117 | 2026_ET-00117 |  | 1 | 2026 | Apr 01, 2026 | 500 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 7.6259 | 1.5483 | 20 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-31 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00117_ACQPKG | 2026_ET-00117_GSPKG | Submitted | 2026_ET-00117_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00117_GCPR | 2025-12-08 | Historical | 2026_ET-00117_ACQ | QC Accepted | 2026_ET-00117_FR | 2025-11-27 | Submitted | 2026_ET-00117_RWR | Submitted | 2025-11-27 | 2026_ET-00117_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-12 |  | 2026_ET-00117_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00117_WR | 2026-03-24 | 03-14-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00117_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00117_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00117_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00117_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VICTORVILLE_ET-00117 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:18 PDT ¦ 2025-10-31 11:59 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VICTOR NO.1 | ET-00299 | 2026_ET-00299 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.9115 | 1.5128 | 14 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-31 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00299_ACQPKG | 2026_ET-00299_GSPKG | Submitted | 2026_ET-00299_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00299_GCPR | 2025-12-08 | Historical | 2026_ET-00299_ACQ | QC Accepted | 2026_ET-00299_FR | 2025-11-27 | Submitted | 2026_ET-00299_RWR | Submitted | 2025-11-27 | 2026_ET-00299_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-12 |  | 2026_ET-00299_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00299_WR | 2026-03-24 | 03-14-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00299_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00299_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00299_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00299_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VICTOR NO.1_ET-00299 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:15 PDT ¦ 2025-10-31 12:11 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-VICTOR NO.2 | ET-00306 | 2026_ET-00306 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 10.9223 | 1.5144 | 14 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-10-31 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00306_ACQPKG | 2026_ET-00306_GSPKG | Submitted | 2026_ET-00306_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00306_GCPR | 2025-12-08 | Historical | 2026_ET-00306_ACQ | QC Accepted | 2026_ET-00306_FR | 2025-11-27 | Submitted | 2026_ET-00306_RWR | Submitted | 2025-11-27 | 2026_ET-00306_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-12 |  | 2026_ET-00306_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00306_WR | 2026-03-24 | 03-14-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00306_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00306_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00306_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00306_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | LUGO-VICTOR NO.2_ET-00306 |  |  | Yes |  | Helicopter | VICTORVILLE | 73 | HC | 2025-10-28 11:18 PDT ¦ 2025-10-31 12:11 PDT | 103125 | 20251031 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-SANTA CLARA NO.2 | ET-00338 | 2026_ET-00338 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 49.156 | 49.156 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2026-01-06 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00338_ACQPKG | 2026_ET-00338_GSPKG | Submitted | 2026_ET-00338_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00338_GCPR | 2025-12-08 | Historical | 2026_ET-00338_ACQ | QC Accepted | 2026_ET-00338_FR | 2026-01-31 | Submitted | 2026_ET-00338_RWR | Submitted | 2026-01-31 | 2026_ET-00338_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00338_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00338_WR | 2026-03-12 | 03-14-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00338_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00338_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00338_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00338_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | GOLETA-SANTA CLARA NO.2_ET-00338 |  |  | Yes | 17:03 & 21:21 & 16:56 - 20:18 |  | SANTA BARBARA | 49 | UNK | 2025-12-28 11:03 PST ¦ 2026-01-06 13:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-ELIZABETH LAKE-FILLMORE | ET-00630 | 2026_ET-00630 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 12.165 | 12.165 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-27 | 02-12-2026 | 02-12-2026 |  | 2026_ET-00630_ACQPKG | 2026_ET-00630_GSPKG | Submitted | 2026_ET-00630_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00630_GCPR | 2025-12-08 | Historical | 2026_ET-00630_ACQ | QC Accepted | 2026_ET-00630_FR | 2026-01-31 | Submitted | 2026_ET-00630_RWR | Submitted | 2026-01-31 | 2026_ET-00630_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00630_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00630_WR | 2026-03-12 | 03-14-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00630_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00630_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00630_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00630_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-ELIZABETH LAKE-FILLMORE_ET-00630 |  |  | No | 21:21 |  | VALENCIA | 59 | UNK | 2025-12-27 13:54 PST ¦ 2025-12-27 15:10 PST | 122725 | 20251227 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VINCENT-WINDSTAR 1 | ET-00153 | 2026_ET-00153 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 1.345 | 1.345 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 01-01-2026 | Flown | 2025-11-04 | 02-13-2026 | 02-13-2026 |  | 2026_ET-00153_ACQPKG | 2026_ET-00153_GSPKG | Submitted | 2026_ET-00153_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00153_GCPR | 2025-12-08 | Historical | 2026_ET-00153_ACQ | QC Accepted | 2026_ET-00153_FR | 2025-11-27 | Submitted | 2026_ET-00153_RWR | Submitted | 2025-11-27 | 2026_ET-00153_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-13 |  | 2026_ET-00153_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00153_WR | 2026-03-24 | 03-15-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00153_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-19 |  | 2026_ET-00153_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00153_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00153_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | VINCENT-WINDSTAR 1_ET-00153 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-10-19 12:34 PDT ¦ 2025-11-04 10:08 PST | 101925 | 20251104 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VILLA PARK-PAPER-PLACENTIA | ET-01295 | 2026_ET-01295 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.75394 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-16 | 02-13-2026 | 02-13-2026 |  | 2026_ET-01295_ACQPKG | 2026_ET-01295_GSPKG | Submitted | 2026_ET-01295_GS |  | Field Complete | 2026_ET-01295_GCPR | 2026-01-31 | Submitted | 2026_ET-01295_ACQ | QC Accepted | 2026_ET-01295_FR | 2026-01-31 | Submitted | 2026_ET-01295_RWR | Submitted | 2026-01-31 | 2026_ET-01295_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01295_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01295_WR | 2026-03-12 | 03-15-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01295_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01295_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01295_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01295_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE VILLA PARK-PAPER-PLACENTIA_ET-01295 |  |  | No | 19:10 |  | FULLERTON | 48 | UNK | 2025-12-16 11:07 PST ¦ 2025-12-16 11:10 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTIAGO-BRYAN-CABRLLO-IRVNE-JOHNNA | ET-01305 | 2026_ET-01305 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.36773 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-11-05 | 02-13-2026 | 02-13-2026 |  | 2026_ET-01305_ACQPKG | 2026_ET-01305_GSPKG | Submitted | 2026_ET-01305_GS |  | Field Complete | 2026_ET-01305_GCPR | 2026-01-31 | Submitted | 2026_ET-01305_ACQ | QC Accepted | 2026_ET-01305_FR | 2026-01-31 | Submitted | 2026_ET-01305_RWR | Submitted | 2026-01-31 | 2026_ET-01305_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01305_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01305_WR | 2026-03-18 | 03-15-2026 | QC Accepted | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-01305_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-01305_VMM1 | 2026-03-18 | QC Accepted |  | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-01305_RR | 2026-03-19 | No Violations | 03-26-2026 | [5 empty] | 2026_ET-01305_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE SANTIAGO-BRYAN-CABRLLO-IRVNE-JOHNNA_ET-01305 |  |  | No | 14:08 |  | SANTA ANA | 29 | UNK | 2026-01-14 06:22 PST ¦ 2026-01-14 06:36 PST | 011426 | 20260114 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEL AMO-LAKEWOOD-TURBO | ET-01347 | 2026_ET-01347 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.039235 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2026-01-09 | 02-13-2026 | 02-13-2026 |  | 2026_ET-01347_ACQPKG | 2026_ET-01347_GSPKG | Submitted | 2026_ET-01347_GS |  | Field Complete | 2026_ET-01347_GCPR | 2026-01-31 | Submitted | 2026_ET-01347_ACQ | QC Accepted | 2026_ET-01347_FR | 2026-01-31 | Submitted | 2026_ET-01347_RWR | Submitted | 2026-01-31 | 2026_ET-01347_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01347_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01347_WR | 2026-03-12 | 03-15-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01347_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01347_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01347_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01347_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE DEL AMO-LAKEWOOD-TURBO_ET-01347 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 11:40 PST ¦ 2026-01-09 11:45 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-HARRY ALLEN | ET-01983 | 2026_ET-01983 |  | 1 | 2026 | Apr 01, 2026 | 500 | NV_E | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.52037 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-30 | 02-13-2026 | 02-13-2026 |  | 2026_ET-01983_ACQPKG | 2026_ET-01983_GSPKG | Submitted | 2026_ET-01983_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01983_GCPR | 2025-12-08 | Historical | 2026_ET-01983_ACQ | QC Accepted | 2026_ET-01983_FR | 2025-11-27 | Submitted | 2026_ET-01983_RWR | Submitted | 2025-11-27 | 2026_ET-01983_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-13 |  | 2026_ET-01983_PROCPKG | In Progress | All Good - Complete | 2026_ET-01983_WR | 2026-03-24 | 03-15-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01983_VMLAZ | 2026-03-16 | QC Accepted |  | 2026-03-23 | 0 | 2026_ET-01983_VMM1 | 2026-03-05 | QC Rejected |  |  | 2026-03-19 | 1 | 2026_ET-01983_RR | 2026-03-09 | No Violations |  |  | 0 |  |  |  | 2026_ET-01983_VER | 2026-03-18 | Uploaded to S123 |  | 2026-03-25 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-HARRY ALLEN_ET-01983 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-30 14:32 PDT | 102925 | 20251030 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARODEAN-LEATHERNECK | ET-00047 | 2026_ET-00047 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 8.9918 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-22 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00047_ACQPKG | 2026_ET-00047_GSPKG | Submitted | 2026_ET-00047_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00047_GCPR | 2025-12-08 | Historical | 2026_ET-00047_ACQ | QC Accepted | 2026_ET-00047_FR | 2026-01-31 | Submitted | 2026_ET-00047_RWR | Submitted | 2026-01-31 | 2026_ET-00047_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00047_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00047_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00047_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00047_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00047_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00047_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CARODEAN-LEATHERNECK_ET-00047 | Done |  | No | 21:49 - 22:16 |  | YUCCA VALLEY | 84 | UNK | 2025-12-22 13:40 PST ¦ 2025-12-22 14:19 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-CYPRESS-MARION | ET-00242 | 2026_ET-00242 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 6.452 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-20 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00242_ACQPKG | 2026_ET-00242_GSPKG | Submitted | 2026_ET-00242_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00242_GCPR | 2025-12-08 | Historical | 2026_ET-00242_ACQ | QC Accepted | 2026_ET-00242_FR | 2026-01-31 | Submitted | 2026_ET-00242_RWR | Submitted | 2026-01-31 | 2026_ET-00242_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00242_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00242_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00242_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00242_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00242_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00242_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BARRE-CYPRESS-MARION_ET-00242 | Done |  | No | 19:32 |  | FULLERTON | 48 | UNK | 2025-12-20 12:52 PST ¦ 2025-12-20 14:09 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COTTONWOOD-SAVAGE | ET-00316 | 2026_ET-00316 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 30.1501 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-14 | 02-14-2026 | 02-05-2026 |  | 2026_ET-00316_ACQPKG | 2026_ET-00316_GSPKG | Submitted | 2026_ET-00316_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00316_GCPR | 2025-12-08 | Historical | 2026_ET-00316_ACQ | QC Accepted | 2026_ET-00316_FR | 2026-01-09 | Submitted | 2026_ET-00316_RWR | Submitted | 2026-01-09 | 2026_ET-00316_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-05 |  | 2026_ET-00316_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00316_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-01 | 1 | 2026_ET-00316_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00316_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00316_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00316_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | COTTONWOOD-SAVAGE_ET-00316 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-12-14 07:59 PST ¦ 2025-12-14 08:45 PST | 121425 | 20251214 | Does not contain Latitude, Longitude, Probe Latitude, or Probe Longitude Values | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ROYAL NO. 2 | ET-00444 | 2026_ET-00444 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 9.7584 | 9.7584 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-08 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00444_ACQPKG | 2026_ET-00444_GSPKG | Submitted | 2026_ET-00444_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00444_GCPR | 2025-12-08 | Historical | 2026_ET-00444_ACQ | QC Accepted | 2026_ET-00444_FR | 2026-01-31 | Submitted | 2026_ET-00444_RWR | Submitted | 2026-01-31 | 2026_ET-00444_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00444_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00444_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00444_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00444_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00444_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00444_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MOORPARK-ROYAL NO. 2_ET-00444 |  |  | No | 17:13 |  | THOUSAND OAKS | 35 | UNK | 2026-01-07 13:39 PST ¦ 2026-01-08 13:38 PST | 010826 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-WAVE NO. 2 | ET-00501 | 2026_ET-00501 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.6304 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00501_ACQPKG | 2026_ET-00501_GSPKG | Submitted | 2026_ET-00501_GS |  | Field Complete | 2026_ET-00501_GCPR | 2026-01-31 | Submitted | 2026_ET-00501_ACQ | QC Accepted | 2026_ET-00501_FR | 2026-01-31 | Submitted | 2026_ET-00501_RWR | Submitted | 2026-01-31 | 2026_ET-00501_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00501_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00501_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00501_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00501_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00501_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00501_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELLIS-WAVE NO. 2_ET-00501 |  |  | No | 22:45 |  | HUNTINGTON BEACH | 33 | UNK | 2025-12-18 14:13 PST ¦ 2025-12-18 14:50 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-NOGALES-RAILROAD NO. 2 | ET-00680 | 2026_ET-00680 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.4838 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-14 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00680_ACQPKG | 2026_ET-00680_GSPKG | Submitted | 2026_ET-00680_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00680_GCPR | 2025-12-08 | Historical | 2026_ET-00680_ACQ | QC Accepted | 2026_ET-00680_FR | 2026-01-31 | Submitted | 2026_ET-00680_RWR | Submitted | 2026-01-31 | 2026_ET-00680_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00680_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00680_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00680_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00680_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00680_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00680_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | WALNUT-NOGALES-RAILROAD NO. 2_ET-00680 |  |  | No | 21:07 & 16:49 |  |  |  | UNK | 2025-12-14 13:05 PST ¦ 2026-01-13 08:18 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VIEJO-CHIQUITA-O'NEILL | ET-00732 | 2026_ET-00732 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.8693 | 1.7254 | 45 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-12-2026 |  | 2026_ET-00732_ACQPKG | 2026_ET-00732_GSPKG | Submitted | 2026_ET-00732_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00732_GCPR | 2025-12-08 | Historical | 2026_ET-00732_ACQ | QC Accepted | 2026_ET-00732_FR | 2026-01-31 | Submitted | 2026_ET-00732_RWR | Submitted | 2026-01-31 | 2026_ET-00732_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00732_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00732_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00732_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00732_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00732_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00732_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VIEJO-CHIQUITA-O_NEILL_ET-00732 |  |  | No | 21:01 |  | SADDLEBACK | 43 | UNK | 2025-12-18 12:45 PST ¦ 2025-12-18 13:04 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OCEANVIEW-SLATER | ET-00746 | 2026_ET-00746 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.3796 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-20 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00746_ACQPKG | 2026_ET-00746_GSPKG | Submitted | 2026_ET-00746_GS |  | Field Complete | 2026_ET-00746_GCPR | 2026-01-31 | Submitted | 2026_ET-00746_ACQ | QC Accepted | 2026_ET-00746_FR | 2026-01-31 | Submitted | 2026_ET-00746_RWR | Submitted | 2026-01-31 | 2026_ET-00746_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00746_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00746_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00746_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00746_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00746_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00746_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | OCEANVIEW-SLATER_ET-00746 |  |  | No | 20:06 |  | HUNTINGTON BEACH | 33 | UNK | 2025-12-20 11:54 PST ¦ 2025-12-20 12:10 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-FRANCIS-SAN ANTONIO | ET-00861 | 2026_ET-00861 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 10.6359 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-15 | 02-14-2026 | 02-06-2026 |  | 2026_ET-00861_ACQPKG | 2026_ET-00861_GSPKG | Submitted | 2026_ET-00861_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00861_GCPR | 2025-12-08 | Historical | 2026_ET-00861_ACQ | QC Accepted | 2026_ET-00861_FR | 2026-01-31 | Submitted | 2026_ET-00861_RWR | Submitted | 2026-01-31 | 2026_ET-00861_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-00861_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00861_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00861_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00861_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00861_RR |  | No Violations | 04-10-2026 |  | 4 |  |  |  | 2026_ET-00861_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CHINO-FRANCIS-SAN ANTONIO_ET-00861 |  |  | No | 20:14 |  | ONTARIO | 34 | UNK | 2025-12-15 11:49 PST ¦ 2025-12-15 12:27 PST | 121525 | 20251215 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-LA CIENEGA | ET-00981 | 2026_ET-00981 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 8.9537 | 0.84015 | 9 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | No Delay | Variable | N/A | Access | N/A | Access | Airspace restricitions, waiting on clearance from FAA/Airport |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2026-01-13 | 02-14-2026 | 02-14-2026 |  | 2026_ET-00981_ACQPKG | 2026_ET-00981_GSPKG | Submitted | 2026_ET-00981_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00981_GCPR | 2025-12-08 | Historical | 2026_ET-00981_ACQ | QC Accepted | 2026_ET-00981_FR |  | Submitted | 2026_ET-00981_RWR | Submitted | 2026-01-31 | 2026_ET-00981_CLAZ | 2026-01-31 | QC Accepted | 02-14-2026 | 2026-02-14 | 0 | 2026_ET-00981_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00981_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00981_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00981_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00981_RR | 2026-03-22 | Violations QC Confirmed | 03-17-2026 | 03-23-2026 | 3 | 2026-03-23 | 3 | 1 | 2026_ET-00981_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | EL NIDO-LA CIENEGA_ET-00981 |  |  | Yes | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2025-10-19 09:57 PDT ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-STANHILL-WINDSOR HILLS | ET-00984 | 2026_ET-00984 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.4482 | 1.4482 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | No Delay | Variable | N/A | Access | N/A | Access | Delays due to airport airspace clearance |  | SCE Approved | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-27 | 12-11-2025 | Flown | 2026-01-13 | 02-14-2026 | 02-14-2026 |  | 2026_ET-00984_ACQPKG | 2026_ET-00984_GSPKG | Submitted | 2026_ET-00984_GS | 2025-11-08 | Field Complete | 2026_ET-00984_GCPR | 2026-01-31 | Submitted | 2026_ET-00984_ACQ | QC Accepted | 2026_ET-00984_FR | 2026-01-31 | Submitted | 2026_ET-00984_RWR | Submitted | 2026-01-31 | 2026_ET-00984_CLAZ | 2026-01-31 | QC Accepted | 02-14-2026 | 2026-02-14 | 0 | 2026_ET-00984_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00984_WR | 2026-03-17 | 03-16-2026 | QC Accepted | 03-31-2026 | 2026-03-24 | 0 | 2026_ET-00984_VMLAZ | 2026-03-10 | QC Accepted | 05-15-2026 | 2026-03-24 | 0 | 2026_ET-00984_VMM1 | 2026-03-09 | QC Accepted |  | 05-15-2026 | 2026-03-24 | 0 | 2026_ET-00984_RR | 2026-03-10 | No Violations | 03-25-2026 |  | 0 |  |  |  | 2026_ET-00984_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | LA CIENEGA-STANHILL-WINDSOR HILLS_ET-00984 |  |  | No | 11:58 - 15:16 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-19 09:56 PDT ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LIGHTHIPE-CARSON NO. 1 | ET-01024 | 2026_ET-01024 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.6859 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-06-2026 |  | 2026_ET-01024_ACQPKG | 2026_ET-01024_GSPKG | Submitted | 2026_ET-01024_GS |  | Field Complete | 2026_ET-01024_GCPR | 2026-01-31 | Submitted | 2026_ET-01024_ACQ | QC Accepted | 2026_ET-01024_FR | 2026-01-31 | Submitted | 2026_ET-01024_RWR | Submitted | 2026-01-31 | 2026_ET-01024_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-01024_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01024_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-01024_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-01024_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-01024_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-01024_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LIGHTHIPE-CARSON NO. 1_ET-01024 |  |  | No | 18:13 - 21:40 |  | LONG BEACH | 46 | UNK | 2025-12-16 13:50 PST ¦ 2026-01-09 13:58 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-EL NIDO-SANTA MONICA | ET-01045 | 2026_ET-01045 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 13.0858 | 1.6973 | 13 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | No Delay | Variable | N/A | Access | N/A | Access | Airspace restricitions, waiting on clearance from FAA/Airport |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2026-01-13 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01045_ACQPKG | 2026_ET-01045_GSPKG | Submitted | 2026_ET-01045_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01045_GCPR | 2025-12-08 | Historical | 2026_ET-01045_ACQ | QC Accepted | 2026_ET-01045_FR | 2026-01-31 | Submitted | 2026_ET-01045_RWR | Submitted | 2026-01-31 | 2026_ET-01045_CLAZ | 2026-01-31 | QC Accepted | 02-14-2026 | 2026-02-14 | 0 | 2026_ET-01045_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01045_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-01045_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01045_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-01045_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-01045_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | LA CIENEGA-EL NIDO-SANTA MONICA_ET-01045 |  |  | No | 14:54 & 11:58 |  | SOUTH BAY | 44 | UNK | 2025-10-19 09:57 PDT ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-SIGNAL HILL-WESTEX | ET-01061 | 2026_ET-01061 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 8.7867 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-11 | 02-14-2026 | 02-06-2026 |  | 2026_ET-01061_ACQPKG | 2026_ET-01061_GSPKG | Submitted | 2026_ET-01061_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01061_GCPR | 2025-12-08 | Historical | 2026_ET-01061_ACQ | QC Accepted | 2026_ET-01061_FR | 2026-01-31 | Submitted | 2026_ET-01061_RWR | Submitted | 2026-01-31 | 2026_ET-01061_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-01061_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01061_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-10 | 0 | 2026_ET-01061_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-10 | 0 | 2026_ET-01061_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-10 | 0 | 2026_ET-01061_RR |  | No Violations | 04-11-2026 | [5 empty] | 2026_ET-01061_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-10 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LIGHTHIPE-SIGNAL HILL-WESTEX_ET-01061 |  |  | No | 18:13 & 15:16 |  | LONG BEACH | 46 | UNK | 2026-01-09 12:17 PST ¦ 2026-01-11 08:06 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-EL NIDO-TAHITI | ET-01171 | 2026_ET-01171 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 11.0951 | 1.7055 | 15 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-13 | 02-14-2026 | 02-06-2026 |  | 2026_ET-01171_ACQPKG | 2026_ET-01171_GSPKG | Submitted | 2026_ET-01171_GS |  | Field Complete | 2026_ET-01171_GCPR | 2026-01-31 | Submitted | 2026_ET-01171_ACQ | QC Accepted | 2026_ET-01171_FR | 2026-01-31 | Submitted | 2026_ET-01171_RWR | Submitted | 2026-01-31 | 2026_ET-01171_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-06 | 0 | 2026_ET-01171_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01171_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-01171_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-01171_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-01171_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-01171_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LA CIENEGA-EL NIDO-TAHITI_ET-01171 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 05:07 PST ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GANESHA-TROPHY | ET-01209 | 2026_ET-01209 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.0602 | 0.10442 | 3 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-14 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01209_ACQPKG | 2026_ET-01209_GSPKG | Submitted | 2026_ET-01209_GS |  | Field Complete | 2026_ET-01209_GCPR | 2026-01-31 | Submitted | 2026_ET-01209_ACQ | QC Accepted | 2026_ET-01209_FR | 2026-01-31 | Submitted | 2026_ET-01209_RWR | Submitted | 2026-01-31 | 2026_ET-01209_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01209_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01209_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01209_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01209_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01209_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01209_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | GANESHA-TROPHY_ET-01209 |  |  | No | 21:48 |  | COVINA | 26 | UNK | 2025-12-14 13:46 PST ¦ 2025-12-18 09:11 PST | 121425 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-VAIL | ET-01218 | 2026_ET-01218 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.0957 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01218_ACQPKG | 2026_ET-01218_GSPKG | Submitted | 2026_ET-01218_GS |  | Field Complete | 2026_ET-01218_GCPR | 2026-01-31 | Submitted | 2026_ET-01218_ACQ | QC Accepted | 2026_ET-01218_FR | 2026-01-31 | Submitted | 2026_ET-01218_RWR | Submitted | 2026-01-31 | 2026_ET-01218_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01218_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01218_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01218_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01218_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01218_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01218_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LAGUNA BELL-VAIL_ET-01218 |  |  | No | 19:43 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 11:33 PST ¦ 2025-12-16 12:02 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-WALTERIA | ET-01234 | 2026_ET-01234 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 5.7857 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-11 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01234_ACQPKG | 2026_ET-01234_GSPKG | Submitted | 2026_ET-01234_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01234_GCPR | 2025-12-08 | Historical | 2026_ET-01234_ACQ | QC Accepted | 2026_ET-01234_FR | 2026-01-31 | Submitted | 2026_ET-01234_RWR | Submitted | 2026-01-31 | 2026_ET-01234_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01234_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01234_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01234_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01234_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01234_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01234_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LA FRESA-WALTERIA_ET-01234 |  |  | No | 15:16 |  | SOUTH BAY | 44 | UNK | 2026-01-11 08:18 PST ¦ 2026-01-11 08:40 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-CREST | ET-01237 | 2026_ET-01237 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.9525 | 3.5577 | 45 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-11 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01237_ACQPKG | 2026_ET-01237_GSPKG | Submitted | 2026_ET-01237_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01237_GCPR | 2025-12-08 | Historical | 2026_ET-01237_ACQ | QC Accepted | 2026_ET-01237_FR | 2026-01-31 | Submitted | 2026_ET-01237_RWR | Submitted | 2026-01-31 | 2026_ET-01237_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01237_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01237_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01237_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01237_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01237_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01237_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LA FRESA-CREST_ET-01237 |  |  | No | 15:16 |  | SOUTH BAY | 44 | UNK | 2026-01-11 08:29 PST ¦ 2026-01-11 09:36 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CYPRESS NO. 1 | ET-01276 | 2026_ET-01276 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.3322 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01276_ACQPKG | 2026_ET-01276_GSPKG | Submitted | 2026_ET-01276_GS |  | Field Complete | 2026_ET-01276_GCPR | 2026-01-31 | Submitted | 2026_ET-01276_ACQ | QC Accepted | 2026_ET-01276_FR | 2026-01-31 | Submitted | 2026_ET-01276_RWR | Submitted | 2026-01-31 | 2026_ET-01276_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01276_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01276_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01276_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01276_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01276_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01276_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | DEL AMO-CYPRESS NO. 1_ET-01276 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2025-12-20 13:55 PST ¦ 2026-01-09 11:21 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-PEYTON-SOQUEL | ET-01300 | 2026_ET-01300 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 5.8015 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-14 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01300_ACQPKG | 2026_ET-01300_GSPKG | Submitted | 2026_ET-01300_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01300_GCPR | 2025-12-08 | Historical | 2026_ET-01300_ACQ | QC Accepted | 2026_ET-01300_FR | 2026-01-31 | Submitted | 2026_ET-01300_RWR | Submitted | 2026-01-31 | 2026_ET-01300_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01300_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01300_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01300_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01300_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01300_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01300_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CHINO-PEYTON-SOQUEL_ET-01300 |  |  | No | 22:23 |  | ONTARIO | 34 | UNK | 2025-12-14 14:08 PST ¦ 2025-12-18 08:49 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CORNUTA | ET-01307 | 2026_ET-01307 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.2624 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01307_ACQPKG | 2026_ET-01307_GSPKG | Submitted | 2026_ET-01307_GS |  | Field Complete | 2026_ET-01307_GCPR | 2026-01-31 | Submitted | 2026_ET-01307_ACQ | QC Accepted | 2026_ET-01307_FR | 2026-01-31 | Submitted | 2026_ET-01307_RWR | Submitted | 2026-01-31 | 2026_ET-01307_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01307_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01307_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01307_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01307_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01307_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01307_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | DEL AMO-CORNUTA_ET-01307 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2025-12-21 14:26 PST ¦ 2026-01-09 12:07 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-CARSON NO. 2 | ET-01324 | 2026_ET-01324 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.0366 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01324_ACQPKG | 2026_ET-01324_GSPKG | Submitted | 2026_ET-01324_GS |  | Field Complete | 2026_ET-01324_GCPR | 2026-01-31 | Submitted | 2026_ET-01324_ACQ | QC Accepted | 2026_ET-01324_FR | 2026-01-31 | Submitted | 2026_ET-01324_RWR | Submitted | 2026-01-31 | 2026_ET-01324_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01324_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01324_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01324_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01324_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01324_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01324_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LIGHTHIPE-CARSON NO. 2_ET-01324 |  |  | No | 18:13 & 21:40 |  | LONG BEACH | 46 | UNK | 2026-01-09 12:16 PST ¦ 2026-01-09 13:58 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GANESHA-SIMPSON | ET-01355 | 2026_ET-01355 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.99285 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-14 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01355_ACQPKG | 2026_ET-01355_GSPKG | Submitted | 2026_ET-01355_GS |  | Field Complete | 2026_ET-01355_GCPR | 2026-01-31 | Submitted | 2026_ET-01355_ACQ | QC Accepted | 2026_ET-01355_FR | 2026-01-31 | Submitted | 2026_ET-01355_RWR | Submitted | 2026-01-31 | 2026_ET-01355_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01355_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01355_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01355_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01355_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01355_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01355_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | GANESHA-SIMPSON_ET-01355 |  |  | No | 21:48 |  | COVINA | 26 | UNK | 2025-12-14 13:50 PST ¦ 2025-12-18 09:11 PST | 121425 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-MOVIE | ET-01420 | 2026_ET-01420 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.5237 | 0.63526 | 42 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-10-19 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01420_ACQPKG | 2026_ET-01420_GSPKG | Submitted | 2026_ET-01420_GS |  | Field Complete | 2026_ET-01420_GCPR | 2026-01-31 | Submitted | 2026_ET-01420_ACQ | QC Accepted | 2026_ET-01420_FR | 2026-01-31 | Submitted | 2026_ET-01420_RWR | Submitted | 2026-01-31 | 2026_ET-01420_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01420_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01420_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01420_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01420_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01420_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01420_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LA CIENEGA-MOVIE_ET-01420 |  |  | No | 15:54 |  | SANTA MONICA | 42 | UNK | 2026-01-13 05:25 PST ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHASE-JEFFERSON | ET-01469 | 2026_ET-01469 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.7225 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-15 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01469_ACQPKG | 2026_ET-01469_GSPKG | Submitted | 2026_ET-01469_GS |  | Field Complete | 2026_ET-01469_GCPR | 2026-01-31 | Submitted | 2026_ET-01469_ACQ | QC Accepted | 2026_ET-01469_FR | 2026-01-31 | Submitted | 2026_ET-01469_RWR | Submitted | 2026-01-31 | 2026_ET-01469_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01469_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01469_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01469_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01469_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01469_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01469_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CHASE-JEFFERSON_ET-01469 |  |  | No | 18:17 |  | ONTARIO | 34 | UNK | 2025-12-15 12:38 PST ¦ 2025-12-15 12:56 PST | 121525 | 20251215 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CHESTNUT | ET-01518 | 2026_ET-01518 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.2481 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-11-05 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01518_ACQPKG | 2026_ET-01518_GSPKG | Submitted | 2026_ET-01518_GS |  | Field Complete | 2026_ET-01518_GCPR | 2026-01-31 | Submitted | 2026_ET-01518_ACQ | QC Accepted | 2026_ET-01518_FR | 2026-01-31 | Submitted | 2026_ET-01518_RWR | Submitted | 2026-01-31 | 2026_ET-01518_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01518_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01518_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01518_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01518_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01518_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01518_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | JOHANNA-CHESTNUT_ET-01518 |  |  | No | 14:08 |  | SANTA ANA | 29 | UNK | 2025-12-21 12:26 PST ¦ 2026-01-14 06:52 PST | 011426 | 20260114 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-ESTRELLA NO. 2 | ET-01521 | 2026_ET-01521 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.9428 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01521_ACQPKG | 2026_ET-01521_GSPKG | Submitted | 2026_ET-01521_GS |  | Field Complete | 2026_ET-01521_GCPR | 2026-01-31 | Submitted | 2026_ET-01521_ACQ | QC Accepted | 2026_ET-01521_FR | 2026-01-31 | Submitted | 2026_ET-01521_RWR | Submitted | 2026-01-31 | 2026_ET-01521_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01521_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01521_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01521_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01521_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01521_RR | 2026-03-18 | Violations QC Confirmed | 03-21-2026 | 03-21-2026 | 1 | 2026-03-11 | 0 | 1 | 2026_ET-01521_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTIAGO-ESTRELLA NO. 2_ET-01521 |  |  | No | 20:17 |  | SADDLEBACK | 43 | UNK | 2025-12-18 13:26 PST ¦ 2025-12-18 14:03 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ICEGEN-JERSEY-NOLA | ET-01537 | 2026_ET-01537 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.4118 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01537_ACQPKG | 2026_ET-01537_GSPKG | Submitted | 2026_ET-01537_GS |  | Field Complete | 2026_ET-01537_GCPR | 2026-01-31 | Submitted | 2026_ET-01537_ACQ | QC Accepted | 2026_ET-01537_FR | 2026-01-31 | Submitted | 2026_ET-01537_RWR | Submitted | 2026-01-31 | 2026_ET-01537_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01537_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01537_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01537_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01537_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01537_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01537_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ICEGEN-JERSEY-NOLA_ET-01537 |  |  | No | 21:40 |  | DOMINGUEZ HILLS | 32 | UNK | 2026-01-09 14:58 PST ¦ 2026-01-09 15:09 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
LAGUNA BELL-NEWMARK-VAIL | ET-01558 | 2026_ET-01558 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 9.446 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-13-2026 |  | 2026_ET-01558_ACQPKG | 2026_ET-01558_GSPKG | Submitted | 2026_ET-01558_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01558_GCPR | 2025-12-08 | Historical | 2026_ET-01558_ACQ | QC Accepted | 2026_ET-01558_FR | 2026-01-31 | Submitted | 2026_ET-01558_RWR | Submitted | 2026-01-31 | 2026_ET-01558_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01558_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01558_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01558_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01558_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01558_RR | 2026-03-18 | Violations QC Confirmed | 03-24-2026 | 03-24-2026 | 4 | 2026-03-11 | 2 | 2 | 2026_ET-01558_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LAGUNA BELL-NEWMARK-VAIL_ET-01558 |  |  | No | 19:43 |  | MONTEBELLO | 22 | UNK | 2025-12-16 11:34 PST ¦ 2025-12-16 11:59 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-CAMARILLO | ET-01561 | 2026_ET-01561 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 21.6252 | 6.3413 | 29 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-07 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01561_ACQPKG | 2026_ET-01561_GSPKG | Submitted | 2026_ET-01561_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01561_GCPR | 2025-12-08 | Historical | 2026_ET-01561_ACQ | QC Accepted | 2026_ET-01561_FR | 2026-01-31 | Submitted | 2026_ET-01561_RWR | Submitted | 2026-01-31 | 2026_ET-01561_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01561_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01561_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01561_VMLAZ | 2026-03-17 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01561_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01561_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01561_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTA CLARA-CAMARILLO_ET-01561 |  |  | No | 20:18 & 17:07 |  | VENTURA | 39 | UNK | 2026-01-06 13:08 PST ¦ 2026-01-07 10:54 PST | 010726 | 20260107 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-CARPINTERIA-DESAL-SANTA BARBARA | ET-01597 | 2026_ET-01597 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 30.2409 | 28.6812 | 95 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-05 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01597_ACQPKG | 2026_ET-01597_GSPKG | Submitted | 2026_ET-01597_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01597_GCPR | 2025-12-08 | Historical | 2026_ET-01597_ACQ | QC Accepted | 2026_ET-01597_FR | 2026-01-31 | Submitted | 2026_ET-01597_RWR | Submitted | 2026-01-31 | 2026_ET-01597_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01597_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01597_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01597_VMLAZ | 2026-03-17 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01597_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01597_RR | 2026-03-18 | Violations QC Confirmed | 03-21-2026 | 03-21-2026 | 23 | 2026-03-11 | 0 | 23 | 2026_ET-01597_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | GOLETA-CARPINTERIA-DESAL-SANTA BARBARA_ET-01597 |  |  | No | 17:03 & 18:31 - 21:21 |  | SANTA BARBARA | 49 | UNK | 2025-12-28 11:49 PST ¦ 2026-01-06 09:47 PST | 010526 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-SHAWNEE-TRASK | ET-01641 | 2026_ET-01641 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 6.2311 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-20 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01641_ACQPKG | 2026_ET-01641_GSPKG | Submitted | 2026_ET-01641_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01641_GCPR | 2025-12-08 | Historical | 2026_ET-01641_ACQ | QC Accepted | 2026_ET-01641_FR | 2026-01-31 | Submitted | 2026_ET-01641_RWR | Submitted | 2026-01-31 | 2026_ET-01641_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01641_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01641_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01641_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01641_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01641_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01641_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BARRE-SHAWNEE-TRASK_ET-01641 | Done |  | No | 20:49 |  | FULLERTON | 48 | UNK | 2025-12-20 12:22 PST ¦ 2025-12-20 12:56 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-CARBONIC-NEPTUNE | ET-01704 | 2026_ET-01704 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.0761 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01704_ACQPKG | 2026_ET-01704_GSPKG | Submitted | 2026_ET-01704_GS |  | Field Complete | 2026_ET-01704_GCPR | 2026-01-31 | Submitted | 2026_ET-01704_ACQ | QC Accepted | 2026_ET-01704_FR | 2026-01-31 | Submitted | 2026_ET-01704_RWR | Submitted | 2026-01-31 | 2026_ET-01704_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01704_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01704_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01704_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01704_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01704_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01704_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | HINSON-CARBONIC-NEPTUNE_ET-01704 |  |  | No | 21:40 |  | DOMINGUEZ HILLS | 32 | UNK | 2026-01-09 12:35 PST ¦ 2026-01-09 14:47 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVMAIN-EL NIDO | ET-01709 | 2026_ET-01709 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.2509 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-11-05 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01709_ACQPKG | 2026_ET-01709_GSPKG | Submitted | 2026_ET-01709_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01709_GCPR | 2025-12-08 | Historical | 2026_ET-01709_ACQ | QC Accepted | 2026_ET-01709_FR | 2026-01-31 | Submitted | 2026_ET-01709_RWR | Submitted | 2026-01-31 | 2026_ET-01709_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01709_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01709_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01709_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01709_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01709_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01709_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CHEVMAIN-EL NIDO_ET-01709 |  |  | Yes | 18:01 |  | SOUTH BAY | 44 | UNK | 2026-01-13 06:05 PST ¦ 2026-01-13 07:37 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVMAIN-EL SEGUNDO | ET-01710 | 2026_ET-01710 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.7732 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-11-05 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01710_ACQPKG | 2026_ET-01710_GSPKG | Submitted | 2026_ET-01710_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01710_GCPR | 2025-12-08 | Historical | 2026_ET-01710_ACQ | QC Accepted | 2026_ET-01710_FR | 2026-01-31 | Submitted | 2026_ET-01710_RWR | Submitted | 2026-01-31 | 2026_ET-01710_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01710_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01710_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01710_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01710_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01710_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01710_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | CHEVMAIN-EL SEGUNDO_ET-01710 |  |  | Yes | 18:01 |  | SOUTH BAY | 44 | UNK | 2026-01-13 06:05 PST ¦ 2026-01-13 06:25 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-SULLIVAN NO.2 | ET-01745 | 2026_ET-01745 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 6.0758 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01745_ACQPKG | 2026_ET-01745_GSPKG | Submitted | 2026_ET-01745_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01745_GCPR | 2025-12-08 | Historical | 2026_ET-01745_ACQ | QC Accepted | 2026_ET-01745_FR | 2026-01-31 | Submitted | 2026_ET-01745_RWR | Submitted | 2026-01-31 | 2026_ET-01745_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01745_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01745_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01745_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01745_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01745_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01745_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELLIS-SULLIVAN NO.2_ET-01745 |  |  | No | 20:17 |  | SANTA ANA | 29 | UNK | 2025-12-18 14:13 PST ¦ 2025-12-18 14:43 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CABRILLO-FAIRVIEW | ET-01891 | 2026_ET-01891 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.0851 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-11-05 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01891_ACQPKG | 2026_ET-01891_GSPKG | Submitted | 2026_ET-01891_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01891_GCPR | 2025-12-08 | Historical | 2026_ET-01891_ACQ | QC Accepted | 2026_ET-01891_FR | 2026-01-31 | Submitted | 2026_ET-01891_RWR | Submitted | 2026-01-31 | 2026_ET-01891_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01891_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01891_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01891_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01891_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01891_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01891_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | JOHANNA-CABRILLO-FAIRVIEW_ET-01891 |  |  | No | 18:23 & 14:08 |  | SADDLEBACK | 43 | UNK | 2025-12-18 13:54 PST ¦ 2026-01-14 06:20 PST | 011426 | 20260114 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HI DESERT-LEATHERNECK-YUCCA | ET-01934 | 2026_ET-01934 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 25.147 | 0.9784 | 4 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-22 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01934_ACQPKG | 2026_ET-01934_GSPKG | Submitted | 2026_ET-01934_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01934_GCPR | 2025-12-08 | Historical | 2026_ET-01934_ACQ | QC Accepted | 2026_ET-01934_FR | 2026-01-31 | Submitted | 2026_ET-01934_RWR | Submitted | 2026-01-31 | 2026_ET-01934_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01934_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01934_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01934_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01934_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01934_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-01934_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | HI DESERT-LEATHERNECK-YUCCA_ET-01934 |  |  | No | 21:15 - 22:20 |  | YUCCA VALLEY | 84 | UNK | 2025-12-22 13:15 PST ¦ 2025-12-22 14:47 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-GOSHEN-LIBERTY | ET-01942 | 2026_ET-01942 |  | 1 | 2026 | May 01, 2026 | 66 | CA_4 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 14.0674 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-12 | 02-14-2026 | 02-05-2026 |  | 2026_ET-01942_ACQPKG | 2026_ET-01942_GSPKG | Submitted | 2026_ET-01942_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01942_GCPR | 2025-12-08 | Historical | 2026_ET-01942_ACQ | QC Accepted | 2026_ET-01942_FR | 2026-01-09 | Submitted | 2026_ET-01942_RWR | Submitted | 2026-01-09 | 2026_ET-01942_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-05 |  | 2026_ET-01942_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01942_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-01942_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01942_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01942_RR | 2026-03-18 | No Violations | 03-24-2026 |  | 15 | 2026-03-27 | 0 |  | 2026_ET-01942_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | RECTOR-GOSHEN-LIBERTY_ET-01942 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-12 15:43 PST ¦ 2025-12-12 16:04 PST | 121225 | 20251212 |  |  |  |  | Attribute - Project |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-GREENING | ET-01955 | 2026_ET-01955 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.0382 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-21 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01955_ACQPKG | 2026_ET-01955_GSPKG | Submitted | 2026_ET-01955_GS |  | Field Complete | 2026_ET-01955_GCPR | 2026-01-31 | Submitted | 2026_ET-01955_ACQ | QC Accepted | 2026_ET-01955_FR | 2026-01-31 | Submitted | 2026_ET-01955_RWR | Submitted | 2026-01-31 | 2026_ET-01955_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01955_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01955_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01955_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01955_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01955_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01955_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | DEL AMO-GREENING_ET-01955 |  |  | No | 21:12 & 18:13 |  | LONG BEACH | 46 | UNK | 2025-12-21 13:33 PST ¦ 2026-01-09 11:16 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-BULLIS-IMPERIAL-RINGMILL-WEBME | ET-01957 | 2026_ET-01957 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.4392 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01957_ACQPKG | 2026_ET-01957_GSPKG | Submitted | 2026_ET-01957_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01957_GCPR | 2025-12-08 | Historical | 2026_ET-01957_ACQ | QC Accepted | 2026_ET-01957_FR | 2026-01-31 | Submitted | 2026_ET-01957_RWR | Submitted | 2026-01-31 | 2026_ET-01957_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01957_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01957_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01957_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01957_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01957_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01957_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LIGHTHIPE-BULLIS-IMPERIAL-RINGMILL-WEBME_ET-01957 |  |  | No | 22:15 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 13:42 PST ¦ 2026-01-09 12:28 PST | 121625 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-SUNCATCHER | ET-01985 | 2026_ET-01985 |  | 1 | 2026 | May 01, 2026 | 220 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.019986 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-10-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01985_ACQPKG | 2026_ET-01985_GSPKG | Submitted | 2026_ET-01985_GS |  | Field Complete | 2026_ET-01985_GCPR | 2026-01-31 | Submitted | 2026_ET-01985_ACQ | QC Accepted | 2026_ET-01985_FR | 2026-01-31 | Submitted | 2026_ET-01985_RWR | Submitted | 2026-01-31 | 2026_ET-01985_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01985_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01985_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01985_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01985_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01985_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01985_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | COLORADO RIVER-SUNCATCHER_ET-01985 |  |  | Yes | 15:52 |  | BLYTHE | 87 | UNK | 2025-12-22 11:01 PST ¦ 2025-12-22 11:10 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VIEJO-CHIQUITA NO.1 | ET-01991 | 2026_ET-01991 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.9797 | 0.84734 | 28 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01991_ACQPKG | 2026_ET-01991_GSPKG | Submitted | 2026_ET-01991_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01991_GCPR | 2025-12-08 | Historical | 2026_ET-01991_ACQ | QC Accepted | 2026_ET-01991_FR | 2026-01-31 | Submitted | 2026_ET-01991_RWR | Submitted | 2026-01-31 | 2026_ET-01991_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01991_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01991_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01991_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01991_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01991_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01991_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VIEJO-CHIQUITA NO.1_ET-01991 |  |  | No | 20:53 |  | SADDLEBACK | 43 | UNK | 2025-12-18 12:51 PST ¦ 2025-12-18 13:04 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VIEJO-CHIQUITA NO.2 | ET-01992 | 2026_ET-01992 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.9832 | 0.83916 | 28 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-14-2026 |  | 2026_ET-01992_ACQPKG | 2026_ET-01992_GSPKG | Submitted | 2026_ET-01992_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01992_GCPR | 2025-12-08 | Historical | 2026_ET-01992_ACQ | QC Accepted | 2026_ET-01992_FR | 2026-01-31 | Submitted | 2026_ET-01992_RWR | Submitted | 2026-01-31 | 2026_ET-01992_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01992_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01992_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01992_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01992_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01992_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01992_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VIEJO-CHIQUITA NO.2_ET-01992 |  |  | No | 20:53 |  | SADDLEBACK | 43 | UNK | 2025-12-18 12:51 PST ¦ 2025-12-18 13:04 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEL AMO-LUCAS NO. 1 | ET-02018 | 2026_ET-02018 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.024088 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-14-2026 |  | 2026_ET-02018_ACQPKG | 2026_ET-02018_GSPKG | Submitted | 2026_ET-02018_GS |  | Field Complete | 2026_ET-02018_GCPR | 2026-01-31 | Submitted | 2026_ET-02018_ACQ | QC Accepted | 2026_ET-02018_FR | 2026-01-31 | Submitted | 2026_ET-02018_RWR | Submitted | 2026-01-31 | 2026_ET-02018_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-02018_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02018_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-02018_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-02018_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-02018_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-02018_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE DEL AMO-LUCAS NO. 1_ET-02018 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 11:27 PST ¦ 2026-01-09 11:32 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEL AMO-LUCAS NO. 2 | ET-02019 | 2026_ET-02019 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.07897 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2026-01-09 | 02-14-2026 | 02-14-2026 |  | 2026_ET-02019_ACQPKG | 2026_ET-02019_GSPKG | Submitted | 2026_ET-02019_GS |  | Field Complete | 2026_ET-02019_GCPR | 2026-01-31 | Submitted | 2026_ET-02019_ACQ | QC Accepted | 2026_ET-02019_FR | 2026-01-31 | Submitted | 2026_ET-02019_RWR | Submitted | 2026-01-31 | 2026_ET-02019_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-02019_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02019_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02019_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02019_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02019_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-02019_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE DEL AMO-LUCAS NO. 2_ET-02019 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 11:27 PST ¦ 2026-01-09 11:47 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ATHOS-RED BLUFF | ET-02038 | 2026_ET-02038 |  | 1 | 2026 | May 01, 2026 | 220 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.16298 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-10-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-02038_ACQPKG | 2026_ET-02038_GSPKG | Submitted | 2026_ET-02038_GS |  | Field Complete | 2026_ET-02038_GCPR | 2026-01-31 | Submitted | 2026_ET-02038_ACQ | QC Accepted | 2026_ET-02038_FR | 2026-01-31 | Submitted | 2026_ET-02038_RWR | Submitted | 2026-01-31 | 2026_ET-02038_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-02038_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02038_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02038_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02038_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02038_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-02038_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ATHOS-RED BLUFF_ET-02038 | Done |  | Yes | 15:52 |  | BLYTHE | 87 | UNK | 2025-12-22 10:36 PST ¦ 2025-12-22 10:45 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-AULD NO.2 | ET-02135 | 2026_ET-02135 |  | 1 | 2026 | May 01, 2026 | 115 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 10.3941 | 6.6035 | 64 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-10 | 02-14-2026 | 02-14-2026 |  | 2026_ET-02135_ACQPKG | 2026_ET-02135_GSPKG | Submitted | 2026_ET-02135_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02135_GCPR | 2025-12-08 | Historical | 2026_ET-02135_ACQ | QC Accepted | 2026_ET-02135_FR | 2026-01-31 | Submitted | 2026_ET-02135_RWR | Submitted | 2026-01-31 | 2026_ET-02135_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-02135_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02135_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02135_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02135_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02135_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-02135_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VALLEY-AULD NO.2_ET-02135 |  |  | No | 18:23 |  | MENIFEE | 77 | UNK | 2025-12-10 10:24 PST ¦ 2025-12-10 13:12 PST | 121025 | 20251210 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BRIGHTON-HOWARD | ET-03193 | 2026_ET-03193 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.945 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2026-01-13 | 02-14-2026 | 02-14-2026 |  | 2026_ET-03193_ACQPKG | 2026_ET-03193_GSPKG | Submitted | 2026_ET-03193_GS |  | Field Complete | 2026_ET-03193_GCPR | 2026-01-31 | Submitted | 2026_ET-03193_ACQ | QC Accepted | 2026_ET-03193_FR | 2026-01-31 | Submitted | 2026_ET-03193_RWR | Submitted | 2026-01-31 | 2026_ET-03193_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-03193_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-03193_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-03193_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-03193_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-03193_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-03193_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BRIGHTON-HOWARD_ET-03193 | Done |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 08:08 PST ¦ 2026-01-13 08:18 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-LEONIS-TRIGAS | ET-04353 | 2026_ET-04353 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 3.9378 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-04353_ACQPKG | 2026_ET-04353_GSPKG | Submitted | 2026_ET-04353_GS |  | Field Complete | 2026_ET-04353_GCPR | 2026-01-31 | Submitted | 2026_ET-04353_ACQ | QC Accepted | 2026_ET-04353_FR | 2026-01-31 | Submitted | 2026_ET-04353_RWR | Submitted | 2026-01-31 | 2026_ET-04353_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-04353_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04353_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-04353_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-04353_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-04353_RR |  | No Violations | 03-24-2026 | [5 empty] | 2026_ET-04353_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LAGUNA BELL-LEONIS-TRIGAS_ET-04353 |  |  | No | 20:11 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 11:33 PST ¦ 2025-12-16 12:13 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-LEONIS | ET-04354 | 2026_ET-04354 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.6792 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-04354_ACQPKG | 2026_ET-04354_GSPKG | Submitted | 2026_ET-04354_GS |  | Field Complete | 2026_ET-04354_GCPR | 2026-01-31 | Submitted | 2026_ET-04354_ACQ | QC Accepted | 2026_ET-04354_FR | 2026-01-31 | Submitted | 2026_ET-04354_RWR | Submitted | 2026-01-31 | 2026_ET-04354_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-04354_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04354_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-04354_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-04354_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-04354_RR |  | No Violations | 03-26-2026 | [5 empty] | 2026_ET-04354_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | LAGUNA BELL-LEONIS_ET-04354 |  |  | No | 20:11 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 11:33 PST ¦ 2025-12-16 12:13 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-NEWMARK NO. 1 | ET-04876 | 2026_ET-04876 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.2036 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-15 | 02-14-2026 | 02-06-2026 |  | 2026_ET-04876_ACQPKG | 2026_ET-04876_GSPKG | Submitted | 2026_ET-04876_GS | 2025-10-15 | Field Complete | 2026_ET-04876_GCPR | 2025-12-08 | Submitted | 2026_ET-04876_ACQ | QC Accepted | 2026_ET-04876_FR | 2026-01-09 | Submitted | 2026_ET-04876_RWR | Submitted | 2026-01-09 | 2026_ET-04876_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-06 |  | 2026_ET-04876_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04876_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-04876_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-04876_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-04876_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-04876_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MESA-NEWMARK NO. 1_ET-04876 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-12-15 10:11 PST ¦ 2025-12-15 10:16 PST | 121525 | 20251215 |  |  |  |  | Attribute - Project |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-NEWMARK NO. 2 | ET-04877 | 2026_ET-04877 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.2034 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-15 | 02-14-2026 | 02-06-2026 |  | 2026_ET-04877_ACQPKG | 2026_ET-04877_GSPKG | Submitted | 2026_ET-04877_GS | 2025-10-15 | Field Complete | 2026_ET-04877_GCPR | 2025-12-08 | Submitted | 2026_ET-04877_ACQ | QC Accepted | 2026_ET-04877_FR | 2026-01-09 | Submitted | 2026_ET-04877_RWR | Submitted | 2026-01-09 | 2026_ET-04877_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-06 |  | 2026_ET-04877_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04877_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-04877_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-04877_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-04877_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-04877_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MESA-NEWMARK NO. 2_ET-04877 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-12-15 10:11 PST ¦ 2025-12-15 10:16 PST | 121525 | 20251215 |  |  |  |  | Attribute - Project |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE OCEANVIEW-TALBERT | ET-05584 | 2026_ET-05584 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.0021 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-18 | 02-14-2026 | 02-14-2026 |  | 2026_ET-05584_ACQPKG | 2026_ET-05584_GSPKG | Submitted | 2026_ET-05584_GS |  | Field Complete | 2026_ET-05584_GCPR | 2026-01-31 | Submitted | 2026_ET-05584_ACQ | QC Accepted | 2026_ET-05584_FR | 2026-01-31 | Submitted | 2026_ET-05584_RWR | Submitted | 2026-01-31 | 2026_ET-05584_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-05584_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-05584_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-05584_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-05584_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-05584_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-05584_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE OCEANVIEW-TALBERT_ET-05584 |  |  | No | 22:40 |  | HUNTINGTON BEACH | 33 | UNK | 2025-12-18 14:24 PST ¦ 2025-12-18 14:41 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MURPHY-SANTA FE SPRINGS | ET-07098 | 2026_ET-07098 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.6059 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-07098_ACQPKG | 2026_ET-07098_GSPKG | Submitted | 2026_ET-07098_GS |  | Field Complete | 2026_ET-07098_GCPR | 2026-01-31 | Submitted | 2026_ET-07098_ACQ | QC Accepted | 2026_ET-07098_FR | 2026-01-31 | Submitted | 2026_ET-07098_RWR | Submitted | 2026-01-31 | 2026_ET-07098_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-07098_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-07098_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-07098_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-07098_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-07098_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-07098_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MURPHY-SANTA FE SPRINGS_ET-07098 |  |  | No | 19:22 |  | WHITTIER | 47 | UNK | 2025-12-16 11:19 PST ¦ 2025-12-16 11:27 PST | 121625 | 20251216 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ROSECRANS-SEPULVEDA | ET-07191 | 2026_ET-07191 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.37455 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-11-05 | 02-14-2026 | 02-14-2026 |  | 2026_ET-07191_ACQPKG | 2026_ET-07191_GSPKG | Submitted | 2026_ET-07191_GS |  | Field Complete | 2026_ET-07191_GCPR | 2026-01-31 | Submitted | 2026_ET-07191_ACQ | QC Accepted | 2026_ET-07191_FR | 2026-01-31 | Submitted | 2026_ET-07191_RWR | Submitted | 2026-01-31 | 2026_ET-07191_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-07191_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-07191_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-07191_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-07191_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-07191_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-07191_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ROSECRANS-SEPULVEDA_ET-07191 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2026-01-13 06:05 PST ¦ 2026-01-13 06:25 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE WESTFLOR-YUKON | ET-08741 | 2026_ET-08741 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.32219 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2026-01-13 | 02-14-2026 | 02-14-2026 |  | 2026_ET-08741_ACQPKG | 2026_ET-08741_GSPKG | Submitted | 2026_ET-08741_GS |  | Field Complete | 2026_ET-08741_GCPR | 2026-01-31 | Submitted | 2026_ET-08741_ACQ | QC Accepted | 2026_ET-08741_FR | 2026-01-31 | Submitted | 2026_ET-08741_RWR | Submitted | 2026-01-31 | 2026_ET-08741_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-08741_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-08741_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-08741_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-08741_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-08741_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-08741_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | IDLE WESTFLOR-YUKON_ET-08741 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 08:26 PST ¦ 2026-01-13 08:32 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE O LINE-SEAL BEACH | ET-76554 | 2026_ET-76554 |  | 1 | 2026 | May 01, 2026 | 115 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 9.8908 | 2.8291 | 29 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-16 | 02-14-2026 | 02-14-2026 |  | 2026_ET-76554_ACQPKG | 2026_ET-76554_GSPKG | Submitted | 2026_ET-76554_GS |  | Field Complete | 2026_ET-76554_GCPR | 2026-01-31 | Submitted | 2026_ET-76554_ACQ | QC Accepted | 2026_ET-76554_FR | 2026-01-31 | Submitted | 2026_ET-76554_RWR | Submitted | 2026-02-12 | 2026_ET-76554_CLAZ | 2026-02-12 | QC Accepted | 02-26-2026 | 2026-02-14 | 0 | 2026_ET-76554_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-76554_WR | 2026-03-12 | 03-16-2026 | QC Accepted | 04-01-2026 | 2026-03-26 | 0 | 2026_ET-76554_VMLAZ | 2026-03-12 | QC Accepted | 04-05-2026 | 2026-03-26 | 0 | 2026_ET-76554_VMM1 | 2026-03-22 | QC Accepted |  | 04-05-2026 | 2026-03-26 | 2 | 2026_ET-76554_RR | 2026-03-22 | Violations QC Confirmed | 03-27-2026 | 03-27-2026 | 73 | 2026-03-11 | 1 | 72 | 2026_ET-76554_VER | 2026-03-18 | Uploaded to S123 | 04-05-2026 | 2026-03-26 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed Late - Program | IDLE O LINE-SEAL BEACH_ET-76554 |  |  | No | 18:30 & 17:47 |  | FOOTHILL | 30 | UNK | 2025-12-15 10:25 PST ¦ 2025-12-16 10:48 PST | 121625 | 20251216 | [5 empty] | Missing subject conductors. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-SAVAGE NO.1 | ET-00309 | 2026_ET-00309 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 7.0488 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-15 | 01-31-2026 | Flown | 2025-12-14 | 02-15-2026 | 02-06-2026 |  | 2026_ET-00309_ACQPKG | 2026_ET-00309_GSPKG | Submitted | 2026_ET-00309_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00309_GCPR | 2025-12-08 | Historical | 2026_ET-00309_ACQ | QC Accepted | 2026_ET-00309_FR | 2026-01-09 | Submitted | 2026_ET-00309_RWR | Submitted | 2026-01-09 | 2026_ET-00309_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-06 |  | 2026_ET-00309_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00309_WR | 2026-03-12 | 03-17-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00309_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-24 | 0 | 2026_ET-00309_VMM1 | 2026-03-15 | QC Accepted |  | 04-29-2026 | 2026-03-30 | 1 | 2026_ET-00309_RR |  | No Violations | 03-31-2026 | [5 empty] | 2026_ET-00309_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VICTOR-SAVAGE NO.1_ET-00309 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-12-14 07:42 PST ¦ 2025-12-14 08:02 PST | 121425 | 20251214 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-IRVINE NO. 2 | ET-01356 | 2026_ET-01356 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.87703 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-15 | 01-31-2026 | Flown | 2025-12-18 | 02-15-2026 | 02-13-2026 |  | 2026_ET-01356_ACQPKG | 2026_ET-01356_GSPKG | Submitted | 2026_ET-01356_GS |  | Field Complete | 2026_ET-01356_GCPR | 2026-01-31 | Submitted | 2026_ET-01356_ACQ | QC Accepted | 2026_ET-01356_FR | 2026-01-31 | Submitted | 2026_ET-01356_RWR | Submitted | 2026-01-31 | 2026_ET-01356_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01356_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01356_WR | 2026-03-12 | 03-17-2026 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01356_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01356_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-24 | 0 | 2026_ET-01356_RR |  | No Violations | 03-25-2026 | [5 empty] | 2026_ET-01356_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-24 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTIAGO-IRVINE NO. 2_ET-01356 |  |  | No | 21:22 |  | SADDLEBACK | 43 | UNK | 2025-12-18 13:22 PST ¦ 2025-12-18 13:46 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-IRVINE NO. 1 | ET-01801 | 2026_ET-01801 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 2.4204 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-15 | 01-31-2026 | Flown | 2025-12-18 | 02-15-2026 | 02-14-2026 |  | 2026_ET-01801_ACQPKG | 2026_ET-01801_GSPKG | Submitted | 2026_ET-01801_GS |  | Field Complete | 2026_ET-01801_GCPR | 2026-01-31 | Submitted | 2026_ET-01801_ACQ | QC Accepted | 2026_ET-01801_FR | 2026-01-31 | Submitted | 2026_ET-01801_RWR | Submitted | 2026-01-31 | 2026_ET-01801_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-01801_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01801_WR | 2026-03-12 | 03-17-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01801_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01801_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01801_RR | 2026-03-18 | Violations QC Confirmed | 03-21-2026 | 03-21-2026 | 1 | 2026-03-11 | 0 | 1 | 2026_ET-01801_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTIAGO-IRVINE NO. 1_ET-01801 |  |  | No | 20:17 |  | SADDLEBACK | 43 | UNK | 2025-12-18 13:22 PST ¦ 2025-12-18 13:46 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-AULD NO.1 | ET-02072 | 2026_ET-02072 |  | 1 | 2026 | May 01, 2026 | 115 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 10.8806 | 7.0823 | 65 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-15 | 01-31-2026 | Flown | 2025-12-10 | 02-15-2026 | 02-14-2026 |  | 2026_ET-02072_ACQPKG | 2026_ET-02072_GSPKG | Submitted | 2026_ET-02072_GS |  | Field Complete | 2026_ET-02072_GCPR | 2026-01-31 | Submitted | 2026_ET-02072_ACQ | QC Accepted | 2026_ET-02072_FR | 2026-01-31 | Submitted | 2026_ET-02072_RWR | Submitted | 2026-01-31 | 2026_ET-02072_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-14 | 0 | 2026_ET-02072_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02072_WR | 2026-03-12 | 03-17-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02072_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02072_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-02072_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-02072_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | VALLEY-AULD NO.1_ET-02072 |  |  | No | 18:23 |  | MENIFEE | 77 | UNK | 2025-12-10 10:24 PST ¦ 2025-12-10 13:12 PST | 121025 | 20251210 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
TEDDY-WHIRLWIND | ET-00021 | 2026_ET-00021 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.52578 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-15 | 02-16-2026 | 02-16-2026 |  | 2026_ET-00021_ACQPKG | 2026_ET-00021_GSPKG | Submitted | 2026_ET-00021_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00021_GCPR | 2025-12-08 | Historical | 2026_ET-00021_ACQ | QC Accepted | 2026_ET-00021_FR | 2026-01-09 | Submitted | 2026_ET-00021_RWR | Submitted | 2026-01-09 | 2026_ET-00021_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-16 |  | 2026_ET-00021_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00021_WR | 2026-03-12 | 03-18-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00021_VMLAZ | 2026-03-15 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00021_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00021_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00021_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | TEDDY-WHIRLWIND_ET-00021 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-15 08:36 PST ¦ 2025-12-15 08:45 PST | 121525 | 20251215 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MERCHANT NO.1 | ET-00369 | 2026_ET-00369 |  | 1 | 2026 | May 01, 2026 | 220 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.0738 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-17 | 02-16-2026 | 02-16-2026 |  | 2026_ET-00369_ACQPKG | 2026_ET-00369_GSPKG | Submitted | 2026_ET-00369_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00369_GCPR | 2025-12-08 | Historical | 2026_ET-00369_ACQ | QC Accepted | 2026_ET-00369_FR | 2026-01-09 | Submitted | 2026_ET-00369_RWR | Submitted | 2026-01-09 | 2026_ET-00369_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-16 |  | 2026_ET-00369_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00369_WR | 2026-03-12 | 03-18-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00369_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-19 | 1 | 2026_ET-00369_VMM1 | 2026-04-15 | QC Accepted |  | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-00369_RR |  | No Violations | 04-22-2026 | [5 empty] | 2026_ET-00369_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MERCHANT NO.1_ET-00369 |  |  | Yes |  | Helicopter |  |  | HC | 2025-12-17 12:29 PST ¦ 2025-12-17 12:43 PST | 121725 | 20251217 |  |  | Missing Epoch 2017.5 |  |  | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-MESA | ET-00926 | 2026_ET-00926 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 12.6286 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-04 | 01-01-2026 | Flown | 2025-11-04 | 02-16-2026 | 02-16-2026 |  | 2026_ET-00926_ACQPKG | 2026_ET-00926_GSPKG | Submitted | 2026_ET-00926_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00926_GCPR | 2025-12-08 | Historical | 2026_ET-00926_ACQ | QC Accepted | 2026_ET-00926_FR | 2025-11-27 | Submitted | 2026_ET-00926_RWR | Submitted | 2025-11-27 | 2026_ET-00926_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-16 | 0 | 2026_ET-00926_PROCPKG | In Progress | All Good - Complete | 2026_ET-00926_WR | 2026-03-24 | 03-18-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-00926_VMLAZ | 2026-03-16 | QC Accepted |  | 2026-03-24 | 0 | 2026_ET-00926_VMM1 | 2026-03-05 | QC Rejected |  |  | 2026-03-19 | 1 | 2026_ET-00926_RR | 2026-03-09 | No Violations |  |  | 0 |  |  |  | 2026_ET-00926_VER | 2026-03-18 | Uploaded to S123 |  | 2026-03-25 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-MESA_ET-00926 |  |  | Yes |  | Helicopter | MONTEBELLO | 22 | HC | 2025-11-04 11:41 PST ¦ 2025-11-04 12:03 PST | 110425 | 20251104 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE GORMAN-OSITO | ET-00259 | 2026_ET-00259 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.6386 | 8.6386 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-19 | 02-17-2026 | 02-17-2026 |  | 2026_ET-00259_ACQPKG | 2026_ET-00259_GSPKG | Submitted | 2026_ET-00259_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00259_GCPR | 2025-12-08 | Historical | 2026_ET-00259_ACQ | QC Accepted | 2026_ET-00259_FR | 2026-01-13 | Submitted | 2026_ET-00259_RWR | Submitted | 2026-01-13 | 2026_ET-00259_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-17 |  | 2026_ET-00259_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00259_WR | 2026-04-15 | 03-19-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00259_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00259_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00259_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 19 | 2026-04-24 |  | 0 | 2026_ET-00259_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE GORMAN-OSITO_ET-00259 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-19 08:49 PST ¦ 2025-12-19 09:14 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BAILEY-GORMAN | ET-00237 | 2026_ET-00237 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.375 | 3.375 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-18 | 03-03-2026 | Flown | 2025-12-19 | 02-18-2026 | 02-16-2026 |  | 2026_ET-00237_ACQPKG | 2026_ET-00237_GSPKG | Submitted | 2026_ET-00237_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00237_GCPR | 2025-12-08 | Historical | 2026_ET-00237_ACQ | QC Accepted | 2026_ET-00237_FR | 2026-01-13 | Submitted | 2026_ET-00237_RWR | Submitted | 2026-01-13 | 2026_ET-00237_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-16 |  | 2026_ET-00237_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00237_WR | 2026-04-13 | 03-20-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00237_VMLAZ | 2026-04-13 | QC Accepted | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-00237_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-00237_RR | 2026-04-13 | No Violations | 04-18-2026 |  | 0 |  |  |  | 2026_ET-00237_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BAILEY-GORMAN_ET-00237 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-19 08:44 PST ¦ 2025-12-19 09:14 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA CIENEGA-LA FRESA | ET-00982 | 2026_ET-00982 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 11.9464 | 0.96755 | 8 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | No Delay | Variable | N/A | Access | N/A | Access | Delays due to airport airspace clearance |  | SCE Approved | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-22 | 12-11-2025 | Flown | 2026-01-13 | 02-18-2026 | 02-18-2026 |  | 2026_ET-00982_ACQPKG | 2026_ET-00982_GSPKG | Submitted | 2026_ET-00982_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00982_GCPR | 2025-12-08 | Historical | 2026_ET-00982_ACQ | QC Accepted | 2026_ET-00982_FR | 2026-01-31 | Submitted | 2026_ET-00982_RWR | Submitted | 2026-01-31 | 2026_ET-00982_CLAZ | 2026-02-06 | QC Accepted | 02-20-2026 | 2026-02-18 | 0 | 2026_ET-00982_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00982_WR | 2026-03-17 | 03-20-2026 | QC Accepted | 03-31-2026 | 2026-03-24 | 0 | 2026_ET-00982_VMLAZ | 2026-03-10 | QC Accepted | 05-15-2026 | 2026-03-24 | 0 | 2026_ET-00982_VMM1 | 2026-03-09 | QC Accepted |  | 05-15-2026 | 2026-03-24 | 0 | 2026_ET-00982_RR | 2026-03-18 | Violations QC Confirmed | 03-25-2026 | 03-25-2026 | 2 | 2026-03-19 | 0 | 2 | 2026_ET-00982_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | LA CIENEGA-LA FRESA_ET-00982 |  |  | Yes | 19:28 & 11:58 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 13:31 PDT ¦ 2026-01-13 09:12 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
SANTIAGO-BORREGO | ET-00551 | 2026_ET-00551 |  | 1 | 2026 | May 01, 2026 | 66 | CA_6 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 5.4012 | 3.6994 | 68 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-12 | 01-31-2026 | Flown | 2025-12-18 | 02-19-2026 | 02-19-2026 |  | 2026_ET-00551_ACQPKG | 2026_ET-00551_GSPKG | Submitted | 2026_ET-00551_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00551_GCPR | 2025-12-08 | Historical | 2026_ET-00551_ACQ | QC Accepted | 2026_ET-00551_FR | 2026-01-31 | Submitted | 2026_ET-00551_RWR | Submitted | 2026-01-31 | 2026_ET-00551_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-19 | 1 | 2026_ET-00551_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00551_WR | 2026-03-12 | 03-21-2026 | QC Accepted | 04-01-2026 | 2026-04-09 | 0 | 2026_ET-00551_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00551_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-09 | 0 | 2026_ET-00551_RR |  | No Violations | 04-10-2026 | [5 empty] | 2026_ET-00551_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-09 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | SANTIAGO-BORREGO_ET-00551 |  |  | No | 20:17 |  | SADDLEBACK | 43 | UNK | 2025-12-18 13:08 PST ¦ 2025-12-18 13:29 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DAWN-ROSAMOND-TWILIGHT | ET-00169 | 2026_ET-00169 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.049048 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2025-12-15 | 02-20-2026 | 02-20-2026 |  | 2026_ET-00169_ACQPKG | 2026_ET-00169_GSPKG | Submitted | 2026_ET-00169_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00169_GCPR | 2025-12-08 | Historical | 2026_ET-00169_ACQ | QC Accepted | 2026_ET-00169_FR | 2026-01-09 | Submitted | 2026_ET-00169_RWR | Submitted | 2026-01-09 | 2026_ET-00169_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-20 |  | 2026_ET-00169_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00169_WR | 2026-03-12 | 03-22-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00169_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-00169_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-00169_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-00169_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | DAWN-ROSAMOND-TWILIGHT_ET-00169 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-15 08:26 PST ¦ 2025-12-15 08:28 PST | 121525 | 20251215 | [6 empty] | Yes | No Delay | Delay | N/A | Variable |  | Done |  | BulkRedelivery |  | Changes in acceptance criteria allowed acceptance | N/A | N/A |  | 12
GOLETA-SANTA CLARA NO.1 | ET-00337 | 2026_ET-00337 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 49.1585 | 49.1585 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2026-01-06 | 02-20-2026 | 02-20-2026 |  | 2026_ET-00337_ACQPKG | 2026_ET-00337_GSPKG | Submitted | 2026_ET-00337_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00337_GCPR | 2025-12-08 | Historical | 2026_ET-00337_ACQ | QC Accepted | 2026_ET-00337_FR | 2026-01-31 | Submitted | 2026_ET-00337_RWR | Submitted | 2026-01-31 | 2026_ET-00337_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-20 | 1 | 2026_ET-00337_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00337_WR | 2026-03-12 | 03-22-2026 | QC Accepted | 04-01-2026 | 2026-04-08 | 0 | 2026_ET-00337_VMLAZ | 2026-03-12 | QC Accepted | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00337_VMM1 | 2026-03-12 | QC Accepted |  | 04-16-2026 | 2026-04-08 | 0 | 2026_ET-00337_RR |  | No Violations | 04-09-2026 | [5 empty] | 2026_ET-00337_VER | 2026-03-18 | Uploaded to S123 | 04-16-2026 | 2026-04-08 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | GOLETA-SANTA CLARA NO.1_ET-00337 |  |  | Yes | 17:03 & 21:21 & 16:56 - 20:18 |  | SANTA BARBARA | 49 | UNK | 2025-12-28 11:03 PST ¦ 2026-01-06 13:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 1-BIG CREEK 2 | ET-00449 | 2026_ET-00449 |  | 1 | 2026 | May 01, 2026 | 220 | CA_4 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.4389 | 4.4389 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-07 | 01-31-2026 | Flown | 2025-12-12 | 02-20-2026 | 02-20-2026 |  | 2026_ET-00449_ACQPKG | 2026_ET-00449_GSPKG | Submitted | 2026_ET-00449_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00449_GCPR | 2025-12-08 | Historical | 2026_ET-00449_ACQ | QC Accepted | 2026_ET-00449_FR | 2026-01-09 | Submitted | 2026_ET-00449_RWR | Submitted | 2026-01-09 | 2026_ET-00449_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-20 |  | 2026_ET-00449_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00449_WR | 2026-03-12 | 03-22-2026 | QC Accepted | 04-01-2026 | 2026-04-29 |  | 2026_ET-00449_VMLAZ | 2026-03-16 | QC Accepted | 04-29-2026 | 2026-03-23 | 0 | 2026_ET-00449_VMM1 | 2026-03-12 | QC Accepted |  | 04-29-2026 | 2026-03-19 | 0 | 2026_ET-00449_RR |  | No Violations | 03-20-2026 | [5 empty] | 2026_ET-00449_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | BIG CREEK 1-BIG CREEK 2_ET-00449 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-12-12 14:45 PST ¦ 2025-12-12 15:03 PST | 121225 | 20251212 |  |  |  |  | Attribute - Height POI |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SPRINGVILLE-ANODE NO.1 | ET-02129 | 2026_ET-02129 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_4 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 01-10-2026 | On Time | 0 | Transmission | 0.1235 | 0.1235 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | Delay | No Delay | SCE | N/A | GCP | N/A | GCP_Folders_DNE | GCP folders were not available when Sharper Shape was ready to upload. IT has now created the folders |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 02-09-2026 | Flown | 2025-10-17 | 02-20-2026 | 02-20-2026 |  | 2026_ET-02129_ACQPKG | 2026_ET-02129_GSPKG | Submitted | 2026_ET-02129_GS | 2025-10-15 | Field Complete | 2026_ET-02129_GCPR | 2025-11-27 | Submitted | 2026_ET-02129_ACQ | QC Accepted | 2026_ET-02129_FR | 2025-11-13 | Submitted | 2026_ET-02129_RWR | Submitted | 2025-11-13 | 2026_ET-02129_CLAZ | 2026-02-09 | QC Accepted | 02-23-2026 | 2026-02-20 | 1 | 2026_ET-02129_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02129_WR | 2026-03-17 | 03-22-2026 | QC Accepted | 03-31-2026 | 2026-04-15 | 1 | 2026_ET-02129_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-02129_VMM1 | 2026-03-09 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-02129_RR | 2026-03-10 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-02129_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Completed On Time | Completed Late - Program | SPRINGVILLE-ANODE NO.1_ET-02129 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-10-13 10:14 PDT ¦ 2025-10-13 10:22 PDT | 101325 | 20251013 | Attribute errors | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
SPRINGVILLE-ANODE NO.2 | ET-02130 | 2026_ET-02130 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_4 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 01-10-2026 | On Time | 0 | Transmission | 0.14487 | 0.14487 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | Delay | No Delay | SCE | N/A | GCP | N/A | GCP_Folders_DNE | GCP folders were not available when Sharper Shape was ready to upload. IT has now created the folders |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-15 | 02-09-2026 | Flown | 2025-10-17 | 02-20-2026 | 02-20-2026 |  | 2026_ET-02130_ACQPKG | 2026_ET-02130_GSPKG | Submitted | 2026_ET-02130_GS | 2025-10-15 | Field Complete | 2026_ET-02130_GCPR | 2025-11-27 | Submitted | 2026_ET-02130_ACQ | QC Accepted | 2026_ET-02130_FR | 2025-11-13 | Submitted | 2026_ET-02130_RWR | Submitted | 2025-11-13 | 2026_ET-02130_CLAZ | 2026-02-09 | QC Accepted | 02-23-2026 | 2026-02-20 | 1 | 2026_ET-02130_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02130_WR | 2026-03-17 | 03-22-2026 | QC Accepted | 03-31-2026 | 2026-04-15 | 1 | 2026_ET-02130_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-02130_VMM1 | 2026-03-16 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-02130_RR | 2026-03-10 | No Violations | 03-28-2026 |  | 0 |  |  |  | 2026_ET-02130_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Completed On Time | Completed Late - Program | SPRINGVILLE-ANODE NO.2_ET-02130 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-10-13 10:14 PDT ¦ 2025-10-13 10:22 PDT | 101325 | 20251013 | Attribute errors | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
ARROYO-EAGLE ROCK | ET-01601 | 2026_ET-01601 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.763 | 4.763 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-24 | 01-01-2026 | Flown | 2025-11-04 | 02-24-2026 | 02-24-2026 |  | 2026_ET-01601_ACQPKG | 2026_ET-01601_GSPKG | Submitted | 2026_ET-01601_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01601_GCPR | 2025-12-08 | Historical | 2026_ET-01601_ACQ | QC Accepted | 2026_ET-01601_FR | 2025-11-27 | Submitted | 2026_ET-01601_RWR | Submitted | 2025-11-27 | 2026_ET-01601_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-02-24 |  | 2026_ET-01601_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01601_WR | 2026-03-24 | 03-26-2026 | QC Accepted | 04-07-2026 | 2026-04-01 | 1 | 2026_ET-01601_VMLAZ | 2026-03-16 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01601_VMM1 | 2026-03-05 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-01601_RR | 2026-03-18 | No Violations | 03-20-2026 |  | 1 | 2026-03-23 | 0 | 0 | 2026_ET-01601_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | ARROYO-EAGLE ROCK_ET-01601 | Done |  | No |  | Helicopter | MONROVIA | 27 | HC | 2025-11-04 14:23 PST ¦ 2025-11-04 14:37 PST | 110425 | 20251104 | Attribute - Air Temp | [5 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-NSO | ET-00179 | 2026_ET-00179 |  | 1 | 2026 | May 01, 2026 | 220 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.046076 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-15 | 01-31-2026 | Flown | 2025-12-17 | 02-27-2026 | 02-27-2026 |  | 2026_ET-00179_ACQPKG | 2026_ET-00179_GSPKG | Submitted | 2026_ET-00179_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00179_GCPR | 2025-12-08 | Historical | 2026_ET-00179_ACQ | QC Accepted | 2026_ET-00179_FR | 2026-01-09 | Submitted | 2026_ET-00179_RWR | Submitted | 2026-01-09 | 2026_ET-00179_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-27 |  | 2026_ET-00179_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00179_WR | 2026-03-12 | 03-29-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00179_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-24 |  | 2026_ET-00179_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-31 |  | 2026_ET-00179_RR |  | No Violations | 04-01-2026 | [5 empty] | 2026_ET-00179_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-NSO_ET-00179 |  |  | No |  | Helicopter |  |  | HC | 2025-12-17 12:29 PST ¦ 2025-12-17 12:40 PST | 121725 | 20251217 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-MERCHANT NO.2 | ET-00378 | 2026_ET-00378 |  | 1 | 2026 | May 01, 2026 | 220 | NV_E | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 1.1102 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-11 | 01-31-2026 | Flown | 2025-12-17 | 02-27-2026 | 02-27-2026 |  | 2026_ET-00378_ACQPKG | 2026_ET-00378_GSPKG | Submitted | 2026_ET-00378_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00378_GCPR | 2025-12-08 | Historical | 2026_ET-00378_ACQ | QC Accepted | 2026_ET-00378_FR | 2026-01-09 | Submitted | 2026_ET-00378_RWR | Submitted | 2026-01-09 | 2026_ET-00378_CLAZ | 2026-01-09 | QC Accepted | 02-15-2026 | 2026-02-27 |  | 2026_ET-00378_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00378_WR | 2026-03-12 | 03-29-2026 | QC Accepted | 04-01-2026 | 2026-04-01 |  | 2026_ET-00378_VMLAZ | 2026-03-12 | QC Accepted | 04-29-2026 | 2026-03-24 |  | 2026_ET-00378_VMM1 | 2026-03-15 | QC Accepted |  | 04-29-2026 | 2026-04-29 |  | 2026_ET-00378_RR |  | No Violations | 04-30-2026 | [5 empty] | 2026_ET-00378_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-27 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | ELDORADO-MERCHANT NO.2_ET-00378 |  |  | Yes |  | Helicopter |  |  | HC | 2025-12-17 12:29 PST ¦ 2025-12-17 12:43 PST | 121725 | 20251217 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-LIVE OAK-SAN ANTONIO-UPLAND | ET-00516 | 2026_ET-00516 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.696 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-18 | 03-06-2026 | 03-06-2026 |  | 2026_ET-00516_ACQPKG | 2026_ET-00516_GSPKG | Submitted | 2026_ET-00516_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00516_GCPR | 2025-12-08 | Historical | 2026_ET-00516_ACQ | QC Accepted | 2026_ET-00516_FR | 2026-03-02 | Submitted | 2026_ET-00516_RWR | Submitted | 2026-03-02 | 2026_ET-00516_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00516_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00516_WR | 2026-04-13 | 04-05-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00516_VMLAZ | 2026-04-13 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00516_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00516_RR | 2026-04-13 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00516_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE CHINO-LIVE OAK-SAN ANTONIO-UPLAND_ET-00516 |  |  | No | 18:34 |  | ONTARIO | 34 | UNK | 2025-12-18 10:26 PST ¦ 2025-12-18 10:41 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-ARCHIBALD-BAIN-JEFFERSON | ET-00921 | 2026_ET-00921 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.097667 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-03-05 | 03-03-2026 | Flown | 2026-01-13 | 03-09-2026 | 03-09-2026 |  | 2026_ET-00921_ACQPKG | 2026_ET-00921_GSPKG | Submitted | 2026_ET-00921_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00921_GCPR | 2025-12-08 | Historical | 2026_ET-00921_ACQ | QC Accepted | 2026_ET-00921_FR | 2026-03-02 | Submitted | 2026_ET-00921_RWR | Submitted | 2026-03-02 | 2026_ET-00921_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00921_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00921_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00921_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00921_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00921_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-00921_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-ARCHIBALD-BAIN-JEFFERSON_ET-00921 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-02-09 11:05 PST ¦ 2026-02-09 11:08 PST | 020926 | 20260209 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-DIAMOND BAR-GANESHA | ET-01497 | 2026_ET-01497 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 14.2769 | 9.3354 | 65 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-05 | 03-03-2026 | Flown | 2025-12-18 | 03-09-2026 | 03-09-2026 |  | 2026_ET-01497_ACQPKG | 2026_ET-01497_GSPKG | Submitted | 2026_ET-01497_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01497_GCPR | 2025-12-08 | Historical | 2026_ET-01497_ACQ | QC Accepted | 2026_ET-01497_FR | 2026-03-02 | Submitted | 2026_ET-01497_RWR | Submitted | 2026-03-02 | 2026_ET-01497_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01497_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01497_WR | 2026-04-13 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01497_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01497_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01497_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 12 | 2026-05-11 |  | 0 | 2026_ET-01497_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | CHINO-DIAMOND BAR-GANESHA_ET-01497 |  |  | No | 17:05 |  | ONTARIO | 34 | UNK | 2025-12-14 13:51 PST ¦ 2025-12-18 09:13 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-APOLLO-SHAWNEE | ET-01642 | 2026_ET-01642 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.591 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-18 | 03-03-2026 | Flown | 2025-12-20 | 03-09-2026 | 03-09-2026 |  | 2026_ET-01642_ACQPKG | 2026_ET-01642_GSPKG | Submitted | 2026_ET-01642_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01642_GCPR | 2025-12-08 | Historical | 2026_ET-01642_ACQ | QC Accepted | 2026_ET-01642_FR | 2026-03-02 | Submitted | 2026_ET-01642_RWR | Submitted | 2026-03-02 | 2026_ET-01642_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01642_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01642_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01642_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01642_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01642_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01642_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BARRE-APOLLO-SHAWNEE_ET-01642 | Done |  | No | 19:32 |  | HUNTINGTON BEACH | 33 | UNK | 2025-12-20 12:14 PST ¦ 2025-12-20 13:09 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEVERS-CARODEAN-HI DESERT-YUCCA | ET-01738 | 2026_ET-01738 |  | 1 | 2026 | Jun 01, 2026 | 115 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.59914 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown |  | 03-09-2026 | 03-09-2026 |  | 2026_ET-01738_ACQPKG | 2026_ET-01738_GSPKG | Submitted | 2026_ET-01738_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01738_GCPR | 2025-12-08 | Historical | 2026_ET-01738_ACQ | QC Accepted | 2026_ET-01738_FR | 2026-03-02 | Submitted | 2026_ET-01738_RWR | Submitted | 2026-03-02 | 2026_ET-01738_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01738_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01738_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01738_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01738_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01738_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01738_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE DEVERS-CARODEAN-HI DESERT-YUCCA_ET-01738 |  |  | No |  |  | YUCCA VALLEY | 84 | UNK | 2025-12-22 13:35 PST ¦ 2025-12-22 14:00 PST | 122225 | 20251222 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOOST-LUCAS | ET-01874 | 2026_ET-01874 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 6.0953 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-05 | 03-03-2026 | Flown | 2026-01-09 | 03-09-2026 | 03-09-2026 |  | 2026_ET-01874_ACQPKG | 2026_ET-01874_GSPKG | Submitted | 2026_ET-01874_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01874_GCPR | 2025-12-08 | Historical | 2026_ET-01874_ACQ | QC Accepted | 2026_ET-01874_FR | 2026-03-02 | Submitted | 2026_ET-01874_RWR | Submitted | 2026-03-02 | 2026_ET-01874_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01874_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01874_WR | 2026-04-13 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01874_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01874_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01874_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01874_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | BOOST-LUCAS_ET-01874 | Done |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 10:46 PST ¦ 2026-01-09 12:08 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LIGHTHIPE-SIGNAL HILL NO.2 | ET-01926 | 2026_ET-01926 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.1491 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2026-01-09 | 03-09-2026 | 03-09-2026 |  | 2026_ET-01926_ACQPKG | 2026_ET-01926_GSPKG | Submitted | 2026_ET-01926_GS | 2026-03-02 | Field Complete | 2026_ET-01926_GCPR | 2026-03-02 | Submitted | 2026_ET-01926_ACQ | QC Accepted | 2026_ET-01926_FR | 2026-03-02 | Submitted | 2026_ET-01926_RWR | Submitted | 2026-03-02 | 2026_ET-01926_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01926_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01926_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01926_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01926_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01926_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01926_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE LIGHTHIPE-SIGNAL HILL NO.2_ET-01926 |  |  | No | 18:13 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 13:49 PST ¦ 2026-01-09 12:28 PST | 010926 | 20260109 | [6 empty] | No | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-LEONIS SOUTH | ET-02085 | 2026_ET-02085 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.3759 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-16 | 03-09-2026 | 03-09-2026 |  | 2026_ET-02085_ACQPKG | 2026_ET-02085_GSPKG | Submitted | 2026_ET-02085_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02085_GCPR | 2025-12-08 | Historical | 2026_ET-02085_ACQ | QC Accepted | 2026_ET-02085_FR | 2026-03-02 | Submitted | 2026_ET-02085_RWR | Submitted | 2026-03-02 | 2026_ET-02085_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02085_PROCPKG | In Progress | All Good - Complete | 2026_ET-02085_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-02085_VMLAZ | 2026-04-15 | QC Accepted |  | 2026-05-18 |  | 2026_ET-02085_VMM1 | 2026-04-15 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-02085_RR | 2026-04-15 | No Violations |  |  | 0 |  |  |  | 2026_ET-02085_VER | 2026-04-15 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE LAGUNA BELL-LEONIS SOUTH_ET-02085 |  |  | No | 20:00 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-16 11:43 PST ¦ 2025-12-16 12:14 PST | 121625 | 20251216 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE FOGARTY-IVYGLEN | ET-02149 | 2026_ET-02149 |  | 1 | 2026 | Jun 01, 2026 | 115 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.10599 | 0.10599 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-19 | 03-09-2026 | 03-09-2026 |  | 2026_ET-02149_ACQPKG | 2026_ET-02149_GSPKG | Submitted | 2026_ET-02149_GS | 2026-03-02 | Field Complete | 2026_ET-02149_GCPR | 2026-03-02 | Submitted | 2026_ET-02149_ACQ | QC Accepted | 2026_ET-02149_FR | 2026-03-02 | Submitted | 2026_ET-02149_RWR | Submitted | 2026-03-02 | 2026_ET-02149_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02149_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02149_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-02149_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-02149_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-02149_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-02149_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE FOGARTY-IVYGLEN_ET-02149 |  |  | No | 21:35 |  | WILDOMAR | 88 | UNK | 2025-12-19 13:34 PST ¦ 2025-12-19 13:55 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTA CLARA-SAN MARCOS | ET-07083 | 2026_ET-07083 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.3239 | 8.3239 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2026-01-06 | 03-09-2026 | 03-09-2026 |  | 2026_ET-07083_ACQPKG | 2026_ET-07083_GSPKG | Submitted | 2026_ET-07083_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07083_GCPR | 2025-12-08 | Historical | 2026_ET-07083_ACQ | QC Accepted | 2026_ET-07083_FR | 2026-03-02 | Submitted | 2026_ET-07083_RWR | Submitted | 2026-03-02 | 2026_ET-07083_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-07083_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-07083_WR | 2026-04-15 | 04-08-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-07083_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-07083_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-07083_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 2 | 2026-05-11 |  | 0 | 2026_ET-07083_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE SANTA CLARA-SAN MARCOS_ET-07083 |  |  | No | 21:21 & 15:56 |  | VENTURA | 39 | UNK | 2025-12-28 14:40 PST ¦ 2026-01-06 11:05 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELY-MARION | ET-00260 | 2026_ET-00260 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.2707 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-20 | 03-10-2026 | 03-06-2026 |  | 2026_ET-00260_ACQPKG | 2026_ET-00260_GSPKG | Submitted | 2026_ET-00260_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00260_GCPR | 2025-12-08 | Historical | 2026_ET-00260_ACQ | QC Accepted | 2026_ET-00260_FR | 2026-03-02 | Submitted | 2026_ET-00260_RWR | Submitted | 2026-03-02 | 2026_ET-00260_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00260_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00260_WR | 2026-04-16 | 04-09-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00260_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00260_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00260_RR | 2026-04-16 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00260_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | BARRE-ELY-MARION_ET-00260 | Done |  | No | 21:46 |  | FULLERTON | 48 | UNK | 2025-12-20 12:52 PST ¦ 2026-01-09 10:58 PST | 122025 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-ELY | ET-00466 | 2026_ET-00466 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.6043 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-20 | 03-10-2026 | 03-10-2026 |  | 2026_ET-00466_ACQPKG | 2026_ET-00466_GSPKG | Submitted | 2026_ET-00466_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00466_GCPR | 2025-12-08 | Historical | 2026_ET-00466_ACQ | QC Accepted | 2026_ET-00466_FR | 2026-03-02 | Submitted | 2026_ET-00466_RWR | Submitted | 2026-03-02 | 2026_ET-00466_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00466_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00466_WR | 2026-04-16 | 04-09-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00466_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00466_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00466_RR | 2026-04-16 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00466_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | BARRE-ELY_ET-00466 | Done |  | No | 21:21 |  | FULLERTON | 48 | UNK | 2025-12-20 13:11 PST ¦ 2025-12-20 14:17 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CORTEZ-GARDEN STATE-LAYFAIR-SAN DMS | ET-00742 | 2026_ET-00742 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.636 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-18 | 03-10-2026 | 03-10-2026 |  | 2026_ET-00742_ACQPKG | 2026_ET-00742_GSPKG | Submitted | 2026_ET-00742_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00742_GCPR | 2025-12-08 | Historical | 2026_ET-00742_ACQ | QC Accepted | 2026_ET-00742_FR | 2026-03-02 | Submitted | 2026_ET-00742_RWR | Submitted | 2026-03-02 | 2026_ET-00742_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00742_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00742_WR | 2026-04-13 | 04-09-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00742_VMLAZ | 2026-04-13 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00742_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00742_RR | 2026-04-13 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00742_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE CORTEZ-GARDEN STATE-LAYFAIR-SAN DMS_ET-00742 |  |  | No | 17:57 |  | COVINA | 26 | UNK | 2025-12-18 09:57 PST ¦ 2025-12-18 10:08 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 1-EASTWOOD | ET-01081 | 2026_ET-01081 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_4 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.7685 | 4.7685 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-19 | 03-10-2026 | 02-18-2026 |  | 2026_ET-01081_ACQPKG | 2026_ET-01081_GSPKG | Submitted | 2026_ET-01081_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01081_GCPR | 2025-12-08 | Historical | 2026_ET-01081_ACQ | QC Accepted | 2026_ET-01081_FR | 2026-01-13 | Submitted | 2026_ET-01081_RWR | Submitted | 2026-01-13 | 2026_ET-01081_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-18 |  | 2026_ET-01081_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01081_WR | 2026-03-25 | 04-09-2026 | QC Accepted | 05-02-2026 | 2026-04-01 |  | 2026_ET-01081_VMLAZ | 2026-03-25 | QC Accepted | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01081_VMM1 | 2026-03-25 | QC Accepted |  | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01081_RR | 2026-03-25 | No Violations | 03-28-2026 | [5 empty] | 2026_ET-01081_VER | 2026-04-17 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BIG CREEK 1-EASTWOOD_ET-01081 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2025-12-19 13:46 PST ¦ 2025-12-19 14:07 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BREA-BROADROCK | ET-01904 | 2026_ET-01904 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.87122 | 0.87122 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-19 | 03-10-2026 | 03-09-2026 |  | 2026_ET-01904_ACQPKG | 2026_ET-01904_GSPKG | Submitted | 2026_ET-01904_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01904_GCPR | 2025-12-08 | Historical | 2026_ET-01904_ACQ | QC Accepted | 2026_ET-01904_FR | 2026-03-02 | Submitted | 2026_ET-01904_RWR | Submitted | 2026-03-02 | 2026_ET-01904_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01904_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01904_WR | 2026-04-15 | 04-09-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01904_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01904_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01904_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01904_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BREA-BROADROCK_ET-01904 | Done |  | No | 22:50 |  | FULLERTON | 48 | UNK | 2025-12-19 14:49 PST ¦ 2025-12-19 14:56 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CPC EAST-WINDHUB | ET-00585 | 2026_ET-00585 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.23244 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-11 | 03-03-2026 | Flown | 2025-12-18 | 03-11-2026 | 02-12-2026 |  | 2026_ET-00585_ACQPKG | 2026_ET-00585_GSPKG | Submitted | 2026_ET-00585_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00585_GCPR | 2025-12-08 | Historical | 2026_ET-00585_ACQ | QC Accepted | 2026_ET-00585_FR | 2026-01-13 | Submitted | 2026_ET-00585_RWR | Submitted | 2026-01-13 | 2026_ET-00585_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00585_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00585_WR | 2026-04-16 | 04-10-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00585_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00585_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00585_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00585_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | CPC EAST-WINDHUB_ET-00585 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-18 15:55 PST ¦ 2025-12-18 16:01 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CPC WEST-WINDHUB | ET-00587 | 2026_ET-00587 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.22824 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-11 | 03-03-2026 | Flown | 2025-12-18 | 03-11-2026 | 02-12-2026 |  | 2026_ET-00587_ACQPKG | 2026_ET-00587_GSPKG | Submitted | 2026_ET-00587_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00587_GCPR | 2025-12-08 | Historical | 2026_ET-00587_ACQ | QC Accepted | 2026_ET-00587_FR | 2026-01-13 | Submitted | 2026_ET-00587_RWR | Submitted | 2026-01-13 | 2026_ET-00587_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00587_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00587_WR | 2026-04-16 | 04-10-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00587_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00587_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00587_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00587_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | CPC WEST-WINDHUB_ET-00587 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-18 15:55 PST ¦ 2025-12-18 16:01 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CRATER-RECLAIM-TAPIA | ET-01596 | 2026_ET-01596 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 6.0404 | 6.0404 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-11 | 03-03-2026 | Flown | 2026-01-08 | 03-11-2026 | 03-09-2026 |  | 2026_ET-01596_ACQPKG | 2026_ET-01596_GSPKG | Submitted | 2026_ET-01596_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01596_GCPR | 2025-12-08 | Historical | 2026_ET-01596_ACQ | QC Accepted | 2026_ET-01596_FR | 2026-03-02 | Submitted | 2026_ET-01596_RWR | Submitted | 2026-03-02 | 2026_ET-01596_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01596_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01596_WR | 2026-04-15 | 04-10-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01596_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01596_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01596_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 1 | 2026-05-11 |  | 0 | 2026_ET-01596_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | CRATER-RECLAIM-TAPIA_ET-01596 |  |  | No | 20:41 |  | THOUSAND OAKS | 35 | UNK | 2026-01-08 13:50 PST ¦ 2026-01-08 14:24 PST | 010826 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COTTONWOOD-PERMANENTE | ET-01669 | 2026_ET-01669 |  | 1 | 2026 | Jun 01, 2026 | 115 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.8965 | 1.5335 | 81 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-11 | 03-03-2026 | Flown | 2025-12-18 | 03-11-2026 | 02-25-2026 |  | 2026_ET-01669_ACQPKG | 2026_ET-01669_GSPKG | Submitted | 2026_ET-01669_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01669_GCPR | 2025-12-08 | Historical | 2026_ET-01669_ACQ | QC Accepted | 2026_ET-01669_FR | 2026-01-13 | Submitted | 2026_ET-01669_RWR | Submitted | 2026-01-13 | 2026_ET-01669_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-25 |  | 2026_ET-01669_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01669_WR | 2026-04-13 | 04-10-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-01669_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-01669_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-01669_RR | 2026-04-13 | No Violations | 04-18-2026 |  | 6 | 2026-04-14 |  | 0 | 2026_ET-01669_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | COTTONWOOD-PERMANENTE_ET-01669 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2025-12-18 09:39 PST ¦ 2025-12-18 09:45 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DESERT STAR - WHIRLWIND | ET-00041 | 2026_ET-00041 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.62747 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-18 | 03-12-2026 | 02-13-2026 |  | 2026_ET-00041_ACQPKG | 2026_ET-00041_GSPKG | Submitted | 2026_ET-00041_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00041_GCPR | 2025-12-08 | Historical | 2026_ET-00041_ACQ | QC Accepted | 2026_ET-00041_FR | 2026-01-13 | Submitted | 2026_ET-00041_RWR | Submitted | 2026-01-13 | 2026_ET-00041_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-13 |  | 2026_ET-00041_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00041_WR | 2026-04-16 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00041_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-28 | 0 | 2026_ET-00041_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-27 | 0 | 2026_ET-00041_RR | 2026-04-16 | No Violations | 04-28-2026 |  | 0 |  |  |  | 2026_ET-00041_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-27 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | DESERT STAR - WHIRLWIND_ET-00041 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-18 16:10 PST ¦ 2025-12-18 16:21 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CREST-MARYMOUNT | ET-00757 | 2026_ET-00757 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.2223 | 2.2223 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2026-01-11 | 03-12-2026 | 03-06-2026 |  | 2026_ET-00757_ACQPKG | 2026_ET-00757_GSPKG | Submitted | 2026_ET-00757_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00757_GCPR | 2025-12-08 | Historical | 2026_ET-00757_ACQ | QC Accepted | 2026_ET-00757_FR | 2026-03-02 | Submitted | 2026_ET-00757_RWR | Submitted | 2026-03-02 | 2026_ET-00757_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00757_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00757_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00757_VMLAZ | 2026-04-13 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00757_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00757_RR | 2026-04-13 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00757_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CREST-MARYMOUNT_ET-00757 |  |  | No | 15:16 |  | SOUTH BAY | 44 | UNK | 2026-01-11 09:00 PST ¦ 2026-01-11 09:13 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-MESA | ET-00771 | 2026_ET-00771 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 24.5559 | 14.2722 | 58 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-20 | 03-12-2026 | 02-13-2026 |  | 2026_ET-00771_ACQPKG | 2026_ET-00771_GSPKG | Submitted | 2026_ET-00771_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00771_GCPR | 2025-12-08 | Historical | 2026_ET-00771_ACQ | QC Accepted | 2026_ET-00771_FR | 2026-01-13 | Submitted | 2026_ET-00771_RWR | Submitted | 2026-01-13 | 2026_ET-00771_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-13 |  | 2026_ET-00771_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00771_WR | 2026-04-16 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00771_VMLAZ | 2026-04-16 | QC Accepted | 05-27-2026 | 2026-04-21 |  | 2026_ET-00771_VMM1 | 2026-05-13 | QC Accepted |  | 05-27-2026 | 2026-05-20 | 1 | 2026_ET-00771_RR | 2026-04-16 | No Violations | 05-21-2026 |  | 1 | 2026-04-24 |  | 0 | 2026_ET-00771_VER | 2026-04-16 | Uploaded to S123 | 05-27-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | EAGLE ROCK-MESA_ET-00771 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | 2025-12-20 09:37 PST ¦ 2025-12-20 11:46 PST | 122025 | 20251220 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CARMENITA | ET-01031 | 2026_ET-01031 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.6066 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-21 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01031_ACQPKG | 2026_ET-01031_GSPKG | Submitted | 2026_ET-01031_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01031_GCPR | 2025-12-08 | Historical | 2026_ET-01031_ACQ | QC Accepted | 2026_ET-01031_FR | 2026-03-02 | Submitted | 2026_ET-01031_RWR | Submitted | 2026-03-02 | 2026_ET-01031_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01031_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01031_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01031_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01031_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01031_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01031_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | DEL AMO-CARMENITA_ET-01031 |  |  | No | 21:12 |  | WHITTIER | 47 | UNK | 2025-12-21 13:37 PST ¦ 2025-12-21 13:58 PST | 122125 | 20251221 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-ARBORS-FORGE-REDUCTION | ET-01065 | 2026_ET-01065 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.8504 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-19 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01065_ACQPKG | 2026_ET-01065_GSPKG | Submitted | 2026_ET-01065_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01065_GCPR | 2025-12-08 | Historical | 2026_ET-01065_ACQ | QC Accepted | 2026_ET-01065_FR | 2026-03-02 | Submitted | 2026_ET-01065_RWR | Submitted | 2026-03-02 | 2026_ET-01065_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01065_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01065_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01065_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01065_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01065_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01065_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ETIWANDA-ARBORS-FORGE-REDUCTION_ET-01065 |  |  | No | 17:01 |  | FOOTHILL | 30 | UNK | 2025-12-19 08:51 PST ¦ 2025-12-19 09:36 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DIEMER-YORBA LINDA | ET-01152 | 2026_ET-01152 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.5215 | 0.17756 | 12 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-19 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01152_ACQPKG | 2026_ET-01152_GSPKG | Submitted | 2026_ET-01152_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01152_GCPR | 2025-12-08 | Historical | 2026_ET-01152_ACQ | QC Accepted | 2026_ET-01152_FR | 2026-03-02 | Submitted | 2026_ET-01152_RWR | Submitted | 2026-03-02 | 2026_ET-01152_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01152_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01152_WR | 2026-04-15 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01152_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01152_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01152_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01152_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | DIEMER-YORBA LINDA_ET-01152 |  |  | No | 20:42 |  | FULLERTON | 48 | UNK | 2025-12-19 14:37 PST ¦ 2025-12-19 14:45 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DIEMER-MWD | ET-01158 | 2026_ET-01158 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.51536 | 0.51536 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-19 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01158_ACQPKG | 2026_ET-01158_GSPKG | Submitted | 2026_ET-01158_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01158_GCPR | 2025-12-08 | Historical | 2026_ET-01158_ACQ | QC Accepted | 2026_ET-01158_FR | 2026-03-02 | Submitted | 2026_ET-01158_RWR | Submitted | 2026-03-02 | 2026_ET-01158_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01158_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01158_WR | 2026-04-15 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01158_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01158_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01158_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01158_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | DIEMER-MWD_ET-01158 |  |  | No | 20:42 |  | FULLERTON | 48 | UNK | 2025-12-19 14:44 PST ¦ 2025-12-19 14:47 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-HUGHESAIR-LA FRESA | ET-01287 | 2026_ET-01287 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.8514 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-11-05 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01287_ACQPKG | 2026_ET-01287_GSPKG | Submitted | 2026_ET-01287_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01287_GCPR | 2025-12-08 | Historical | 2026_ET-01287_ACQ | QC Accepted | 2026_ET-01287_FR | 2026-03-02 | Submitted | 2026_ET-01287_RWR | Submitted | 2026-03-02 | 2026_ET-01287_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01287_PROCPKG | In Progress | All Good - Complete | 2026_ET-01287_WR | 2026-04-15 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01287_VMLAZ | 2026-04-15 | QC Accepted |  | 2026-05-18 |  | 2026_ET-01287_VMM1 | 2026-04-15 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-01287_RR | 2026-04-15 | No Violations |  |  | 0 |  |  |  | 2026_ET-01287_VER | 2026-04-15 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | EL NIDO-HUGHESAIR-LA FRESA_ET-01287 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2026-01-11 09:34 PST ¦ 2026-01-13 08:06 PST | 011326 | 20260113 | [5 empty] | Subject conductors strung incorrectly. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-LUCAS NO. 1 | ET-01426 | 2026_ET-01426 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.1429 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2026-01-09 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01426_ACQPKG | 2026_ET-01426_GSPKG | Submitted | 2026_ET-01426_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01426_GCPR | 2025-12-08 | Historical | 2026_ET-01426_ACQ | QC Accepted | 2026_ET-01426_FR | 2026-03-02 | Submitted | 2026_ET-01426_RWR | Submitted | 2026-03-02 | 2026_ET-01426_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01426_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01426_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01426_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01426_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01426_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01426_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-LUCAS NO. 1_ET-01426 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 10:41 PST ¦ 2026-01-09 11:47 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-LUCAS NO. 3 | ET-01428 | 2026_ET-01428 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.3756 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2026-01-09 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01428_ACQPKG | 2026_ET-01428_GSPKG | Submitted | 2026_ET-01428_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01428_GCPR | 2025-12-08 | Historical | 2026_ET-01428_ACQ | QC Accepted | 2026_ET-01428_FR | 2026-03-02 | Submitted | 2026_ET-01428_RWR | Submitted | 2026-03-02 | 2026_ET-01428_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01428_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01428_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01428_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01428_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01428_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01428_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-LUCAS NO. 3_ET-01428 |  |  | No | 18:13 |  | LONG BEACH | 46 | UNK | 2026-01-09 10:42 PST ¦ 2026-01-09 11:21 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-APPGEN-THATCHER GLASS | ET-01463 | 2026_ET-01463 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.24354 | 0.24354 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-02-15 | 03-03-2026 | Flown | 2025-12-27 | 03-12-2026 | 03-12-2026 |  | 2026_ET-01463_ACQPKG | 2026_ET-01463_GSPKG | Submitted | 2026_ET-01463_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01463_GCPR | 2025-12-08 | Historical | 2026_ET-01463_ACQ | QC Accepted | 2026_ET-01463_FR | 2026-03-02 | Submitted | 2026_ET-01463_RWR | Submitted | 2026-03-02 | 2026_ET-01463_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-12 | 0 | 2026_ET-01463_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01463_WR | 2026-04-15 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01463_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01463_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01463_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01463_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-APPGEN-THATCHER GLASS_ET-01463 |  |  | No | 17:54 |  | VALENCIA | 59 | UNK | 2025-12-27 10:38 PST ¦ 2025-12-27 11:00 PST | 122725 | 20251227 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EARLIMART-PIXLEY | ET-01690 | 2026_ET-01690 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_4 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 9.1881 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-19 | 03-12-2026 | 03-02-2026 |  | 2026_ET-01690_ACQPKG | 2026_ET-01690_GSPKG | Submitted | 2026_ET-01690_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01690_GCPR | 2025-12-08 | Historical | 2026_ET-01690_ACQ | QC Accepted | 2026_ET-01690_FR | 2026-01-13 | Submitted | 2026_ET-01690_RWR | Submitted | 2026-01-13 | 2026_ET-01690_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-03-02 |  | 2026_ET-01690_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01690_WR | 2026-03-25 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-04-01 |  | 2026_ET-01690_VMLAZ | 2026-03-25 | QC Accepted | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01690_VMM1 | 2026-03-25 | QC Accepted |  | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01690_RR | 2026-03-25 | No Violations | 03-28-2026 |  | 0 |  |  |  | 2026_ET-01690_VER | 2026-03-25 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | EARLIMART-PIXLEY_ET-01690 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-19 10:45 PST ¦ 2025-12-19 11:01 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOCK-NAVY MOLE | ET-01830 | 2026_ET-01830 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.6476 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2026-01-10 | 03-12-2026 | 03-09-2026 |  | 2026_ET-01830_ACQPKG | 2026_ET-01830_GSPKG | Submitted | 2026_ET-01830_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01830_GCPR | 2025-12-08 | Historical | 2026_ET-01830_ACQ | QC Accepted | 2026_ET-01830_FR | 2026-03-02 | Submitted | 2026_ET-01830_RWR | Submitted | 2026-03-02 | 2026_ET-01830_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01830_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01830_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01830_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01830_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01830_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01830_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DOCK-NAVY MOLE_ET-01830 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:42 PST ¦ 2026-01-10 12:05 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-FELTON-LA CIENEGA | ET-01961 | 2026_ET-01961 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 9.7516 | 0.64549 | 7 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | Delay | No Delay | Variable | N/A | Access | N/A | Access | Airspace restricitions, waiting on clearance from FAA/Airport |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2026-01-13 | 03-12-2026 | 03-12-2026 |  | 2026_ET-01961_ACQPKG | 2026_ET-01961_GSPKG | Submitted | 2026_ET-01961_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01961_GCPR | 2025-12-08 | Historical | 2026_ET-01961_ACQ | QC Accepted | 2026_ET-01961_FR | 2026-03-04 | Submitted | 2026_ET-01961_RWR | Submitted | 2026-03-04 | 2026_ET-01961_CLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-12 | 1 | 2026_ET-01961_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01961_WR | 2026-04-17 | 04-11-2026 | QC Accepted | 05-01-2026 | 2026-05-01 | 0 | 2026_ET-01961_VMLAZ | 2026-04-07 | QC Accepted | 05-01-2026 | 2026-05-01 | 0 | 2026_ET-01961_VMM1 | 2026-04-17 | QC Accepted |  | 05-01-2026 | 2026-05-01 | 0 | 2026_ET-01961_RR | 2026-04-17 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-01961_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | EL NIDO-FELTON-LA CIENEGA_ET-01961 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2025-10-19 09:57 PDT ¦ 2026-01-13 08:53 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL ROSA-SAN MANUEL | ET-02036 | 2026_ET-02036 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.0218 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-18 | 03-12-2026 | 03-09-2026 |  | 2026_ET-02036_ACQPKG | 2026_ET-02036_GSPKG | Submitted | 2026_ET-02036_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02036_GCPR | 2025-12-08 | Historical | 2026_ET-02036_ACQ | QC Accepted | 2026_ET-02036_FR | 2026-03-02 | Submitted | 2026_ET-02036_RWR | Submitted | 2026-03-02 | 2026_ET-02036_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02036_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02036_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-02036_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-02036_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-02036_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-02036_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | DEL ROSA-SAN MANUEL_ET-02036 |  |  | No | 18:58 |  | REDLANDS | 31 | UNK | 2025-12-18 10:56 PST ¦ 2025-12-18 11:00 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SUNWARD-WINDHUB NO.2 | ET-02128 | 2026_ET-02128 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.18825 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-05 | 01-01-2026 | Flown | 2025-11-02 | 03-12-2026 | 03-12-2026 |  | 2026_ET-02128_ACQPKG | 2026_ET-02128_GSPKG | Submitted | 2026_ET-02128_GS | 2025-10-17 | Field Complete | 2026_ET-02128_GCPR | 2025-12-08 | Submitted | 2026_ET-02128_ACQ | QC Accepted | 2026_ET-02128_FR | 2025-11-27 | Submitted | 2026_ET-02128_RWR | Submitted | 2025-11-27 | 2026_ET-02128_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-03-12 | 2 | 2026_ET-02128_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02128_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 04-27-2026 | 2026-04-20 |  | 2026_ET-02128_VMLAZ | 2026-04-07 | QC Accepted | 04-27-2026 | 2026-04-20 |  | 2026_ET-02128_VMM1 | 2026-04-13 | QC Accepted |  | 04-27-2026 | 2026-04-17 | 0 | 2026_ET-02128_RR | 2026-04-13 | No Violations | 04-18-2026 |  | 0 |  |  |  | 2026_ET-02128_VER | 2026-04-13 | Uploaded to S123 | 04-27-2026 | 2026-04-20 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | SUNWARD-WINDHUB NO.2_ET-02128 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-11-02 10:24 PST ¦ 2025-11-02 10:31 PST | 110225 | 20251102 | [6 empty] | No | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CUMMINGS-MONOLITH | ET-02157 | 2026_ET-02157 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 7.4796 | 6.6708 | 89 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-12 | 03-03-2026 | Flown | 2025-12-19 | 03-12-2026 | 02-24-2026 |  | 2026_ET-02157_ACQPKG | 2026_ET-02157_GSPKG | Submitted | 2026_ET-02157_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02157_GCPR | 2025-12-08 | Historical | 2026_ET-02157_ACQ | QC Accepted | 2026_ET-02157_FR | 2026-01-13 | Submitted | 2026_ET-02157_RWR | Submitted | 2026-01-13 | 2026_ET-02157_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-24 |  | 2026_ET-02157_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02157_WR | 2026-04-13 | 04-11-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-02157_VMLAZ | 2026-04-13 | QC Accepted | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-02157_VMM1 | 2026-04-13 | QC Accepted |  | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-02157_RR | 2026-04-13 | No Violations | 04-18-2026 |  | 0 |  |  |  | 2026_ET-02157_VER | 2026-04-13 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | CUMMINGS-MONOLITH_ET-02157 |  |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-19 15:28 PST ¦ 2025-12-19 15:41 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
FOGARTY-IVYGLEN | ET-00152 | 2026_ET-00152 |  | 1 | 2026 | Jun 01, 2026 | 115 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 9.3206 | 9.3179 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-12-19 | 03-13-2026 | 03-06-2026 |  | 2026_ET-00152_ACQPKG | 2026_ET-00152_GSPKG | Submitted | 2026_ET-00152_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00152_GCPR | 2025-12-08 | Historical | 2026_ET-00152_ACQ | QC Accepted | 2026_ET-00152_FR | 2026-03-02 | Submitted | 2026_ET-00152_RWR | Submitted | 2026-03-02 | 2026_ET-00152_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00152_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00152_WR | 2026-04-16 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00152_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00152_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00152_RR | 2026-04-16 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00152_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | FOGARTY-IVYGLEN_ET-00152 |  |  | No | 21:35 |  | WILDOMAR | 88 | UNK | 2025-12-19 13:29 PST ¦ 2025-12-19 13:59 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOULD-SYLMAR | ET-00701 | 2026_ET-00701 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 27.3597 | 22.6689 | 83 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-12-20 | 03-13-2026 | 02-18-2026 |  | 2026_ET-00701_ACQPKG | 2026_ET-00701_GSPKG | Submitted | 2026_ET-00701_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00701_GCPR | 2025-12-08 | Historical | 2026_ET-00701_ACQ | QC Accepted | 2026_ET-00701_FR | 2026-01-13 | Submitted | 2026_ET-00701_RWR | Submitted | 2026-01-13 | 2026_ET-00701_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-18 |  | 2026_ET-00701_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00701_WR | 2026-04-20 | 04-12-2026 | QC Accepted | 05-04-2026 | 2026-04-29 |  | 2026_ET-00701_VMLAZ | 2026-04-20 | QC Accepted | 05-04-2026 | 2026-04-28 | 0 | 2026_ET-00701_VMM1 | 2026-04-20 | QC Accepted |  | 05-04-2026 | 2026-04-24 | 0 | 2026_ET-00701_RR | 2026-04-20 | No Violations | 04-25-2026 |  | 15 | 2026-04-27 | 0 | 0 | 2026_ET-00701_VER | 2026-04-20 | Uploaded to S123 | 05-04-2026 | 2026-05-04 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | GOULD-SYLMAR_ET-00701 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | 2025-04-06 09:45 PDT ¦ 2025-12-20 12:15 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CORNUTA-SOMERSET | ET-01308 | 2026_ET-01308 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.9759 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-09 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01308_ACQPKG | 2026_ET-01308_GSPKG | Submitted | 2026_ET-01308_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01308_GCPR | 2025-12-08 | Historical | 2026_ET-01308_ACQ | QC Accepted | 2026_ET-01308_FR | 2026-03-02 | Submitted | 2026_ET-01308_RWR | Submitted | 2026-03-02 | 2026_ET-01308_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01308_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01308_WR | 2026-04-15 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01308_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01308_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01308_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01308_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-CORNUTA-SOMERSET_ET-01308 |  |  | No | 18:13 |  | DOMINGUEZ HILLS | 32 | UNK | 2025-12-21 14:20 PST ¦ 2026-01-09 12:09 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-INLAND-WIMBLEDON | ET-01336 | 2026_ET-01336 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.2001 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-12-19 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01336_ACQPKG | 2026_ET-01336_GSPKG | Submitted | 2026_ET-01336_GS | 2026-03-02 | Field Complete | 2026_ET-01336_GCPR | 2026-03-02 | Submitted | 2026_ET-01336_ACQ | QC Accepted | 2026_ET-01336_FR | 2026-03-02 | Submitted | 2026_ET-01336_RWR | Submitted | 2026-03-02 | 2026_ET-01336_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01336_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01336_WR | 2026-04-13 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01336_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01336_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01336_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01336_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ETIWANDA-INLAND-WIMBLEDON_ET-01336 |  |  | No | 18:12 |  | FOOTHILL | 30 | UNK | 2025-12-19 09:01 PST ¦ 2025-12-19 10:21 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
FELTON-LENNOX | ET-01367 | 2026_ET-01367 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.8138 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-13 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01367_ACQPKG | 2026_ET-01367_GSPKG | Submitted | 2026_ET-01367_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01367_GCPR | 2025-12-08 | Historical | 2026_ET-01367_ACQ | QC Accepted | 2026_ET-01367_FR | 2026-03-02 | Submitted | 2026_ET-01367_RWR | Submitted | 2026-03-02 | 2026_ET-01367_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01367_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01367_WR | 2026-04-15 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01367_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01367_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01367_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01367_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | FELTON-LENNOX_ET-01367 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 04:31 PST ¦ 2026-01-13 07:23 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHANNEL ISLAND-MANDALAY-UNIOIL | ET-01466 | 2026_ET-01466 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.5114 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-06 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01466_ACQPKG | 2026_ET-01466_GSPKG | Submitted | 2026_ET-01466_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01466_GCPR | 2025-12-08 | Historical | 2026_ET-01466_ACQ | QC Accepted | 2026_ET-01466_FR | 2026-03-02 | Submitted | 2026_ET-01466_RWR | Submitted | 2026-03-02 | 2026_ET-01466_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01466_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01466_WR | 2026-04-13 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01466_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01466_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01466_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01466_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | CHANNEL ISLAND-MANDALAY-UNIOIL_ET-01466 |  |  | No | 20:18 |  | VENTURA | 39 | UNK | 2026-01-06 14:12 PST ¦ 2026-01-06 14:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HARBORGEN-HINSON | ET-01495 | 2026_ET-01495 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.0773 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-10-18 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01495_ACQPKG | 2026_ET-01495_GSPKG | Submitted | 2026_ET-01495_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01495_GCPR | 2025-12-08 | Historical | 2026_ET-01495_ACQ | QC Accepted | 2026_ET-01495_FR | 2026-03-02 | Submitted | 2026_ET-01495_RWR | Submitted | 2026-03-02 | 2026_ET-01495_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01495_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01495_WR | 2026-04-16 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01495_VMLAZ | 2026-04-16 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01495_VMM1 | 2026-04-16 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01495_RR | 2026-04-16 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01495_VER | 2026-04-16 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | HARBORGEN-HINSON_ET-01495 |  |  | Yes | 15:38 |  | LONG BEACH | 46 | UNK | 2026-01-09 14:22 PST ¦ 2026-01-10 11:40 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHARMIN-PROCGEN | ET-01531 | 2026_ET-01531 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.047657 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-07 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01531_ACQPKG | 2026_ET-01531_GSPKG | Submitted | 2026_ET-01531_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01531_GCPR | 2025-12-08 | Historical | 2026_ET-01531_ACQ | QC Accepted | 2026_ET-01531_FR | 2026-03-02 | Submitted | 2026_ET-01531_RWR | Submitted | 2026-03-02 | 2026_ET-01531_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01531_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01531_WR | 2026-04-15 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01531_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01531_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01531_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01531_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | CHARMIN-PROCGEN_ET-01531 |  |  | No | 17:07 |  | VENTURA | 39 | UNK | 2026-01-07 09:19 PST ¦ 2026-01-07 09:24 PST | 010726 | 20260107 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
FURNACE-GALVANIZING | ET-01598 | 2026_ET-01598 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.29229 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-12-19 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01598_ACQPKG | 2026_ET-01598_GSPKG | Submitted | 2026_ET-01598_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01598_GCPR | 2025-12-08 | Historical | 2026_ET-01598_ACQ | QC Accepted | 2026_ET-01598_FR | 2026-03-02 | Submitted | 2026_ET-01598_RWR | Submitted | 2026-03-02 | 2026_ET-01598_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01598_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01598_WR | 2026-04-13 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01598_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01598_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01598_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01598_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | FURNACE-GALVANIZING_ET-01598 |  |  | No | 17:27 |  | FOOTHILL | 30 | UNK | 2025-12-19 09:26 PST ¦ 2025-12-19 09:33 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOCK-FUEL-LONG BEACH | ET-01827 | 2026_ET-01827 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.0644 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-10 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01827_ACQPKG | 2026_ET-01827_GSPKG | Submitted | 2026_ET-01827_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01827_GCPR | 2025-12-08 | Historical | 2026_ET-01827_ACQ | QC Accepted | 2026_ET-01827_FR | 2026-03-02 | Submitted | 2026_ET-01827_RWR | Submitted | 2026-03-02 | 2026_ET-01827_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01827_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01827_WR | 2026-04-15 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01827_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01827_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01827_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01827_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DOCK-FUEL-LONG BEACH_ET-01827 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:17 PST ¦ 2026-01-10 12:09 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-DECLEZ-LINDE | ET-01893 | 2026_ET-01893 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 10.1684 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2025-12-19 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01893_ACQPKG | 2026_ET-01893_GSPKG | Submitted | 2026_ET-01893_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01893_GCPR | 2025-12-08 | Historical | 2026_ET-01893_ACQ | QC Accepted | 2026_ET-01893_FR | 2026-03-02 | Submitted | 2026_ET-01893_RWR | Submitted | 2026-03-02 | 2026_ET-01893_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01893_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01893_WR | 2026-04-15 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01893_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01893_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01893_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01893_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ETIWANDA-DECLEZ-LINDE_ET-01893 |  |  | No | 17:57 |  | FOOTHILL | 30 | UNK | 2025-12-19 09:01 PST ¦ 2025-12-19 09:58 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HARBORGEN-LIGHTHIPE | ET-01951 | 2026_ET-01951 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.4795 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-13 | 03-03-2026 | Flown | 2026-01-10 | 03-13-2026 | 03-09-2026 |  | 2026_ET-01951_ACQPKG | 2026_ET-01951_GSPKG | Submitted | 2026_ET-01951_GS | 2026-03-02 | Field Complete | 2026_ET-01951_GCPR | 2026-03-02 | Submitted | 2026_ET-01951_ACQ | QC Accepted | 2026_ET-01951_FR | 2026-03-02 | Submitted | 2026_ET-01951_RWR | Submitted | 2026-03-02 | 2026_ET-01951_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01951_PROCPKG | In Progress | All Good - Complete | 2026_ET-01951_WR | 2026-04-16 | 04-12-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01951_VMLAZ | 2026-04-16 | QC Accepted |  | 2026-05-18 |  | 2026_ET-01951_VMM1 | 2026-04-16 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-01951_RR | 2026-04-16 | No Violations |  |  | 0 |  |  |  | 2026_ET-01951_VER | 2026-04-16 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HARBORGEN-LIGHTHIPE_ET-01951 |  |  | Yes | 18:13 & 17:50 |  | LONG BEACH | 46 | UNK | 2025-12-16 13:49 PST ¦ 2026-01-10 11:41 PST | 011026 | 20260110 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANAVERDE-RITTER RANCH | ET-00666 | 2026_ET-00666 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.4914 | 5.4914 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-14 | 03-03-2026 | Flown | 2025-12-20 | 03-14-2026 | 02-17-2026 |  | 2026_ET-00666_ACQPKG | 2026_ET-00666_GSPKG | Submitted | 2026_ET-00666_GS | 2025-10-17 | Field Complete | 2026_ET-00666_GCPR | 2025-12-08 | Submitted | 2026_ET-00666_ACQ | QC Accepted | 2026_ET-00666_FR | 2026-01-13 | Submitted | 2026_ET-00666_RWR | Submitted | 2026-01-13 | 2026_ET-00666_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-17 |  | 2026_ET-00666_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00666_WR | 2026-04-13 | 04-13-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00666_VMLAZ | 2026-04-13 | QC Accepted | 05-27-2026 | 2026-04-17 | 0 | 2026_ET-00666_VMM1 | 2026-05-13 | QC Accepted |  | 05-27-2026 | 2026-05-20 | 1 | 2026_ET-00666_RR | 2026-04-13 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-00666_VER | 2026-04-13 | Uploaded to S123 | 05-27-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ANAVERDE-RITTER RANCH_ET-00666 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-20 08:22 PST ¦ 2025-12-20 08:33 PST | 122025 | 20251220 | [5 empty] | Missing subject conductors. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-LAGUNA BELL-NARROWS | ET-01559 | 2026_ET-01559 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 9.6125 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-14 | 03-03-2026 | Flown | 2025-12-20 | 03-14-2026 | 02-13-2026 |  | 2026_ET-01559_ACQPKG | 2026_ET-01559_GSPKG | Submitted | 2026_ET-01559_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01559_GCPR | 2025-12-08 | Historical | 2026_ET-01559_ACQ | QC Accepted | 2026_ET-01559_FR | 2026-01-13 | Submitted | 2026_ET-01559_RWR | Submitted | 2026-01-13 | 2026_ET-01559_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-13 |  | 2026_ET-01559_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01559_WR | 2026-04-15 | 04-13-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-01559_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-01559_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-01559_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-01559_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | MESA-LAGUNA BELL-NARROWS_ET-01559 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2025-12-20 10:33 PST ¦ 2025-12-20 10:59 PST | 122025 | 20251220 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARBOGEN-HANJIN-LONG BEACH | ET-01735 | 2026_ET-01735 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.3238 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-14 | 03-03-2026 | Flown | 2026-01-10 | 03-14-2026 | 03-09-2026 |  | 2026_ET-01735_ACQPKG | 2026_ET-01735_GSPKG | Submitted | 2026_ET-01735_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01735_GCPR | 2025-12-08 | Historical | 2026_ET-01735_ACQ | QC Accepted | 2026_ET-01735_FR | 2026-03-02 | Submitted | 2026_ET-01735_RWR | Submitted | 2026-03-02 | 2026_ET-01735_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01735_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01735_WR | 2026-04-15 | 04-13-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01735_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01735_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01735_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01735_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | CARBOGEN-HANJIN-LONG BEACH_ET-01735 | Done |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 10:48 PST ¦ 2026-01-10 12:09 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WINDHUB-KALAMA | ET-00027 | 2026_ET-00027 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.011881 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-12-2026 |  | 2026_ET-00027_ACQPKG | 2026_ET-00027_GSPKG | Submitted | 2026_ET-00027_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00027_GCPR | 2025-12-08 | Historical | 2026_ET-00027_ACQ | QC Accepted | 2026_ET-00027_FR | 2026-01-13 | Submitted | 2026_ET-00027_RWR | Submitted | 2026-01-13 | 2026_ET-00027_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00027_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00027_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00027_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00027_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00027_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00027_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | WINDHUB-KALAMA_ET-00027 |  |  | No |  | Helicopter |  |  | HC | 2025-12-18 15:57 PST ¦ 2025-12-18 16:00 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WINDHUB-SUNSPOT | ET-00031 | 2026_ET-00031 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.017525 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-12-2026 |  | 2026_ET-00031_ACQPKG | 2026_ET-00031_GSPKG | Submitted | 2026_ET-00031_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00031_GCPR | 2025-12-08 | Historical | 2026_ET-00031_ACQ | QC Accepted | 2026_ET-00031_FR | 2026-01-13 | Submitted | 2026_ET-00031_RWR | Submitted | 2026-01-13 | 2026_ET-00031_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00031_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00031_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00031_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00031_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00031_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00031_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | WINDHUB-SUNSPOT_ET-00031 |  |  | No |  | Helicopter |  |  | HC | 2025-12-18 15:57 PST ¦ 2025-12-18 16:00 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LUGO-MOHAVE | ET-00081 | 2026_ET-00081 |  | 1 | 2026 | Jun 01, 2026 | 500 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 174.9913 | 18.8118 | 11 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-18-2026 |  | 2026_ET-00081_ACQPKG | 2026_ET-00081_GSPKG | Submitted | 2026_ET-00081_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00081_GCPR | 2025-12-08 | Historical | 2026_ET-00081_ACQ | QC Accepted | 2026_ET-00081_FR | 2026-01-13 | Submitted | 2026_ET-00081_RWR | Submitted | 2026-01-13 | 2026_ET-00081_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-18 |  | 2026_ET-00081_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00081_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00081_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-00081_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00081_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00081_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LUGO-MOHAVE_ET-00081 |  |  | Yes |  | Helicopter | BARSTOW | 72 | HC | 2025-12-17 11:13 PST ¦ 2025-12-18 13:25 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GREAT LAKES-LANCASTER-ROSAMOND | ET-00157 | 2026_ET-00157 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 18.7236 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-12-2026 |  | 2026_ET-00157_ACQPKG | 2026_ET-00157_GSPKG | Submitted | 2026_ET-00157_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00157_GCPR | 2025-12-08 | Historical | 2026_ET-00157_ACQ | QC Accepted | 2026_ET-00157_FR | 2026-01-13 | Submitted | 2026_ET-00157_RWR | Submitted | 2026-01-13 | 2026_ET-00157_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00157_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00157_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00157_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00157_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00157_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00157_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | GREAT LAKES-LANCASTER-ROSAMOND_ET-00157 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-18 15:18 PST ¦ 2025-12-18 15:43 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-OJAI | ET-00297 | 2026_ET-00297 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 12.6386 | 12.6386 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-06 | 03-15-2026 | 03-06-2026 |  | 2026_ET-00297_ACQPKG | 2026_ET-00297_GSPKG | Submitted | 2026_ET-00297_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00297_GCPR | 2025-12-08 | Historical | 2026_ET-00297_ACQ | QC Accepted | 2026_ET-00297_FR | 2026-03-02 | Submitted | 2026_ET-00297_RWR | Submitted | 2026-03-02 | 2026_ET-00297_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00297_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00297_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00297_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00297_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00297_RR | 2026-04-15 | Violations QC Confirmed | 04-21-2026 | 04-21-2026 | 4 | 2026-04-16 | 0 | 4 | 2026_ET-00297_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-OJAI_ET-00297 |  |  | No | 16:56 - 20:18 |  | VENTURA | 39 | UNK | 2026-01-06 10:14 PST ¦ 2026-01-06 13:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-TAYSHELL | ET-00423 | 2026_ET-00423 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 10.0262 | 10.0262 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-06 | 03-15-2026 | 03-06-2026 |  | 2026_ET-00423_ACQPKG | 2026_ET-00423_GSPKG | Submitted | 2026_ET-00423_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00423_GCPR | 2025-12-08 | Historical | 2026_ET-00423_ACQ | QC Accepted | 2026_ET-00423_FR | 2026-03-02 | Submitted | 2026_ET-00423_RWR | Submitted | 2026-03-02 | 2026_ET-00423_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00423_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00423_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00423_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00423_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00423_RR | 2026-04-15 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00423_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-TAYSHELL_ET-00423 |  |  | No | 21:21 & 16:56 - 20:18 |  | VENTURA | 39 | UNK | 2026-01-05 14:55 PST ¦ 2026-01-06 13:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MARYMOUNT-ROLLING HILLS | ET-00758 | 2026_ET-00758 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 6.5269 | 5.7462 | 88 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-11 | 03-15-2026 | 03-10-2026 |  | 2026_ET-00758_ACQPKG | 2026_ET-00758_GSPKG | Submitted | 2026_ET-00758_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00758_GCPR | 2025-12-08 | Historical | 2026_ET-00758_ACQ | QC Accepted | 2026_ET-00758_FR | 2026-03-02 | Submitted | 2026_ET-00758_RWR | Submitted | 2026-03-02 | 2026_ET-00758_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00758_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00758_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00758_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00758_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00758_RR | 2026-04-15 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00758_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MARYMOUNT-ROLLING HILLS_ET-00758 |  |  | No | 15:16 |  | SOUTH BAY | 44 | UNK | 2026-01-11 08:29 PST ¦ 2026-01-11 09:12 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ROSE MEADOW-WHIRLWIND | ET-00840 | 2026_ET-00840 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.30797 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-12-2026 |  | 2026_ET-00840_ACQPKG | 2026_ET-00840_GSPKG | Submitted | 2026_ET-00840_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00840_GCPR | 2025-12-08 | Historical | 2026_ET-00840_ACQ | QC Accepted | 2026_ET-00840_FR | 2026-01-13 | Submitted | 2026_ET-00840_RWR | Submitted | 2026-01-13 | 2026_ET-00840_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00840_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00840_WR | 2026-04-16 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00840_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00840_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00840_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00840_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ROSE MEADOW-WHIRLWIND_ET-00840 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-18 16:10 PST ¦ 2025-12-18 16:21 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PADUA-LAYFAIR | ET-00860 | 2026_ET-00860 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 13.4513 | 5.9118 | 44 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 03-09-2026 |  | 2026_ET-00860_ACQPKG | 2026_ET-00860_GSPKG | Submitted | 2026_ET-00860_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00860_GCPR | 2025-12-08 | Historical | 2026_ET-00860_ACQ | QC Accepted | 2026_ET-00860_FR | 2026-03-02 | Submitted | 2026_ET-00860_RWR | Submitted | 2026-03-02 | 2026_ET-00860_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00860_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00860_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00860_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00860_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00860_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 2 | 2026-05-11 |  | 0 | 2026_ET-00860_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | PADUA-LAYFAIR_ET-00860 |  |  | No | 18:17 & 16:35 |  | COVINA | 26 | UNK | 2025-12-15 10:56 PST ¦ 2025-12-18 10:20 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
STEVEDORE-WHARF | ET-00866 | 2026_ET-00866 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.13076 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-10 | 03-15-2026 | 03-09-2026 |  | 2026_ET-00866_ACQPKG | 2026_ET-00866_GSPKG | Submitted | 2026_ET-00866_GS | 2026-03-02 | Field Complete | 2026_ET-00866_GCPR | 2026-03-02 | Submitted | 2026_ET-00866_ACQ | QC Accepted | 2026_ET-00866_FR | 2026-03-02 | Submitted | 2026_ET-00866_RWR | Submitted | 2026-03-02 | 2026_ET-00866_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00866_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00866_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-00866_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00866_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00866_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-00866_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | STEVEDORE-WHARF_ET-00866 |  |  | No | 17:50 | Helicopter | LONG BEACH | 46 | HC | 2026-01-10 11:25 PST ¦ 2026-01-10 11:29 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA VETA-WASHINGTON | ET-00909 | 2026_ET-00909 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.6992 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-21 | 03-15-2026 | 03-09-2026 |  | 2026_ET-00909_ACQPKG | 2026_ET-00909_GSPKG | Submitted | 2026_ET-00909_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00909_GCPR | 2025-12-08 | Historical | 2026_ET-00909_ACQ | QC Accepted | 2026_ET-00909_FR | 2026-03-02 | Submitted | 2026_ET-00909_RWR | Submitted | 2026-03-02 | 2026_ET-00909_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00909_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00909_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00909_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00909_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00909_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-00909_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LA VETA-WASHINGTON_ET-00909 |  |  | No | 20:33 |  | SANTA ANA | 29 | UNK | 2025-12-21 12:18 PST ¦ 2025-12-21 12:40 PST | 122125 | 20251221 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SUNCREEK-WINDHUB | ET-00910 | 2026_ET-00910 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.36397 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-18 | 03-15-2026 | 02-17-2026 |  | 2026_ET-00910_ACQPKG | 2026_ET-00910_GSPKG | Submitted | 2026_ET-00910_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00910_GCPR | 2025-12-08 | Historical | 2026_ET-00910_ACQ | QC Accepted | 2026_ET-00910_FR | 2026-01-13 | Submitted | 2026_ET-00910_RWR | Submitted | 2026-01-13 | 2026_ET-00910_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-17 |  | 2026_ET-00910_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00910_WR | 2026-04-16 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00910_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00910_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00910_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00910_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SUNCREEK-WINDHUB_ET-00910 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-18 15:55 PST ¦ 2025-12-18 15:56 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LONG BEACH-SEABRIGHT | ET-00995 | 2026_ET-00995 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.9115 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-10 | 03-15-2026 | 03-09-2026 |  | 2026_ET-00995_ACQPKG | 2026_ET-00995_GSPKG | Submitted | 2026_ET-00995_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00995_GCPR | 2025-12-08 | Historical | 2026_ET-00995_ACQ | QC Accepted | 2026_ET-00995_FR | 2026-03-02 | Submitted | 2026_ET-00995_RWR | Submitted | 2026-03-02 | 2026_ET-00995_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00995_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00995_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00995_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00995_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00995_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-00995_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LONG BEACH-SEABRIGHT_ET-00995 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 10:49 PST ¦ 2026-01-10 12:09 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-LONG BEACH | ET-01004 | 2026_ET-01004 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.7896 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-10 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01004_ACQPKG | 2026_ET-01004_GSPKG | Submitted | 2026_ET-01004_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01004_GCPR | 2025-12-08 | Historical | 2026_ET-01004_ACQ | QC Accepted | 2026_ET-01004_FR | 2026-03-02 | Submitted | 2026_ET-01004_RWR | Submitted | 2026-03-02 | 2026_ET-01004_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01004_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01004_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01004_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01004_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01004_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01004_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HINSON-LONG BEACH_ET-01004 |  |  | No | 21:40 & 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 10:49 PST ¦ 2026-01-10 12:09 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GONZALES-MANDALAY-MCGRATH | ET-01039 | 2026_ET-01039 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.3735 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-06 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01039_ACQPKG | 2026_ET-01039_GSPKG | Submitted | 2026_ET-01039_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01039_GCPR | 2025-12-08 | Historical | 2026_ET-01039_ACQ | QC Accepted | 2026_ET-01039_FR | 2026-03-02 | Submitted | 2026_ET-01039_RWR | Submitted | 2026-03-02 | 2026_ET-01039_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01039_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01039_WR | 2026-04-13 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01039_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01039_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01039_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 1 | 2026-05-11 |  | 0 | 2026_ET-01039_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | GONZALES-MANDALAY-MCGRATH_ET-01039 |  |  | No | 20:18 |  | VENTURA | 39 | UNK | 2026-01-06 14:04 PST ¦ 2026-01-06 14:46 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PADUA-MWD-SAN DIMAS | ET-01236 | 2026_ET-01236 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 13.6903 | 6.0974 | 45 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 01-31-2026 | Flown |  | 03-15-2026 | 02-13-2026 |  | 2026_ET-01236_ACQPKG | 2026_ET-01236_GSPKG | Submitted | 2026_ET-01236_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01236_GCPR | 2025-12-08 | Historical | 2026_ET-01236_ACQ | QC Accepted | 2026_ET-01236_FR | 2026-01-31 | Submitted | 2026_ET-01236_RWR | Submitted | 2026-01-31 | 2026_ET-01236_CLAZ | 2026-01-31 | QC Accepted | 02-15-2026 | 2026-02-13 | 0 | 2026_ET-01236_PROCPKG | Submitted | All Good - Complete | 2026_ET-01236_WR | 2026-03-12 | 04-14-2026 | QC Accepted | 04-01-2026 | 2026-03-25 | 0 | 2026_ET-01236_VMLAZ | 2026-03-12 | QC Accepted | 04-07-2026 | 2026-03-25 | 0 | 2026_ET-01236_VMM1 | 2026-03-24 | QC Accepted |  | 04-07-2026 | 2026-03-25 | 0 | 2026_ET-01236_RR | 2026-03-22 | Violations Detected | 03-26-2026 | 03-26-2026 | 2 | 2026-03-11 | 2 | 0 | 2026_ET-01236_VER | 2026-03-24 | Uploaded to S123 | 04-07-2026 | 2026-03-25 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | PADUA-MWD SAN DIMAS_ET-01236 |  |  | No |  |  |  |  | UNK | 2025-12-15 10:43 PST ¦ 2025-12-18 10:22 PST | 121525 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-OAK PARK | ET-01339 | 2026_ET-01339 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 12.765 | 12.765 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-08 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01339_ACQPKG | 2026_ET-01339_GSPKG | Submitted | 2026_ET-01339_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01339_GCPR | 2025-12-08 | Historical | 2026_ET-01339_ACQ | QC Accepted | 2026_ET-01339_FR | 2026-03-02 | Submitted | 2026_ET-01339_RWR | Submitted | 2026-03-02 | 2026_ET-01339_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01339_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01339_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01339_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01339_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01339_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01339_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-OAK PARK_ET-01339 |  |  | No | 21:02 & 17:13 - 20:41 |  | THOUSAND OAKS | 35 | UNK | 2026-01-07 13:40 PST ¦ 2026-01-08 13:36 PST | 010826 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-BRYAN | ET-01510 | 2026_ET-01510 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 9.6671 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-21 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01510_ACQPKG | 2026_ET-01510_GSPKG | Submitted | 2026_ET-01510_GS | 2026-03-02 | Field Complete | 2026_ET-01510_GCPR | 2026-03-02 | Submitted | 2026_ET-01510_ACQ | QC Accepted | 2026_ET-01510_FR | 2026-03-02 | Submitted | 2026_ET-01510_RWR | Submitted | 2026-03-02 | 2026_ET-01510_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01510_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01510_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01510_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01510_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01510_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01510_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | VILLA PARK-BRYAN_ET-01510 |  |  | No | 18:23 & 19:49 |  | SANTA ANA | 29 | UNK | 2025-12-21 12:12 PST ¦ 2026-01-14 06:50 PST | 011426 | 20260114 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-HASKELL | ET-01571 | 2026_ET-01571 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.9793 | 2.9793 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-28 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01571_ACQPKG | 2026_ET-01571_GSPKG | Submitted | 2026_ET-01571_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01571_GCPR | 2025-12-08 | Historical | 2026_ET-01571_ACQ | QC Accepted | 2026_ET-01571_FR | 2026-03-02 | Submitted | 2026_ET-01571_RWR | Submitted | 2026-03-02 | 2026_ET-01571_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01571_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01571_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01571_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01571_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01571_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01571_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-HASKELL_ET-01571 |  |  | No | 17:54 & 17:03 |  | VALENCIA | 59 | UNK | 2025-12-27 11:47 PST ¦ 2026-01-08 09:59 PST | 010826 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-COLONIA-PROCGEN | ET-01572 | 2026_ET-01572 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 15.7779 | 1.5238 | 10 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-07 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01572_ACQPKG | 2026_ET-01572_GSPKG | Submitted | 2026_ET-01572_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01572_GCPR | 2025-12-08 | Historical | 2026_ET-01572_ACQ | QC Accepted | 2026_ET-01572_FR | 2026-03-02 | Submitted | 2026_ET-01572_RWR | Submitted | 2026-03-02 | 2026_ET-01572_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01572_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01572_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01572_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01572_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01572_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 9 | 2026-05-11 |  | 0 | 2026_ET-01572_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program |  |  |  | No | 20:18 & 17:07 |  | VENTURA | 39 | UNK | 2026-01-06 13:08 PST ¦ 2026-01-07 09:41 PST | 010726 | 20260107 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-CUDAHY-SHULTZ | ET-01662 | 2026_ET-01662 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.3169 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-10 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01662_ACQPKG | 2026_ET-01662_GSPKG | Submitted | 2026_ET-01662_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01662_GCPR | 2025-12-08 | Historical | 2026_ET-01662_ACQ | QC Accepted | 2026_ET-01662_FR | 2026-03-02 | Submitted | 2026_ET-01662_RWR | Submitted | 2026-03-02 | 2026_ET-01662_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01662_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01662_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01662_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01662_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01662_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01662_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-CUDAHY-SHULTZ_ET-01662 |  |  | No | 17:50 |  | DOMINGUEZ HILLS | 32 | UNK | 2026-01-10 10:19 PST ¦ 2026-01-10 10:39 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
FULLERTON-GILBERT-SUNNYHILLS | ET-01707 | 2026_ET-01707 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.7536 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-21 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01707_ACQPKG | 2026_ET-01707_GSPKG | Submitted | 2026_ET-01707_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01707_GCPR | 2025-12-08 | Historical | 2026_ET-01707_ACQ | QC Accepted | 2026_ET-01707_FR | 2026-03-02 | Submitted | 2026_ET-01707_RWR | Submitted | 2026-03-02 | 2026_ET-01707_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01707_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01707_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01707_VMLAZ | 2026-04-07 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01707_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01707_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01707_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | FULLERTON-GILBERT-SUNNYHILLS_ET-01707 |  |  | No | 20:53 |  | FULLERTON | 48 | UNK | 2025-12-21 12:48 PST ¦ 2025-12-21 13:03 PST | 122125 | 20251221 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-LIGHTHIPE-POLYPRO | ET-01752 | 2026_ET-01752 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 6.9874 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-09 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01752_ACQPKG | 2026_ET-01752_GSPKG | Submitted | 2026_ET-01752_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01752_GCPR | 2025-12-08 | Historical | 2026_ET-01752_ACQ | QC Accepted | 2026_ET-01752_FR | 2026-03-02 | Submitted | 2026_ET-01752_RWR | Submitted | 2026-03-02 | 2026_ET-01752_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01752_PROCPKG | In Progress | All Good - Complete | 2026_ET-01752_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01752_VMLAZ | 2026-04-15 | QC Accepted |  | 2026-05-18 |  | 2026_ET-01752_VMM1 | 2026-04-15 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-01752_RR | 2026-04-15 | No Violations |  |  | 5 | 2026-05-11 |  | 0 | 2026_ET-01752_VER | 2026-04-15 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HINSON-LIGHTHIPE-POLYPRO_ET-01752 |  |  | No | 18:13 - 21:40 |  | LONG BEACH | 46 | UNK | 2025-12-16 13:48 PST ¦ 2026-01-09 14:47 PST | 010926 | 20260109 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HATHAWAY-INJECTION | ET-01824 | 2026_ET-01824 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.2319 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-11 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01824_ACQPKG | 2026_ET-01824_GSPKG | Submitted | 2026_ET-01824_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01824_GCPR | 2025-12-08 | Historical | 2026_ET-01824_ACQ | QC Accepted | 2026_ET-01824_FR | 2026-03-02 | Submitted | 2026_ET-01824_RWR | Submitted | 2026-03-02 | 2026_ET-01824_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01824_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01824_WR | 2026-04-13 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01824_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01824_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01824_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01824_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HATHAWAY-INJECTION_ET-01824 |  |  | No | 15:16 |  | LONG BEACH | 46 | UNK | 2026-01-11 07:38 PST ¦ 2026-01-11 08:11 PST | 011126 | 20260111 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HAAGEN-PROTEIN-TULARE | ET-01838 | 2026_ET-01838 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_4 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 4.3326 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-19 | 03-15-2026 | 02-26-2026 |  | 2026_ET-01838_ACQPKG | 2026_ET-01838_GSPKG | Submitted | 2026_ET-01838_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01838_GCPR | 2025-12-08 | Historical | 2026_ET-01838_ACQ | QC Accepted | 2026_ET-01838_FR | 2026-01-13 | Submitted | 2026_ET-01838_RWR | Submitted | 2026-01-13 | 2026_ET-01838_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-26 |  | 2026_ET-01838_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01838_WR | 2026-03-25 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-01 |  | 2026_ET-01838_VMLAZ | 2026-03-25 | QC Accepted | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01838_VMM1 | 2026-03-25 | QC Accepted |  | 05-02-2026 | 2026-03-27 | 0 | 2026_ET-01838_RR | 2026-03-25 | No Violations | 03-28-2026 |  | 0 |  |  |  | 2026_ET-01838_VER | 2026-03-25 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | HAAGEN-PROTEIN-TULARE_ET-01838 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-19 11:50 PST ¦ 2025-12-19 12:03 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PICO-THUMSGEN | ET-01861 | 2026_ET-01861 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.86944 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-10 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01861_ACQPKG | 2026_ET-01861_GSPKG | Submitted | 2026_ET-01861_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01861_GCPR | 2025-12-08 | Historical | 2026_ET-01861_ACQ | QC Accepted | 2026_ET-01861_FR | 2026-03-02 | Submitted | 2026_ET-01861_RWR | Submitted | 2026-03-02 | 2026_ET-01861_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01861_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01861_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01861_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01861_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01861_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01861_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | PICO-THUMSGEN_ET-01861 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:10 PST ¦ 2026-01-10 11:20 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-CASITAS | ET-01862 | 2026_ET-01862 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 11.5882 | 11.5882 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-06 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01862_ACQPKG | 2026_ET-01862_GSPKG | Submitted | 2026_ET-01862_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01862_GCPR | 2025-12-08 | Historical | 2026_ET-01862_ACQ | QC Accepted | 2026_ET-01862_FR | 2026-03-02 | Submitted | 2026_ET-01862_RWR | Submitted | 2026-03-02 | 2026_ET-01862_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01862_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01862_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01862_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01862_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01862_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01862_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-CASITAS_ET-01862 |  |  | No | 21:21 & 16:56 - 20:18 |  | VENTURA | 39 | UNK | 2025-12-28 14:50 PST ¦ 2026-01-06 13:31 PST | 010626 | 20260106 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LINDE-WIMBLEDON | ET-01869 | 2026_ET-01869 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.4158 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-19 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01869_ACQPKG | 2026_ET-01869_GSPKG | Submitted | 2026_ET-01869_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01869_GCPR | 2025-12-08 | Historical | 2026_ET-01869_ACQ | QC Accepted | 2026_ET-01869_FR | 2026-03-02 | Submitted | 2026_ET-01869_RWR | Submitted | 2026-03-02 | 2026_ET-01869_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01869_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01869_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01869_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01869_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01869_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01869_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LINDE-WIMBLEDON_ET-01869 |  |  | No | 17:48 |  | FOOTHILL | 30 | UNK | 2025-12-19 09:38 PST ¦ 2025-12-19 10:22 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HOLLYWOOD PARK-LENNOX | ET-01999 | 2026_ET-01999 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.22777 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-13 | 03-15-2026 | 03-09-2026 |  | 2026_ET-01999_ACQPKG | 2026_ET-01999_GSPKG | Submitted | 2026_ET-01999_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01999_GCPR | 2025-12-08 | Historical | 2026_ET-01999_ACQ | QC Accepted | 2026_ET-01999_FR | 2026-03-02 | Submitted | 2026_ET-01999_RWR | Submitted | 2026-03-02 | 2026_ET-01999_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01999_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01999_WR | 2026-04-13 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01999_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01999_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01999_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01999_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HOLLYWOOD PARK-LENNOX_ET-01999 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 04:57 PST ¦ 2026-01-13 05:00 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HOLLYWOOD PARK-INGLEWOOD | ET-02000 | 2026_ET-02000 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.1415 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-13 | 03-15-2026 | 03-09-2026 |  | 2026_ET-02000_ACQPKG | 2026_ET-02000_GSPKG | Submitted | 2026_ET-02000_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02000_GCPR | 2025-12-08 | Historical | 2026_ET-02000_ACQ | QC Accepted | 2026_ET-02000_FR | 2026-03-02 | Submitted | 2026_ET-02000_RWR | Submitted | 2026-03-02 | 2026_ET-02000_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02000_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02000_WR | 2026-04-13 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-02000_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-02000_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-02000_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-02000_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HOLLYWOOD PARK-INGLEWOOD_ET-02000 |  |  | No | 3:00 - 10:00 |  | SOUTH BAY | 44 | UNK | 2026-01-13 04:33 PST ¦ 2026-01-13 08:58 PST | 011326 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-CATHODE NO.2 | ET-02133 | 2026_ET-02133 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.20999 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-09 | 03-15-2026 | 03-09-2026 |  | 2026_ET-02133_ACQPKG | 2026_ET-02133_GSPKG | Submitted | 2026_ET-02133_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02133_GCPR | 2025-12-08 | Historical | 2026_ET-02133_ACQ | QC Accepted | 2026_ET-02133_FR | 2026-03-02 | Submitted | 2026_ET-02133_RWR | Submitted | 2026-03-02 | 2026_ET-02133_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02133_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02133_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-02133_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-02133_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-02133_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-02133_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | HINSON-CATHODE NO.2_ET-02133 |  |  | No | 21:40 |  | LONG BEACH | 46 | UNK | 2026-01-09 12:35 PST ¦ 2026-01-09 14:45 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-VICTORIA NO. 2 | ET-04309 | 2026_ET-04309 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.1198 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-11 | 03-15-2026 | 03-09-2026 |  | 2026_ET-04309_ACQPKG | 2026_ET-04309_GSPKG | Submitted | 2026_ET-04309_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04309_GCPR | 2025-12-08 | Historical | 2026_ET-04309_ACQ | QC Accepted | 2026_ET-04309_FR | 2026-03-02 | Submitted | 2026_ET-04309_RWR | Submitted | 2026-03-02 | 2026_ET-04309_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-04309_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04309_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-04309_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-04309_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-04309_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 3 | 2026-05-11 |  | 0 | 2026_ET-04309_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LA FRESA-VICTORIA NO. 2_ET-04309 |  |  | No | 15:16 |  | SOUTH BAY | 44 | UNK | 2026-01-11 09:34 PST ¦ 2026-01-13 07:51 PST | 011126 | 20260113 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ROYAL NO. 1 | ET-04985 | 2026_ET-04985 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.6484 | 8.6484 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-07 | 03-15-2026 | 03-09-2026 |  | 2026_ET-04985_ACQPKG | 2026_ET-04985_GSPKG | Submitted | 2026_ET-04985_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04985_GCPR | 2025-12-08 | Historical | 2026_ET-04985_ACQ | QC Accepted | 2026_ET-04985_FR | 2026-03-02 | Submitted | 2026_ET-04985_RWR | Submitted | 2026-03-02 | 2026_ET-04985_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-04985_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04985_WR | 2026-04-15 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-04985_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-04985_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-04985_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-04985_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-ROYAL NO. 1_ET-04985 |  |  | No | 21:02 |  | THOUSAND OAKS | 35 | UNK | 2026-01-07 13:36 PST ¦ 2026-01-08 11:21 PST | 010726 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-OAKGROVE | ET-06601 | 2026_ET-06601 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_4 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 9.2577 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-19 | 03-15-2026 | 02-20-2026 |  | 2026_ET-06601_ACQPKG | 2026_ET-06601_GSPKG | Submitted | 2026_ET-06601_GS | 2025-10-15 | Field Complete | 2026_ET-06601_GCPR | 2025-12-08 | Submitted | 2026_ET-06601_ACQ | QC Accepted | 2026_ET-06601_FR | 2026-01-13 | Submitted | 2026_ET-06601_RWR | Submitted | 2026-01-13 | 2026_ET-06601_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-20 |  | 2026_ET-06601_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-06601_WR | 2026-03-25 | 04-14-2026 | QC Accepted | 05-02-2026 | 2026-04-01 |  | 2026_ET-06601_VMLAZ | 2026-03-25 | QC Accepted | 05-27-2026 | 2026-03-27 | 0 | 2026_ET-06601_VMM1 | 2026-05-13 | QC Accepted |  | 05-27-2026 | 2026-05-20 | 1 | 2026_ET-06601_RR | 2026-03-25 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-06601_VER | 2026-03-25 | Uploaded to S123 | 05-27-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | RECTOR-OAKGROVE_ET-06601 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-19 12:09 PST ¦ 2025-12-19 12:26 PST | 121925 | 20251219 | [5 empty] | Missing subject conductors. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PIER-PROCESS | ET-00049 | 2026_ET-00049 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.95 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-10 | 03-17-2026 | 03-06-2026 |  | 2026_ET-00049_ACQPKG | 2026_ET-00049_GSPKG | Submitted | 2026_ET-00049_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00049_GCPR | 2025-12-08 | Historical | 2026_ET-00049_ACQ | QC Accepted | 2026_ET-00049_FR | 2026-03-02 | Submitted | 2026_ET-00049_RWR | Submitted | 2026-03-02 | 2026_ET-00049_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00049_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00049_WR | 2026-04-15 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00049_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00049_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00049_RR | 2026-04-15 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00049_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | PIER-PROCESS_ET-00049 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:20 PST ¦ 2026-01-10 11:33 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PROCESS-WHARF | ET-00050 | 2026_ET-00050 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.36777 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-10 | 03-17-2026 | 03-06-2026 |  | 2026_ET-00050_ACQPKG | 2026_ET-00050_GSPKG | Submitted | 2026_ET-00050_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00050_GCPR | 2025-12-08 | Historical | 2026_ET-00050_ACQ | QC Accepted | 2026_ET-00050_FR | 2026-03-02 | Submitted | 2026_ET-00050_RWR | Submitted | 2026-03-02 | 2026_ET-00050_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00050_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00050_WR | 2026-04-15 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00050_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00050_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00050_RR | 2026-04-15 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00050_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | PROCESS-WHARF_ET-00050 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:25 PST ¦ 2026-01-10 11:32 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SERRANO-VALLEY | ET-00132 | 2026_ET-00132 |  | 1 | 2026 | Jun 01, 2026 | 500 | CA_6 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 40.1885 | 36.9049 | 92 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2025-12-19 | 03-17-2026 | 03-17-2026 |  | 2026_ET-00132_ACQPKG | 2026_ET-00132_GSPKG | Submitted | 2026_ET-00132_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00132_GCPR | 2025-12-08 | Historical | 2026_ET-00132_ACQ | QC Accepted | 2026_ET-00132_FR | 2026-03-02 | Submitted | 2026_ET-00132_RWR | Submitted | 2026-03-02 | 2026_ET-00132_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-17 | 0 | 2026_ET-00132_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00132_WR | 2026-04-15 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00132_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00132_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-20 | 0 | 2026_ET-00132_RR | 2026-04-15 | Violations QC Confirmed | 04-21-2026 | 04-21-2026 | 3 | 2026-04-16 | 1 | 2 | 2026_ET-00132_VER | 2026-04-17 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | SERRANO-VALLEY_ET-00132 |  |  | Yes | 21:06 |  | MENIFEE | 77 | UNK | 2025-12-10 10:37 PST ¦ 2025-12-19 14:33 PST | 121925 | 20251219 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RISING TREE-WINDHUB | ET-00399 | 2026_ET-00399 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.17013 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2025-12-18 | 03-17-2026 | 02-17-2026 |  | 2026_ET-00399_ACQPKG | 2026_ET-00399_GSPKG | Submitted | 2026_ET-00399_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00399_GCPR | 2025-12-08 | Historical | 2026_ET-00399_ACQ | QC Accepted | 2026_ET-00399_FR | 2026-01-13 | Submitted | 2026_ET-00399_RWR | Submitted | 2026-01-13 | 2026_ET-00399_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-17 |  | 2026_ET-00399_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00399_WR | 2026-04-16 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00399_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00399_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00399_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00399_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | RISING TREE-WINDHUB_ET-00399 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-18 15:55 PST ¦ 2025-12-18 15:56 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-OJAI-SANTA BARBARA | ET-00436 | 2026_ET-00436 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 50.8014 | 49.9695 | 98 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-06 | 03-17-2026 | 03-10-2026 |  | 2026_ET-00436_ACQPKG | 2026_ET-00436_GSPKG | Submitted | 2026_ET-00436_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00436_GCPR | 2025-12-08 | Historical | 2026_ET-00436_ACQ | QC Accepted | 2026_ET-00436_FR | 2026-03-02 | Submitted | 2026_ET-00436_RWR | Submitted | 2026-03-02 | 2026_ET-00436_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00436_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00436_WR | 2026-04-15 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-05-02 | 0 | 2026_ET-00436_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-05-02 | 0 | 2026_ET-00436_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-05-02 | 1 | 2026_ET-00436_RR | 2026-04-16 | Violations QC Confirmed | 05-03-2026 | 05-03-2026 | 10 | 2026-04-17 | 0 | 10 | 2026_ET-00436_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-05-02 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTA CLARA-OJAI-SANTA BARBARA_ET-00436 |  |  | No | 21:03 & 18:31 - 21:21 & 16:56 - 20:18 |  | VENTURA | 39 | UNK | 2025-12-28 11:03 PST ¦ 2026-02-02 12:17 PST | 010626 | 20260202 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ORMOND BEACH NO. 2 | ET-00653 | 2026_ET-00653 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 21.9496 | 12.5846 | 57 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-07 | 03-17-2026 | 03-06-2026 |  | 2026_ET-00653_ACQPKG | 2026_ET-00653_GSPKG | Submitted | 2026_ET-00653_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00653_GCPR | 2025-12-08 | Historical | 2026_ET-00653_ACQ | QC Accepted | 2026_ET-00653_FR | 2026-03-02 | Submitted | 2026_ET-00653_RWR | Submitted | 2026-03-02 | 2026_ET-00653_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00653_PROCPKG | In Progress | All Good - Complete | 2026_ET-00653_WR | 2026-04-17 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-05-02 | 0 | 2026_ET-00653_VMLAZ | 2026-04-17 | QC Accepted |  | 2026-05-02 | 0 | 2026_ET-00653_VMM1 | 2026-04-17 | QC Rejected |  |  | 2026-05-02 | 1 | 2026_ET-00653_RR | 2026-04-17 | No Violations |  |  | 0 |  |  |  | 2026_ET-00653_VER | 2026-04-17 | Uploaded to S123 |  | 2026-05-02 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-ORMOND BEACH NO. 2_ET-00653 |  |  | Yes | 17:07 - 21:02 |  | VENTURA | 39 | UNK | 2026-01-07 11:14 PST ¦ 2026-01-08 10:44 PST | 010726 | 20260108 | [5 empty] | Missing subject conductors., Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ORMOND BEACH NO. 3 | ET-00838 | 2026_ET-00838 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 21.7137 | 12.3286 | 57 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-07 | 03-17-2026 | 03-10-2026 |  | 2026_ET-00838_ACQPKG | 2026_ET-00838_GSPKG | Submitted | 2026_ET-00838_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00838_GCPR | 2025-12-08 | Historical | 2026_ET-00838_ACQ | QC Accepted | 2026_ET-00838_FR | 2026-03-02 | Submitted | 2026_ET-00838_RWR | Submitted | 2026-03-02 | 2026_ET-00838_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00838_PROCPKG | In Progress | All Good - Complete | 2026_ET-00838_WR | 2026-04-17 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-05-02 | 0 | 2026_ET-00838_VMLAZ | 2026-04-17 | QC Accepted |  | 2026-05-02 | 0 | 2026_ET-00838_VMM1 | 2026-04-17 | QC Rejected |  |  | 2026-05-02 | 1 | 2026_ET-00838_RR | 2026-04-17 | No Violations |  |  | 0 |  |  |  | 2026_ET-00838_VER | 2026-04-17 | Uploaded to S123 |  | 2026-05-02 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-ORMOND BEACH NO. 3_ET-00838 |  |  | Yes | 17:07 - 21:02 |  | VENTURA | 39 | UNK | 2026-01-07 11:14 PST ¦ 2026-01-08 10:44 PST | 010726 | 20260108 | [5 empty] | Missing subject conductors., Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ORMOND BEACH NO. 4 | ET-00839 | 2026_ET-00839 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 21.9973 | 12.609 | 57 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-17 | 03-03-2026 | Flown | 2026-01-07 | 03-17-2026 | 03-09-2026 |  | 2026_ET-00839_ACQPKG | 2026_ET-00839_GSPKG | Submitted | 2026_ET-00839_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00839_GCPR | 2025-12-08 | Historical | 2026_ET-00839_ACQ | QC Accepted | 2026_ET-00839_FR | 2026-03-02 | Submitted | 2026_ET-00839_RWR | Submitted | 2026-03-02 | 2026_ET-00839_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-00839_PROCPKG | In Progress | All Good - Complete | 2026_ET-00839_WR | 2026-04-17 | 04-16-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00839_VMLAZ | 2026-04-17 | QC Accepted |  | 2026-05-18 |  | 2026_ET-00839_VMM1 | 2026-04-17 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-00839_RR | 2026-04-17 | No Violations |  |  | 0 |  |  |  | 2026_ET-00839_VER | 2026-04-17 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-ORMOND BEACH NO. 4_ET-00839 |  |  | Yes | 17:07 - 21:02 |  | VENTURA | 39 | UNK | 2026-01-07 11:14 PST ¦ 2026-01-08 10:44 PST | 010726 | 20260108 | [5 empty] | Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-HASKELL-LOCKHEED | ET-00073 | 2026_ET-00073 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.3619 | 3.3619 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-18 | 03-03-2026 | Flown | 2025-10-25 | 03-18-2026 | 03-06-2026 |  | 2026_ET-00073_ACQPKG | 2026_ET-00073_GSPKG | Submitted | 2026_ET-00073_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00073_GCPR | 2025-12-08 | Historical | 2026_ET-00073_ACQ | QC Accepted | 2026_ET-00073_FR | 2026-03-02 | Submitted | 2026_ET-00073_RWR | Submitted | 2026-03-02 | 2026_ET-00073_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00073_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00073_WR | 2026-04-15 | 04-17-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00073_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00073_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00073_RR | 2026-04-15 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00073_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-HASKELL-LOCKHEED_ET-00073 |  |  | No | 22:16 |  | VALENCIA | 59 | UNK | 2025-12-27 12:22 PST ¦ 2025-12-27 12:30 PST | 122725 | 20251227 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-DOUGLAS-ROSECRANS | ET-00584 | 2026_ET-00584 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 4.2794 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-01 | 01-01-2026 | Flown | 2025-11-05 | 03-19-2026 | 03-19-2026 |  | 2026_ET-00584_ACQPKG | 2026_ET-00584_GSPKG | Submitted | 2026_ET-00584_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00584_GCPR | 2025-12-08 | Historical | 2026_ET-00584_ACQ | QC Accepted | 2026_ET-00584_FR | 2026-01-01 | Submitted | 2026_ET-00584_RWR | Submitted | 2026-01-01 | 2026_ET-00584_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-03-19 | 0 | 2026_ET-00584_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00584_WR | 2026-04-15 | 04-18-2026 | QC Accepted | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-00584_VMLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-00584_VMM1 | 2026-04-15 | QC Accepted |  | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-00584_RR | 2026-04-15 | No Violations | 04-21-2026 |  | 0 |  |  |  | 2026_ET-00584_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-20 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | EL NIDO-DOUGLAS-ROSECRANS_ET-00584 |  |  | No | 18:01 |  | SOUTH BAY | 44 | UNK | 2025-10-18 13:51 PDT ¦ 2025-11-05 12:16 PST | 110525 | 20251105 | [6 empty] | No | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-ORMOND BEACH NO. 1 | ET-00662 | 2026_ET-00662 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 21.9463 | 12.5838 | 57 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-19 | 03-03-2026 | Flown | 2026-01-07 | 03-19-2026 | 03-10-2026 |  | 2026_ET-00662_ACQPKG | 2026_ET-00662_GSPKG | Submitted | 2026_ET-00662_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00662_GCPR | 2025-12-08 | Historical | 2026_ET-00662_ACQ | QC Accepted | 2026_ET-00662_FR | 2026-03-02 | Submitted | 2026_ET-00662_RWR | Submitted | 2026-03-02 | 2026_ET-00662_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-10 | 0 | 2026_ET-00662_PROCPKG | In Progress | All Good - Complete | 2026_ET-00662_WR | 2026-04-17 | 04-18-2026 | QC Accepted | 05-02-2026 | 2026-05-02 | 0 | 2026_ET-00662_VMLAZ | 2026-04-17 | QC Accepted |  | 2026-05-02 | 0 | 2026_ET-00662_VMM1 | 2026-04-17 | QC Rejected |  |  | 2026-05-02 | 1 | 2026_ET-00662_RR | 2026-04-17 | No Violations |  |  | 0 |  |  |  | 2026_ET-00662_VER | 2026-04-17 | Uploaded to S123 |  | 2026-05-02 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MOORPARK-ORMOND BEACH NO. 1_ET-00662 |  |  | Yes | 17:07 - 21:02 |  | VENTURA | 39 | UNK | 2026-01-07 11:13 PST ¦ 2026-01-08 10:44 PST | 010726 | 20260108 | [5 empty] | Missing subject conductors., Subject conductors strung inaccurately. | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PICO-SHIP-TIDELANDS | ET-00700 | 2026_ET-00700 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.48607 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 03-03-2026 | Flown | 2026-01-10 | 03-19-2026 | 03-06-2026 |  | 2026_ET-00700_ACQPKG | 2026_ET-00700_GSPKG | Submitted | 2026_ET-00700_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00700_GCPR | 2025-12-08 | Historical | 2026_ET-00700_ACQ | QC Accepted | 2026_ET-00700_FR | 2026-03-02 | Submitted | 2026_ET-00700_RWR | Submitted | 2026-03-02 | 2026_ET-00700_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-06 | 0 | 2026_ET-00700_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00700_WR | 2026-04-15 | 04-18-2026 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00700_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00700_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-05-01 | 0 | 2026_ET-00700_RR | 2026-04-15 | No Violations | 05-02-2026 |  | 0 |  |  |  | 2026_ET-00700_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-05-01 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | PICO-SHIP-TIDELANDS_ET-00700 |  |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:10 PST ¦ 2026-01-10 11:20 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-IMPERIAL | ET-00871 | 2026_ET-00871 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 3.6373 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-14 | 03-03-2026 | Flown | 2026-03-04 | 03-19-2026 | 03-19-2026 |  | 2026_ET-00871_ACQPKG | 2026_ET-00871_GSPKG | Submitted | 2026_ET-00871_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00871_GCPR | 2025-12-08 | Historical | 2026_ET-00871_ACQ | QC Accepted | 2026_ET-00871_FR | 2026-03-13 | Submitted | 2026_ET-00871_RWR | Submitted | 2026-03-13 | 2026_ET-00871_CLAZ | 2026-03-13 | QC Accepted | 03-27-2026 | 2026-03-19 | 0 | 2026_ET-00871_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00871_WR | 2026-04-15 | 04-18-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-00871_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-00871_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-00871_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-00871_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed Late - Program | CENTER-IMPERIAL_ET-00871 |  |  | No | 21:29 & 21:12 |  | WHITTIER | 47 | UNK | 2025-12-16 13:38 PST ¦ 2026-03-01 13:26 PST | 122125 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-BAIN-PEDLEY | ET-01809 | 2026_ET-01809 |  | 1 | 2026 | Apr 01, 2026 | 66 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 17.6356 | 1.2534 | 7 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_02 | 2026-02-18 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 01-01-2026 | Flown | 2026-03-04 | 03-19-2026 | 03-19-2026 |  | 2026_ET-01809_ACQPKG | 2026_ET-01809_GSPKG | Submitted | 2026_ET-01809_GS | 2025-11-08 | Field Complete | 2026_ET-01809_GCPR | 2026-01-01 | Submitted | 2026_ET-01809_ACQ | QC Accepted | 2026_ET-01809_FR | 2026-01-01 | Submitted | 2026_ET-01809_RWR | Submitted | 2026-01-01 | 2026_ET-01809_CLAZ | 2026-03-13 | QC Accepted | 03-27-2026 | 2026-03-19 | 1 | 2026_ET-01809_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01809_WR | 2026-04-15 | 04-18-2026 | QC Accepted | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-01809_VMLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-01809_VMM1 | 2026-04-15 | QC Accepted |  | 04-29-2026 | 2026-04-20 | 0 | 2026_ET-01809_RR | 2026-04-15 | Violations QC Confirmed | 04-21-2026 | 04-21-2026 | 2 | 2026-04-16 | 0 | 2 | 2026_ET-01809_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-20 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed Late - Program | MIRA LOMA-BAIN-PEDLEY_ET-01809 |  |  | No | 15:52 & 15:48 |  | FOOTHILL | 30 | UNK | 2025-10-16 14:35 PDT ¦ 2026-03-04 08:47 PST | 020926 | 20260304 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-NEWHALL-NORTH OAKS | ET-02075 | 2026_ET-02075 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 13.4678 | 13.4678 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 03-03-2026 | Flown | 2025-12-27 | 03-19-2026 | 03-09-2026 |  | 2026_ET-02075_ACQPKG | 2026_ET-02075_GSPKG | Submitted | 2026_ET-02075_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02075_GCPR | 2025-12-08 | Historical | 2026_ET-02075_ACQ | QC Accepted | 2026_ET-02075_FR | 2026-03-02 | Submitted | 2026_ET-02075_RWR | Submitted | 2026-03-02 | 2026_ET-02075_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-02075_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02075_WR | 2026-04-15 | 04-18-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-02075_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-02075_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-02075_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 4 | 2026-05-11 |  | 0 | 2026_ET-02075_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-NEWHALL-NORTH OAKS_ET-02075 |  |  | No | 17:54 |  | VALENCIA | 59 | UNK | 2025-12-27 10:32 PST ¦ 2026-01-08 09:59 PST | 122725 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAPTIVE-WELLGEN | ET-00136 | 2026_ET-00136 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 1.834 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-19 | 03-20-2026 | 03-20-2026 |  | 2026_ET-00136_ACQPKG | 2026_ET-00136_GSPKG | Submitted | 2026_ET-00136_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00136_GCPR | 2025-12-08 | Historical | 2026_ET-00136_ACQ | QC Accepted | 2026_ET-00136_FR | 2026-01-13 | Submitted | 2026_ET-00136_RWR | Submitted | 2026-01-13 | 2026_ET-00136_CLAZ | 2026-03-18 | QC Accepted | 04-01-2026 | 2026-03-20 | 1 | 2026_ET-00136_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00136_WR | 2026-04-15 | 04-19-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00136_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-00136_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-17 | 0 | 2026_ET-00136_RR | 2026-04-15 | No Violations | 04-18-2026 |  | 0 |  |  |  | 2026_ET-00136_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed Late - Program | CAPTIVE-WELLGEN_ET-00136 | Done |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-19 10:36 PST ¦ 2025-12-19 10:39 PST | 121925 | 20251219 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
POLYPRO-WATSON | ET-01750 | 2026_ET-01750 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 4.2176 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-02-14 | 01-31-2026 | Flown | 2026-02-02 | 03-20-2026 | 03-20-2026 |  | 2026_ET-01750_ACQPKG | 2026_ET-01750_GSPKG | Submitted | 2026_ET-01750_GS |  | Field Complete | 2026_ET-01750_GCPR | 2026-01-31 | Submitted | 2026_ET-01750_ACQ | QC Accepted | 2026_ET-01750_FR | 2026-01-31 | Submitted | 2026_ET-01750_RWR | Submitted | 2026-03-20 | 2026_ET-01750_CLAZ | 2026-02-20 | QC Accepted | 03-06-2026 | 2026-03-06 | 0 | 2026_ET-01750_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01750_WR | 2026-03-12 | 04-19-2026 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01750_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01750_VMM1 | 2026-03-12 | QC Accepted |  | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-01750_RR |  | No Violations | 03-21-2026 | [5 empty] | 2026_ET-01750_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-20 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed Late - Program | POLYPRO-WATSON_ET-01750 |  |  | No | 21:40 |  | DOMINGUEZ HILLS | 32 | UNK | 2026-01-09 14:15 PST ¦ 2026-02-02 13:08 PST | 020226 | 20260202 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELDORADO-SLOAN CANYON | ET-01984 | 2026_ET-01984 |  | 1 | 2026 | Apr 01, 2026 | 220 | NV_E | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.23075 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-01-23 | 01-01-2026 | Flown | 2025-10-30 | 03-20-2026 | 03-20-2026 |  | 2026_ET-01984_ACQPKG | 2026_ET-01984_GSPKG | Submitted | 2026_ET-01984_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01984_GCPR | 2025-12-08 | Historical | 2026_ET-01984_ACQ | QC Accepted | 2026_ET-01984_FR | 2025-11-27 | Submitted | 2026_ET-01984_RWR | Submitted | 2025-11-27 | 2026_ET-01984_CLAZ | 2025-11-27 | QC Accepted | 01-23-2026 | 2026-03-20 |  | 2026_ET-01984_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01984_WR | 2026-03-25 | 04-19-2026 | QC Accepted | 04-08-2026 | 2026-04-01 |  | 2026_ET-01984_VMLAZ | 2026-04-17 | QC Accepted | 05-01-2026 | 2026-04-28 | 0 | 2026_ET-01984_VMM1 | 2026-03-25 | QC Accepted |  | 05-01-2026 | 2026-03-27 | 0 | 2026_ET-01984_RR | 2026-03-25 | No Violations | 03-28-2026 |  | 0 |  |  |  | 2026_ET-01984_VER | 2026-03-25 | Uploaded to S123 | 05-01-2026 | 2026-04-20 | [5 empty] | Completed Late - Program | Completed On Time | Completed On Time - Program | ELDORADO-SLOAN CANYON_ET-01984 |  |  | Yes |  | Helicopter |  |  | HC | 2025-10-29 11:45 PDT ¦ 2025-10-29 11:52 PDT | 102925 | 20251029 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ROY-SOLAR RANCH-WHIRLWIND | ET-00013 | 2026_ET-00013 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.47152 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-03-21 | 03-03-2026 | Flown | 2025-12-18 | 03-21-2026 | 02-12-2026 |  | 2026_ET-00013_ACQPKG | 2026_ET-00013_GSPKG | Submitted | 2026_ET-00013_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00013_GCPR | 2025-12-08 | Historical | 2026_ET-00013_ACQ | QC Accepted | 2026_ET-00013_FR | 2026-01-13 | Submitted | 2026_ET-00013_RWR | Submitted | 2026-01-13 | 2026_ET-00013_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-12 |  | 2026_ET-00013_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00013_WR | 2026-04-16 | 04-20-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00013_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00013_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00013_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00013_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | ROY-SOLAR RANCH-WHIRLWIND_ET-00013 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2025-12-18 16:10 PST ¦ 2025-12-18 16:21 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WINDHUB-BROOKFIELD DESERT-CAMERON RIDGE | ET-00229 | 2026_ET-00229 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.071492 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-21 | 03-03-2026 | Flown | 2025-12-18 | 03-21-2026 | 02-16-2026 |  | 2026_ET-00229_ACQPKG | 2026_ET-00229_GSPKG | Submitted | 2026_ET-00229_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00229_GCPR | 2025-12-08 | Historical | 2026_ET-00229_ACQ | QC Accepted | 2026_ET-00229_FR | 2026-01-13 | Submitted | 2026_ET-00229_RWR | Submitted | 2026-01-13 | 2026_ET-00229_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-16 |  | 2026_ET-00229_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00229_WR | 2026-04-15 | 04-20-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-00229_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-00229_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-00229_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-00229_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | WINDHUB-BROOKFIELD DESERT-CAMERON RIDGE_ET-00229 |  |  | No |  | Helicopter |  |  | HC | 2025-12-18 15:55 PST ¦ 2025-12-18 15:56 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-NORTH OAKS-TENGEN | ET-01653 | 2026_ET-01653 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 8.7978 | 8.7978 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-21 | 03-03-2026 | Flown | 2025-12-27 | 03-21-2026 | 03-09-2026 |  | 2026_ET-01653_ACQPKG | 2026_ET-01653_GSPKG | Submitted | 2026_ET-01653_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01653_GCPR | 2025-12-08 | Historical | 2026_ET-01653_ACQ | QC Accepted | 2026_ET-01653_FR | 2026-03-02 | Submitted | 2026_ET-01653_RWR | Submitted | 2026-03-02 | 2026_ET-01653_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01653_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01653_WR | 2026-04-15 | 04-20-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01653_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01653_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01653_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01653_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-NORTH OAKS-TENGEN_ET-01653 |  |  | No | 17:54 |  | VALENCIA | 59 | UNK | 2025-12-27 10:32 PST ¦ 2026-01-08 09:58 PST | 122725 | 20260108 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BREEZE-MONOLITH NO. 1 | ET-01436 | 2026_ET-01436 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.31504 | 0.31504 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-19 | 03-26-2026 | 03-26-2026 |  | 2026_ET-01436_ACQPKG | 2026_ET-01436_GSPKG | Submitted | 2026_ET-01436_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01436_GCPR | 2025-12-08 | Historical | 2026_ET-01436_ACQ | QC Accepted | 2026_ET-01436_FR | 2026-01-13 | Submitted | 2026_ET-01436_RWR | Submitted | 2026-01-13 | 2026_ET-01436_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-03-26 | 0 | 2026_ET-01436_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01436_WR | 2026-04-15 | 04-25-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-01436_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-01436_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-01436_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-01436_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BREEZE-MONOLITH NO. 1_ET-01436 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-19 15:41 PST ¦ 2025-12-19 15:45 PST | 121925 | 20251219 | [6 empty] | No | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BREEZE-MONOLITH NO. 2 | ET-01437 | 2026_ET-01437 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.29934 | 0.29934 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-10 | 03-03-2026 | Flown | 2025-12-19 | 03-26-2026 | 03-26-2026 |  | 2026_ET-01437_ACQPKG | 2026_ET-01437_GSPKG | Submitted | 2026_ET-01437_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01437_GCPR | 2025-12-08 | Historical | 2026_ET-01437_ACQ | QC Accepted | 2026_ET-01437_FR | 2026-01-13 | Submitted | 2026_ET-01437_RWR | Submitted | 2026-01-13 | 2026_ET-01437_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-03-26 | 0 | 2026_ET-01437_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01437_WR | 2026-04-15 | 04-25-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-01437_VMLAZ | 2026-04-15 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-01437_VMM1 | 2026-04-15 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-01437_RR | 2026-04-15 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-01437_VER | 2026-04-15 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | BREEZE-MONOLITH NO. 2_ET-01437 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-19 15:41 PST ¦ 2025-12-19 15:45 PST | 121925 | 20251219 | [6 empty] | No | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-PARDEE NO.4 | ET-01989 | 2026_ET-01989 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 25.7248 | 25.7248 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A | GCP_Upload_Failure |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-03-2026 | Flown | 2026-01-08 | 03-27-2026 | 03-27-2026 |  | 2026_ET-01989_ACQPKG | 2026_ET-01989_GSPKG | Submitted | 2026_ET-01989_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01989_GCPR | 2025-12-08 | Historical | 2026_ET-01989_ACQ | QC Accepted | 2026_ET-01989_FR | 2026-03-02 | Submitted | 2026_ET-01989_RWR | Submitted | 2026-03-02 | 2026_ET-01989_CLAZ | 2026-03-25 | QC Accepted | 04-08-2026 | 2026-03-27 | 0 | 2026_ET-01989_PROCPKG | In Progress | All Good - Complete | 2026_ET-01989_WR | 2026-04-15 | 04-26-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01989_VMLAZ | 2026-04-15 | QC Accepted |  | 2026-05-18 |  | 2026_ET-01989_VMM1 | 2026-04-15 | QC Rejected |  |  | 2026-05-15 | 1 | 2026_ET-01989_RR | 2026-04-15 | No Violations |  |  | 0 |  |  |  | 2026_ET-01989_VER | 2026-04-15 | Uploaded to S123 |  | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MOORPARK-PARDEE NO.4_ET-01989 |  |  | Yes | 17:54 & 21:02 & 17:13 |  | VALENCIA | 59 | UNK | 2025-12-27 12:08 PST ¦ 2026-01-08 10:37 PST | 010726 | 20260108 | [5 empty] | Subject conductors strung inaccurately. |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-ALON-PACLINE-REFINERY | ET-01681 | 2026_ET-01681 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 7.3933 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-07 | 03-03-2026 | Flown | 2026-01-09 | 04-07-2026 | 03-09-2026 |  | 2026_ET-01681_ACQPKG | 2026_ET-01681_GSPKG | Submitted | 2026_ET-01681_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01681_GCPR | 2025-12-08 | Historical | 2026_ET-01681_ACQ | QC Accepted | 2026_ET-01681_FR | 2026-03-02 | Submitted | 2026_ET-01681_RWR | Submitted | 2026-03-02 | 2026_ET-01681_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01681_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01681_WR | 2026-04-15 | 05-07-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01681_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01681_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01681_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01681_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-ALON-PACLINE-REFINERY_ET-01681 |  |  | No | 18:13 & 21:40 |  | LONG BEACH | 46 | UNK | 2025-12-16 13:48 PST ¦ 2026-01-09 14:20 PST | 010926 | 20260109 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-DALTON-FINANCE-LARK ELLEN | ET-01711 | 2026_ET-01711 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 5.6139 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-07 | 03-03-2026 | Flown | 2025-12-18 | 04-07-2026 | 03-12-2026 |  | 2026_ET-01711_ACQPKG | 2026_ET-01711_GSPKG | Submitted | 2026_ET-01711_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01711_GCPR | 2025-12-08 | Historical | 2026_ET-01711_ACQ | QC Accepted | 2026_ET-01711_FR | 2026-03-02 | Submitted | 2026_ET-01711_RWR | Submitted | 2026-03-02 | 2026_ET-01711_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-12 | 0 | 2026_ET-01711_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01711_WR | 2026-04-15 | 05-07-2026 | QC Accepted | 05-02-2026 | 2026-05-18 |  | 2026_ET-01711_VMLAZ | 2026-04-15 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01711_VMM1 | 2026-04-15 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01711_RR | 2026-04-15 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01711_VER | 2026-04-15 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | RIO HONDO-DALTON-FINANCE-LARK ELLEN_ET-01711 |  |  | No | 17:46 |  | MONROVIA | 27 | UNK | 2025-12-18 09:22 PST ¦ 2025-12-18 09:49 PST | 121825 | 20251218 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ACTON-RITTER RANCH | ET-00904 | 2026_ET-00904 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.9181 | 5.9181 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-24 | 04-02-2026 | Flown | 2026-03-04 | 04-08-2026 | 04-08-2026 |  | 2026_ET-00904_ACQPKG | 2026_ET-00904_GSPKG | Submitted | 2026_ET-00904_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00904_GCPR | 2025-12-08 | Historical | 2026_ET-00904_ACQ | QC Accepted | 2026_ET-00904_FR | 2026-04-02 | Submitted | 2026_ET-00904_RWR | Submitted | 2026-04-02 | 2026_ET-00904_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00904_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00904_WR | 2026-05-06 | 05-08-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00904_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00904_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00904_RR | 2026-05-06 | No Violations | 05-20-2026 |  | 0 |  |  |  | 2026_ET-00904_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | ACTON-RITTER RANCH_ET-00904 | Done |  | No |  |  | ANTELOPE VALLEY | 36 | UNK | 2026-03-04 10:06 PST ¦ 2026-03-04 10:27 PST | 030426 | 20260304 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-LA HABRA NO. 1 | ET-00005 | 2026_ET-00005 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.6813 | 8.1126 | 93 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-11-30 | 12-11-2025 | Flown | 2025-10-17 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00005_ACQPKG | 2026_ET-00005_GSPKG | Submitted | 2026_ET-00005_GS | 2025-11-08 | Field Complete | 2026_ET-00005_GCPR | 2025-12-01 | Submitted | 2026_ET-00005_ACQ | QC Accepted | 2026_ET-00005_FR | 2025-12-01 | Submitted | 2026_ET-00005_RWR | Submitted | 2025-12-01 | 2026_ET-00005_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00005_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00005_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00005_VMLAZ | 2026-02-01 | QC Accepted | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00005_VMM1 | 2026-02-01 | QC Accepted |  | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00005_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00005_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-LA HABRA NO. 1_ET-00005 |  |  | No | 15:48 | Helicopter | COVINA | 26 | HC | 2025-10-17 10:28 PDT ¦ 2025-10-25 15:28 PDT | 102425 | 20251025 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CHINO-LA HABRA NO. 2 | ET-00006 | 2026_ET-00006 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.6814 | 8.1121 | 93 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-11-30 | 12-11-2025 | Flown | 2025-10-17 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00006_ACQPKG | 2026_ET-00006_GSPKG | Submitted | 2026_ET-00006_GS | 2025-11-08 | Field Complete | 2026_ET-00006_GCPR | 2025-12-01 | Submitted | 2026_ET-00006_ACQ | QC Accepted | 2026_ET-00006_FR | 2025-12-01 | Submitted | 2026_ET-00006_RWR | Submitted | 2025-12-01 | 2026_ET-00006_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00006_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00006_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00006_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00006_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00006_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00006_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-LA HABRA NO. 2_ET-00006 |  |  | No | 15:48 | Helicopter | COVINA | 26 | HC | 2025-10-17 10:28 PDT ¦ 2025-10-25 15:28 PDT | 102525 | 20251025 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-FALCON RIDGE | ET-00089 | 2026_ET-00089 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 7.7563 | 3.731 | 48 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-20 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00089_ACQPKG | 2026_ET-00089_GSPKG | Submitted | 2026_ET-00089_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00089_GCPR | 2025-12-08 | Historical | 2026_ET-00089_ACQ | QC Accepted | 2026_ET-00089_FR | 2025-11-29 | Submitted | 2026_ET-00089_RWR | Submitted | 2025-11-29 | 2026_ET-00089_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00089_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00089_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00089_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00089_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00089_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00089_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ETIWANDA-FALCON RIDGE_ET-00089 |  |  | No | 15:52 - 19:31 | Helicopter | FOOTHILL | 30 | HC | 2025-10-20 10:29 PDT ¦ 2025-10-21 10:17 PDT | 102125 | 20251021 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-NEWBURY | ET-00177 | 2026_ET-00177 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 8.5428 | 8.5428 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-19 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00177_ACQPKG | 2026_ET-00177_GSPKG | Submitted | 2026_ET-00177_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00177_GCPR | 2025-12-08 | Historical | 2026_ET-00177_ACQ | QC Accepted | 2026_ET-00177_FR | 2025-11-29 | Submitted | 2026_ET-00177_RWR | Submitted | 2025-11-29 | 2026_ET-00177_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00177_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00177_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00177_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00177_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00177_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00177_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | MOORPARK-NEWBURY_ET-00177 |  |  | No | 20:43 | Helicopter | THOUSAND OAKS | 35 | HC | 2025-10-19 10:46 PDT ¦ 2025-10-31 16:24 PDT | 101925 | 20251031 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JULIAN HINDS-MIRAGE | ET-00226 | 2026_ET-00226 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 46.21 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-15 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00226_ACQPKG | 2026_ET-00226_GSPKG | Submitted | 2026_ET-00226_GS | 2025-11-08 | Field Complete | 2026_ET-00226_GCPR | 2025-11-20 | Submitted | 2026_ET-00226_ACQ | QC Accepted | 2026_ET-00226_FR | 2025-11-23 | Submitted | 2026_ET-00226_RWR | Submitted | 2025-11-20 | 2026_ET-00226_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00226_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00226_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00226_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00226_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00226_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00226_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | JULIAN HINDS-MIRAGE_ET-00226 |  |  | Yes | 20:25 | Helicopter |  |  | HC | 2025-10-15 15:15 PDT ¦ 2025-10-15 16:16 PDT | 101525 | 20251015 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-LAYFAIR | ET-00302 | 2026_ET-00302 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.2309 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-25 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00302_ACQPKG | 2026_ET-00302_GSPKG | Submitted | 2026_ET-00302_GS | 2025-11-08 | Field Complete | 2026_ET-00302_GCPR | 2025-11-29 | Submitted | 2026_ET-00302_ACQ | QC Accepted | 2026_ET-00302_FR | 2025-11-29 | Submitted | 2026_ET-00302_RWR | Submitted | 2025-11-29 | 2026_ET-00302_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00302_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00302_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00302_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00302_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00302_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00302_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-LAYFAIR_ET-00302 |  |  | No | 20:08 | Helicopter | ONTARIO | 34 | HC | 2025-10-25 13:26 PDT ¦ 2025-10-25 13:30 PDT | 102525 | 20251025 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LIGHTHIPE-CLEANSTEEL-NEPTUNE | ET-00335 | 2026_ET-00335 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.47817 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-18 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00335_ACQPKG | 2026_ET-00335_GSPKG | Submitted | 2026_ET-00335_GS | 2025-11-08 | Field Complete | 2026_ET-00335_GCPR | 2025-12-01 | Submitted | 2026_ET-00335_ACQ | QC Accepted | 2026_ET-00335_FR | 2025-12-01 | Submitted | 2026_ET-00335_RWR | Submitted | 2025-12-01 | 2026_ET-00335_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00335_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00335_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00335_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00335_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00335_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00335_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LIGHTHIPE-CLEANSTEEL-NEPTUNE_ET-00335 |  |  | No | 15:38 | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2025-10-18 11:13 PDT ¦ 2025-10-18 11:15 PDT | 101825 | 20251018 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SERRANO-VILLA PARK NO.2 | ET-00475 | 2026_ET-00475 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 3.2046 | 2.1123 | 66 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-23 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00475_ACQPKG | 2026_ET-00475_GSPKG | Submitted | 2026_ET-00475_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00475_GCPR | 2025-12-08 | Historical | 2026_ET-00475_ACQ | QC Accepted | 2026_ET-00475_FR | 2025-11-23 | Submitted | 2026_ET-00475_RWR | Submitted | 2025-11-23 | 2026_ET-00475_CLAZ | 2025-11-23 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00475_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00475_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00475_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00475_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00475_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00475_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | SERRANO-VILLA PARK NO.2_ET-00475 |  |  | Yes | 20:32 | Helicopter | SANTA ANA | 29 | HC | 2025-10-23 14:26 PDT ¦ 2025-10-23 15:04 PDT | 102325 | 20251023 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-DEL AMO | ET-00490 | 2026_ET-00490 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.0729 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-18 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00490_ACQPKG | 2026_ET-00490_GSPKG | Submitted | 2026_ET-00490_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00490_GCPR | 2025-12-08 | Historical | 2026_ET-00490_ACQ | QC Accepted | 2026_ET-00490_FR | 2025-12-01 | Submitted | 2026_ET-00490_RWR | Submitted | 2025-12-01 | 2026_ET-00490_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00490_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00490_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00490_VMLAZ | 2026-02-01 | QC Accepted | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00490_VMM1 | 2026-02-01 | QC Accepted |  | 05-21-2026 | 2026-02-12 | 0 | 2026_ET-00490_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00490_VER | 2026-05-07 | Uploaded to S123 | 05-21-2026 | 2026-05-19 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CENTER-DEL AMO_ET-00490 |  |  | Yes | 15:38 | Helicopter | LONG BEACH | 46 | HC | 2025-10-18 10:31 PDT ¦ 2025-10-18 10:39 PDT | 101825 | 20251018 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE CRATER-POTRERO-THOUSAND OAKS | ET-00536 | 2026_ET-00536 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.39916 | 0.39916 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-19 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00536_ACQPKG | 2026_ET-00536_GSPKG | Submitted | 2026_ET-00536_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00536_GCPR | 2025-12-08 | Historical | 2026_ET-00536_ACQ | QC Accepted | 2026_ET-00536_FR | 2025-11-29 | Submitted | 2026_ET-00536_RWR | Submitted | 2025-11-29 | 2026_ET-00536_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00536_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00536_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00536_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00536_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00536_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00536_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CRATER-POTRERO-THOUSAND OAKS_ET-00536 |  |  | No | 20:43 | Helicopter | THOUSAND OAKS | 35 | HC | 2025-10-19 10:40 PDT ¦ 2025-10-29 14:43 PDT | 101925 | 20251029 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-CORONA | ET-00572 | 2026_ET-00572 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 2.2303 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-17 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00572_ACQPKG | 2026_ET-00572_GSPKG | Submitted | 2026_ET-00572_GS | 2025-11-08 | Field Complete | 2026_ET-00572_GCPR | 2025-11-29 | Submitted | 2026_ET-00572_ACQ | QC Accepted | 2026_ET-00572_FR | 2025-11-29 | Submitted | 2026_ET-00572_RWR | Submitted | 2025-11-29 | 2026_ET-00572_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00572_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00572_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00572_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00572_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00572_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00572_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-CORONA_ET-00572 |  |  | No | 18:59 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 12:18 PDT ¦ 2025-10-17 12:45 PDT | 101725 | 20251017 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-VINCENT NO. 2 | ET-00669 | 2026_ET-00669 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 31.9385 | 31.9385 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-25 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00669_ACQPKG | 2026_ET-00669_GSPKG | Submitted | 2026_ET-00669_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00669_GCPR | 2025-12-08 | Historical | 2026_ET-00669_ACQ | QC Accepted | 2026_ET-00669_FR | 2025-12-01 | Submitted | 2026_ET-00669_RWR | Submitted | 2025-12-01 | 2026_ET-00669_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00669_PROCPKG | In Progress | All Good - Complete | 2026_ET-00669_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00669_VMLAZ | 2026-02-01 | QC Accepted |  | 2026-02-12 | 0 | 2026_ET-00669_VMM1 | 2026-02-01 | QC Accepted |  |  | 2026-02-12 | 0 | 2026_ET-00669_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00669_VER | 2026-05-13 | QC Rejected |  | 2026-05-21 | 4 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | PARDEE-VINCENT NO. 2_ET-00669 |  |  | Yes | 18:56 - 22:16 | Helicopter | VALENCIA | 59 | HC | 2025-10-25 12:47 PDT ¦ 2025-10-25 16:19 PDT | 102525 | 20251025 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE ROYAL-SHELLINE-VALDEZ | ET-00750 | 2026_ET-00750 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.43699 | 0.43699 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-31 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00750_ACQPKG | 2026_ET-00750_GSPKG | Submitted | 2026_ET-00750_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00750_GCPR | 2025-12-08 | Historical | 2026_ET-00750_ACQ | QC Accepted | 2026_ET-00750_FR | 2025-11-29 | Submitted | 2026_ET-00750_RWR | Submitted | 2025-11-29 | 2026_ET-00750_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00750_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00750_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00750_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00750_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00750_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00750_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ROYAL-SHELLINE-VALDEZ_ET-00750 |  |  | No | 23:00 | Helicopter | THOUSAND OAKS | 35 | HC | 2025-10-29 15:23 PDT ¦ 2025-11-06 08:26 PST | 102925 | 20251106 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ALDER-DECLEZ | ET-00918 | 2026_ET-00918 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.20002 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-20 | 12-20-2025 | 12-15-2025 |  | 2026_ET-00918_ACQPKG | 2026_ET-00918_GSPKG | Submitted | 2026_ET-00918_GS | 2025-11-08 | Field Complete | 2026_ET-00918_GCPR | 2025-11-29 | Submitted | 2026_ET-00918_ACQ | QC Accepted | 2026_ET-00918_FR | 2025-11-29 | Submitted | 2026_ET-00918_RWR | Submitted | 2025-11-29 | 2026_ET-00918_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00918_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00918_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00918_VMLAZ | 2026-02-01 | QC Accepted | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00918_VMM1 | 2026-02-01 | QC Accepted |  | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00918_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00918_VER | 2026-02-01 | Uploaded to S123 | 02-15-2026 | 2026-02-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ALDER-DECLEZ_ET-00918 |  |  | No | 19:31 | Helicopter | FOOTHILL | 30 | HC | 2025-10-20 14:35 PDT ¦ 2025-10-20 14:36 PDT | 102025 | 20251020 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ETIWANDA-AMERON-GRAPELAND-PIPE | ET-01037 | 2026_ET-01037 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.34906 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-21 | 12-20-2025 | 12-11-2025 |  | 2026_ET-01037_ACQPKG | 2026_ET-01037_GSPKG | Submitted | 2026_ET-01037_GS | 2025-11-08 | Field Complete | 2026_ET-01037_GCPR | 2025-11-29 | Submitted | 2026_ET-01037_ACQ | QC Accepted | 2026_ET-01037_FR | 2025-11-29 | Submitted | 2026_ET-01037_RWR | Submitted | 2025-11-29 | 2026_ET-01037_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-11 | 0 | 2026_ET-01037_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01037_WR | 2026-02-01 | 01-19-2026 | QC Accepted | 02-13-2026 | 2026-02-11 | 0 | 2026_ET-01037_VMLAZ | 2026-02-01 | QC Accepted | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01037_VMM1 | 2026-02-01 | QC Accepted |  | 05-15-2026 | 2026-02-11 | 0 | 2026_ET-01037_RR | 2026-02-01 | No Violations | 02-12-2026 |  | 0 |  |  |  | 2026_ET-01037_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE ETIWANDA-AMERON-GRAPELAND-PIPE_ET-01037 |  |  | No | 15:48 | Helicopter | FOOTHILL | 30 | HC | 2025-10-21 10:01 PDT ¦ 2025-10-21 10:10 PDT | 102125 | 20251021 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
DESERT SUNLIGHT-RED BLUFF | ET-00123 | 2026_ET-00123 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 0.16158 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-29 | 12-11-2025 | Flown | 2025-10-16 | 12-29-2025 | 12-15-2025 |  | 2026_ET-00123_ACQPKG | 2026_ET-00123_GSPKG | Submitted | 2026_ET-00123_GS | 2025-11-08 | Field Complete | 2026_ET-00123_GCPR | 2025-11-29 | Submitted | 2026_ET-00123_ACQ | QC Accepted | 2026_ET-00123_FR | 2025-11-23 | Submitted | 2026_ET-00123_RWR | Submitted | 2025-11-20 | 2026_ET-00123_CLAZ | 2025-11-20 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00123_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00123_WR | 2026-02-01 | 01-28-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00123_VMLAZ | 2026-02-01 | QC Accepted | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00123_VMM1 | 2026-02-01 | QC Accepted |  | 02-15-2026 | 2026-02-12 | 0 | 2026_ET-00123_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00123_VER | 2026-02-01 | Uploaded to S123 | 02-15-2026 | 2026-02-17 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DESERT SUNLIGHT-RED BLUFF_ET-00123 |  |  | Yes | 15:52 | Helicopter | BLYTHE | 87 | HC | 2025-10-16 10:26 PDT ¦ 2025-10-16 10:35 PDT | 101625 | 20251016 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-MIRA LOMA NO.3 | ET-00592 | 2026_ET-00592 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 6.7535 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2025-12-11 | 12-11-2025 | Flown | 2025-10-23 | 12-29-2025 | 12-29-2025 |  | 2026_ET-00592_ACQPKG | 2026_ET-00592_GSPKG | Submitted | 2026_ET-00592_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00592_GCPR | 2025-12-08 | Historical | 2026_ET-00592_ACQ | QC Accepted | 2026_ET-00592_FR | 2025-11-29 | Submitted | 2026_ET-00592_RWR | Submitted | 2025-12-29 | 2026_ET-00592_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00592_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00592_WR | 2026-02-01 | 01-28-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00592_VMLAZ | 2026-02-01 | QC Accepted | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00592_VMM1 | 2026-02-01 | QC Accepted |  | 05-01-2026 | 2026-02-12 | 0 | 2026_ET-00592_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00592_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-04-27 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CHINO-MIRA LOMA NO.3_ET-00592 |  |  | Yes | 17:14 | Helicopter | ONTARIO | 34 | HC | 2025-10-17 10:54 PDT ¦ 2025-10-25 13:53 PDT | 102325 | 20251025 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LA FRESA-AMCO-NATIONAL SUPPLY | ET-01032 | 2026_ET-01032 |  | 11 | 2026 | Mar 11, 2026 | 66 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.2705 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2025-12-10 | 12-11-2025 | Flown | 2025-10-18 | 12-31-2025 | 12-31-2025 |  | 2026_ET-01032_ACQPKG | 2026_ET-01032_GSPKG | Submitted | 2026_ET-01032_GS | 2025-11-08 | Field Complete | 2026_ET-01032_GCPR | 2025-12-01 | Submitted | 2026_ET-01032_ACQ | QC Accepted | 2026_ET-01032_FR | 2025-12-01 | Submitted | 2026_ET-01032_RWR | Submitted | 2025-12-01 | 2026_ET-01032_CLAZ | 2025-12-01 | QC Accepted | 12-26-2025 | 2025-12-31 | 0 | 2026_ET-01032_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01032_WR |  | 01-30-2026 | QC Accepted |  |  | 1 | 2026_ET-01032_VMLAZ | 2026-03-05 | QC Accepted | 05-15-2026 | 2026-02-20 | 0 | 2026_ET-01032_VMM1 | 2026-02-03 | QC Accepted |  | 05-15-2026 | 2026-03-12 | 1 | 2026_ET-01032_RR | 2026-02-03 | No Violations | 03-13-2026 |  | 0 |  |  |  | 2026_ET-01032_VER | 2026-05-01 | Uploaded to S123 | 05-15-2026 | 2026-05-05 | 1 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | IDLE LA FRESA-AMCO-NATIONAL SUPPLY_ET-01032 |  |  | No | 19:28 | Helicopter | SOUTH BAY | 44 | HC | 2025-10-18 12:53 PDT ¦ 2025-10-18 12:53 PDT | 101825 | 20251018 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE DEL AMO-CARMENITA | ET-00003 | 2026_ET-00003 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.53361 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-01 | 04-14-2026 | 04-10-2026 |  | 2026_ET-00003_ACQPKG | 2026_ET-00003_GSPKG | Submitted | 2026_ET-00003_GS | 2025-12-08 | Field Complete | 2026_ET-00003_GCPR | 2026-04-02 | Submitted | 2026_ET-00003_ACQ | QC Accepted | 2026_ET-00003_FR | 2026-04-02 | Submitted | 2026_ET-00003_RWR | Submitted | 2026-04-02 | 2026_ET-00003_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-00003_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00003_WR | 2026-05-10 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00003_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00003_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00003_RR | 2026-05-10 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-00003_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE DEL AMO-CARMENITA_ET-00003 |  |  | No |  |  | WHITTIER | 47 | UNK | 2026-03-01 13:44 PST ¦ 2026-03-01 13:45 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ETIWANDA-SAN BERNARDINO | ET-00004 | 2026_ET-00004 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 9.8748 | 1.9135 | 19 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-13 | 04-02-2026 | Flown | 2026-02-22 | 05-04-2026 | 05-04-2026 |  | 2026_ET-00004_ACQPKG | 2026_ET-00004_GSPKG | Submitted | 2026_ET-00004_GS | 2025-10-15 | Field Complete | 2026_ET-00004_GCPR | 2025-12-08 | Submitted | 2026_ET-00004_ACQ | QC Accepted | 2026_ET-00004_FR | 2026-03-16 | Submitted | 2026_ET-00004_RWR | Submitted | 2026-03-16 | 2026_ET-00004_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-05-04 | 1 | 2026_ET-00004_PROCPKG | Submitted | All Good - Complete | 2026_ET-00004_WR | 2026-05-13 | 06-03-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00004_VMLAZ | 2026-05-12 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00004_VMM1 | 2026-05-13 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00004_RR | 2026-05-13 | No Violations | [6 empty] | 2026_ET-00004_VER | 2026-05-13 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | IDLE ETIWANDA-SAN BERNARDINO_ET-00004 |  |  | No |  | Helicopter | FOOTHILL | 30 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SOUTH RECTOR-VISALIA | ET-00007 | 2026_ET-00007 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 1.7369 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00007_ACQPKG | 2026_ET-00007_GSPKG | Submitted | 2026_ET-00007_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00007_GCPR | 2025-12-08 | Historical | 2026_ET-00007_ACQ | In Progress | 2026_ET-00007_FR |  | Not Started | 2026_ET-00007_RWR | Not Started |  | 2026_ET-00007_CLAZ |  | Not Started |  |  |  | 2026_ET-00007_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00007_WR |  |  | Not Started |  |  |  | 2026_ET-00007_VMLAZ |  | Not Started |  |  |  | 2026_ET-00007_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00007_RR |  | Not Started | [6 empty] | 2026_ET-00007_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE SOUTH RECTOR-VISALIA_ET-00007 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ETIWANDA-DECLEZ-LINDE | ET-00009 | 2026_ET-00009 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.3186 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-01-30 | 04-14-2026 | 04-10-2026 |  | 2026_ET-00009_ACQPKG | 2026_ET-00009_GSPKG | Submitted | 2026_ET-00009_GS | 2025-12-08 | Field Complete | 2026_ET-00009_GCPR | 2026-04-02 | Submitted | 2026_ET-00009_ACQ | QC Accepted | 2026_ET-00009_FR | 2026-04-02 | Submitted | 2026_ET-00009_RWR | Submitted | 2026-04-02 | 2026_ET-00009_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-00009_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00009_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00009_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00009_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00009_RR | 2026-05-10 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-00009_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE ETIWANDA-DECLEZ-LINDE_ET-00009 |  |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-30 09:14 PST ¦ 2026-02-15 13:01 PST | 013026 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VESTAL-GROWERS-KERN RIVER 3 | ET-00011 | 2026_ET-00011 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 44.262 | 34.8478 | 79 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00011_ACQPKG | 2026_ET-00011_GSPKG | Submitted | 2026_ET-00011_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00011_GCPR | 2025-12-08 | Historical | 2026_ET-00011_ACQ | In Progress | 2026_ET-00011_FR |  | Not Started | 2026_ET-00011_RWR | Not Started |  | 2026_ET-00011_CLAZ |  | Not Started |  |  |  | 2026_ET-00011_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00011_WR |  |  | Not Started |  |  |  | 2026_ET-00011_VMLAZ |  | Not Started |  |  |  | 2026_ET-00011_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00011_RR |  | Not Started | [6 empty] | 2026_ET-00011_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VESTAL-GROWERS-KERN RIVER 3_ET-00011 |  |  | No |  | Helicopter | KERNVILLE | 53 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-LA COLINA | ET-00019 | 2026_ET-00019 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.8674 | 1.311 | 46 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00019_ACQPKG | 2026_ET-00019_GSPKG | Submitted | 2026_ET-00019_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00019_GCPR | 2025-12-08 | Historical | 2026_ET-00019_ACQ | In Progress | 2026_ET-00019_FR |  | Not Started | 2026_ET-00019_RWR | Not Started |  | 2026_ET-00019_CLAZ |  | Not Started |  |  |  | 2026_ET-00019_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00019_WR |  |  | Not Started |  |  |  | 2026_ET-00019_VMLAZ |  | Not Started |  |  |  | 2026_ET-00019_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00019_RR |  | Not Started | [6 empty] | 2026_ET-00019_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-LA COLINA_ET-00019 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL SUR-GOLDFINGER | ET-00029 | 2026_ET-00029 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.015246 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-17 |  | 05-15-2026 |  | 2026_ET-00029_ACQPKG | 2026_ET-00029_GSPKG | Submitted | 2026_ET-00029_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00029_GCPR | 2025-12-08 | Historical | 2026_ET-00029_ACQ | QC Accepted | 2026_ET-00029_FR | 2026-05-08 | Submitted | 2026_ET-00029_RWR | Submitted | 2026-05-08 | 2026_ET-00029_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-00029_PROCPKG | In Progress | SCE | 2026_ET-00029_WR |  |  | Not Started |  |  |  | 2026_ET-00029_VMLAZ |  | Not Started |  |  |  | 2026_ET-00029_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00029_RR |  | Not Started | [6 empty] | 2026_ET-00029_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEL SUR-GOLDFINGER_ET-00029 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OASIS-SOLARIS | ET-00030 | 2026_ET-00030 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.10773 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-02-21 | 04-21-2026 | 04-21-2026 |  | 2026_ET-00030_ACQPKG | 2026_ET-00030_GSPKG | Submitted | 2026_ET-00030_GS | 2025-10-17 | Field Complete | 2026_ET-00030_GCPR | 2025-12-08 | Submitted | 2026_ET-00030_ACQ | QC Accepted | 2026_ET-00030_FR | 2026-03-16 | Submitted | 2026_ET-00030_RWR | Submitted | 2026-03-16 | 2026_ET-00030_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-00030_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00030_WR | 2026-04-29 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-00030_VMLAZ | 2026-04-29 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-00030_VMM1 | 2026-04-29 | QC Accepted |  | 06-01-2026 | 2026-05-04 |  | 2026_ET-00030_RR |  | No Violations | 05-05-2026 |  | 0 |  |  |  | 2026_ET-00030_VER | 2026-04-29 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | OASIS-SOLARIS_ET-00030 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-21 10:15 PST ¦ 2026-02-21 10:17 PST | 022126 | 20260221 |  | Metadata issue. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
LITTLE ROCK-SPARKLE-WILSONA | ET-00032 | 2026_ET-00032 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 16.6822 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 04-17-2026 |  | 2026_ET-00032_ACQPKG | 2026_ET-00032_GSPKG | Submitted | 2026_ET-00032_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00032_GCPR | 2025-12-08 | Historical | 2026_ET-00032_ACQ | QC Accepted | 2026_ET-00032_FR | 2026-03-16 | Submitted | 2026_ET-00032_RWR | Submitted | 2026-03-16 | 2026_ET-00032_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-00032_PROCPKG | In Progress | SCE | 2026_ET-00032_WR |  |  | In Progress |  |  |  | 2026_ET-00032_VMLAZ |  | In Progress |  |  |  | 2026_ET-00032_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00032_RR |  | In Progress | [6 empty] | 2026_ET-00032_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LITTLE ROCK-SPARKLE-WILSONA_ET-00032 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 14:04 PST ¦ 2026-02-20 14:28 PST | 022026 | 20260220 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-GOULD | ET-00035 | 2026_ET-00035 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.9973 | 13.9973 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-21 | 04-24-2026 | 04-16-2026 |  | 2026_ET-00035_ACQPKG | 2026_ET-00035_GSPKG | Submitted | 2026_ET-00035_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00035_GCPR | 2025-12-08 | Historical | 2026_ET-00035_ACQ | QC Accepted | 2026_ET-00035_FR | 2026-03-16 | Submitted | 2026_ET-00035_RWR | Submitted | 2026-03-16 | 2026_ET-00035_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-00035_PROCPKG | Submitted | All Good - Complete | 2026_ET-00035_WR | 2026-05-13 | 05-24-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00035_VMLAZ | 2026-04-30 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00035_VMM1 | 2026-05-13 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00035_RR | 2026-05-13 | No Violations | [6 empty] | 2026_ET-00035_VER | 2026-05-13 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | EAGLE ROCK-GOULD_ET-00035 |  |  | Yes |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-VICTOR NO. 2 | ET-00037 | 2026_ET-00037 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 37.435 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-20 | 01-01-2026 | Flown | 2026-02-01 | 05-08-2026 | 05-08-2026 |  | 2026_ET-00037_ACQPKG | 2026_ET-00037_GSPKG | Submitted | 2026_ET-00037_GS | 2026-01-23 | Field Complete | 2026_ET-00037_GCPR | 2026-01-30 | Submitted | 2026_ET-00037_ACQ | Submitted | 2026_ET-00037_FR |  | Not Started | 2026_ET-00037_RWR | Submitted | 2026-04-29 | 2026_ET-00037_CLAZ | 2026-05-16 | Ready for QC | 05-30-2026 | 2026-05-08 | 1 | 2026_ET-00037_PROCPKG | In Progress | All Good - Complete | 2026_ET-00037_WR |  |  | Not Started |  |  |  | 2026_ET-00037_VMLAZ |  | Not Started |  |  |  | 2026_ET-00037_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00037_RR |  | Not Started | [6 empty] | 2026_ET-00037_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed Late - Program | KRAMER-VICTOR NO. 2_ET-00037 |  |  | Yes |  |  | VICTORVILLE | 73 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PAUBA-TRITON | ET-00068 | 2026_ET-00068 |  | 1 | 2026 | Oct 01, 2026 | 115 | CA_6 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 7.9516 | 4.2662 | 54 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00068_ACQPKG | 2026_ET-00068_GSPKG | Submitted | 2026_ET-00068_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00068_GCPR | 2025-12-08 | Historical | 2026_ET-00068_ACQ | In Progress | 2026_ET-00068_FR |  | Not Started | 2026_ET-00068_RWR | Not Started |  | 2026_ET-00068_CLAZ |  | Not Started |  |  |  | 2026_ET-00068_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00068_WR |  |  | Not Started |  |  |  | 2026_ET-00068_VMLAZ |  | Not Started |  |  |  | 2026_ET-00068_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00068_RR |  | Not Started | [6 empty] | 2026_ET-00068_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | PAUBA-TRITON_ET-00068 |  |  | No |  |  | WILDOMAR | 88 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-VALLEY NO 1 | ET-00071 | 2026_ET-00071 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 41.6846 | 35.2679 | 85 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-02-07 | 04-24-2026 | 04-08-2026 |  | 2026_ET-00071_ACQPKG | 2026_ET-00071_GSPKG | Submitted | 2026_ET-00071_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00071_GCPR | 2025-12-08 | Historical | 2026_ET-00071_ACQ | QC Accepted | 2026_ET-00071_FR | 2026-04-02 | Submitted | 2026_ET-00071_RWR | Submitted | 2026-04-02 | 2026_ET-00071_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00071_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00071_WR | 2026-05-04 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00071_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00071_VMM1 | 2026-05-04 | QC Accepted |  | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00071_RR | 2026-05-04 | No Violations | 05-08-2026 | [5 empty] | 2026_ET-00071_VER | 2026-05-04 | Uploaded to S123 | 06-01-2026 | 2026-05-07 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEVERS-VALLEY NO 1_ET-00071 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-VALLEY NO 2 | ET-00072 | 2026_ET-00072 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 41.6799 | 35.2041 | 84 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-02-07 | 04-24-2026 | 04-08-2026 |  | 2026_ET-00072_ACQPKG | 2026_ET-00072_GSPKG | Submitted | 2026_ET-00072_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00072_GCPR | 2025-12-08 | Historical | 2026_ET-00072_ACQ | QC Accepted | 2026_ET-00072_FR | 2026-04-02 | Submitted | 2026_ET-00072_RWR | Submitted | 2026-04-02 | 2026_ET-00072_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00072_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00072_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00072_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00072_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00072_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00072_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEVERS-VALLEY NO 2_ET-00072 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-BERRENDO | ET-00074 | 2026_ET-00074 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.033608 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-17 |  | 05-11-2026 |  | 2026_ET-00074_ACQPKG | 2026_ET-00074_GSPKG | Submitted | 2026_ET-00074_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00074_GCPR | 2025-12-08 | Historical | 2026_ET-00074_ACQ | QC Accepted | 2026_ET-00074_FR | 2026-05-08 | Submitted | 2026_ET-00074_RWR | Submitted | 2026-05-08 | 2026_ET-00074_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-11 | 0 | 2026_ET-00074_PROCPKG | In Progress | SCE | 2026_ET-00074_WR |  |  | Not Started |  |  |  | 2026_ET-00074_VMLAZ |  | Not Started |  |  |  | 2026_ET-00074_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00074_RR |  | Not Started | [6 empty] | 2026_ET-00074_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ANTELOPE-BERRENDO_ET-00074 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-VENWIND | ET-00091 | 2026_ET-00091 |  | 1 | 2026 | Aug 01, 2026 | 115 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.6184 | 1.2107 | 46 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-18 | 05-03-2026 | Flown | 2026-02-20 | 05-18-2026 | 05-11-2026 |  | 2026_ET-00091_ACQPKG | 2026_ET-00091_GSPKG | Submitted | 2026_ET-00091_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00091_GCPR | 2025-12-08 | Historical | 2026_ET-00091_ACQ | QC Accepted | 2026_ET-00091_FR | 2026-05-03 | Submitted | 2026_ET-00091_RWR | Submitted | 2026-05-03 | 2026_ET-00091_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00091_PROCPKG | In Progress | All Good - Complete | 2026_ET-00091_WR |  | 06-17-2026 | In Progress |  |  |  | 2026_ET-00091_VMLAZ |  | In Progress |  |  |  | 2026_ET-00091_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00091_RR |  | In Progress | [6 empty] | 2026_ET-00091_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | DEVERS-VENWIND_ET-00091 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NIETOS-SANTA FE SPRINGS | ET-00092 | 2026_ET-00092 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.32139 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00092_ACQPKG | 2026_ET-00092_GSPKG | Submitted | 2026_ET-00092_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00092_GCPR | 2025-12-08 | Historical | 2026_ET-00092_ACQ | In Progress | 2026_ET-00092_FR |  | Not Started | 2026_ET-00092_RWR | Not Started |  | 2026_ET-00092_CLAZ |  | Not Started |  |  |  | 2026_ET-00092_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00092_WR |  |  | Not Started |  |  |  | 2026_ET-00092_VMLAZ |  | Not Started |  |  |  | 2026_ET-00092_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00092_RR |  | Not Started | [6 empty] | 2026_ET-00092_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | NIETOS-SANTA FE SPRINGS_ET-00092 |  |  | No |  |  | WHITTIER | 47 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOSHEN-MASCOT | ET-00097 | 2026_ET-00097 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 9.6333 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00097_ACQPKG | 2026_ET-00097_GSPKG | Submitted | 2026_ET-00097_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00097_GCPR | 2025-12-08 | Historical | 2026_ET-00097_ACQ | In Progress | 2026_ET-00097_FR |  | Not Started | 2026_ET-00097_RWR | Not Started |  | 2026_ET-00097_CLAZ |  | Not Started |  |  |  | 2026_ET-00097_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00097_WR |  |  | Not Started |  |  |  | 2026_ET-00097_VMLAZ |  | Not Started |  |  |  | 2026_ET-00097_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00097_RR |  | Not Started | [6 empty] | 2026_ET-00097_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | GOSHEN-MASCOT_ET-00097 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HANFORD-MASCOT | ET-00098 | 2026_ET-00098 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.3246 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00098_ACQPKG | 2026_ET-00098_GSPKG | Submitted | 2026_ET-00098_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00098_GCPR | 2025-12-08 | Historical | 2026_ET-00098_ACQ | In Progress | 2026_ET-00098_FR |  | Not Started | 2026_ET-00098_RWR | Not Started |  | 2026_ET-00098_CLAZ |  | Not Started |  |  |  | 2026_ET-00098_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00098_WR |  |  | Not Started |  |  |  | 2026_ET-00098_VMLAZ |  | Not Started |  |  |  | 2026_ET-00098_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00098_RR |  | Not Started | [6 empty] | 2026_ET-00098_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | HANFORD-MASCOT_ET-00098 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALMASOL-RED BLUFF | ET-00128 | 2026_ET-00128 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.11278 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-21 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00128_ACQPKG | 2026_ET-00128_GSPKG | Submitted | 2026_ET-00128_GS | 2026-01-31 | Field Complete | 2026_ET-00128_GCPR | 2026-05-03 | Submitted | 2026_ET-00128_ACQ | QC Accepted | 2026_ET-00128_FR | 2026-05-03 | Submitted | 2026_ET-00128_RWR | Submitted | 2026-05-03 | 2026_ET-00128_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00128_PROCPKG | In Progress | All Good - Complete | 2026_ET-00128_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00128_VMLAZ |  | In Progress |  |  |  | 2026_ET-00128_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00128_RR |  | In Progress | [6 empty] | 2026_ET-00128_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ALMASOL-RED BLUFF_ET-00128 | Done |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-SERRANO NO.1 | ET-00134 | 2026_ET-00134 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 19.7754 | 11.5958 | 59 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-30 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00134_ACQPKG | 2026_ET-00134_GSPKG | Submitted | 2026_ET-00134_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00134_GCPR | 2025-12-08 | Historical | 2026_ET-00134_ACQ | QC Accepted | 2026_ET-00134_FR | 2026-04-02 | Submitted | 2026_ET-00134_RWR | Submitted | 2026-04-02 | 2026_ET-00134_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00134_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00134_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00134_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00134_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00134_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00134_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-SERRANO NO.1_ET-00134 |  |  | Yes |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-VICTOR NO. 1 | ET-00036 | 2026_ET-00036 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 37.433 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 01-01-2026 | Flown | 2026-02-01 | 05-08-2026 | 05-08-2026 |  | 2026_ET-00036_ACQPKG | 2026_ET-00036_GSPKG | Submitted | 2026_ET-00036_GS | 2026-01-23 | Field Complete | 2026_ET-00036_GCPR | 2026-01-30 | Submitted | 2026_ET-00036_ACQ | Submitted | 2026_ET-00036_FR |  | Not Started | 2026_ET-00036_RWR | Submitted | 2026-04-29 | 2026_ET-00036_CLAZ | 2026-05-16 | Ready for QC | 05-30-2026 | 2026-05-08 | 1 | 2026_ET-00036_PROCPKG | In Progress | All Good - Complete | 2026_ET-00036_WR |  |  | Not Started |  |  |  | 2026_ET-00036_VMLAZ |  | Not Started |  |  |  | 2026_ET-00036_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00036_RR |  | Not Started | [6 empty] | 2026_ET-00036_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed Late - Program | KRAMER-VICTOR NO. 1_ET-00036 |  |  | Yes |  |  | VICTORVILLE | 73 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-SERRANO NO.2 | ET-00135 | 2026_ET-00135 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 19.7612 | 11.5598 | 58 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-30 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00135_ACQPKG | 2026_ET-00135_GSPKG | Submitted | 2026_ET-00135_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00135_GCPR | 2025-12-08 | Historical | 2026_ET-00135_ACQ | QC Accepted | 2026_ET-00135_FR | 2026-04-02 | Submitted | 2026_ET-00135_RWR | Submitted | 2026-04-02 | 2026_ET-00135_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00135_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00135_WR | 2026-05-04 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00135_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00135_VMM1 | 2026-05-04 | QC Accepted |  | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00135_RR | 2026-05-04 | No Violations | 05-08-2026 | [5 empty] | 2026_ET-00135_VER | 2026-05-04 | Uploaded to S123 | 06-01-2026 | 2026-05-07 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-SERRANO NO.2_ET-00135 |  |  | Yes |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DELANO-MARIPOSA-WELLGEN | ET-00137 | 2026_ET-00137 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 9.5319 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00137_ACQPKG | 2026_ET-00137_GSPKG | Submitted | 2026_ET-00137_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00137_GCPR | 2025-12-08 | Historical | 2026_ET-00137_ACQ | In Progress | 2026_ET-00137_FR |  | Not Started | 2026_ET-00137_RWR | Not Started |  | 2026_ET-00137_CLAZ |  | Not Started |  |  |  | 2026_ET-00137_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00137_WR |  |  | Not Started |  |  |  | 2026_ET-00137_VMLAZ |  | Not Started |  |  |  | 2026_ET-00137_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00137_RR |  | Not Started | [6 empty] | 2026_ET-00137_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | DELANO-MARIPOSA-WELLGEN_ET-00137 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MACNEIL-SAN FERNANDO | ET-00146 | 2026_ET-00146 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 9.9053 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00146_ACQPKG | 2026_ET-00146_GSPKG | Submitted | 2026_ET-00146_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00146_GCPR | 2025-12-08 | Historical | 2026_ET-00146_ACQ | Submitted | 2026_ET-00146_FR | 2026-05-22 | Submitted | 2026_ET-00146_RWR | Submitted | 2026-05-22 | 2026_ET-00146_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00146_PROCPKG | In Progress | SCE | 2026_ET-00146_WR |  |  | Not Started |  |  |  | 2026_ET-00146_VMLAZ |  | Not Started |  |  |  | 2026_ET-00146_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00146_RR |  | Not Started | [6 empty] | 2026_ET-00146_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | MACNEIL-SAN FERNANDO_ET-00146 |  |  | No |  | Helicopter |  |  | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NEWHALL-SAN FERNANDO-SUNSHINE | ET-00147 | 2026_ET-00147 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.3859 | 7.4455 | 65 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-03-04 | 04-23-2026 | 04-08-2026 |  | 2026_ET-00147_ACQPKG | 2026_ET-00147_GSPKG | Submitted | 2026_ET-00147_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00147_GCPR | 2025-12-08 | Historical | 2026_ET-00147_ACQ | QC Accepted | 2026_ET-00147_FR | 2026-04-02 | Submitted | 2026_ET-00147_RWR | Submitted | 2026-04-02 | 2026_ET-00147_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00147_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00147_WR | 2026-05-14 | 05-23-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00147_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00147_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00147_RR | 2026-05-06 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 4 | 2026-05-07 | 0 | 4 | 2026_ET-00147_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | NEWHALL-SAN FERNANDO-SUNSHINE_ET-00147 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:25 PST ¦ 2026-03-15 11:57 PDT | 030426 | 20260315 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NATURAL-SUNSHINE | ET-00148 | 2026_ET-00148 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.8584 | 3.8584 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-04 | 04-21-2026 | 04-08-2026 |  | 2026_ET-00148_ACQPKG | 2026_ET-00148_GSPKG | Submitted | 2026_ET-00148_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00148_GCPR | 2025-12-08 | Historical | 2026_ET-00148_ACQ | QC Accepted | 2026_ET-00148_FR | 2026-04-02 | Submitted | 2026_ET-00148_RWR | Submitted | 2026-04-02 | 2026_ET-00148_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00148_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00148_WR | 2026-05-06 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00148_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00148_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00148_RR | 2026-05-06 | No Violations | 05-14-2026 |  | 0 |  |  |  | 2026_ET-00148_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | NATURAL-SUNSHINE_ET-00148 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 11:51 PST ¦ 2026-03-15 11:50 PDT | 030426 | 20260315 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ANTELOPE-ANAVRDE-LTTLE ROCK-PALMDLE | ET-00150 | 2026_ET-00150 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.9683 | 0.31089 | 16 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-21 | 05-07-2026 | 04-17-2026 |  | 2026_ET-00150_ACQPKG | 2026_ET-00150_GSPKG | Submitted | 2026_ET-00150_GS | 2025-10-17 | Field Complete | 2026_ET-00150_GCPR | 2025-12-08 | Submitted | 2026_ET-00150_ACQ | QC Accepted | 2026_ET-00150_FR | 2026-03-16 | Submitted | 2026_ET-00150_RWR | Submitted | 2026-03-16 | 2026_ET-00150_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-00150_PROCPKG | In Progress | All Good - Complete | 2026_ET-00150_WR |  | 06-06-2026 | In Progress |  |  |  | 2026_ET-00150_VMLAZ |  | In Progress |  |  |  | 2026_ET-00150_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00150_RR |  | In Progress | [6 empty] | 2026_ET-00150_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE ANTELOPE-ANAVRDE-LTTLE ROCK-PALMDLE_ET-00150 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-21 09:34 PST ¦ 2026-02-21 10:03 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-PLAINVIEW | ET-00159 | 2026_ET-00159 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 0.039529 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00159_ACQPKG | 2026_ET-00159_GSPKG | Submitted | 2026_ET-00159_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00159_GCPR | 2025-12-08 | Historical | 2026_ET-00159_ACQ | In Progress | 2026_ET-00159_FR |  | Not Started | 2026_ET-00159_RWR | Not Started |  | 2026_ET-00159_CLAZ |  | Not Started |  |  |  | 2026_ET-00159_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00159_WR |  |  | Not Started |  |  |  | 2026_ET-00159_VMLAZ |  | Not Started |  |  |  | 2026_ET-00159_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00159_RR |  | Not Started | [6 empty] | 2026_ET-00159_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | ANTELOPE-PLAINVIEW_ET-00159 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOWNS-INYOKERN | ET-00163 | 2026_ET-00163 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 8.0672 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Weather Delay |  |  |  |  | 2026_ET-00163_ACQPKG | 2026_ET-00163_GSPKG | In Progress | 2026_ET-00163_GS |  | Not Started | 2026_ET-00163_GCPR |  | Not Started | 2026_ET-00163_ACQ | In Progress | 2026_ET-00163_FR |  | Not Started | 2026_ET-00163_RWR | Not Started |  | 2026_ET-00163_CLAZ |  | Not Started |  |  |  | 2026_ET-00163_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00163_WR |  |  | Not Started |  |  |  | 2026_ET-00163_VMLAZ |  | Not Started |  |  |  | 2026_ET-00163_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00163_RR |  | Not Started | [6 empty] | 2026_ET-00163_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | DOWNS-INYOKERN_ET-00163 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COOLWATER-KRAMER | ET-00173 | 2026_ET-00173 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-30-2025 | 11-29-2025 | Late | 18 | Transmission | 44.1294 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 12-29-2025 | Flown | 2025-12-21 | 05-22-2026 | 05-22-2026 |  | 2026_ET-00173_ACQPKG | 2026_ET-00173_GSPKG | Submitted | 2026_ET-00173_GS | 2026-01-23 | Field Complete | 2026_ET-00173_GCPR | 2026-01-30 | Submitted | 2026_ET-00173_ACQ | QC Accepted | 2026_ET-00173_FR |  | Not Started | 2026_ET-00173_RWR | Submitted | 2026-05-05 | 2026_ET-00173_CLAZ | 2026-05-18 | QC Accepted | 06-01-2026 | 2026-05-22 | 1 | 2026_ET-00173_PROCPKG | In Progress | All Good - Complete | 2026_ET-00173_WR |  | 06-21-2026 | Not Started |  |  |  | 2026_ET-00173_VMLAZ |  | Not Started |  |  |  | 2026_ET-00173_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00173_RR |  | Not Started | [6 empty] | 2026_ET-00173_VER |  | Not Started | [7 empty] | Projected Late | Projected Late | Completed Late - Program | COOLWATER-KRAMER_ET-00173 |  |  | Yes |  |  | BARSTOW | 72 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIDWAY-WHIRLWIND | ET-00194 | 2026_ET-00194 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 21.0852 | 20.1461 | 96 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-25 | 04-24-2026 | 04-21-2026 |  | 2026_ET-00194_ACQPKG | 2026_ET-00194_GSPKG | Submitted | 2026_ET-00194_GS | 2025-10-17 | Field Complete | 2026_ET-00194_GCPR | 2025-12-08 | Submitted | 2026_ET-00194_ACQ | QC Accepted | 2026_ET-00194_FR | 2026-03-16 | Submitted | 2026_ET-00194_RWR | Submitted | 2026-03-16 | 2026_ET-00194_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-00194_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00194_WR | 2026-05-13 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-14 | 0 | 2026_ET-00194_VMLAZ | 2026-05-12 | QC Accepted | 06-01-2026 | 2026-05-12 |  | 2026_ET-00194_VMM1 | 2026-05-13 | QC Accepted |  | 06-01-2026 | 2026-05-14 |  | 2026_ET-00194_RR | 2026-05-13 | No Violations | 05-15-2026 | [5 empty] | 2026_ET-00194_VER | 2026-05-13 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MIDWAY-WHIRLWIND_ET-00194 |  |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC |  |  |  |  | Metadata issue. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
KRAMER-ROADWAY | ET-00199 | 2026_ET-00199 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 29.887 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 01-01-2026 | Flown |  |  |  |  | 2026_ET-00199_ACQPKG | 2026_ET-00199_GSPKG | In Progress | 2026_ET-00199_GS |  | Not Started | 2026_ET-00199_GCPR |  | Not Started | 2026_ET-00199_ACQ | In Progress | 2026_ET-00199_FR |  | Not Started | 2026_ET-00199_RWR | Not Started |  | 2026_ET-00199_CLAZ |  | Not Started |  |  |  | 2026_ET-00199_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00199_WR |  |  | Not Started |  |  |  | 2026_ET-00199_VMLAZ |  | Not Started |  |  |  | 2026_ET-00199_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00199_RR |  | Not Started | [6 empty] | 2026_ET-00199_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-ROADWAY_ET-00199 |  |  | No |  |  | VICTORVILLE | 73 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-SENTINEL | ET-00204 | 2026_ET-00204 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.40401 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-20 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00204_ACQPKG | 2026_ET-00204_GSPKG | Submitted | 2026_ET-00204_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00204_GCPR | 2025-12-08 | Historical | 2026_ET-00204_ACQ | QC Accepted | 2026_ET-00204_FR | 2026-05-03 | Submitted | 2026_ET-00204_RWR | Submitted | 2026-05-03 | 2026_ET-00204_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00204_PROCPKG | In Progress | All Good - Complete | 2026_ET-00204_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00204_VMLAZ |  | In Progress |  |  |  | 2026_ET-00204_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00204_RR |  | In Progress | [6 empty] | 2026_ET-00204_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | DEVERS-SENTINEL_ET-00204 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-OCEANVIEW-TRASK | ET-00225 | 2026_ET-00225 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 7.2548 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00225_ACQPKG | 2026_ET-00225_GSPKG | Submitted | 2026_ET-00225_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00225_GCPR | 2025-12-08 | Historical | 2026_ET-00225_ACQ | In Progress | 2026_ET-00225_FR |  | Not Started | 2026_ET-00225_RWR | Not Started |  | 2026_ET-00225_CLAZ |  | Not Started |  |  |  | 2026_ET-00225_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00225_WR |  |  | Not Started |  |  |  | 2026_ET-00225_VMLAZ |  | Not Started |  |  |  | 2026_ET-00225_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00225_RR |  | Not Started | [6 empty] | 2026_ET-00225_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BARRE-OCEANVIEW-TRASK_ET-00225 | Done |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VILLA PARK-PAPER-ORANGE | ET-00231 | 2026_ET-00231 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.45917 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-02-03 | 04-14-2026 | 04-08-2026 |  | 2026_ET-00231_ACQPKG | 2026_ET-00231_GSPKG | Submitted | 2026_ET-00231_GS | 2025-12-08 | Field Complete | 2026_ET-00231_GCPR | 2026-04-02 | Submitted | 2026_ET-00231_ACQ | QC Accepted | 2026_ET-00231_FR | 2026-04-02 | Submitted | 2026_ET-00231_RWR | Submitted | 2026-04-02 | 2026_ET-00231_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00231_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00231_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-00231_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-00231_VMM1 | 2026-05-14 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-00231_RR | 2026-05-07 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-00231_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE VILLA PARK-PAPER-ORANGE_ET-00231 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-01-30 08:57 PST ¦ 2026-03-03 10:52 PST | 020326 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BUCK BLVD.-JULIAN HINDS | ET-00245 | 2026_ET-00245 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.12271 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-21 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00245_ACQPKG | 2026_ET-00245_GSPKG | Submitted | 2026_ET-00245_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00245_GCPR | 2025-12-08 | Historical | 2026_ET-00245_ACQ | QC Accepted | 2026_ET-00245_FR | 2026-05-03 | Submitted | 2026_ET-00245_RWR | Submitted | 2026-05-03 | 2026_ET-00245_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00245_PROCPKG | In Progress | All Good - Complete | 2026_ET-00245_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00245_VMLAZ |  | In Progress |  |  |  | 2026_ET-00245_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00245_RR |  | In Progress | [6 empty] | 2026_ET-00245_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | BUCK BLVD.-JULIAN HINDS_ET-00245 | Done |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COOLWATER-TIEFORT | ET-00257 | 2026_ET-00257 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 29.5586 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 01-31-2026 | Flown | 2026-05-09 |  |  |  | 2026_ET-00257_ACQPKG | 2026_ET-00257_GSPKG | Submitted | 2026_ET-00257_GS | 2026-01-23 | Field Complete | 2026_ET-00257_GCPR | 2026-01-30 | Submitted | 2026_ET-00257_ACQ | In Progress | 2026_ET-00257_FR |  | Not Started | 2026_ET-00257_RWR | Not Started |  | 2026_ET-00257_CLAZ |  | QC Accepted |  | 2026-05-20 |  | 2026_ET-00257_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00257_WR |  |  | Not Started |  |  |  | 2026_ET-00257_VMLAZ |  | Not Started |  |  |  | 2026_ET-00257_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00257_RR |  | Not Started | [6 empty] | 2026_ET-00257_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | COOLWATER-TIEFORT_ET-00257 |  |  | No |  |  | BARSTOW | 72 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COOLWATER-SANDLOT | ET-00262 | 2026_ET-00262 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-30-2025 | 11-29-2025 | Late | 18 | Transmission | 29.9457 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 12-29-2025 | Flown | 2025-12-21 | 05-05-2026 | 05-05-2026 |  | 2026_ET-00262_ACQPKG | 2026_ET-00262_GSPKG | Submitted | 2026_ET-00262_GS | 2026-01-23 | Field Complete | 2026_ET-00262_GCPR | 2026-01-30 | Submitted | 2026_ET-00262_ACQ | QC Accepted | 2026_ET-00262_FR |  | Not Started | 2026_ET-00262_RWR | Submitted | 2026-05-05 | 2026_ET-00262_CLAZ | 2026-02-03 | QC Accepted | 02-17-2026 | 2026-04-17 | 2 | 2026_ET-00262_PROCPKG | In Progress | All Good - Complete | 2026_ET-00262_WR |  | 06-04-2026 | In Progress |  |  |  | 2026_ET-00262_VMLAZ | 2026-03-16 | QC Accepted | 05-01-2026 | 2026-03-20 | 0 | 2026_ET-00262_VMM1 | 2026-03-23 | QC Accepted |  | 05-01-2026 | 2026-04-02 | 1 | 2026_ET-00262_RR | 2026-03-10 | No Violations | 04-03-2026 |  | 0 |  |  |  | 2026_ET-00262_VER | 2026-04-17 | Uploaded to S123 | 05-01-2026 | 2026-05-01 | 1 |  |  |  |  | Completed Late - Program | Projected Late | Completed Late - Program | COOLWATER-SANDLOT_ET-00262 |  |  | Yes |  |  | BARSTOW | 72 | UNK | 2025-12-20 13:25 PST ¦ 2025-12-21 13:09 PST | 122125 | 20251221 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A | [7 empty] | 1
IDLE DEVERS-JULIAN HINDS | ET-00267 | 2026_ET-00267 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 6.2001 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-02-07 | 04-24-2026 | 04-08-2026 |  | 2026_ET-00267_ACQPKG | 2026_ET-00267_GSPKG | Submitted | 2026_ET-00267_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00267_GCPR | 2025-12-08 | Historical | 2026_ET-00267_ACQ | QC Accepted | 2026_ET-00267_FR | 2026-04-02 | Submitted | 2026_ET-00267_RWR | Submitted | 2026-04-02 | 2026_ET-00267_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00267_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00267_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00267_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00267_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00267_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00267_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE DEVERS-JULIAN HINDS_ET-00267 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-HOMART | ET-00270 | 2026_ET-00270 |  | 1 | 2026 | Nov 01, 2026 | 115 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 2.4003 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00270_ACQPKG | 2026_ET-00270_GSPKG | Submitted | 2026_ET-00270_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00270_GCPR | 2025-12-08 | Historical | 2026_ET-00270_ACQ | In Progress | 2026_ET-00270_FR |  | Not Started | 2026_ET-00270_RWR | Not Started |  | 2026_ET-00270_CLAZ |  | Not Started |  |  |  | 2026_ET-00270_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00270_WR |  |  | Not Started |  |  |  | 2026_ET-00270_VMLAZ |  | Not Started |  |  |  | 2026_ET-00270_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00270_RR |  | Not Started | [6 empty] | 2026_ET-00270_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CALECTRIC-HOMART_ET-00270 | Done |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-SANDLOT | ET-00276 | 2026_ET-00276 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 14.2435 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 01-01-2026 | Flown | 2025-12-20 | 05-05-2026 | 05-05-2026 |  | 2026_ET-00276_ACQPKG | 2026_ET-00276_GSPKG | Submitted | 2026_ET-00276_GS | 2026-01-23 | Field Complete | 2026_ET-00276_GCPR | 2026-01-30 | Submitted | 2026_ET-00276_ACQ | QC Accepted | 2026_ET-00276_FR |  | Not Started | 2026_ET-00276_RWR | Submitted | 2026-05-05 | 2026_ET-00276_CLAZ |  | QC Accepted |  | 2026-02-04 |  | 2026_ET-00276_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00276_WR | 2026-03-24 | 06-04-2026 | QC Accepted | 04-07-2026 | 2026-04-15 | 2 | 2026_ET-00276_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-00276_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00276_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00276_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-26 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Projected On Time | KRAMER-SANDLOT_ET-00276 |  |  | Yes |  |  | RIDGECREST | 86 | UNK | 2025-12-20 12:49 PST ¦ 2025-12-21 10:42 PST | 122125 | 20251221 | Attribute errors | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
IDLE DEVERS-SANTA ROSA | ET-00279 | 2026_ET-00279 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.2168 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00279_ACQPKG | 2026_ET-00279_GSPKG | Submitted | 2026_ET-00279_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00279_GCPR | 2025-12-08 | Historical | 2026_ET-00279_ACQ | In Progress | 2026_ET-00279_FR |  | Not Started | 2026_ET-00279_RWR | Not Started |  | 2026_ET-00279_CLAZ |  | Not Started |  |  |  | 2026_ET-00279_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00279_WR |  |  | Not Started |  |  |  | 2026_ET-00279_VMLAZ |  | Not Started |  |  |  | 2026_ET-00279_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00279_RR |  | Not Started | [6 empty] | 2026_ET-00279_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE DEVERS-SANTA ROSA_ET-00279 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
REDLANDS-TENNESSEE-YUCAIPA | ET-00281 | 2026_ET-00281 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 9.6408 | 3.9266 | 41 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00281_ACQPKG | 2026_ET-00281_GSPKG | Submitted | 2026_ET-00281_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00281_GCPR | 2025-12-08 | Historical | 2026_ET-00281_ACQ | In Progress | 2026_ET-00281_FR |  | Not Started | 2026_ET-00281_RWR | Not Started |  | 2026_ET-00281_CLAZ |  | Not Started |  |  |  | 2026_ET-00281_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00281_WR |  |  | Not Started |  |  |  | 2026_ET-00281_VMLAZ |  | Not Started |  |  |  | 2026_ET-00281_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00281_RR |  | Not Started | [6 empty] | 2026_ET-00281_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | REDLANDS-TENNESSEE-YUCAIPA_ET-00281 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VISTA-REDLANDS-TENNESSEE-YUCIAIPA | ET-00282 | 2026_ET-00282 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.6534 | 2.0538 | 77 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00282_ACQPKG | 2026_ET-00282_GSPKG | Submitted | 2026_ET-00282_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00282_GCPR | 2025-12-08 | Historical | 2026_ET-00282_ACQ | In Progress | 2026_ET-00282_FR |  | Not Started | 2026_ET-00282_RWR | Not Started |  | 2026_ET-00282_CLAZ |  | Not Started |  |  |  | 2026_ET-00282_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00282_WR |  |  | Not Started |  |  |  | 2026_ET-00282_VMLAZ |  | Not Started |  |  |  | 2026_ET-00282_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00282_RR |  | Not Started | [6 empty] | 2026_ET-00282_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE VISTA-REDLANDS-TENNESSEE-YUCIAIPA_ET-00282 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALBA-SANDLOT | ET-00284 | 2026_ET-00284 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 0.052774 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 01-01-2026 | Flown | 2025-12-21 |  |  |  | 2026_ET-00284_ACQPKG | 2026_ET-00284_GSPKG | In Progress | 2026_ET-00284_GS |  | Not Started | 2026_ET-00284_GCPR |  | Not Started | 2026_ET-00284_ACQ | QC Accepted | 2026_ET-00284_FR |  | Not Started | 2026_ET-00284_RWR | Submitted | 2026-05-05 | 2026_ET-00284_CLAZ |  | QC Accepted |  | 2026-02-04 |  | 2026_ET-00284_PROCPKG | QC Accepted | ACQ Vendor | 2026_ET-00284_WR | 2026-03-24 |  | QC Accepted | 04-07-2026 | 2026-04-15 | 2 | 2026_ET-00284_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-00284_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00284_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00284_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-23 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Projected On Time | ALBA-SANDLOT_ET-00284 | Done |  | Yes |  |  | BARSTOW | 72 | UNK | 2025-12-20 13:25 PST ¦ 2025-12-21 10:41 PST | 122025 | 20251221 | Attribute errors | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
HIGHGROVE-PEPPER | ET-00292 | 2026_ET-00292 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.7588 | 3.5254 | 52 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00292_ACQPKG | 2026_ET-00292_GSPKG | In Progress | 2026_ET-00292_GS |  | Not Started | 2026_ET-00292_GCPR |  | Not Started | 2026_ET-00292_ACQ | In Progress | 2026_ET-00292_FR |  | Not Started | 2026_ET-00292_RWR | Not Started |  | 2026_ET-00292_CLAZ |  | Not Started |  |  |  | 2026_ET-00292_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00292_WR |  |  | Not Started |  |  |  | 2026_ET-00292_VMLAZ |  | Not Started |  |  |  | 2026_ET-00292_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00292_RR |  | Not Started | [6 empty] | 2026_ET-00292_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | HIGHGROVE-PEPPER_ET-00292 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOSHEN-HANFORD-LAUREL | ET-00293 | 2026_ET-00293 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 19.2627 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00293_ACQPKG | 2026_ET-00293_GSPKG | Submitted | 2026_ET-00293_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00293_GCPR | 2025-12-08 | Historical | 2026_ET-00293_ACQ | In Progress | 2026_ET-00293_FR |  | Not Started | 2026_ET-00293_RWR | Not Started |  | 2026_ET-00293_CLAZ |  | Not Started |  |  |  | 2026_ET-00293_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00293_WR |  |  | Not Started |  |  |  | 2026_ET-00293_VMLAZ |  | Not Started |  |  |  | 2026_ET-00293_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00293_RR |  | Not Started | [6 empty] | 2026_ET-00293_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | GOSHEN-HANFORD-LAUREL_ET-00293 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VISTA-NELSON | ET-00295 | 2026_ET-00295 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.080903 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00295_ACQPKG | 2026_ET-00295_GSPKG | Submitted | 2026_ET-00295_GS | 2025-12-08 | Field Complete | 2026_ET-00295_GCPR | 2026-05-22 | Submitted | 2026_ET-00295_ACQ | Submitted | 2026_ET-00295_FR | 2026-05-22 | Submitted | 2026_ET-00295_RWR | Submitted | 2026-05-22 | 2026_ET-00295_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00295_PROCPKG | In Progress | SCE | 2026_ET-00295_WR |  |  | Not Started |  |  |  | 2026_ET-00295_VMLAZ |  | Not Started |  |  |  | 2026_ET-00295_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00295_RR |  | Not Started | [6 empty] | 2026_ET-00295_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE VISTA-NELSON_ET-00295 |  |  | No |  | Helicopter | MENIFEE | 77 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-SAVAGE NO.2 | ET-00311 | 2026_ET-00311 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.4491 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-26 | 04-02-2026 | Flown | 2026-02-23 | 04-26-2026 | 04-24-2026 |  | 2026_ET-00311_ACQPKG | 2026_ET-00311_GSPKG | Submitted | 2026_ET-00311_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00311_GCPR | 2025-12-08 | Historical | 2026_ET-00311_ACQ | QC Accepted | 2026_ET-00311_FR | 2026-03-16 | Submitted | 2026_ET-00311_RWR | Submitted | 2026-03-16 | 2026_ET-00311_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-24 | 1 | 2026_ET-00311_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00311_WR | 2026-05-10 | 05-26-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-00311_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-00311_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-00311_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-00311_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | VICTOR-SAVAGE NO.2_ET-00311 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2026-02-23 09:25 PST ¦ 2026-02-23 09:45 PST | 022326 | 20260223 |  | Metadata issue. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
GOLETA-VEGAS | ET-00324 | 2026_ET-00324 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.4474 | 6.2615 | 84 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-18 | 05-03-2026 | Flown | 2026-03-14 | 05-18-2026 | 05-11-2026 |  | 2026_ET-00324_ACQPKG | 2026_ET-00324_GSPKG | Submitted | 2026_ET-00324_GS | 2026-01-31 | Field Complete | 2026_ET-00324_GCPR | 2026-05-03 | Submitted | 2026_ET-00324_ACQ | QC Accepted | 2026_ET-00324_FR | 2026-05-03 | Submitted | 2026_ET-00324_RWR | Submitted | 2026-05-03 | 2026_ET-00324_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00324_PROCPKG | In Progress | All Good - Complete | 2026_ET-00324_WR |  | 06-17-2026 | In Progress |  |  |  | 2026_ET-00324_VMLAZ |  | In Progress |  |  |  | 2026_ET-00324_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00324_RR |  | In Progress | [6 empty] | 2026_ET-00324_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | GOLETA-VEGAS_ET-00324 |  |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-SAN MARCOS | ET-00330 | 2026_ET-00330 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 10.3338 | 10.3338 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-18 | 05-03-2026 | Flown | 2026-03-14 | 05-18-2026 | 05-11-2026 |  | 2026_ET-00330_ACQPKG | 2026_ET-00330_GSPKG | Submitted | 2026_ET-00330_GS | 2026-01-31 | Field Complete | 2026_ET-00330_GCPR | 2026-05-03 | Submitted | 2026_ET-00330_ACQ | QC Accepted | 2026_ET-00330_FR | 2026-05-03 | Submitted | 2026_ET-00330_RWR | Submitted | 2026-05-03 | 2026_ET-00330_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00330_PROCPKG | In Progress | All Good - Complete | 2026_ET-00330_WR |  | 06-17-2026 | In Progress |  |  |  | 2026_ET-00330_VMLAZ |  | In Progress |  |  |  | 2026_ET-00330_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00330_RR |  | In Progress | [6 empty] | 2026_ET-00330_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | GOLETA-SAN MARCOS_ET-00330 |  |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA BARBARA-SAN MARCOS | ET-00336 | 2026_ET-00336 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 10.6678 | 10.1008 | 95 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-14 |  | 05-11-2026 |  | 2026_ET-00336_ACQPKG | 2026_ET-00336_GSPKG | Submitted | 2026_ET-00336_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00336_GCPR | 2025-12-08 | Historical | 2026_ET-00336_ACQ | QC Accepted | 2026_ET-00336_FR | 2026-05-03 | Submitted | 2026_ET-00336_RWR | Submitted | 2026-05-03 | 2026_ET-00336_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00336_PROCPKG | In Progress | SCE | 2026_ET-00336_WR |  |  | In Progress |  |  |  | 2026_ET-00336_VMLAZ |  | In Progress |  |  |  | 2026_ET-00336_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00336_RR |  | In Progress | [6 empty] | 2026_ET-00336_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | SANTA BARBARA-SAN MARCOS_ET-00336 |  |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-SANTA BARBARA | ET-00339 | 2026_ET-00339 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 17.0864 | 16.378 | 96 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-01-06 |  | 05-11-2026 |  | 2026_ET-00339_ACQPKG | 2026_ET-00339_GSPKG | Submitted | 2026_ET-00339_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00339_GCPR | 2025-12-08 | Historical | 2026_ET-00339_ACQ | QC Accepted | 2026_ET-00339_FR | 2026-05-03 | Submitted | 2026_ET-00339_RWR | Submitted | 2026-05-03 | 2026_ET-00339_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00339_PROCPKG | In Progress | SCE | 2026_ET-00339_WR |  |  | In Progress |  |  |  | 2026_ET-00339_VMLAZ |  | In Progress |  |  |  | 2026_ET-00339_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00339_RR |  | In Progress | [6 empty] | 2026_ET-00339_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | GOLETA-SANTA BARBARA_ET-00339 |  |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CRATER-LATIGO | ET-00343 | 2026_ET-00343 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 8.9188 | 8.9188 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-11 |  | 05-11-2026 |  | 2026_ET-00343_ACQPKG | 2026_ET-00343_GSPKG | Submitted | 2026_ET-00343_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00343_GCPR | 2025-12-08 | Historical | 2026_ET-00343_ACQ | QC Accepted | 2026_ET-00343_FR | 2026-05-03 | Submitted | 2026_ET-00343_RWR | Submitted | 2026-05-03 | 2026_ET-00343_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00343_PROCPKG | In Progress | SCE | 2026_ET-00343_WR |  |  | In Progress |  |  |  | 2026_ET-00343_VMLAZ |  | In Progress |  |  |  | 2026_ET-00343_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00343_RR |  | In Progress | [6 empty] | 2026_ET-00343_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CRATER-LATIGO_ET-00343 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CRATER-MALIBU | ET-00345 | 2026_ET-00345 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.6956 | 3.6956 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-10 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00345_ACQPKG | 2026_ET-00345_GSPKG | Submitted | 2026_ET-00345_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00345_GCPR | 2025-12-08 | Historical | 2026_ET-00345_ACQ | QC Accepted | 2026_ET-00345_FR | 2026-05-03 | Submitted | 2026_ET-00345_RWR | Submitted | 2026-05-03 | 2026_ET-00345_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00345_PROCPKG | In Progress | All Good - Complete | 2026_ET-00345_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00345_VMLAZ |  | In Progress |  |  |  | 2026_ET-00345_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00345_RR |  | In Progress | [6 empty] | 2026_ET-00345_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE CRATER-MALIBU_ET-00345 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-JERSEY | ET-00347 | 2026_ET-00347 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.567 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-11-2026 |  | 2026_ET-00347_ACQPKG | 2026_ET-00347_GSPKG | Submitted | 2026_ET-00347_GS | 2026-01-31 | Field Complete | 2026_ET-00347_GCPR | 2026-05-03 | Submitted | 2026_ET-00347_ACQ | QC Accepted | 2026_ET-00347_FR | 2026-05-03 | Submitted | 2026_ET-00347_RWR | Submitted | 2026-05-03 | 2026_ET-00347_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00347_PROCPKG | In Progress | SCE | 2026_ET-00347_WR |  |  | In Progress |  |  |  | 2026_ET-00347_VMLAZ |  | In Progress |  |  |  | 2026_ET-00347_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00347_RR |  | In Progress | [6 empty] | 2026_ET-00347_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIGHTHIPE-JERSEY_ET-00347 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO-SAWTELLE | ET-00356 | 2026_ET-00356 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.4688 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00356_ACQPKG | 2026_ET-00356_GSPKG | Submitted | 2026_ET-00356_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00356_GCPR | 2025-12-08 | Historical | 2026_ET-00356_ACQ | In Progress | 2026_ET-00356_FR |  | Not Started | 2026_ET-00356_RWR | Not Started |  | 2026_ET-00356_CLAZ |  | Not Started |  |  |  | 2026_ET-00356_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00356_WR |  |  | Not Started |  |  |  | 2026_ET-00356_VMLAZ |  | Not Started |  |  |  | 2026_ET-00356_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00356_RR |  | Not Started | [6 empty] | 2026_ET-00356_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | COLORADO-SAWTELLE_ET-00356 |  |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MACNEIL-NEWHALL-SAN FERNANDO | ET-00365 | 2026_ET-00365 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 20.5737 | 6.6956 | 33 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00365_ACQPKG | 2026_ET-00365_GSPKG | Submitted | 2026_ET-00365_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00365_GCPR | 2025-12-08 | Historical | 2026_ET-00365_ACQ | Submitted | 2026_ET-00365_FR | 2026-05-22 | Submitted | 2026_ET-00365_RWR | Submitted | 2026-05-22 | 2026_ET-00365_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00365_PROCPKG | In Progress | SCE | 2026_ET-00365_WR |  |  | Not Started |  |  |  | 2026_ET-00365_VMLAZ |  | Not Started |  |  |  | 2026_ET-00365_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00365_RR |  | Not Started | [6 empty] | 2026_ET-00365_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | MACNEIL-NEWHALL-SAN FERNANDO_ET-00365 |  |  | No |  | Helicopter | VALENCIA | 59 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-SAN BERNARDINO | ET-00397 | 2026_ET-00397 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 23.3656 | 9.4502 | 40 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-31 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00397_ACQPKG | 2026_ET-00397_GSPKG | Submitted | 2026_ET-00397_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00397_GCPR | 2025-12-08 | Historical | 2026_ET-00397_ACQ | QC Accepted | 2026_ET-00397_FR | 2026-04-02 | Submitted | 2026_ET-00397_RWR | Submitted | 2026-04-02 | 2026_ET-00397_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00397_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00397_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00397_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00397_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00397_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00397_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ETIWANDA-SAN BERNARDINO_ET-00397 |  |  | Yes |  |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN BERNARDINO-DEL ROSA-VISTA | ET-00411 | 2026_ET-00411 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 15.2542 | 0.37282 | 2 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00411_ACQPKG | 2026_ET-00411_GSPKG | Submitted | 2026_ET-00411_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00411_GCPR | 2025-12-08 | Historical | 2026_ET-00411_ACQ | In Progress | 2026_ET-00411_FR |  | Not Started | 2026_ET-00411_RWR | Not Started |  | 2026_ET-00411_CLAZ |  | Not Started |  |  |  | 2026_ET-00411_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00411_WR |  |  | Not Started |  |  |  | 2026_ET-00411_VMLAZ |  | Not Started |  |  |  | 2026_ET-00411_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00411_RR |  | Not Started | [6 empty] | 2026_ET-00411_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SAN BERNARDINO-DEL ROSA-VISTA_ET-00411 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VISTA-COLTON-WHEEL | ET-00412 | 2026_ET-00412 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 0.46206 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00412_ACQPKG | 2026_ET-00412_GSPKG | Submitted | 2026_ET-00412_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00412_GCPR | 2025-12-08 | Historical | 2026_ET-00412_ACQ | In Progress | 2026_ET-00412_FR |  | Not Started | 2026_ET-00412_RWR | Not Started |  | 2026_ET-00412_CLAZ |  | Not Started |  |  |  | 2026_ET-00412_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00412_WR |  |  | Not Started |  |  |  | 2026_ET-00412_VMLAZ |  | Not Started |  |  |  | 2026_ET-00412_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00412_RR |  | Not Started | [6 empty] | 2026_ET-00412_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE VISTA-COLTON-WHEEL_ET-00412 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN BERNARDINO-REDLANDS-TENNESSEE | ET-00428 | 2026_ET-00428 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 10.7872 | 2.1963 | 20 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00428_ACQPKG | 2026_ET-00428_GSPKG | Submitted | 2026_ET-00428_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00428_GCPR | 2025-12-08 | Historical | 2026_ET-00428_ACQ | In Progress | 2026_ET-00428_FR |  | Not Started | 2026_ET-00428_RWR | Not Started |  | 2026_ET-00428_CLAZ |  | Not Started |  |  |  | 2026_ET-00428_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00428_WR |  |  | Not Started |  |  |  | 2026_ET-00428_VMLAZ |  | Not Started |  |  |  | 2026_ET-00428_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00428_RR |  | Not Started | [6 empty] | 2026_ET-00428_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SAN BERNARDINO-REDLANDS-TENNESSEE_ET-00428 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE MESA-SYLMAR | ET-00429 | 2026_ET-00429 |  | 1 | 2026 | Sep 01, 2026 | 220 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 5.7977 | 5.7977 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-15-2026 |  | 2026_ET-00429_ACQPKG | 2026_ET-00429_GSPKG | Submitted | 2026_ET-00429_GS | 2025-10-15 | Field Complete | 2026_ET-00429_GCPR | 2025-12-08 | Submitted | 2026_ET-00429_ACQ | QC Accepted | 2026_ET-00429_FR | 2026-05-08 | Submitted | 2026_ET-00429_RWR | Submitted | 2026-05-08 | 2026_ET-00429_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-00429_PROCPKG | In Progress | SCE | 2026_ET-00429_WR |  |  | Not Started |  |  |  | 2026_ET-00429_VMLAZ |  | Not Started |  |  |  | 2026_ET-00429_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00429_RR |  | Not Started | [6 empty] | 2026_ET-00429_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | IDLE MESA-SYLMAR_ET-00429 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-CLARK-DEL AMO | ET-00430 | 2026_ET-00430 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.953 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-13-2026 |  | 2026_ET-00430_ACQPKG | 2026_ET-00430_GSPKG | Submitted | 2026_ET-00430_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00430_GCPR | 2025-12-08 | Historical | 2026_ET-00430_ACQ | QC Accepted | 2026_ET-00430_FR | 2026-05-03 | Submitted | 2026_ET-00430_RWR | Submitted | 2026-05-03 | 2026_ET-00430_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-00430_PROCPKG | In Progress | SCE | 2026_ET-00430_WR |  |  | In Progress |  |  |  | 2026_ET-00430_VMLAZ |  | In Progress |  |  |  | 2026_ET-00430_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00430_RR |  | In Progress | [6 empty] | 2026_ET-00430_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ALAMITOS-CLARK-DEL AMO_ET-00430 | Done |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CYPRESS NO.2 | ET-00431 | 2026_ET-00431 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 3.7878 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00431_ACQPKG | 2026_ET-00431_GSPKG | Submitted | 2026_ET-00431_GS | 2025-12-08 | Field Complete | 2026_ET-00431_GCPR | 2026-05-22 | Submitted | 2026_ET-00431_ACQ | Submitted | 2026_ET-00431_FR | 2026-05-22 | Submitted | 2026_ET-00431_RWR | Submitted | 2026-05-22 | 2026_ET-00431_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00431_PROCPKG | In Progress | SCE | 2026_ET-00431_WR |  |  | Not Started |  |  |  | 2026_ET-00431_VMLAZ |  | Not Started |  |  |  | 2026_ET-00431_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00431_RR |  | Not Started | [6 empty] | 2026_ET-00431_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | DEL AMO-CYPRESS NO.2_ET-00431 |  |  | No |  | Helicopter | LONG BEACH | 46 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-CYPRESS NO.3 | ET-00432 | 2026_ET-00432 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 6.5016 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-11-2026 |  | 2026_ET-00432_ACQPKG | 2026_ET-00432_GSPKG | Submitted | 2026_ET-00432_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00432_GCPR | 2025-12-08 | Historical | 2026_ET-00432_ACQ | QC Accepted | 2026_ET-00432_FR | 2026-05-03 | Submitted | 2026_ET-00432_RWR | Submitted | 2026-05-03 | 2026_ET-00432_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00432_PROCPKG | In Progress | SCE | 2026_ET-00432_WR |  |  | In Progress |  |  |  | 2026_ET-00432_VMLAZ |  | In Progress |  |  |  | 2026_ET-00432_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00432_RR |  | In Progress | [6 empty] | 2026_ET-00432_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEL AMO-CYPRESS NO.3_ET-00432 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-HATHAWAY | ET-00433 | 2026_ET-00433 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.3935 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-21 | 05-03-2026 | Flown | 2026-03-02 | 05-21-2026 | 05-11-2026 |  | 2026_ET-00433_ACQPKG | 2026_ET-00433_GSPKG | Submitted | 2026_ET-00433_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00433_GCPR | 2025-12-08 | Historical | 2026_ET-00433_ACQ | QC Accepted | 2026_ET-00433_FR | 2026-05-03 | Submitted | 2026_ET-00433_RWR | Submitted | 2026-05-03 | 2026_ET-00433_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00433_PROCPKG | In Progress | All Good - Complete | 2026_ET-00433_WR |  | 06-20-2026 | In Progress |  |  |  | 2026_ET-00433_VMLAZ |  | In Progress |  |  |  | 2026_ET-00433_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00433_RR |  | In Progress | [6 empty] | 2026_ET-00433_VER |  | In Progress | [7 empty] | Projected Late | Completed On Time | Completed On Time - Program | ALAMITOS-HATHAWAY_ET-00433 | Done |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HUNTINGTON BEACH-WAVE | ET-00446 | 2026_ET-00446 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.1935 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-11-2026 |  | 2026_ET-00446_ACQPKG | 2026_ET-00446_GSPKG | Submitted | 2026_ET-00446_GS | 2026-01-31 | Field Complete | 2026_ET-00446_GCPR | 2026-05-03 | Submitted | 2026_ET-00446_ACQ | QC Accepted | 2026_ET-00446_FR | 2026-05-03 | Submitted | 2026_ET-00446_RWR | Submitted | 2026-05-03 | 2026_ET-00446_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00446_PROCPKG | In Progress | SCE | 2026_ET-00446_WR |  |  | In Progress |  |  |  | 2026_ET-00446_VMLAZ |  | In Progress |  |  |  | 2026_ET-00446_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00446_RR |  | In Progress | [6 empty] | 2026_ET-00446_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | HUNTINGTON BEACH-WAVE_ET-00446 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
TENNESSEE-YUCAIPA | ET-00451 | 2026_ET-00451 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.0716 | 2.6824 | 66 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00451_ACQPKG | 2026_ET-00451_GSPKG | Submitted | 2026_ET-00451_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00451_GCPR | 2025-12-08 | Historical | 2026_ET-00451_ACQ | In Progress | 2026_ET-00451_FR |  | Not Started | 2026_ET-00451_RWR | Not Started |  | 2026_ET-00451_CLAZ |  | Not Started |  |  |  | 2026_ET-00451_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00451_WR |  |  | Not Started |  |  |  | 2026_ET-00451_VMLAZ |  | Not Started |  |  |  | 2026_ET-00451_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00451_RR |  | Not Started | [6 empty] | 2026_ET-00451_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | TENNESSEE-YUCAIPA_ET-00451 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-LIGHTHIPE | ET-00461 | 2026_ET-00461 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 11.8787 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Proceed with Wire Temp at Ambient | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-02 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00461_ACQPKG | 2026_ET-00461_GSPKG | Submitted | 2026_ET-00461_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00461_GCPR | 2025-12-08 | Historical | 2026_ET-00461_ACQ | QC Accepted | 2026_ET-00461_FR | 2026-05-03 | Submitted | 2026_ET-00461_RWR | Submitted | 2026-05-03 | 2026_ET-00461_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00461_PROCPKG | In Progress | All Good - Complete | 2026_ET-00461_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00461_VMLAZ |  | In Progress |  |  |  | 2026_ET-00461_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00461_RR |  | In Progress | [6 empty] | 2026_ET-00461_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ALAMITOS-LIGHTHIPE_ET-00461 | Done |  | Yes |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BARRE-LA HABRA | ET-00467 | 2026_ET-00467 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.063677 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-02 | 04-14-2026 | 04-08-2026 |  | 2026_ET-00467_ACQPKG | 2026_ET-00467_GSPKG | Submitted | 2026_ET-00467_GS | 2025-12-08 | Field Complete | 2026_ET-00467_GCPR | 2026-04-02 | Submitted | 2026_ET-00467_ACQ | QC Accepted | 2026_ET-00467_FR | 2026-04-02 | Submitted | 2026_ET-00467_RWR | Submitted | 2026-04-02 | 2026_ET-00467_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00467_PROCPKG | Submitted | All Good - Complete | 2026_ET-00467_WR | 2026-05-14 | 05-14-2026 | Under QC | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00467_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00467_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00467_RR | 2026-05-07 | No Violations | 05-14-2026 |  | 0 |  |  |  | 2026_ET-00467_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE BARRE-LA HABRA_ET-00467 |  |  | No |  |  | FULLERTON | 48 | UNK | 2026-03-02 09:11 PST ¦ 2026-03-02 09:15 PST | 030226 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN ONOFRE-SERRANO | ET-00471 | 2026_ET-00471 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 01-13-2026 | 02-12-2026 | Late | 72 | Transmission | 40.0632 | 37.4559 | 93 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2026-01-12 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | Delay | Variable | SCE | Restricted Air Space | Upload Challenge | Access | Airspace restricitions, waiting on clearance from Camp Pendleton (Working with AirOps) | UploadChallenge | N/A | SCE Approved |  | 14 | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 03-14-2026 | Flown | 2026-03-10 | 04-29-2026 | 04-29-2026 |  | 2026_ET-00471_ACQPKG | 2026_ET-00471_GSPKG | Submitted | 2026_ET-00471_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00471_GCPR | 2025-12-08 | Historical | 2026_ET-00471_ACQ | QC Accepted | 2026_ET-00471_FR |  | Not Started | 2026_ET-00471_RWR | Submitted | 2026-03-11 | 2026_ET-00471_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-29 | 0 | 2026_ET-00471_PROCPKG | In Progress | All Good - Complete | 2026_ET-00471_WR |  | 06-12-2026 | Not Started |  |  |  | 2026_ET-00471_VMLAZ |  | In Progress |  |  |  | 2026_ET-00471_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00471_RR |  | In Progress | [6 empty] | 2026_ET-00471_VER |  | In Progress | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | SAN ONOFRE-SERRANO_ET-00471 |  |  | Yes |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-BARRE NO. 1 | ET-00483 | 2026_ET-00483 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.3656 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-03 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00483_ACQPKG | 2026_ET-00483_GSPKG | Submitted | 2026_ET-00483_GS | 2026-01-31 | Field Complete | 2026_ET-00483_GCPR | 2026-05-03 | Submitted | 2026_ET-00483_ACQ | QC Accepted | 2026_ET-00483_FR | 2026-05-03 | Submitted | 2026_ET-00483_RWR | Submitted | 2026-05-03 | 2026_ET-00483_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00483_PROCPKG | In Progress | All Good - Complete | 2026_ET-00483_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00483_VMLAZ |  | In Progress |  |  |  | 2026_ET-00483_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00483_RR |  | In Progress | [6 empty] | 2026_ET-00483_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ALAMITOS-BARRE NO. 1_ET-00483 | Done |  | Yes |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ESTRELLA-LAS LOMAS | ET-00484 | 2026_ET-00484 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.2859 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00484_ACQPKG | 2026_ET-00484_GSPKG | Submitted | 2026_ET-00484_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00484_GCPR | 2025-12-08 | Historical | 2026_ET-00484_ACQ | In Progress | 2026_ET-00484_FR |  | Not Started | 2026_ET-00484_RWR | Not Started |  | 2026_ET-00484_CLAZ |  | Not Started |  |  |  | 2026_ET-00484_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00484_WR |  |  | Not Started |  |  |  | 2026_ET-00484_VMLAZ |  | Not Started |  |  |  | 2026_ET-00484_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00484_RR |  | Not Started | [6 empty] | 2026_ET-00484_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | ESTRELLA-LAS LOMAS_ET-00484 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-CENTER | ET-00488 | 2026_ET-00488 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 11.5563 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-02 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00488_ACQPKG | 2026_ET-00488_GSPKG | Submitted | 2026_ET-00488_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00488_GCPR | 2025-12-08 | Historical | 2026_ET-00488_ACQ | QC Accepted | 2026_ET-00488_FR | 2026-05-03 | Submitted | 2026_ET-00488_RWR | Submitted | 2026-05-03 | 2026_ET-00488_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00488_PROCPKG | In Progress | All Good - Complete | 2026_ET-00488_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00488_VMLAZ |  | In Progress |  |  |  | 2026_ET-00488_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00488_RR |  | In Progress | [6 empty] | 2026_ET-00488_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ALAMITOS-CENTER_ET-00488 | Done |  | Yes |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-NEWHALL NO. 2 | ET-00494 | 2026_ET-00494 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 1.6041 | 1.6041 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-03-09 | 04-15-2026 | 04-09-2026 |  | 2026_ET-00494_ACQPKG | 2026_ET-00494_GSPKG | Submitted | 2026_ET-00494_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00494_GCPR | 2025-12-08 | Historical | 2026_ET-00494_ACQ | QC Accepted | 2026_ET-00494_FR | 2026-04-02 | Submitted | 2026_ET-00494_RWR | Submitted | 2026-04-02 | 2026_ET-00494_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00494_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00494_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00494_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00494_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00494_RR | 2026-05-06 | No Violations | 05-20-2026 |  | 0 |  |  |  | 2026_ET-00494_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-NEWHALL NO. 2_ET-00494 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 11:55 PST ¦ 2026-03-18 09:20 PDT | 030926 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-NEWHALL NO.1 | ET-00495 | 2026_ET-00495 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 1.5952 | 1.5952 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-03-09 | 04-16-2026 | 04-10-2026 |  | 2026_ET-00495_ACQPKG | 2026_ET-00495_GSPKG | Submitted | 2026_ET-00495_GS | 2025-12-08 | Field Complete | 2026_ET-00495_GCPR | 2026-04-02 | Submitted | 2026_ET-00495_ACQ | QC Accepted | 2026_ET-00495_FR | 2026-04-02 | Submitted | 2026_ET-00495_RWR | Submitted | 2026-04-02 | 2026_ET-00495_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-00495_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00495_WR | 2026-05-14 | 05-16-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00495_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00495_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00495_RR | 2026-05-06 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 3 | 2026-05-07 | 0 | 3 | 2026_ET-00495_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-NEWHALL NO.1_ET-00495 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:49 PST ¦ 2026-03-18 09:20 PDT | 031826 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BORREGO-MOULTON-NIGUEL | ET-00497 | 2026_ET-00497 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 6.6905 | 2.8024 | 42 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-06 | 04-22-2026 | 04-09-2026 |  | 2026_ET-00497_ACQPKG | 2026_ET-00497_GSPKG | Submitted | 2026_ET-00497_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00497_GCPR | 2025-12-08 | Historical | 2026_ET-00497_ACQ | QC Accepted | 2026_ET-00497_FR | 2026-04-02 | Submitted | 2026_ET-00497_RWR | Submitted | 2026-04-02 | 2026_ET-00497_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00497_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00497_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00497_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00497_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00497_RR | 2026-05-07 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 7 | 2026-05-08 | 0 | 7 | 2026_ET-00497_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BORREGO-MOULTON-NIGUEL_ET-00497 | Done |  | No |  |  | SADDLEBACK | 43 | UNK | 2026-02-06 11:53 PST ¦ 2026-02-27 14:45 PST | 022726 | 20260227 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MORENO-MOVAL-VISTA | ET-00505 | 2026_ET-00505 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.6275 | 12.1044 | 89 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-01-31 | 04-22-2026 | 04-08-2026 |  | 2026_ET-00505_ACQPKG | 2026_ET-00505_GSPKG | Submitted | 2026_ET-00505_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00505_GCPR | 2025-12-08 | Historical | 2026_ET-00505_ACQ | QC Accepted | 2026_ET-00505_FR | 2026-04-02 | Submitted | 2026_ET-00505_RWR | Submitted | 2026-04-02 | 2026_ET-00505_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00505_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00505_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00505_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00505_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00505_RR | 2026-05-07 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 2 | 2026-05-08 | 0 | 2 | 2026_ET-00505_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | MORENO-MOVAL-VISTA_ET-00505 |  |  | No |  |  | REDLANDS | 31 | UNK | 2026-01-31 08:37 PST ¦ 2026-01-31 11:05 PST | 013126 | 20260131 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
TIPTON-WOODVILLE NO.1 | ET-00506 | 2026_ET-00506 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.9309 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00506_ACQPKG | 2026_ET-00506_GSPKG | Submitted | 2026_ET-00506_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00506_GCPR | 2025-12-08 | Historical | 2026_ET-00506_ACQ | In Progress | 2026_ET-00506_FR |  | Not Started | 2026_ET-00506_RWR | Not Started |  | 2026_ET-00506_CLAZ |  | Not Started |  |  |  | 2026_ET-00506_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00506_WR |  |  | Not Started |  |  |  | 2026_ET-00506_VMLAZ |  | Not Started |  |  |  | 2026_ET-00506_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00506_RR |  | Not Started | [6 empty] | 2026_ET-00506_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | TIPTON-WOODVILLE NO.1_ET-00506 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
TIPTON-WOODVILLE NO.2 | ET-00507 | 2026_ET-00507 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.9508 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00507_ACQPKG | 2026_ET-00507_GSPKG | Submitted | 2026_ET-00507_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00507_GCPR | 2025-12-08 | Historical | 2026_ET-00507_ACQ | In Progress | 2026_ET-00507_FR |  | Not Started | 2026_ET-00507_RWR | Not Started |  | 2026_ET-00507_CLAZ |  | Not Started |  |  |  | 2026_ET-00507_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00507_WR |  |  | Not Started |  |  |  | 2026_ET-00507_VMLAZ |  | Not Started |  |  |  | 2026_ET-00507_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00507_RR |  | Not Started | [6 empty] | 2026_ET-00507_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | TIPTON-WOODVILLE NO.2_ET-00507 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PORTERVILLE-WOODVILLE | ET-00511 | 2026_ET-00511 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 14.3379 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00511_ACQPKG | 2026_ET-00511_GSPKG | Submitted | 2026_ET-00511_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00511_GCPR | 2025-12-08 | Historical | 2026_ET-00511_ACQ | In Progress | 2026_ET-00511_FR |  | Not Started | 2026_ET-00511_RWR | Not Started |  | 2026_ET-00511_CLAZ |  | Not Started |  |  |  | 2026_ET-00511_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00511_WR |  |  | Not Started |  |  |  | 2026_ET-00511_VMLAZ |  | Not Started |  |  |  | 2026_ET-00511_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00511_RR |  | Not Started | [6 empty] | 2026_ET-00511_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | PORTERVILLE-WOODVILLE_ET-00511 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-MANDALAY NO. 4 | ET-00531 | 2026_ET-00531 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.97 | 2.313 | 26 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00531_ACQPKG | 2026_ET-00531_GSPKG | In Progress | 2026_ET-00531_GS |  | Not Started | 2026_ET-00531_GCPR |  | Not Started | 2026_ET-00531_ACQ | In Progress | 2026_ET-00531_FR |  | Not Started | 2026_ET-00531_RWR | Not Started |  | 2026_ET-00531_CLAZ |  | Not Started |  |  |  | 2026_ET-00531_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00531_WR |  |  | Not Started |  |  |  | 2026_ET-00531_VMLAZ |  | Not Started |  |  |  | 2026_ET-00531_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00531_RR |  | Not Started | [6 empty] | 2026_ET-00531_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-MANDALAY NO. 4_ET-00531 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-MANDALAY NO. 3 | ET-00538 | 2026_ET-00538 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.9591 | 2.3092 | 26 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00538_ACQPKG | 2026_ET-00538_GSPKG | Submitted | 2026_ET-00538_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00538_GCPR | 2025-12-08 | Historical | 2026_ET-00538_ACQ | In Progress | 2026_ET-00538_FR |  | Not Started | 2026_ET-00538_RWR | Not Started |  | 2026_ET-00538_CLAZ |  | Not Started |  |  |  | 2026_ET-00538_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00538_WR |  |  | Not Started |  |  |  | 2026_ET-00538_VMLAZ |  | Not Started |  |  |  | 2026_ET-00538_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00538_RR |  | Not Started | [6 empty] | 2026_ET-00538_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-MANDALAY NO. 3_ET-00538 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-LA PALMA NO. 1 | ET-00540 | 2026_ET-00540 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.6924 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00540_ACQPKG | 2026_ET-00540_GSPKG | Submitted | 2026_ET-00540_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00540_GCPR | 2025-12-08 | Historical | 2026_ET-00540_ACQ | In Progress | 2026_ET-00540_FR |  | Not Started | 2026_ET-00540_RWR | Not Started |  | 2026_ET-00540_CLAZ |  | Not Started |  |  |  | 2026_ET-00540_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00540_WR |  |  | Not Started |  |  |  | 2026_ET-00540_VMLAZ |  | Not Started |  |  |  | 2026_ET-00540_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00540_RR |  | Not Started | [6 empty] | 2026_ET-00540_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BARRE-LA PALMA NO. 1_ET-00540 | Done |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-MOULTON | ET-00544 | 2026_ET-00544 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 5.2004 | 1.5136 | 29 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00544_ACQPKG | 2026_ET-00544_GSPKG | Submitted | 2026_ET-00544_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00544_GCPR | 2025-12-08 | Historical | 2026_ET-00544_ACQ | In Progress | 2026_ET-00544_FR |  | Not Started | 2026_ET-00544_RWR | Not Started |  | 2026_ET-00544_CLAZ |  | Not Started |  |  |  | 2026_ET-00544_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00544_WR |  |  | Not Started |  |  |  | 2026_ET-00544_VMLAZ |  | Not Started |  |  |  | 2026_ET-00544_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00544_RR |  | Not Started | [6 empty] | 2026_ET-00544_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTIAGO-MOULTON_ET-00544 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-TORTILLA | ET-00560 | 2026_ET-00560 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 31.8849 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 01-01-2026 | Flown | 2026-02-01 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00560_ACQPKG | 2026_ET-00560_GSPKG | Submitted | 2026_ET-00560_GS | 2026-01-23 | Field Complete | 2026_ET-00560_GCPR | 2026-01-30 | Submitted | 2026_ET-00560_ACQ | QC Accepted | 2026_ET-00560_FR |  | Not Started | 2026_ET-00560_RWR | Submitted | 2026-02-01 | 2026_ET-00560_CLAZ | 2026-04-22 | QC Accepted | 05-06-2026 | 2026-05-11 | 1 | 2026_ET-00560_PROCPKG | In Progress | All Good - Complete | 2026_ET-00560_WR |  | 06-10-2026 | Not Started |  |  |  | 2026_ET-00560_VMLAZ |  | Not Started |  |  |  | 2026_ET-00560_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00560_RR |  | Not Started | [6 empty] | 2026_ET-00560_VER |  | Not Started | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | KRAMER-TORTILLA_ET-00560 |  |  | No |  |  | BARSTOW | 72 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-COOLWATER | ET-00561 | 2026_ET-00561 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 44.0168 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-20 | 01-01-2026 | Flown | 2025-12-21 |  |  |  | 2026_ET-00561_ACQPKG | 2026_ET-00561_GSPKG | In Progress | 2026_ET-00561_GS |  | Not Started | 2026_ET-00561_GCPR |  | Not Started | 2026_ET-00561_ACQ | In Progress | 2026_ET-00561_FR |  | Not Started | 2026_ET-00561_RWR | Not Started |  | 2026_ET-00561_CLAZ | 2025-12-21 | QC Accepted |  | 2026-02-05 |  | 2026_ET-00561_PROCPKG | QC Accepted | ACQ Vendor | 2026_ET-00561_WR | 2026-03-24 |  | QC Accepted | 04-07-2026 | 2026-04-15 | 2 | 2026_ET-00561_VMLAZ | 2026-03-04 | QC Accepted | 04-01-2026 | 2026-03-20 | 0 | 2026_ET-00561_VMM1 | 2026-03-04 | QC Accepted |  | 04-01-2026 | 2026-03-19 | 0 | 2026_ET-00561_RR | 2026-03-09 | No Violations | 03-20-2026 |  | 0 |  |  |  | 2026_ET-00561_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-03-25 | 1 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | KRAMER-COOLWATER_ET-00561 |  |  | No |  |  | BARSTOW | 72 | UNK | 2025-12-20 12:49 PST ¦ 2025-12-21 13:09 PST | 122125 | 20251221 | Attribute errors | [5 empty] | Yes | No Delay | Delay | N/A | Variable |  |  |  | BulkRedelivery |  |  | N/A | N/A
EAGLE ROCK-PS 197 | ET-00562 | 2026_ET-00562 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 3.644 | 3.644 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00562_ACQPKG | 2026_ET-00562_GSPKG | Submitted | 2026_ET-00562_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00562_GCPR | 2025-12-08 | Historical | 2026_ET-00562_ACQ | In Progress | 2026_ET-00562_FR |  | Not Started | 2026_ET-00562_RWR | Not Started |  | 2026_ET-00562_CLAZ |  | Not Started |  |  |  | 2026_ET-00562_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00562_WR |  |  | Not Started |  |  |  | 2026_ET-00562_VMLAZ |  | Not Started |  |  |  | 2026_ET-00562_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00562_RR |  | Not Started | [6 empty] | 2026_ET-00562_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | EAGLE ROCK-PS 197_ET-00562 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARROYO-EAGLE ROCK-LA CANADA | ET-00564 | 2026_ET-00564 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.9644 | 5.9644 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-21 | 04-22-2026 | 04-16-2026 |  | 2026_ET-00564_ACQPKG | 2026_ET-00564_GSPKG | Submitted | 2026_ET-00564_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00564_GCPR | 2025-12-08 | Historical | 2026_ET-00564_ACQ | QC Accepted | 2026_ET-00564_FR | 2026-03-16 | Submitted | 2026_ET-00564_RWR | Submitted | 2026-03-16 | 2026_ET-00564_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 | 1 | 2026_ET-00564_PROCPKG | Submitted | All Good - Complete | 2026_ET-00564_WR | 2026-05-11 | 05-22-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00564_VMLAZ | 2026-05-11 | Under QC | 06-01-2026 |  |  | 2026_ET-00564_VMM1 | 2026-05-11 | Under QC |  | 06-01-2026 |  |  | 2026_ET-00564_RR | 2026-05-11 | Ready for QC |  |  | 2 |  |  |  | 2026_ET-00564_VER | 2026-05-11 | Under QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | ARROYO-EAGLE ROCK-LA CANADA_ET-00564 | Done |  | No |  | Helicopter | MONROVIA | 27 | HC | 2026-02-21 13:15 PST ¦ 2026-02-21 13:45 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-HAMILTON NO. 1 | ET-00567 | 2026_ET-00567 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_6 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 2.5237 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00567_ACQPKG | 2026_ET-00567_GSPKG | Submitted | 2026_ET-00567_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00567_GCPR | 2025-12-08 | Historical | 2026_ET-00567_ACQ | In Progress | 2026_ET-00567_FR |  | Not Started | 2026_ET-00567_RWR | Not Started |  | 2026_ET-00567_CLAZ |  | Not Started |  |  |  | 2026_ET-00567_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00567_WR |  |  | Not Started |  |  |  | 2026_ET-00567_VMLAZ |  | Not Started |  |  |  | 2026_ET-00567_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00567_RR |  | Not Started | [6 empty] | 2026_ET-00567_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | ELLIS-HAMILTON NO. 1_ET-00567 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-HAMILTON NO. 2 | ET-00570 | 2026_ET-00570 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.8378 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-13-2026 |  | 2026_ET-00570_ACQPKG | 2026_ET-00570_GSPKG | Submitted | 2026_ET-00570_GS | 2026-01-31 | Field Complete | 2026_ET-00570_GCPR | 2026-05-03 | Submitted | 2026_ET-00570_ACQ | QC Accepted | 2026_ET-00570_FR | 2026-05-03 | Submitted | 2026_ET-00570_RWR | Submitted | 2026-05-03 | 2026_ET-00570_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-00570_PROCPKG | In Progress | SCE | 2026_ET-00570_WR |  |  | In Progress |  |  |  | 2026_ET-00570_VMLAZ |  | In Progress |  |  |  | 2026_ET-00570_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00570_RR |  | In Progress | [6 empty] | 2026_ET-00570_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ELLIS-HAMILTON NO. 2_ET-00570 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-LAFAYETTE | ET-00571 | 2026_ET-00571 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.3628 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00571_ACQPKG | 2026_ET-00571_GSPKG | Submitted | 2026_ET-00571_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00571_GCPR | 2025-12-08 | Historical | 2026_ET-00571_ACQ | In Progress | 2026_ET-00571_FR |  | Not Started | 2026_ET-00571_RWR | Not Started |  | 2026_ET-00571_CLAZ |  | Not Started |  |  |  | 2026_ET-00571_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00571_WR |  |  | Not Started |  |  |  | 2026_ET-00571_VMLAZ |  | Not Started |  |  |  | 2026_ET-00571_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00571_RR |  | Not Started | [6 empty] | 2026_ET-00571_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | ELLIS-LAFAYETTE_ET-00571 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARDIFF-STODDARD | ET-00579 | 2026_ET-00579 |  | 1 | 2026 | Dec 01, 2026 | 33 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 0.70395 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00579_ACQPKG | 2026_ET-00579_GSPKG | Submitted | 2026_ET-00579_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00579_GCPR | 2025-12-08 | Historical | 2026_ET-00579_ACQ | In Progress | 2026_ET-00579_FR |  | Not Started | 2026_ET-00579_RWR | Not Started |  | 2026_ET-00579_CLAZ |  | Not Started |  |  |  | 2026_ET-00579_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00579_WR |  |  | Not Started |  |  |  | 2026_ET-00579_VMLAZ |  | Not Started |  |  |  | 2026_ET-00579_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00579_RR |  | Not Started | [6 empty] | 2026_ET-00579_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CARDIFF-STODDARD_ET-00579 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SAUGUS NO.4 | ET-00603 | 2026_ET-00603 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.4504 | 1.4504 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-09 |  | 05-11-2026 |  | 2026_ET-00603_ACQPKG | 2026_ET-00603_GSPKG | Submitted | 2026_ET-00603_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00603_GCPR | 2025-12-08 | Historical | 2026_ET-00603_ACQ | QC Accepted | 2026_ET-00603_FR | 2026-05-03 | Submitted | 2026_ET-00603_RWR | Submitted | 2026-05-03 | 2026_ET-00603_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00603_PROCPKG | In Progress | SCE | 2026_ET-00603_WR |  |  | In Progress |  |  |  | 2026_ET-00603_VMLAZ |  | In Progress |  |  |  | 2026_ET-00603_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00603_RR |  | In Progress | [6 empty] | 2026_ET-00603_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | PARDEE-SAUGUS NO.4_ET-00603 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-LOCKHEED-THATCHER GLASS | ET-00607 | 2026_ET-00607 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.15903 | 0.15903 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-04 | 04-14-2026 | 04-08-2026 |  | 2026_ET-00607_ACQPKG | 2026_ET-00607_GSPKG | Submitted | 2026_ET-00607_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00607_GCPR | 2025-12-08 | Historical | 2026_ET-00607_ACQ | QC Accepted | 2026_ET-00607_FR | 2026-04-02 | Submitted | 2026_ET-00607_RWR | Submitted | 2026-04-02 | 2026_ET-00607_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00607_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00607_WR | 2026-05-06 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00607_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00607_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00607_RR | 2026-05-06 | No Violations | 05-14-2026 |  | 0 |  |  |  | 2026_ET-00607_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-LOCKHEED-THATCHER GLASS_ET-00607 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:46 PST ¦ 2026-03-04 10:48 PST | 030426 | 20260304 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-P.S. 128 | ET-00614 | 2026_ET-00614 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.0043 | 10.0496 | 77 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-09 | 04-14-2026 | 04-09-2026 |  | 2026_ET-00614_ACQPKG | 2026_ET-00614_GSPKG | Submitted | 2026_ET-00614_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00614_GCPR | 2025-12-08 | Historical | 2026_ET-00614_ACQ | QC Accepted | 2026_ET-00614_FR | 2026-04-02 | Submitted | 2026_ET-00614_RWR | Submitted | 2026-04-02 | 2026_ET-00614_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00614_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00614_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00614_VMLAZ | 2026-05-06 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00614_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00614_RR | 2026-05-06 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 9 | 2026-05-07 | 0 | 9 | 2026_ET-00614_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-P.S. 128_ET-00614 |  |  | No |  |  | VENTURA | 39 | UNK | 2026-03-09 10:45 PDT ¦ 2026-03-10 12:59 PDT | 031026 | 20260310 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-POTRERO-THOUSAND OAKS | ET-00636 | 2026_ET-00636 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 12.0006 | 12.0006 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-10 |  | 05-11-2026 |  | 2026_ET-00636_ACQPKG | 2026_ET-00636_GSPKG | Submitted | 2026_ET-00636_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00636_GCPR | 2025-12-08 | Historical | 2026_ET-00636_ACQ | QC Accepted | 2026_ET-00636_FR | 2026-05-03 | Submitted | 2026_ET-00636_RWR | Submitted | 2026-05-03 | 2026_ET-00636_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00636_PROCPKG | In Progress | SCE | 2026_ET-00636_WR |  |  | In Progress |  |  |  | 2026_ET-00636_VMLAZ |  | In Progress |  |  |  | 2026_ET-00636_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00636_RR |  | In Progress | [6 empty] | 2026_ET-00636_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MOORPARK-POTRERO-THOUSAND OAKS_ET-00636 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MALIBU-POTRERO | ET-00645 | 2026_ET-00645 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.062 | 4.062 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-10 |  | 05-11-2026 |  | 2026_ET-00645_ACQPKG | 2026_ET-00645_GSPKG | Submitted | 2026_ET-00645_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00645_GCPR | 2025-12-08 | Historical | 2026_ET-00645_ACQ | QC Accepted | 2026_ET-00645_FR | 2026-05-03 | Submitted | 2026_ET-00645_RWR | Submitted | 2026-05-03 | 2026_ET-00645_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00645_PROCPKG | In Progress | SCE | 2026_ET-00645_WR |  |  | In Progress |  |  |  | 2026_ET-00645_VMLAZ |  | In Progress |  |  |  | 2026_ET-00645_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00645_RR |  | In Progress | [6 empty] | 2026_ET-00645_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MALIBU-POTRERO_ET-00645 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-QUARTZ HILL NO. 1 | ET-00648 | 2026_ET-00648 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.2409 | 0.3916 | 7 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-20 | 04-16-2026 | 04-16-2026 |  | 2026_ET-00648_ACQPKG | 2026_ET-00648_GSPKG | Submitted | 2026_ET-00648_GS | 2025-10-17 | Field Complete | 2026_ET-00648_GCPR | 2025-12-08 | Submitted | 2026_ET-00648_ACQ | QC Accepted | 2026_ET-00648_FR | 2026-03-16 | Submitted | 2026_ET-00648_RWR | Submitted | 2026-03-16 | 2026_ET-00648_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-00648_PROCPKG | Submitted | All Good - Complete | 2026_ET-00648_WR | 2026-05-10 | 05-16-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00648_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00648_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00648_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-00648_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected On Time | Completed On Time | Completed Late - Program | ANTELOPE-QUARTZ HILL NO. 1_ET-00648 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 10:57 PST ¦ 2026-02-20 11:29 PST | 022026 | 20260220 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-QUARTZ HILL NO. 2 | ET-00649 | 2026_ET-00649 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.609 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-02-20 | 04-16-2026 | 04-16-2026 |  | 2026_ET-00649_ACQPKG | 2026_ET-00649_GSPKG | Submitted | 2026_ET-00649_GS | 2025-10-17 | Field Complete | 2026_ET-00649_GCPR | 2025-12-08 | Submitted | 2026_ET-00649_ACQ | QC Accepted | 2026_ET-00649_FR | 2026-03-16 | Submitted | 2026_ET-00649_RWR | Submitted | 2026-03-16 | 2026_ET-00649_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-00649_PROCPKG | Submitted | All Good - Complete | 2026_ET-00649_WR | 2026-05-10 | 05-16-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00649_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00649_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00649_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-00649_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected On Time | Completed On Time | Completed Late - Program | ANTELOPE-QUARTZ HILL NO. 2_ET-00649 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 10:52 PST ¦ 2026-02-20 11:28 PST | 022026 | 20260220 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MAGUNDEN-PASTORIA NO. 1 | ET-00654 | 2026_ET-00654 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 30.1399 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-02-23 | 04-24-2026 | 04-24-2026 |  | 2026_ET-00654_ACQPKG | 2026_ET-00654_GSPKG | Submitted | 2026_ET-00654_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00654_GCPR | 2025-12-08 | Historical | 2026_ET-00654_ACQ | QC Accepted | 2026_ET-00654_FR | 2026-03-16 | Submitted | 2026_ET-00654_RWR | Submitted | 2026-03-16 | 2026_ET-00654_CLAZ | 2026-04-17 | QC Accepted | 05-01-2026 | 2026-04-24 | 1 | 2026_ET-00654_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00654_WR | 2026-05-13 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-14 | 0 | 2026_ET-00654_VMLAZ | 2026-05-12 | QC Accepted | 06-01-2026 | 2026-05-12 |  | 2026_ET-00654_VMM1 | 2026-05-13 | QC Accepted |  | 06-01-2026 | 2026-05-14 |  | 2026_ET-00654_RR | 2026-05-13 | No Violations | 05-15-2026 | [5 empty] | 2026_ET-00654_VER | 2026-05-13 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MAGUNDEN-PASTORIA NO. 1_ET-00654 |  |  | Yes |  | Helicopter |  |  | HC |  |  |  |  | Metadata issue., Relative accuracy is not within 3 inches RMSE or a single instance over 6 inches. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
MAGUNDEN-PASTORIA NO. 2 | ET-00657 | 2026_ET-00657 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 30.1416 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-02-23 | 04-24-2026 | 04-24-2026 |  | 2026_ET-00657_ACQPKG | 2026_ET-00657_GSPKG | Submitted | 2026_ET-00657_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00657_GCPR | 2025-12-08 | Historical | 2026_ET-00657_ACQ | QC Accepted | 2026_ET-00657_FR | 2026-03-16 | Submitted | 2026_ET-00657_RWR | Submitted | 2026-03-16 | 2026_ET-00657_CLAZ | 2026-04-17 | QC Accepted | 05-01-2026 | 2026-04-24 | 1 | 2026_ET-00657_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00657_WR | 2026-05-13 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-14 | 0 | 2026_ET-00657_VMLAZ | 2026-05-12 | QC Accepted | 06-01-2026 | 2026-05-12 |  | 2026_ET-00657_VMM1 | 2026-05-13 | QC Accepted |  | 06-01-2026 | 2026-05-14 |  | 2026_ET-00657_RR | 2026-05-13 | No Violations | 05-15-2026 | [5 empty] | 2026_ET-00657_VER | 2026-05-13 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MAGUNDEN-PASTORIA NO. 2_ET-00657 |  |  | Yes |  | Helicopter |  |  | HC |  |  |  |  | Metadata issue., Relative accuracy is not within 3 inches RMSE or a single instance over 6 inches. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
MAGUNDEN-PASTORIA NO. 3 | ET-00659 | 2026_ET-00659 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 30.1424 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-02-23 | 04-24-2026 | 04-24-2026 |  | 2026_ET-00659_ACQPKG | 2026_ET-00659_GSPKG | Submitted | 2026_ET-00659_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00659_GCPR | 2025-12-08 | Historical | 2026_ET-00659_ACQ | QC Accepted | 2026_ET-00659_FR | 2026-03-16 | Submitted | 2026_ET-00659_RWR | Submitted | 2026-03-16 | 2026_ET-00659_CLAZ | 2026-04-17 | QC Accepted | 05-01-2026 | 2026-04-24 | 1 | 2026_ET-00659_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00659_WR | 2026-05-13 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-14 | 0 | 2026_ET-00659_VMLAZ | 2026-05-12 | QC Accepted | 06-01-2026 | 2026-05-12 |  | 2026_ET-00659_VMM1 | 2026-05-13 | QC Accepted |  | 06-01-2026 | 2026-05-14 |  | 2026_ET-00659_RR | 2026-05-13 | No Violations | 05-15-2026 | [5 empty] | 2026_ET-00659_VER | 2026-05-13 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MAGUNDEN-PASTORIA NO. 3_ET-00659 |  |  | Yes |  | Helicopter |  |  | HC |  |  |  |  | Metadata issue., Relative accuracy is not within 3 inches RMSE or a single instance over 6 inches. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
BEVERLY-FAIRFAX | ET-00660 | 2026_ET-00660 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.1719 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00660_ACQPKG | 2026_ET-00660_GSPKG | Submitted | 2026_ET-00660_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00660_GCPR | 2025-12-08 | Historical | 2026_ET-00660_ACQ | In Progress | 2026_ET-00660_FR |  | Not Started | 2026_ET-00660_RWR | Not Started |  | 2026_ET-00660_CLAZ |  | Not Started |  |  |  | 2026_ET-00660_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00660_WR |  |  | Not Started |  |  |  | 2026_ET-00660_VMLAZ |  | Not Started |  |  |  | 2026_ET-00660_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00660_RR |  | Not Started | [6 empty] | 2026_ET-00660_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BEVERLY-FAIRFAX_ET-00660 | Done |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SYLMAR NO.1 | ET-00664 | 2026_ET-00664 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.4686 | 11.1931 | 98 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-03-09 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00664_ACQPKG | 2026_ET-00664_GSPKG | Submitted | 2026_ET-00664_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00664_GCPR | 2025-12-08 | Historical | 2026_ET-00664_ACQ | QC Accepted | 2026_ET-00664_FR | 2026-04-02 | Submitted | 2026_ET-00664_RWR | Submitted | 2026-04-02 | 2026_ET-00664_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00664_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00664_WR | 2026-05-07 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00664_VMLAZ | 2026-05-04 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00664_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00664_RR | 2026-05-07 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00664_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | PARDEE-SYLMAR NO.1_ET-00664 |  |  | Yes |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SAUGUS NO.1 | ET-00670 | 2026_ET-00670 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.4718 | 1.4718 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-09 |  | 05-11-2026 |  | 2026_ET-00670_ACQPKG | 2026_ET-00670_GSPKG | Submitted | 2026_ET-00670_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00670_GCPR | 2025-12-08 | Historical | 2026_ET-00670_ACQ | QC Accepted | 2026_ET-00670_FR | 2026-05-03 | Submitted | 2026_ET-00670_RWR | Submitted | 2026-05-03 | 2026_ET-00670_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00670_PROCPKG | In Progress | SCE | 2026_ET-00670_WR |  |  | In Progress |  |  |  | 2026_ET-00670_VMLAZ |  | In Progress |  |  |  | 2026_ET-00670_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00670_RR |  | In Progress | [6 empty] | 2026_ET-00670_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | PARDEE-SAUGUS NO.1_ET-00670 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SAUGUS NO.3 | ET-00674 | 2026_ET-00674 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.4477 | 1.4477 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-09 |  | 05-11-2026 |  | 2026_ET-00674_ACQPKG | 2026_ET-00674_GSPKG | Submitted | 2026_ET-00674_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00674_GCPR | 2025-12-08 | Historical | 2026_ET-00674_ACQ | QC Accepted | 2026_ET-00674_FR | 2026-05-03 | Submitted | 2026_ET-00674_RWR | Submitted | 2026-05-03 | 2026_ET-00674_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00674_PROCPKG | In Progress | SCE | 2026_ET-00674_WR |  |  | In Progress |  |  |  | 2026_ET-00674_VMLAZ |  | In Progress |  |  |  | 2026_ET-00674_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00674_RR |  | In Progress | [6 empty] | 2026_ET-00674_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | PARDEE-SAUGUS NO.3_ET-00674 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SYLMAR NO.2 | ET-00677 | 2026_ET-00677 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.4769 | 11.2009 | 98 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-03-09 | 04-24-2026 | 04-10-2026 |  | 2026_ET-00677_ACQPKG | 2026_ET-00677_GSPKG | Submitted | 2026_ET-00677_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00677_GCPR | 2025-12-08 | Historical | 2026_ET-00677_ACQ | QC Accepted | 2026_ET-00677_FR | 2026-04-02 | Submitted | 2026_ET-00677_RWR | Submitted | 2026-04-02 | 2026_ET-00677_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-00677_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00677_WR | 2026-05-04 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00677_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00677_VMM1 | 2026-05-04 | QC Accepted |  | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00677_RR | 2026-05-04 | No Violations | 05-08-2026 | [5 empty] | 2026_ET-00677_VER | 2026-05-04 | Uploaded to S123 | 06-01-2026 | 2026-05-07 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | PARDEE-SYLMAR NO.2_ET-00677 |  |  | Yes |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARDEE-SAUGUS NO.2 | ET-00679 | 2026_ET-00679 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.4751 | 1.4751 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-09 |  | 05-11-2026 |  | 2026_ET-00679_ACQPKG | 2026_ET-00679_GSPKG | Submitted | 2026_ET-00679_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00679_GCPR | 2025-12-08 | Historical | 2026_ET-00679_ACQ | QC Accepted | 2026_ET-00679_FR | 2026-05-03 | Submitted | 2026_ET-00679_RWR | Submitted | 2026-05-03 | 2026_ET-00679_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00679_PROCPKG | In Progress | SCE | 2026_ET-00679_WR |  |  | In Progress |  |  |  | 2026_ET-00679_VMLAZ |  | In Progress |  |  |  | 2026_ET-00679_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00679_RR |  | In Progress | [6 empty] | 2026_ET-00679_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | PARDEE-SAUGUS NO.2_ET-00679 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-NOGALES-RAILROAD NO. 1 | ET-00685 | 2026_ET-00685 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.5096 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00685_ACQPKG | 2026_ET-00685_GSPKG | Submitted | 2026_ET-00685_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00685_GCPR | 2025-12-08 | Historical | 2026_ET-00685_ACQ | In Progress | 2026_ET-00685_FR |  | Not Started | 2026_ET-00685_RWR | Not Started |  | 2026_ET-00685_CLAZ |  | Not Started |  |  |  | 2026_ET-00685_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00685_WR |  |  | Not Started |  |  |  | 2026_ET-00685_VMLAZ |  | Not Started |  |  |  | 2026_ET-00685_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00685_RR |  | Not Started | [6 empty] | 2026_ET-00685_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | WALNUT-NOGALES-RAILROAD NO. 1_ET-00685 |  |  | No |  | Helicopter |  |  | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MARINE-TAHITI | ET-00714 | 2026_ET-00714 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.5905 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00714_ACQPKG | 2026_ET-00714_GSPKG | Submitted | 2026_ET-00714_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00714_GCPR | 2025-12-08 | Historical | 2026_ET-00714_ACQ | In Progress | 2026_ET-00714_FR |  | Not Started | 2026_ET-00714_RWR | Not Started |  | 2026_ET-00714_CLAZ |  | Not Started |  |  |  | 2026_ET-00714_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00714_WR |  |  | Not Started |  |  |  | 2026_ET-00714_VMLAZ |  | Not Started |  |  |  | 2026_ET-00714_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00714_RR |  | Not Started | [6 empty] | 2026_ET-00714_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MARINE-TAHITI_ET-00714 |  |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE EL NIDO-MARINE | ET-00715 | 2026_ET-00715 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 06-02-2026 | On Time | 0 | Transmission | 8.8946 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Airspace issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-02-2026 | Access Delay |  |  |  |  | 2026_ET-00715_ACQPKG | 2026_ET-00715_GSPKG | Submitted | 2026_ET-00715_GS | 2026-01-31 | Field Complete | 2026_ET-00715_GCPR | 2026-05-03 | Submitted | 2026_ET-00715_ACQ | In Progress | 2026_ET-00715_FR |  | Not Started | 2026_ET-00715_RWR | Not Started |  | 2026_ET-00715_CLAZ |  | Not Started |  |  |  | 2026_ET-00715_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00715_WR |  |  | Not Started |  |  |  | 2026_ET-00715_VMLAZ |  | Not Started |  |  |  | 2026_ET-00715_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00715_RR |  | Not Started | [6 empty] | 2026_ET-00715_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | IDLE EL NIDO-MARINE_ET-00715 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAYFAIR-SAN ANTONIO | ET-00725 | 2026_ET-00725 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.8032 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-11-2026 |  | 2026_ET-00725_ACQPKG | 2026_ET-00725_GSPKG | Submitted | 2026_ET-00725_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00725_GCPR | 2025-12-08 | Historical | 2026_ET-00725_ACQ | QC Accepted | 2026_ET-00725_FR | 2026-05-03 | Submitted | 2026_ET-00725_RWR | Submitted | 2026-05-03 | 2026_ET-00725_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00725_PROCPKG | In Progress | SCE | 2026_ET-00725_WR |  |  | In Progress |  |  |  | 2026_ET-00725_VMLAZ |  | In Progress |  |  |  | 2026_ET-00725_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00725_RR |  | In Progress | [6 empty] | 2026_ET-00725_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LAYFAIR-SAN ANTONIO_ET-00725 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-PARDEE NO. 2 | ET-00729 | 2026_ET-00729 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.8667 | 25.8667 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-26 | 04-02-2026 | Flown | 2026-03-08 | 04-26-2026 | 04-09-2026 |  | 2026_ET-00729_ACQPKG | 2026_ET-00729_GSPKG | Submitted | 2026_ET-00729_GS | 2025-12-08 | Field Complete | 2026_ET-00729_GCPR | 2026-04-02 | Submitted | 2026_ET-00729_ACQ | QC Accepted | 2026_ET-00729_FR | 2026-04-02 | Submitted | 2026_ET-00729_RWR | Submitted | 2026-04-02 | 2026_ET-00729_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00729_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00729_WR | 2026-05-18 | 05-26-2026 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00729_VMLAZ | 2026-05-04 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00729_VMM1 | 2026-05-18 | QC Accepted |  | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00729_RR | 2026-05-18 | No Violations | 05-23-2026 | [5 empty] | 2026_ET-00729_VER | 2026-05-18 | Uploaded to S123 | 06-01-2026 | 2026-05-22 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MOORPARK-PARDEE NO. 2_ET-00729 |  |  | Yes |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-PARDEE NO. 3 | ET-00731 | 2026_ET-00731 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.8686 | 25.8686 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-03-08 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00731_ACQPKG | 2026_ET-00731_GSPKG | Submitted | 2026_ET-00731_GS | 2025-12-08 | Field Complete | 2026_ET-00731_GCPR | 2026-04-02 | Submitted | 2026_ET-00731_ACQ | QC Accepted | 2026_ET-00731_FR | 2026-04-02 | Submitted | 2026_ET-00731_RWR | Submitted | 2026-04-02 | 2026_ET-00731_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00731_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00731_WR | 2026-05-18 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00731_VMLAZ | 2026-05-01 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00731_VMM1 | 2026-05-18 | QC Accepted |  | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00731_RR | 2026-05-18 | No Violations | 05-23-2026 | [5 empty] | 2026_ET-00731_VER | 2026-05-18 | Uploaded to S123 | 06-01-2026 | 2026-05-22 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MOORPARK-PARDEE NO. 3_ET-00731 |  |  | Yes |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-QUARTZ HILL-SHUTTLE | ET-00739 | 2026_ET-00739 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 13.1551 | 0.39332 | 3 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-05-2026 |  | 2026_ET-00739_ACQPKG | 2026_ET-00739_GSPKG | Submitted | 2026_ET-00739_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00739_GCPR | 2025-12-08 | Historical | 2026_ET-00739_ACQ | QC Accepted | 2026_ET-00739_FR | 2026-04-28 | Submitted | 2026_ET-00739_RWR | Submitted | 2026-04-30 | 2026_ET-00739_CLAZ | 2026-04-24 | QC Accepted | 06-18-2026 | 2026-05-05 | 0 | 2026_ET-00739_PROCPKG | In Progress | SCE | 2026_ET-00739_WR |  |  | Not Started |  |  |  | 2026_ET-00739_VMLAZ |  | Not Started |  |  |  | 2026_ET-00739_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00739_RR |  | Not Started | [6 empty] | 2026_ET-00739_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ANTELOPE-QUARTZ HILL-SHUTTLE_ET-00739 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-LANCASTER-OASIS | ET-00741 | 2026_ET-00741 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 16.7771 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-13-2026 |  | 2026_ET-00741_ACQPKG | 2026_ET-00741_GSPKG | Submitted | 2026_ET-00741_GS | 2025-10-17 | Field Complete | 2026_ET-00741_GCPR | 2025-12-08 | Submitted | 2026_ET-00741_ACQ | QC Accepted | 2026_ET-00741_FR | 2026-05-08 | Submitted | 2026_ET-00741_RWR | Submitted | 2026-05-08 | 2026_ET-00741_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-13 | 0 | 2026_ET-00741_PROCPKG | In Progress | SCE | 2026_ET-00741_WR |  |  | Not Started |  |  |  | 2026_ET-00741_VMLAZ |  | Not Started |  |  |  | 2026_ET-00741_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00741_RR |  | Not Started | [6 empty] | 2026_ET-00741_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ANTELOPE-LANCASTER-OASIS_ET-00741 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OASIS-PALMDALE-QUARTZ HILL | ET-00747 | 2026_ET-00747 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 19.4034 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-17 |  | 05-15-2026 |  | 2026_ET-00747_ACQPKG | 2026_ET-00747_GSPKG | Submitted | 2026_ET-00747_GS | 2025-10-17 | Field Complete | 2026_ET-00747_GCPR | 2025-12-08 | Submitted | 2026_ET-00747_ACQ | QC Accepted | 2026_ET-00747_FR | 2026-05-08 | Submitted | 2026_ET-00747_RWR | Submitted | 2026-05-08 | 2026_ET-00747_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-00747_PROCPKG | In Progress | SCE | 2026_ET-00747_WR |  |  | Not Started |  |  |  | 2026_ET-00747_VMLAZ |  | Not Started |  |  |  | 2026_ET-00747_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00747_RR |  | Not Started | [6 empty] | 2026_ET-00747_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | OASIS-PALMDALE-QUARTZ HILL_ET-00747 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DIAMOND BAR-GRAND CROSSING-SOPIPE | ET-00754 | 2026_ET-00754 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.317 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00754_ACQPKG | 2026_ET-00754_GSPKG | Submitted | 2026_ET-00754_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00754_GCPR | 2025-12-08 | Historical | 2026_ET-00754_ACQ | In Progress | 2026_ET-00754_FR |  | Not Started | 2026_ET-00754_RWR | Not Started |  | 2026_ET-00754_CLAZ |  | Not Started |  |  |  | 2026_ET-00754_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00754_WR |  |  | Not Started |  |  |  | 2026_ET-00754_VMLAZ |  | Not Started |  |  |  | 2026_ET-00754_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00754_RR |  | Not Started | [6 empty] | 2026_ET-00754_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | DIAMOND BAR-GRAND CROSSING-SOPIPE_ET-00754 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-SYLMAR | ET-00755 | 2026_ET-00755 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.3645 | 20.6735 | 82 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-25 | 04-02-2026 | Flown | 2026-02-21 | 04-25-2026 | 04-16-2026 |  | 2026_ET-00755_ACQPKG | 2026_ET-00755_GSPKG | Submitted | 2026_ET-00755_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00755_GCPR | 2025-12-08 | Historical | 2026_ET-00755_ACQ | QC Accepted | 2026_ET-00755_FR | 2026-03-16 | Submitted | 2026_ET-00755_RWR | Submitted | 2026-03-16 | 2026_ET-00755_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-00755_PROCPKG | Submitted | All Good - Complete | 2026_ET-00755_WR | 2026-05-13 | 05-25-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00755_VMLAZ | 2026-04-30 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00755_VMM1 | 2026-05-13 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00755_RR | 2026-05-13 | No Violations | [6 empty] | 2026_ET-00755_VER | 2026-05-13 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | EAGLE ROCK-SYLMAR_ET-00755 |  |  | Yes |  | Helicopter | VALENCIA | 59 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARPINTERIA-ORTEGA-SANTA BARBARA | ET-00756 | 2026_ET-00756 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.8007 | 12.1524 | 77 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-14 |  | 05-11-2026 |  | 2026_ET-00756_ACQPKG | 2026_ET-00756_GSPKG | Submitted | 2026_ET-00756_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00756_GCPR | 2025-12-08 | Historical | 2026_ET-00756_ACQ | QC Accepted | 2026_ET-00756_FR | 2026-05-03 | Submitted | 2026_ET-00756_RWR | Submitted | 2026-05-03 | 2026_ET-00756_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00756_PROCPKG | In Progress | SCE | 2026_ET-00756_WR |  |  | In Progress |  |  |  | 2026_ET-00756_VMLAZ |  | In Progress |  |  |  | 2026_ET-00756_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00756_RR |  | In Progress | [6 empty] | 2026_ET-00756_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CARPINTERIA-ORTEGA-SANTA BARBARA_ET-00756 | Done |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CORTEZ-SAN DIMAS | ET-00759 | 2026_ET-00759 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 5.8088 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00759_ACQPKG | 2026_ET-00759_GSPKG | Submitted | 2026_ET-00759_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00759_GCPR | 2025-12-08 | Historical | 2026_ET-00759_ACQ | Submitted | 2026_ET-00759_FR | 2026-05-22 | Submitted | 2026_ET-00759_RWR | Submitted | 2026-05-22 | 2026_ET-00759_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00759_PROCPKG | In Progress | SCE | 2026_ET-00759_WR |  |  | Not Started |  |  |  | 2026_ET-00759_VMLAZ |  | Not Started |  |  |  | 2026_ET-00759_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00759_RR |  | Not Started | [6 empty] | 2026_ET-00759_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | CORTEZ-SAN DIMAS_ET-00759 |  |  | No |  | Helicopter | COVINA | 26 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-SANTA CLARA NO. 1 | ET-00775 | 2026_ET-00775 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.5622 | 24.7735 | 97 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-18 | 04-02-2026 | Flown | 2026-03-09 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00775_ACQPKG | 2026_ET-00775_GSPKG | Submitted | 2026_ET-00775_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00775_GCPR | 2025-12-08 | Historical | 2026_ET-00775_ACQ | QC Accepted | 2026_ET-00775_FR | 2026-04-02 | Submitted | 2026_ET-00775_RWR | Submitted | 2026-04-02 | 2026_ET-00775_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00775_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00775_WR | 2026-05-01 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00775_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00775_VMM1 | 2026-05-01 | QC Accepted |  | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00775_RR | 2026-05-01 | No Violations | 05-08-2026 | [5 empty] | 2026_ET-00775_VER | 2026-05-01 | Uploaded to S123 | 06-01-2026 | 2026-05-07 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-SANTA CLARA NO. 1_ET-00775 |  |  | Yes |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-SANTA CLARA NO. 2 | ET-00778 | 2026_ET-00778 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.5581 | 24.7711 | 97 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-03-09 | 04-24-2026 | 04-08-2026 |  | 2026_ET-00778_ACQPKG | 2026_ET-00778_GSPKG | Submitted | 2026_ET-00778_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00778_GCPR | 2025-12-08 | Historical | 2026_ET-00778_ACQ | QC Accepted | 2026_ET-00778_FR | 2026-04-02 | Submitted | 2026_ET-00778_RWR | Submitted | 2026-04-02 | 2026_ET-00778_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00778_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00778_WR | 2026-05-01 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00778_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00778_VMM1 | 2026-05-01 | QC Accepted |  | 06-01-2026 | 2026-05-07 | 0 | 2026_ET-00778_RR | 2026-05-01 | No Violations | 05-08-2026 | [5 empty] | 2026_ET-00778_VER | 2026-05-01 | Uploaded to S123 | 06-01-2026 | 2026-05-07 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-SANTA CLARA NO. 2_ET-00778 |  |  | Yes |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRAGE-CONCHO | ET-00787 | 2026_ET-00787 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.4795 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00787_ACQPKG | 2026_ET-00787_GSPKG | Submitted | 2026_ET-00787_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00787_GCPR | 2025-12-08 | Historical | 2026_ET-00787_ACQ | In Progress | 2026_ET-00787_FR |  | Not Started | 2026_ET-00787_RWR | Not Started |  | 2026_ET-00787_CLAZ |  | Not Started |  |  |  | 2026_ET-00787_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00787_WR |  |  | Not Started |  |  |  | 2026_ET-00787_VMLAZ |  | Not Started |  |  |  | 2026_ET-00787_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00787_RR |  | Not Started | [6 empty] | 2026_ET-00787_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MIRAGE-CONCHO_ET-00787 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAMGEN-COLONIA | ET-00818 | 2026_ET-00818 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.2732 | 0.29313 | 5 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00818_ACQPKG | 2026_ET-00818_GSPKG | In Progress | 2026_ET-00818_GS |  | Not Started | 2026_ET-00818_GCPR |  | Not Started | 2026_ET-00818_ACQ | In Progress | 2026_ET-00818_FR |  | Not Started | 2026_ET-00818_RWR | Not Started |  | 2026_ET-00818_CLAZ |  | Not Started |  |  |  | 2026_ET-00818_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00818_WR |  |  | Not Started |  |  |  | 2026_ET-00818_VMLAZ |  | Not Started |  |  |  | 2026_ET-00818_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00818_RR |  | Not Started | [6 empty] | 2026_ET-00818_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CAMGEN-COLONIA_ET-00818 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAPSULE-CARDIFF | ET-00823 | 2026_ET-00823 |  | 11 | 2026 | Mar 11, 2026 | 33 | CA_5 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 10-12-2025 | 11-11-2025 | On Time | 0 | Transmission | 1.0772 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-28 | 12-11-2025 | Flown | 2025-10-22 | 04-28-2026 | 12-15-2025 |  | 2026_ET-00823_ACQPKG | 2026_ET-00823_GSPKG | Submitted | 2026_ET-00823_GS | 2025-11-08 | Field Complete | 2026_ET-00823_GCPR | 2025-11-29 | Submitted | 2026_ET-00823_ACQ | QC Accepted | 2026_ET-00823_FR | 2025-11-29 | Submitted | 2026_ET-00823_RWR | Submitted | 2025-11-29 | 2026_ET-00823_CLAZ | 2025-11-29 | QC Accepted | 12-26-2025 | 2025-12-15 | 0 | 2026_ET-00823_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00823_WR | 2026-02-01 | 05-28-2026 | QC Accepted | 02-13-2026 | 2026-02-12 | 0 | 2026_ET-00823_VMLAZ | 2026-02-01 | QC Accepted | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00823_VMM1 | 2026-02-01 | QC Accepted |  | 04-29-2026 | 2026-02-12 | 0 | 2026_ET-00823_RR | 2026-02-01 | No Violations | 02-13-2026 |  | 0 | 2026-02-02 | 0 | 0 | 2026_ET-00823_VER | 2026-04-15 | Uploaded to S123 | 04-29-2026 | 2026-04-22 | 3 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | CAPSULE-CARDIFF_ET-00823 | Done |  | No | 19:43 | Helicopter | REDLANDS | 31 | HC | 2025-10-22 13:59 PDT ¦ 2025-11-03 13:17 PST | 102225 | 20251103 |  |  |  |  | Attribute - Latitude, Attribute - Longitude |  | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAYFAIR-SAN DIMAS | ET-00830 | 2026_ET-00830 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 9.1095 | 5.3065 | 58 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00830_ACQPKG | 2026_ET-00830_GSPKG | Submitted | 2026_ET-00830_GS | 2025-12-08 | Field Complete | 2026_ET-00830_GCPR | 2026-05-22 | Submitted | 2026_ET-00830_ACQ | In Progress | 2026_ET-00830_FR |  | Not Started | 2026_ET-00830_RWR | Not Started |  | 2026_ET-00830_CLAZ |  | Not Started |  |  |  | 2026_ET-00830_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00830_WR |  |  | Not Started |  |  |  | 2026_ET-00830_VMLAZ |  | Not Started |  |  |  | 2026_ET-00830_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00830_RR |  | Not Started | [6 empty] | 2026_ET-00830_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LAYFAIR-SAN DIMAS_ET-00830 |  |  | No |  | Helicopter | COVINA | 26 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARROWHEAD-CALECTRIC-DEVIL CANYON-SHANDIN | ET-00833 | 2026_ET-00833 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 29.7109 | 26.9022 | 91 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-01 | 04-20-2026 | 04-08-2026 |  | 2026_ET-00833_ACQPKG | 2026_ET-00833_GSPKG | Submitted | 2026_ET-00833_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00833_GCPR | 2025-12-08 | Historical | 2026_ET-00833_ACQ | QC Accepted | 2026_ET-00833_FR | 2026-04-02 | Submitted | 2026_ET-00833_RWR | Submitted | 2026-04-02 | 2026_ET-00833_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00833_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00833_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00833_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00833_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-00833_RR | 2026-05-10 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 6 | 2026-05-11 | 0 | 6 | 2026_ET-00833_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ARROWHEAD-CALECTRIC-DEVIL CANYON-SHANDIN_ET-00833 | Done |  | No |  |  | REDLANDS | 31 | UNK | 2026-02-01 08:15 PST ¦ 2026-03-18 13:15 PDT | 020126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARMENITA-ERIC | ET-00841 | 2026_ET-00841 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.189 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-01 | 04-21-2026 | 04-08-2026 |  | 2026_ET-00841_ACQPKG | 2026_ET-00841_GSPKG | Submitted | 2026_ET-00841_GS | 2025-12-08 | Field Complete | 2026_ET-00841_GCPR | 2026-04-02 | Submitted | 2026_ET-00841_ACQ | QC Accepted | 2026_ET-00841_FR | 2026-04-02 | Submitted | 2026_ET-00841_RWR | Submitted | 2026-04-02 | 2026_ET-00841_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-00841_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00841_WR | 2026-05-10 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00841_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00841_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00841_RR | 2026-05-10 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-00841_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CARMENITA-ERIC_ET-00841 | Done |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-01 13:28 PST ¦ 2026-03-01 13:40 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-PARDEE NO. 1 | ET-00845 | 2026_ET-00845 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 25.8908 | 25.8908 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-03-08 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00845_ACQPKG | 2026_ET-00845_GSPKG | Submitted | 2026_ET-00845_GS | 2025-12-08 | Field Complete | 2026_ET-00845_GCPR | 2026-04-02 | Submitted | 2026_ET-00845_ACQ | QC Accepted | 2026_ET-00845_FR | 2026-04-02 | Submitted | 2026_ET-00845_RWR | Submitted | 2026-04-02 | 2026_ET-00845_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00845_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00845_WR | 2026-05-21 | 05-24-2026 | QC Accepted | 06-04-2026 | 2026-05-25 | 0 | 2026_ET-00845_VMLAZ | 2026-05-01 | QC Accepted | 06-04-2026 | 2026-05-25 | 0 | 2026_ET-00845_VMM1 | 2026-05-21 | QC Accepted |  | 06-04-2026 | 2026-05-25 |  | 2026_ET-00845_RR | 2026-05-18 | No Violations | 05-26-2026 | [5 empty] | 2026_ET-00845_VER | 2026-05-21 | QC Accepted | 06-04-2026 | 2026-05-25 | 0 |  |  |  |  | Completed Late - Program | Projected On Time | Completed On Time - Program | MOORPARK-PARDEE NO. 1_ET-00845 |  |  | Yes |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARRO-CARDIFF-STODDARD | ET-00849 | 2026_ET-00849 |  | 1 | 2026 | Apr 01, 2026 | 33 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 2.7666 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-28 | 01-01-2026 | Flown | 2025-10-22 | 04-28-2026 | 01-12-2026 |  | 2026_ET-00849_ACQPKG | 2026_ET-00849_GSPKG | Submitted | 2026_ET-00849_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00849_GCPR | 2025-12-08 | Historical | 2026_ET-00849_ACQ | QC Accepted | 2026_ET-00849_FR | 2026-01-01 | Submitted | 2026_ET-00849_RWR | Submitted | 2026-01-01 | 2026_ET-00849_CLAZ | 2026-01-01 | QC Accepted | 01-16-2026 | 2026-01-12 | 0 | 2026_ET-00849_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-00849_WR | 2026-03-12 | 05-28-2026 | QC Accepted | 03-26-2026 | 2026-03-16 | 0 | 2026_ET-00849_VMLAZ | 2026-03-04 | QC Accepted | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00849_VMM1 | 2026-03-04 | QC Accepted |  | 03-18-2026 | 2026-03-16 | 0 | 2026_ET-00849_RR | 2026-03-09 | No Violations | 03-17-2026 |  | 0 |  |  |  | 2026_ET-00849_VER | 2026-03-04 | Uploaded to S123 | 03-18-2026 | 2026-03-16 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | ARRO-CARDIFF-STODDARD_ET-00849 | Done |  | No | 19:43 |  | REDLANDS | 31 | UNK | 2025-10-22 14:04 PDT ¦ 2025-10-22 14:08 PDT | 102225 | 20251022 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-NEWHALL NO.3 | ET-00858 | 2026_ET-00858 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.017 | 5.017 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-04 |  | 05-11-2026 |  | 2026_ET-00858_ACQPKG | 2026_ET-00858_GSPKG | Submitted | 2026_ET-00858_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00858_GCPR | 2025-12-08 | Historical | 2026_ET-00858_ACQ | QC Accepted | 2026_ET-00858_FR | 2026-05-03 | Submitted | 2026_ET-00858_RWR | Submitted | 2026-05-03 | 2026_ET-00858_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00858_PROCPKG | In Progress | SCE | 2026_ET-00858_WR |  |  | In Progress |  |  |  | 2026_ET-00858_VMLAZ |  | In Progress |  |  |  | 2026_ET-00858_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00858_RR |  | In Progress | [6 empty] | 2026_ET-00858_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | SAUGUS-NEWHALL NO.3_ET-00858 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-ESTRELLA NO. 1 | ET-00865 | 2026_ET-00865 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 6.2841 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-06 | 04-16-2026 | 04-09-2026 |  | 2026_ET-00865_ACQPKG | 2026_ET-00865_GSPKG | Submitted | 2026_ET-00865_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00865_GCPR | 2025-12-08 | Historical | 2026_ET-00865_ACQ | QC Accepted | 2026_ET-00865_FR | 2026-04-02 | Submitted | 2026_ET-00865_RWR | Submitted | 2026-04-02 | 2026_ET-00865_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00865_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00865_WR | 2026-05-14 | 05-16-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00865_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00865_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-00865_RR | 2026-05-07 | Violations QC Confirmed | 05-19-2026 | 05-19-2026 | 3 | 2026-05-08 | 0 | 3 | 2026_ET-00865_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTIAGO-ESTRELLA NO. 1_ET-00865 |  |  | No |  |  | SADDLEBACK | 43 | UNK | 2026-02-06 07:54 PST ¦ 2026-02-27 13:51 PST | 020626 | 20260227 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN ONOFRE-VIEJO | ET-00881 | 2026_ET-00881 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_6 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 02-26-2026 | 03-28-2026 | Late | 116 | Transmission | 23.312 | 20.7049 | 89 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2026-02-25 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | Delay | Variable | SCE | Access | Upload Challenge | Access | Airspace restricitions, waiting on clearance from FAA/Airport | UploadChallenge | N/A | SCE Approved |  | 14 | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-19 | 04-27-2026 | Flown | 2026-03-11 | 04-29-2026 | 04-29-2026 |  | 2026_ET-00881_ACQPKG | 2026_ET-00881_GSPKG | Submitted | 2026_ET-00881_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00881_GCPR | 2025-12-08 | Historical | 2026_ET-00881_ACQ | QC Accepted | 2026_ET-00881_FR |  | Not Started | 2026_ET-00881_RWR | Submitted | 2026-03-11 | 2026_ET-00881_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-29 | 0 | 2026_ET-00881_PROCPKG | In Progress | All Good - Complete | 2026_ET-00881_WR |  | 06-12-2026 | Not Started |  |  |  | 2026_ET-00881_VMLAZ |  | In Progress |  |  |  | 2026_ET-00881_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00881_RR |  | In Progress | [6 empty] | 2026_ET-00881_VER |  | In Progress | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | SAN ONOFRE-VIEJO_ET-00881 |  |  | Yes | 17:14 |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CASA DIABLO-RUSH CREEK | ET-00886 | 2026_ET-00886 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_3 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 04-02-2026 | On Time | 0 | Transmission | 19.6371 | 19.6371 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repetitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | SCE Approved | N/A | 30 |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 05-02-2026 | Flown | 2026-04-09 | 04-28-2026 | 04-28-2026 |  | 2026_ET-00886_ACQPKG | 2026_ET-00886_GSPKG | Submitted | 2026_ET-00886_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00886_GCPR | 2025-12-08 | Historical | 2026_ET-00886_ACQ | QC Accepted | 2026_ET-00886_FR | 2026-04-28 | Submitted | 2026_ET-00886_RWR | Submitted | 2026-04-28 | 2026_ET-00886_CLAZ | 2026-04-24 | QC Accepted | 05-08-2026 | 2026-04-27 |  | 2026_ET-00886_PROCPKG | Submitted | All Good - Complete | 2026_ET-00886_WR | 2026-05-12 | 05-28-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00886_VMLAZ | 2026-05-12 | Ready for QC | 06-01-2026 |  |  | 2026_ET-00886_VMM1 | 2026-05-12 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-00886_RR | 2026-05-12 | Ready for QC |  |  | 10 |  |  |  | 2026_ET-00886_VER | 2026-05-12 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Projected Late | Completed Late - Program | CASA DIABLO-RUSH CREEK_ET-00886 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | 1969-12-31 16:00 PST ¦ 1969-12-31 16:00 PST | 123169 | 19691231 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-MOORPARK-SANTA SUSANA-TORREY | ET-00900 | 2026_ET-00900 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 36.6141 | 36.6141 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-11 |  | 05-13-2026 |  | 2026_ET-00900_ACQPKG | 2026_ET-00900_GSPKG | Submitted | 2026_ET-00900_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00900_GCPR | 2025-12-08 | Historical | 2026_ET-00900_ACQ | QC Accepted | 2026_ET-00900_FR | 2026-05-03 | Submitted | 2026_ET-00900_RWR | Submitted | 2026-05-03 | 2026_ET-00900_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-00900_PROCPKG | In Progress | SCE | 2026_ET-00900_WR |  |  | In Progress |  |  |  | 2026_ET-00900_VMLAZ |  | In Progress |  |  |  | 2026_ET-00900_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00900_RR |  | In Progress | [6 empty] | 2026_ET-00900_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | SAUGUS-MOORPARK-SANTA SUSANA-TORREY_ET-00900 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-SUN CITY | ET-00901 | 2026_ET-00901 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 3.96 | 2.0694 | 52 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00901_ACQPKG | 2026_ET-00901_GSPKG | Submitted | 2026_ET-00901_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00901_GCPR | 2025-12-08 | Historical | 2026_ET-00901_ACQ | In Progress | 2026_ET-00901_FR |  | Not Started | 2026_ET-00901_RWR | Not Started |  | 2026_ET-00901_CLAZ |  | Not Started |  |  |  | 2026_ET-00901_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00901_WR |  |  | Not Started |  |  |  | 2026_ET-00901_VMLAZ |  | Not Started |  |  |  | 2026_ET-00901_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00901_RR |  | Not Started | [6 empty] | 2026_ET-00901_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VALLEY-SUN CITY_ET-00901 |  |  | No |  |  | MENIFEE | 77 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ACTON-PALMDALE-SHUTTLE | ET-00905 | 2026_ET-00905 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 20.2724 | 9.4642 | 47 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 04-16-2026 |  | 2026_ET-00905_ACQPKG | 2026_ET-00905_GSPKG | Submitted | 2026_ET-00905_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00905_GCPR | 2025-12-08 | Historical | 2026_ET-00905_ACQ | QC Accepted | 2026_ET-00905_FR | 2026-03-16 | Submitted | 2026_ET-00905_RWR | Submitted | 2026-03-16 | 2026_ET-00905_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-16 |  | 2026_ET-00905_PROCPKG | In Progress | SCE | 2026_ET-00905_WR |  |  | In Progress |  |  |  | 2026_ET-00905_VMLAZ |  | In Progress |  |  |  | 2026_ET-00905_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00905_RR |  | In Progress | [6 empty] | 2026_ET-00905_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ACTON-PALMDALE-SHUTTLE_ET-00905 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 13:03 PST ¦ 2026-02-21 09:49 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAYFAIR-WEYMOUTH | ET-00906 | 2026_ET-00906 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 1.2314 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00906_ACQPKG | 2026_ET-00906_GSPKG | Submitted | 2026_ET-00906_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00906_GCPR | 2025-12-08 | Historical | 2026_ET-00906_ACQ | In Progress | 2026_ET-00906_FR |  | Not Started | 2026_ET-00906_RWR | Not Started |  | 2026_ET-00906_CLAZ |  | Not Started |  |  |  | 2026_ET-00906_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00906_WR |  |  | Not Started |  |  |  | 2026_ET-00906_VMLAZ |  | Not Started |  |  |  | 2026_ET-00906_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00906_RR |  | Not Started | [6 empty] | 2026_ET-00906_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LAYFAIR-WEYMOUTH_ET-00906 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIVE OAK-WEYMOUTH | ET-00907 | 2026_ET-00907 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.61 | 0.84851 | 24 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-13-2026 |  | 2026_ET-00907_ACQPKG | 2026_ET-00907_GSPKG | Submitted | 2026_ET-00907_GS | 2026-01-31 | Field Complete | 2026_ET-00907_GCPR | 2026-05-03 | Submitted | 2026_ET-00907_ACQ | QC Accepted | 2026_ET-00907_FR | 2026-05-03 | Submitted | 2026_ET-00907_RWR | Submitted | 2026-05-03 | 2026_ET-00907_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-00907_PROCPKG | In Progress | SCE | 2026_ET-00907_WR |  |  | In Progress |  |  |  | 2026_ET-00907_VMLAZ |  | In Progress |  |  |  | 2026_ET-00907_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00907_RR |  | In Progress | [6 empty] | 2026_ET-00907_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIVE OAK-WEYMOUTH_ET-00907 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-DRACKER | ET-00908 | 2026_ET-00908 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.095849 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-21 | 05-11-2026 | 05-11-2026 |  | 2026_ET-00908_ACQPKG | 2026_ET-00908_GSPKG | Submitted | 2026_ET-00908_GS | 2026-01-31 | Field Complete | 2026_ET-00908_GCPR | 2026-05-03 | Submitted | 2026_ET-00908_ACQ | QC Accepted | 2026_ET-00908_FR | 2026-05-03 | Submitted | 2026_ET-00908_RWR | Submitted | 2026-05-03 | 2026_ET-00908_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00908_PROCPKG | In Progress | All Good - Complete | 2026_ET-00908_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-00908_VMLAZ |  | In Progress |  |  |  | 2026_ET-00908_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00908_RR |  | In Progress | [6 empty] | 2026_ET-00908_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | COLORADO RIVER-DRACKER_ET-00908 |  |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-COMPRESS NO. 1 | ET-00914 | 2026_ET-00914 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.79749 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00914_ACQPKG | 2026_ET-00914_GSPKG | Submitted | 2026_ET-00914_GS | 2025-12-08 | Field Complete | 2026_ET-00914_GCPR | 2026-05-22 | Submitted | 2026_ET-00914_ACQ | Submitted | 2026_ET-00914_FR | 2026-05-22 | Submitted | 2026_ET-00914_RWR | Submitted | 2026-05-22 | 2026_ET-00914_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00914_PROCPKG | In Progress | SCE | 2026_ET-00914_WR |  |  | Not Started |  |  |  | 2026_ET-00914_VMLAZ |  | Not Started |  |  |  | 2026_ET-00914_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00914_RR |  | Not Started | [6 empty] | 2026_ET-00914_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | LA FRESA-COMPRESS NO. 1_ET-00914 |  |  | No |  | Helicopter | SOUTH BAY | 44 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-COMPRESS NO. 2 | ET-00915 | 2026_ET-00915 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.32814 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00915_ACQPKG | 2026_ET-00915_GSPKG | Submitted | 2026_ET-00915_GS | 2025-12-08 | Field Complete | 2026_ET-00915_GCPR | 2026-05-22 | Submitted | 2026_ET-00915_ACQ | Submitted | 2026_ET-00915_FR | 2026-05-22 | Submitted | 2026_ET-00915_RWR | Submitted | 2026-05-22 | 2026_ET-00915_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00915_PROCPKG | In Progress | SCE | 2026_ET-00915_WR |  |  | Not Started |  |  |  | 2026_ET-00915_VMLAZ |  | Not Started |  |  |  | 2026_ET-00915_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00915_RR |  | Not Started | [6 empty] | 2026_ET-00915_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | LA FRESA-COMPRESS NO. 2_ET-00915 |  |  | No |  | Helicopter | SOUTH BAY | 44 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-STEWART | ET-00922 | 2026_ET-00922 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 6.4944 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00922_ACQPKG | 2026_ET-00922_GSPKG | Submitted | 2026_ET-00922_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00922_GCPR | 2025-12-08 | Historical | 2026_ET-00922_ACQ | In Progress | 2026_ET-00922_FR |  | Not Started | 2026_ET-00922_RWR | Not Started |  | 2026_ET-00922_CLAZ |  | Not Started |  |  |  | 2026_ET-00922_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00922_WR |  |  | Not Started |  |  |  | 2026_ET-00922_VMLAZ |  | Not Started |  |  |  | 2026_ET-00922_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00922_RR |  | Not Started | [6 empty] | 2026_ET-00922_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CENTER-STEWART_ET-00922 |  |  | No |  |  | WHITTIER | 47 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-VAIL-WHITEWALL | ET-00929 | 2026_ET-00929 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.65999 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00929_ACQPKG | 2026_ET-00929_GSPKG | Submitted | 2026_ET-00929_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00929_GCPR | 2025-12-08 | Historical | 2026_ET-00929_ACQ | In Progress | 2026_ET-00929_FR |  | Not Started | 2026_ET-00929_RWR | Not Started |  | 2026_ET-00929_CLAZ |  | Not Started |  |  |  | 2026_ET-00929_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00929_WR |  |  | Not Started |  |  |  | 2026_ET-00929_VMLAZ |  | Not Started |  |  |  | 2026_ET-00929_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00929_RR |  | Not Started | [6 empty] | 2026_ET-00929_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE LAGUNA BELL-VAIL-WHITEWALL_ET-00929 |  |  | No |  |  | MONTEBELLO | 22 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-GENESIS | ET-00935 | 2026_ET-00935 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.096132 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-11-2026 |  | 2026_ET-00935_ACQPKG | 2026_ET-00935_GSPKG | Submitted | 2026_ET-00935_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00935_GCPR | 2025-12-08 | Historical | 2026_ET-00935_ACQ | QC Accepted | 2026_ET-00935_FR | 2026-05-03 | Submitted | 2026_ET-00935_RWR | Submitted | 2026-05-03 | 2026_ET-00935_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00935_PROCPKG | In Progress | SCE | 2026_ET-00935_WR |  |  | In Progress |  |  |  | 2026_ET-00935_VMLAZ |  | In Progress |  |  |  | 2026_ET-00935_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00935_RR |  | In Progress | [6 empty] | 2026_ET-00935_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | COLORADO RIVER-GENESIS_ET-00935 |  |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTA CLARA-CHARMIN-LEVY | ET-00941 | 2026_ET-00941 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 1.2688 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-00941_ACQPKG | 2026_ET-00941_GSPKG | Submitted | 2026_ET-00941_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00941_GCPR | 2025-12-08 | Historical | 2026_ET-00941_ACQ | In Progress | 2026_ET-00941_FR |  | Not Started | 2026_ET-00941_RWR | Not Started |  | 2026_ET-00941_CLAZ |  | Not Started |  |  |  | 2026_ET-00941_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00941_WR |  |  | Not Started |  |  |  | 2026_ET-00941_VMLAZ |  | Not Started |  |  |  | 2026_ET-00941_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00941_RR |  | Not Started | [6 empty] | 2026_ET-00941_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE SANTA CLARA-CHARMIN-LEVY_ET-00941 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-RED BLUFF NO.1 | ET-00942 | 2026_ET-00942 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 80.1231 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 04-02-2026 | Flown | 2026-02-03 | 05-07-2026 | 04-29-2026 |  | 2026_ET-00942_ACQPKG | 2026_ET-00942_GSPKG | Submitted | 2026_ET-00942_GS | 2026-01-23 | Field Complete | 2026_ET-00942_GCPR | 2026-01-30 | Submitted | 2026_ET-00942_ACQ | QC Accepted | 2026_ET-00942_FR |  | Not Started | 2026_ET-00942_RWR | Submitted | 2026-04-29 | 2026_ET-00942_CLAZ | 2026-03-06 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00942_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00942_WR | 2026-05-18 | 06-06-2026 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00942_VMLAZ | 2026-05-04 | QC Accepted | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00942_VMM1 | 2026-05-18 | QC Accepted |  | 06-01-2026 | 2026-05-22 | 0 | 2026_ET-00942_RR | 2026-05-18 | No Violations | 05-23-2026 | [5 empty] | 2026_ET-00942_VER | 2026-05-18 | Uploaded to S123 | 06-01-2026 | 2026-05-22 | 0 |  |  |  |  | Completed Late - Program | Completed On Time | Completed On Time - Program | DEVERS-RED BLUFF NO.1_ET-00942 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLORADO RIVER-PALO VERDE | ET-00945 | 2026_ET-00945 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 128.2056 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-02-09 | 04-24-2026 | 04-14-2026 |  | 2026_ET-00945_ACQPKG | 2026_ET-00945_GSPKG | Submitted | 2026_ET-00945_GS | 2025-12-08 | Field Complete | 2026_ET-00945_GCPR | 2026-04-02 | Submitted | 2026_ET-00945_ACQ | QC Accepted | 2026_ET-00945_FR | 2026-04-02 | Submitted | 2026_ET-00945_RWR | Submitted | 2026-04-02 | 2026_ET-00945_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-00945_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00945_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-06 |  | 2026_ET-00945_VMLAZ | 2026-05-04 | QC Accepted | 06-01-2026 | 2026-05-05 |  | 2026_ET-00945_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-06 |  | 2026_ET-00945_RR | 2026-05-06 | No Violations | 05-07-2026 | [5 empty] | 2026_ET-00945_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | COLORADO RIVER-PALO VERDE_ET-00945 |  |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-DEL AMO | ET-00946 | 2026_ET-00946 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 9.7492 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-19 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-09-2026 |  | 2026_ET-00946_ACQPKG | 2026_ET-00946_GSPKG | Submitted | 2026_ET-00946_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00946_GCPR | 2025-12-08 | Historical | 2026_ET-00946_ACQ | QC Accepted | 2026_ET-00946_FR | 2026-04-02 | Submitted | 2026_ET-00946_RWR | Submitted | 2026-04-02 | 2026_ET-00946_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-00946_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00946_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00946_VMLAZ | 2026-05-01 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00946_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-00946_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-00946_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-DEL AMO_ET-00946 | Done |  | Yes |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-INYOKERN-RANDSBURG NO. 1 | ET-00948 | 2026_ET-00948 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 96.7439 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 01-01-2026 | Weather Delay |  |  |  |  | 2026_ET-00948_ACQPKG | 2026_ET-00948_GSPKG | In Progress | 2026_ET-00948_GS |  | Not Started | 2026_ET-00948_GCPR |  | Not Started | 2026_ET-00948_ACQ | In Progress | 2026_ET-00948_FR |  | Not Started | 2026_ET-00948_RWR | Not Started |  | 2026_ET-00948_CLAZ |  | Not Started |  |  |  | 2026_ET-00948_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00948_WR |  |  | Not Started |  |  |  | 2026_ET-00948_VMLAZ |  | Not Started |  |  |  | 2026_ET-00948_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00948_RR |  | Not Started | [6 empty] | 2026_ET-00948_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-INYOKERN-RANDSBURG NO. 1_ET-00948 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-INYOKERN-RANDSBURG NO. 3 | ET-00949 | 2026_ET-00949 |  | 1 | 2026 | May 01, 2026 | 115 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 49.7275 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 01-31-2026 | Weather Delay |  |  |  |  | 2026_ET-00949_ACQPKG | 2026_ET-00949_GSPKG | Submitted | 2026_ET-00949_GS | 2026-01-23 | Field Complete | 2026_ET-00949_GCPR | 2026-01-30 | Submitted | 2026_ET-00949_ACQ | In Progress | 2026_ET-00949_FR |  | Not Started | 2026_ET-00949_RWR | Not Started |  | 2026_ET-00949_CLAZ |  | Not Started |  |  |  | 2026_ET-00949_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00949_WR |  |  | Not Started |  |  |  | 2026_ET-00949_VMLAZ |  | Not Started |  |  |  | 2026_ET-00949_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00949_RR |  | Not Started | [6 empty] | 2026_ET-00949_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-INYOKERN-RANDSBURG NO. 3_ET-00949 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CASA DIABLO-CONTROL | ET-00951 | 2026_ET-00951 |  | 1 | 2026 | Aug 01, 2026 | 115 | CA_3 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 05-03-2026 | On Time | 0 | Transmission | 53.0439 | 48.8503 | 92 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repetitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | SCE Approved | N/A | 30 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-02-2026 | Flown | 2026-04-09 |  | 05-05-2026 |  | 2026_ET-00951_ACQPKG | 2026_ET-00951_GSPKG | Submitted | 2026_ET-00951_GS | 2024-09-07 | Field Complete | 2026_ET-00951_GCPR | 2025-12-08 | Submitted | 2026_ET-00951_ACQ | QC Accepted | 2026_ET-00951_FR | 2026-04-28 | Submitted | 2026_ET-00951_RWR | Submitted | 2026-04-28 | 2026_ET-00951_CLAZ | 2026-04-24 | QC Accepted | 05-18-2026 | 2026-05-05 | 0 | 2026_ET-00951_PROCPKG | In Progress | SCE | 2026_ET-00951_WR |  |  | In Progress |  |  |  | 2026_ET-00951_VMLAZ |  | In Progress |  |  |  | 2026_ET-00951_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00951_RR |  | In Progress | [6 empty] | 2026_ET-00951_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Completed On Time - Program | CASA DIABLO-CONTROL_ET-00951 | Done |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-RED BLUFF NO.2 | ET-00958 | 2026_ET-00958 |  | 1 | 2026 | Jul 01, 2026 | 500 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 80.0877 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-08 | 04-24-2026 | 04-14-2026 |  | 2026_ET-00958_ACQPKG | 2026_ET-00958_GSPKG | Submitted | 2026_ET-00958_GS | 2025-12-08 | Field Complete | 2026_ET-00958_GCPR | 2026-04-02 | Submitted | 2026_ET-00958_ACQ | QC Accepted | 2026_ET-00958_FR | 2026-04-02 | Submitted | 2026_ET-00958_RWR | Submitted | 2026-04-02 | 2026_ET-00958_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-00958_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-00958_WR | 2026-05-04 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-06 |  | 2026_ET-00958_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-00958_VMM1 | 2026-05-04 | QC Accepted |  | 06-01-2026 | 2026-05-06 |  | 2026_ET-00958_RR | 2026-05-04 | No Violations | 05-07-2026 | [5 empty] | 2026_ET-00958_VER | 2026-05-04 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEVERS-RED BLUFF NO.2_ET-00958 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GRAND CROSSING-TROPHY | ET-00965 | 2026_ET-00965 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.88092 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-00965_ACQPKG | 2026_ET-00965_GSPKG | Submitted | 2026_ET-00965_GS | 2025-12-08 | Field Complete | 2026_ET-00965_GCPR | 2026-05-22 | Submitted | 2026_ET-00965_ACQ | Submitted | 2026_ET-00965_FR | 2026-05-22 | Submitted | 2026_ET-00965_RWR | Submitted | 2026-05-22 | 2026_ET-00965_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-00965_PROCPKG | In Progress | SCE | 2026_ET-00965_WR |  |  | Not Started |  |  |  | 2026_ET-00965_VMLAZ |  | Not Started |  |  |  | 2026_ET-00965_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00965_RR |  | Not Started | [6 empty] | 2026_ET-00965_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | GRAND CROSSING-TROPHY_ET-00965 |  |  | No |  | Helicopter | COVINA | 26 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AULD-MORAGA NO.1 | ET-00968 | 2026_ET-00968 |  | 1 | 2026 | Oct 01, 2026 | 115 | CA_6 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 8.2427 | 2.2682 | 28 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00968_ACQPKG | 2026_ET-00968_GSPKG | Submitted | 2026_ET-00968_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00968_GCPR | 2025-12-08 | Historical | 2026_ET-00968_ACQ | In Progress | 2026_ET-00968_FR |  | Not Started | 2026_ET-00968_RWR | Not Started |  | 2026_ET-00968_CLAZ |  | Not Started |  |  |  | 2026_ET-00968_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00968_WR |  |  | Not Started |  |  |  | 2026_ET-00968_VMLAZ |  | Not Started |  |  |  | 2026_ET-00968_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00968_RR |  | Not Started | [6 empty] | 2026_ET-00968_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | AULD-MORAGA NO.1_ET-00968 | Done |  | No |  |  | WILDOMAR | 88 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AULD-MORAGA NO.2 | ET-00969 | 2026_ET-00969 |  | 1 | 2026 | Oct 01, 2026 | 115 | CA_6 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 8.9406 | 4.5692 | 51 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-00969_ACQPKG | 2026_ET-00969_GSPKG | Submitted | 2026_ET-00969_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00969_GCPR | 2025-12-08 | Historical | 2026_ET-00969_ACQ | In Progress | 2026_ET-00969_FR |  | Not Started | 2026_ET-00969_RWR | Not Started |  | 2026_ET-00969_CLAZ |  | Not Started |  |  |  | 2026_ET-00969_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00969_WR |  |  | Not Started |  |  |  | 2026_ET-00969_VMLAZ |  | Not Started |  |  |  | 2026_ET-00969_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00969_RR |  | Not Started | [6 empty] | 2026_ET-00969_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | AULD-MORAGA NO.2_ET-00969 | Done |  | No |  |  | WILDOMAR | 88 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-GANESHA-LA HABRA-SOUTH- WALNT | ET-00976 | 2026_ET-00976 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.2309 | 1.2309 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-28 | 05-13-2026 | 05-13-2026 |  | 2026_ET-00976_ACQPKG | 2026_ET-00976_GSPKG | Submitted | 2026_ET-00976_GS | 2026-01-31 | Field Complete | 2026_ET-00976_GCPR | 2026-05-03 | Submitted | 2026_ET-00976_ACQ | QC Accepted | 2026_ET-00976_FR | 2026-05-03 | Submitted | 2026_ET-00976_RWR | Submitted | 2026-05-03 | 2026_ET-00976_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-00976_PROCPKG | In Progress | All Good - Complete | 2026_ET-00976_WR |  | 06-12-2026 | In Progress |  |  |  | 2026_ET-00976_VMLAZ |  | In Progress |  |  |  | 2026_ET-00976_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00976_RR |  | In Progress | [6 empty] | 2026_ET-00976_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE CHINO-GANESHA-LA HABRA-SOUTH- WALNT_ET-00976 |  |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLACK CREEK-COLORADO RIVER | ET-00978 | 2026_ET-00978 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.097247 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-11-2026 |  | 2026_ET-00978_ACQPKG | 2026_ET-00978_GSPKG | Submitted | 2026_ET-00978_GS | 2026-01-31 | Field Complete | 2026_ET-00978_GCPR | 2026-05-03 | Submitted | 2026_ET-00978_ACQ | QC Accepted | 2026_ET-00978_FR | 2026-05-03 | Submitted | 2026_ET-00978_RWR | Submitted | 2026-05-03 | 2026_ET-00978_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00978_PROCPKG | In Progress | SCE | 2026_ET-00978_WR |  |  | In Progress |  |  |  | 2026_ET-00978_VMLAZ |  | In Progress |  |  |  | 2026_ET-00978_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00978_RR |  | In Progress | [6 empty] | 2026_ET-00978_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BLACK CREEK-COLORADO RIVER_ET-00978 | Done |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-RTS 48 | ET-00993 | 2026_ET-00993 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 16.0445 | 11.2944 | 70 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-09 |  | 05-11-2026 |  | 2026_ET-00993_ACQPKG | 2026_ET-00993_GSPKG | Submitted | 2026_ET-00993_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00993_GCPR | 2025-12-08 | Historical | 2026_ET-00993_ACQ | QC Accepted | 2026_ET-00993_FR | 2026-05-03 | Submitted | 2026_ET-00993_RWR | Submitted | 2026-05-03 | 2026_ET-00993_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-00993_PROCPKG | In Progress | SCE | 2026_ET-00993_WR |  |  | In Progress |  |  |  | 2026_ET-00993_VMLAZ |  | In Progress |  |  |  | 2026_ET-00993_VMM1 |  | In Progress |  |  |  |  | 2026_ET-00993_RR |  | In Progress | [6 empty] | 2026_ET-00993_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MOORPARK-RTS 48_ET-00993 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MANDALAY-SAN MIGUEL | ET-00994 | 2026_ET-00994 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.4178 | 0.45824 | 10 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-00994_ACQPKG | 2026_ET-00994_GSPKG | Submitted | 2026_ET-00994_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00994_GCPR | 2025-12-08 | Historical | 2026_ET-00994_ACQ | In Progress | 2026_ET-00994_FR |  | Not Started | 2026_ET-00994_RWR | Not Started |  | 2026_ET-00994_CLAZ |  | Not Started |  |  |  | 2026_ET-00994_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-00994_WR |  |  | Not Started |  |  |  | 2026_ET-00994_VMLAZ |  | Not Started |  |  |  | 2026_ET-00994_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00994_RR |  | Not Started | [6 empty] | 2026_ET-00994_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MANDALAY-SAN MIGUEL_ET-00994 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CARDIFF-CAPSULE-STODDARD | ET-01005 | 2026_ET-01005 |  | 1 | 2026 | Jul 01, 2026 | 33 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.57078 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-01-31 | 04-15-2026 | 04-15-2026 |  | 2026_ET-01005_ACQPKG | 2026_ET-01005_GSPKG | Submitted | 2026_ET-01005_GS | 2025-12-08 | Field Complete | 2026_ET-01005_GCPR | 2026-04-02 | Submitted | 2026_ET-01005_ACQ | QC Accepted | 2026_ET-01005_FR | 2026-04-02 | Submitted | 2026_ET-01005_RWR | Submitted | 2026-04-02 | 2026_ET-01005_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01005_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01005_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01005_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01005_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01005_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01005_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE CARDIFF-CAPSULE-STODDARD_ET-01005 |  |  | No |  |  | REDLANDS | 31 | UNK | 2026-01-31 09:24 PST ¦ 2026-03-18 11:57 PDT | 013126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOWL-LONG BEACH | ET-01009 | 2026_ET-01009 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.3962 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-05 |  | 05-13-2026 |  | 2026_ET-01009_ACQPKG | 2026_ET-01009_GSPKG | Submitted | 2026_ET-01009_GS | 2026-01-31 | Field Complete | 2026_ET-01009_GCPR | 2026-05-03 | Submitted | 2026_ET-01009_ACQ | QC Accepted | 2026_ET-01009_FR | 2026-05-03 | Submitted | 2026_ET-01009_RWR | Submitted | 2026-05-03 | 2026_ET-01009_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-01009_PROCPKG | In Progress | SCE | 2026_ET-01009_WR |  |  | In Progress |  |  |  | 2026_ET-01009_VMLAZ |  | In Progress |  |  |  | 2026_ET-01009_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01009_RR |  | In Progress | [6 empty] | 2026_ET-01009_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BOWL-LONG BEACH_ET-01009 | Done |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DIKE-LONG BEACH | ET-01016 | 2026_ET-01016 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.1855 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-05 |  | 05-13-2026 |  | 2026_ET-01016_ACQPKG | 2026_ET-01016_GSPKG | Submitted | 2026_ET-01016_GS | 2026-01-31 | Field Complete | 2026_ET-01016_GCPR | 2026-05-03 | Submitted | 2026_ET-01016_ACQ | QC Accepted | 2026_ET-01016_FR | 2026-05-03 | Submitted | 2026_ET-01016_RWR | Submitted | 2026-05-03 | 2026_ET-01016_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-13 | 0 | 2026_ET-01016_PROCPKG | In Progress | SCE | 2026_ET-01016_WR |  |  | In Progress |  |  |  | 2026_ET-01016_VMLAZ |  | In Progress |  |  |  | 2026_ET-01016_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01016_RR |  | In Progress | [6 empty] | 2026_ET-01016_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DIKE-LONG BEACH_ET-01016 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LATIGO-POTRERO | ET-01019 | 2026_ET-01019 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 17.2735 | 17.2735 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-11 |  | 05-14-2026 |  | 2026_ET-01019_ACQPKG | 2026_ET-01019_GSPKG | Submitted | 2026_ET-01019_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01019_GCPR | 2025-12-08 | Historical | 2026_ET-01019_ACQ | QC Accepted | 2026_ET-01019_FR | 2026-05-03 | Submitted | 2026_ET-01019_RWR | Submitted | 2026-05-03 | 2026_ET-01019_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-14 | 0 | 2026_ET-01019_PROCPKG | In Progress | SCE | 2026_ET-01019_WR |  |  | In Progress |  |  |  | 2026_ET-01019_VMLAZ |  | In Progress |  |  |  | 2026_ET-01019_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01019_RR |  | In Progress | [6 empty] | 2026_ET-01019_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LATIGO-POTRERO_ET-01019 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NEWBURY-THOUSAND OAKS | ET-01020 | 2026_ET-01020 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 12.3655 | 12.3655 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-10 |  | 05-20-2026 |  | 2026_ET-01020_ACQPKG | 2026_ET-01020_GSPKG | Submitted | 2026_ET-01020_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01020_GCPR | 2025-12-08 | Historical | 2026_ET-01020_ACQ | QC Accepted | 2026_ET-01020_FR | 2026-05-03 | Submitted | 2026_ET-01020_RWR | Submitted | 2026-05-03 | 2026_ET-01020_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01020_PROCPKG | In Progress | SCE | 2026_ET-01020_WR |  |  | Not Started |  |  |  | 2026_ET-01020_VMLAZ |  | Not Started |  |  |  | 2026_ET-01020_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01020_RR |  | Not Started | [6 empty] | 2026_ET-01020_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | NEWBURY-THOUSAND OAKS_ET-01020 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARCHIBALD-CHINO-CORONA | ET-01029 | 2026_ET-01029 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 14.5458 | 1.7238 | 12 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-16 | 04-20-2026 | 04-09-2026 |  | 2026_ET-01029_ACQPKG | 2026_ET-01029_GSPKG | Submitted | 2026_ET-01029_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01029_GCPR | 2025-12-08 | Historical | 2026_ET-01029_ACQ | QC Accepted | 2026_ET-01029_FR | 2026-04-02 | Submitted | 2026_ET-01029_RWR | Submitted | 2026-04-02 | 2026_ET-01029_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-01029_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01029_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01029_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01029_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01029_RR | 2026-05-10 | Violations QC Confirmed | 05-20-2026 | 05-20-2026 | 3 | 2026-05-11 | 0 | 3 | 2026_ET-01029_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | ARCHIBALD-CHINO-CORONA_ET-01029 | Done |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-29 10:50 PST ¦ 2026-03-16 13:05 PDT | 021526 | 20260316 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 3-RECTOR NO.1 | ET-01046 | 2026_ET-01046 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_4 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 64.6985 | 25.2117 | 39 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repetitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | N/A | N/A | 30 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 04-22-2026 |  | 2026_ET-01046_ACQPKG | 2026_ET-01046_GSPKG | Submitted | 2026_ET-01046_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01046_GCPR | 2025-12-08 | Historical | 2026_ET-01046_ACQ | QC Accepted | 2026_ET-01046_FR | 2026-03-16 | Submitted | 2026_ET-01046_RWR | Submitted | 2026-03-16 | 2026_ET-01046_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-22 | 0 | 2026_ET-01046_PROCPKG | In Progress | SCE | 2026_ET-01046_WR |  |  | In Progress |  |  |  | 2026_ET-01046_VMLAZ |  | In Progress |  |  |  | 2026_ET-01046_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01046_RR |  | In Progress | [6 empty] | 2026_ET-01046_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BIG CREEK 3-RECTOR NO.1_ET-01046 | Done |  | Yes |  | Helicopter | TULARE | 51 | HC | 2026-02-26 13:58 PST ¦ 2026-03-01 10:28 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COSMIC-HOWARD-YUKON | ET-01052 | 2026_ET-01052 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.689 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01052_ACQPKG | 2026_ET-01052_GSPKG | Submitted | 2026_ET-01052_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01052_GCPR | 2025-12-08 | Historical | 2026_ET-01052_ACQ | In Progress | 2026_ET-01052_FR |  | Not Started | 2026_ET-01052_RWR | Not Started |  | 2026_ET-01052_CLAZ |  | Not Started |  |  |  | 2026_ET-01052_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01052_WR |  |  | Not Started |  |  |  | 2026_ET-01052_VMLAZ |  | Not Started |  |  |  | 2026_ET-01052_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01052_RR |  | Not Started | [6 empty] | 2026_ET-01052_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | COSMIC-HOWARD-YUKON_ET-01052 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-BORREGO-MORRO | ET-01056 | 2026_ET-01056 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 9.3492 | 7.6401 | 82 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-20-2026 |  | 2026_ET-01056_ACQPKG | 2026_ET-01056_GSPKG | Submitted | 2026_ET-01056_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01056_GCPR | 2025-12-08 | Historical | 2026_ET-01056_ACQ | QC Accepted | 2026_ET-01056_FR | 2026-05-03 | Submitted | 2026_ET-01056_RWR | Submitted | 2026-05-03 | 2026_ET-01056_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01056_PROCPKG | In Progress | SCE | 2026_ET-01056_WR |  |  | Not Started |  |  |  | 2026_ET-01056_VMLAZ |  | Not Started |  |  |  | 2026_ET-01056_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01056_RR |  | Not Started | [6 empty] | 2026_ET-01056_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | SANTIAGO-BORREGO-MORRO_ET-01056 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 3-RECTOR NO.2 | ET-01058 | 2026_ET-01058 |  | 1 | 2026 | Sep 01, 2026 | 220 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 74.7803 | 55.6443 | 74 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-15 |  | 05-11-2026 |  | 2026_ET-01058_ACQPKG | 2026_ET-01058_GSPKG | Submitted | 2026_ET-01058_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01058_GCPR | 2025-12-08 | Historical | 2026_ET-01058_ACQ | QC Accepted | 2026_ET-01058_FR | 2026-05-08 | Submitted | 2026_ET-01058_RWR | Submitted | 2026-05-08 | 2026_ET-01058_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-11 | 0 | 2026_ET-01058_PROCPKG | In Progress | SCE | 2026_ET-01058_WR |  |  | Not Started |  |  |  | 2026_ET-01058_VMLAZ |  | Not Started |  |  |  | 2026_ET-01058_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01058_RR |  | Not Started | [6 empty] | 2026_ET-01058_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BIG CREEK 3-RECTOR NO.2_ET-01058 | Done |  | Yes |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-BARRE NO. 2 | ET-01063 | 2026_ET-01063 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.4697 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-03 | 05-07-2026 | 05-05-2026 |  | 2026_ET-01063_ACQPKG | 2026_ET-01063_GSPKG | Submitted | 2026_ET-01063_GS | 2026-01-31 | Field Complete | 2026_ET-01063_GCPR | 2026-05-03 | Submitted | 2026_ET-01063_ACQ | QC Accepted | 2026_ET-01063_FR | 2026-05-03 | Submitted | 2026_ET-01063_RWR | Submitted | 2026-05-03 | 2026_ET-01063_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-05 |  | 2026_ET-01063_PROCPKG | In Progress | All Good - Complete | 2026_ET-01063_WR |  | 06-06-2026 | In Progress |  |  |  | 2026_ET-01063_VMLAZ |  | In Progress |  |  |  | 2026_ET-01063_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01063_RR |  | In Progress | [6 empty] | 2026_ET-01063_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ALAMITOS-BARRE NO. 2_ET-01063 | Done |  | Yes |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-INYO | ET-01064 | 2026_ET-01064 |  | 1 | 2026 | Nov 01, 2026 | 115 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 2.8823 | 2.8823 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01064_ACQPKG | 2026_ET-01064_GSPKG | Submitted | 2026_ET-01064_GS | 2024-09-07 | Field Complete | 2026_ET-01064_GCPR | 2025-12-08 | Submitted | 2026_ET-01064_ACQ | In Progress | 2026_ET-01064_FR |  | Not Started | 2026_ET-01064_RWR | Not Started |  | 2026_ET-01064_CLAZ |  | Not Started |  |  |  | 2026_ET-01064_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01064_WR |  |  | Not Started |  |  |  | 2026_ET-01064_VMLAZ |  | Not Started |  |  |  | 2026_ET-01064_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01064_RR |  | Not Started | [6 empty] | 2026_ET-01064_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CONTROL-INYO_ET-01064 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
M.W.D.-REDUCTION | ET-01069 | 2026_ET-01069 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.034481 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-01-30 | 04-21-2026 | 04-15-2026 |  | 2026_ET-01069_ACQPKG | 2026_ET-01069_GSPKG | Submitted | 2026_ET-01069_GS | 2025-12-08 | Field Complete | 2026_ET-01069_GCPR | 2026-04-02 | Submitted | 2026_ET-01069_ACQ | QC Accepted | 2026_ET-01069_FR | 2026-04-02 | Submitted | 2026_ET-01069_RWR | Submitted | 2026-04-02 | 2026_ET-01069_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01069_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01069_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01069_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01069_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01069_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01069_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | M.W.D.-REDUCTION_ET-01069 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-30 09:38 PST ¦ 2026-01-30 09:39 PST | 013026 | 20260130 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-SPRINGVILLE | ET-01073 | 2026_ET-01073 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_4 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 47.7034 | 20.9267 | 44 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-25 |  | 04-17-2026 |  | 2026_ET-01073_ACQPKG | 2026_ET-01073_GSPKG | Submitted | 2026_ET-01073_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01073_GCPR | 2025-12-08 | Historical | 2026_ET-01073_ACQ | QC Accepted | 2026_ET-01073_FR | 2026-03-16 | Submitted | 2026_ET-01073_RWR | Submitted | 2026-03-16 | 2026_ET-01073_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-01073_PROCPKG | In Progress | SCE | 2026_ET-01073_WR |  |  | In Progress |  |  |  | 2026_ET-01073_VMLAZ |  | In Progress |  |  |  | 2026_ET-01073_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01073_RR |  | In Progress | [6 empty] | 2026_ET-01073_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RECTOR-SPRINGVILLE_ET-01073 |  |  | Yes |  | Helicopter | TULARE | 51 | HC | 2026-02-25 11:36 PST ¦ 2026-02-25 13:33 PST | 022526 | 20260225 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEVERS-EISENHOWER-IID | ET-01078 | 2026_ET-01078 |  | 1 | 2026 | Aug 01, 2026 | 115 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.21261 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-20 | 05-15-2026 | 05-15-2026 |  | 2026_ET-01078_ACQPKG | 2026_ET-01078_GSPKG | Submitted | 2026_ET-01078_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01078_GCPR | 2025-12-08 | Historical | 2026_ET-01078_ACQ | QC Accepted | 2026_ET-01078_FR | 2026-05-03 | Submitted | 2026_ET-01078_RWR | Submitted | 2026-05-03 | 2026_ET-01078_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01078_PROCPKG | In Progress | All Good - Complete | 2026_ET-01078_WR |  | 06-14-2026 | In Progress |  |  |  | 2026_ET-01078_VMLAZ |  | In Progress |  |  |  | 2026_ET-01078_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01078_RR |  | In Progress | [6 empty] | 2026_ET-01078_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE DEVERS-EISENHOWER-IID_ET-01078 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 1-RECTOR | ET-01082 | 2026_ET-01082 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_4 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 74.4488 | 35.1758 | 47 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repetitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | N/A | N/A | 30 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 04-17-2026 |  | 2026_ET-01082_ACQPKG | 2026_ET-01082_GSPKG | Submitted | 2026_ET-01082_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01082_GCPR | 2025-12-08 | Historical | 2026_ET-01082_ACQ | QC Accepted | 2026_ET-01082_FR | 2026-03-16 | Submitted | 2026_ET-01082_RWR | Submitted | 2026-03-16 | 2026_ET-01082_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 |  | 2026_ET-01082_PROCPKG | In Progress | SCE | 2026_ET-01082_WR |  |  | In Progress |  |  |  | 2026_ET-01082_VMLAZ |  | In Progress |  |  |  | 2026_ET-01082_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01082_RR |  | In Progress | [6 empty] | 2026_ET-01082_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BIG CREEK 1-RECTOR_ET-01082 | Done |  | Yes |  | Helicopter | SHAVER LAKE | 50 | HC | 2026-02-26 13:58 PST ¦ 2026-03-01 10:28 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
COLONIA-ESTERO | ET-01086 | 2026_ET-01086 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 5.8931 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01086_ACQPKG | 2026_ET-01086_GSPKG | Submitted | 2026_ET-01086_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01086_GCPR | 2025-12-08 | Historical | 2026_ET-01086_ACQ | In Progress | 2026_ET-01086_FR |  | Not Started | 2026_ET-01086_RWR | Not Started |  | 2026_ET-01086_CLAZ |  | Not Started |  |  |  | 2026_ET-01086_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01086_WR |  |  | Not Started |  |  |  | 2026_ET-01086_VMLAZ |  | Not Started |  |  |  | 2026_ET-01086_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01086_RR |  | Not Started | [6 empty] | 2026_ET-01086_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | COLONIA-ESTERO_ET-01086 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLAST-BOTTLE-WINDFARM | ET-01088 | 2026_ET-01088 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 13.5691 | 6.9839 | 51 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01088_ACQPKG | 2026_ET-01088_GSPKG | Submitted | 2026_ET-01088_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01088_GCPR | 2025-12-08 | Historical | 2026_ET-01088_ACQ | Submitted | 2026_ET-01088_FR | 2026-05-22 | Submitted | 2026_ET-01088_RWR | Submitted | 2026-05-22 | 2026_ET-01088_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01088_PROCPKG | In Progress | SCE | 2026_ET-01088_WR |  |  | Not Started |  |  |  | 2026_ET-01088_VMLAZ |  | Not Started |  |  |  | 2026_ET-01088_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01088_RR |  | Not Started | [6 empty] | 2026_ET-01088_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | BLAST-BOTTLE-WINDFARM_ET-01088 | Done |  | No |  | Helicopter | PALM SPRINGS | 79 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLAST-GARNET | ET-01089 | 2026_ET-01089 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.90821 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01089_ACQPKG | 2026_ET-01089_GSPKG | Submitted | 2026_ET-01089_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01089_GCPR | 2025-12-08 | Historical | 2026_ET-01089_ACQ | Submitted | 2026_ET-01089_FR | 2026-05-22 | Submitted | 2026_ET-01089_RWR | Submitted | 2026-05-22 | 2026_ET-01089_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01089_PROCPKG | In Progress | SCE | 2026_ET-01089_WR |  |  | Not Started |  |  |  | 2026_ET-01089_VMLAZ |  | Not Started |  |  |  | 2026_ET-01089_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01089_RR |  | Not Started | [6 empty] | 2026_ET-01089_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | BLAST-GARNET_ET-01089 | Done |  | No |  | Helicopter | PALM SPRINGS | 79 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE COLONIA-LEVY | ET-01090 | 2026_ET-01090 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 0.19664 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01090_ACQPKG | 2026_ET-01090_GSPKG | Submitted | 2026_ET-01090_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01090_GCPR | 2025-12-08 | Historical | 2026_ET-01090_ACQ | In Progress | 2026_ET-01090_FR |  | Not Started | 2026_ET-01090_RWR | Not Started |  | 2026_ET-01090_CLAZ |  | Not Started |  |  |  | 2026_ET-01090_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01090_WR |  |  | Not Started |  |  |  | 2026_ET-01090_VMLAZ |  | Not Started |  |  |  | 2026_ET-01090_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01090_RR |  | Not Started | [6 empty] | 2026_ET-01090_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE COLONIA-LEVY_ET-01090 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MARINE-SANTA MONICA | ET-01092 | 2026_ET-01092 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 0.84164 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01092_ACQPKG | 2026_ET-01092_GSPKG | Submitted | 2026_ET-01092_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01092_GCPR | 2025-12-08 | Historical | 2026_ET-01092_ACQ | In Progress | 2026_ET-01092_FR |  | Not Started | 2026_ET-01092_RWR | Not Started |  | 2026_ET-01092_CLAZ |  | Not Started |  |  |  | 2026_ET-01092_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01092_WR |  |  | Not Started |  |  |  | 2026_ET-01092_VMLAZ |  | Not Started |  |  |  | 2026_ET-01092_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01092_RR |  | Not Started | [6 empty] | 2026_ET-01092_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MARINE-SANTA MONICA_ET-01092 |  |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-GARNET | ET-01104 | 2026_ET-01104 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 3.6221 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01104_ACQPKG | 2026_ET-01104_GSPKG | Submitted | 2026_ET-01104_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01104_GCPR | 2025-12-08 | Historical | 2026_ET-01104_ACQ | Submitted | 2026_ET-01104_FR | 2026-05-22 | Submitted | 2026_ET-01104_RWR | Submitted | 2026-05-22 | 2026_ET-01104_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01104_PROCPKG | In Progress | SCE | 2026_ET-01104_WR |  |  | Not Started |  |  |  | 2026_ET-01104_VMLAZ |  | Not Started |  |  |  | 2026_ET-01104_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01104_RR |  | Not Started | [6 empty] | 2026_ET-01104_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | DEVERS-GARNET_ET-01104 |  |  | No |  | Helicopter | PALM SPRINGS | 79 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHATSWORTH-SUNSHINE | ET-01105 | 2026_ET-01105 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.37831 | 0.37831 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-04 | 04-14-2026 | 04-14-2026 |  | 2026_ET-01105_ACQPKG | 2026_ET-01105_GSPKG | Submitted | 2026_ET-01105_GS | 2025-12-08 | Field Complete | 2026_ET-01105_GCPR | 2026-04-02 | Submitted | 2026_ET-01105_ACQ | QC Accepted | 2026_ET-01105_FR | 2026-04-02 | Submitted | 2026_ET-01105_RWR | Submitted | 2026-04-02 | 2026_ET-01105_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01105_PROCPKG | Submitted | All Good - Complete | 2026_ET-01105_WR | 2026-05-12 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01105_VMLAZ | 2026-05-12 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01105_VMM1 | 2026-05-12 | QC Accepted |  | 06-01-2026 | 2026-05-22 |  | 2026_ET-01105_RR | 2026-05-12 | No Violations | 05-23-2026 |  | 0 |  |  |  | 2026_ET-01105_VER | 2026-05-12 | Under QC | 06-01-2026 | [6 empty] | Projected On Time | Projected On Time | Completed On Time - Program | IDLE CHATSWORTH-SUNSHINE_ET-01105 |  |  | No |  |  | VALENCIA | 59 | UNK | 1969-12-31 16:00 PST ¦ 1969-12-31 16:00 PST | 123169 | 19691231 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-VICTOR | ET-01118 | 2026_ET-01118 |  | 1 | 2026 | Apr 01, 2026 | 115 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 34.8439 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-21 | 01-01-2026 | Flown | 2025-12-27 |  |  |  | 2026_ET-01118_ACQPKG | 2026_ET-01118_GSPKG | In Progress | 2026_ET-01118_GS |  | Not Started | 2026_ET-01118_GCPR |  | Not Started | 2026_ET-01118_ACQ | Submitted | 2026_ET-01118_FR |  | Not Started | 2026_ET-01118_RWR | Submitted | 2026-04-29 | 2026_ET-01118_CLAZ | 2026-05-16 | Ready for QC |  | 2026-05-08 | 1 | 2026_ET-01118_PROCPKG | In Progress | ACQ Vendor | 2026_ET-01118_WR |  |  | Not Started |  |  |  | 2026_ET-01118_VMLAZ |  | Not Started |  |  |  | 2026_ET-01118_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01118_RR |  | Not Started | [6 empty] | 2026_ET-01118_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed Late - Program | KRAMER-VICTOR_ET-01118 |  |  | No |  |  | VICTORVILLE | 73 | UNK | 1969-12-31 16:00 PST ¦ 1969-12-31 16:00 PST | 123169 | 19691231 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOREL-HAVILAH-LORAINE-MONOLITH-WALKER BA | ET-01119 | 2026_ET-01119 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 38.6562 | 38.6562 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-24 | 04-20-2026 | 04-16-2026 |  | 2026_ET-01119_ACQPKG | 2026_ET-01119_GSPKG | Submitted | 2026_ET-01119_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01119_GCPR | 2025-12-08 | Historical | 2026_ET-01119_ACQ | QC Accepted | 2026_ET-01119_FR | 2026-03-16 | Submitted | 2026_ET-01119_RWR | Submitted | 2026-03-16 | 2026_ET-01119_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01119_PROCPKG | Submitted | ACQ Vendor and SCE | 2026_ET-01119_WR | 2026-05-10 | 05-20-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01119_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01119_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01119_RR | 2026-05-10 | Ready for QC |  |  | 4 |  |  |  | 2026_ET-01119_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | BOREL-HAVILAH-LORAINE-MONOLITH-WALKER BA_ET-01119 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | 2026-02-24 09:04 PST ¦ 2026-02-24 10:03 PST | 022426 | 20260224 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-MIRAGE NO 1 | ET-01124 | 2026_ET-01124 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.0888 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 05-06-2026 |  | 2026_ET-01124_ACQPKG | 2026_ET-01124_GSPKG | Submitted | 2026_ET-01124_GS | 2026-01-31 | Field Complete | 2026_ET-01124_GCPR | 2026-05-03 | Submitted | 2026_ET-01124_ACQ | QC Accepted | 2026_ET-01124_FR | 2026-05-03 | Submitted | 2026_ET-01124_RWR | Submitted | 2026-05-03 | 2026_ET-01124_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-01124_PROCPKG | In Progress | SCE | 2026_ET-01124_WR |  |  | In Progress |  |  |  | 2026_ET-01124_VMLAZ |  | In Progress |  |  |  | 2026_ET-01124_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01124_RR |  | In Progress | [6 empty] | 2026_ET-01124_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEVERS-MIRAGE NO 1_ET-01124 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-MIRAGE NO 2 | ET-01125 | 2026_ET-01125 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.0845 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 05-07-2026 |  | 2026_ET-01125_ACQPKG | 2026_ET-01125_GSPKG | Submitted | 2026_ET-01125_GS | 2026-01-31 | Field Complete | 2026_ET-01125_GCPR | 2026-05-03 | Submitted | 2026_ET-01125_ACQ | QC Accepted | 2026_ET-01125_FR | 2026-05-03 | Submitted | 2026_ET-01125_RWR | Submitted | 2026-05-03 | 2026_ET-01125_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01125_PROCPKG | In Progress | SCE | 2026_ET-01125_WR |  |  | In Progress |  |  |  | 2026_ET-01125_VMLAZ |  | In Progress |  |  |  | 2026_ET-01125_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01125_RR |  | In Progress | [6 empty] | 2026_ET-01125_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEVERS-MIRAGE NO 2_ET-01125 |  |  | Yes |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIBERTY-TULARE | ET-01131 | 2026_ET-01131 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.9722 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01131_ACQPKG | 2026_ET-01131_GSPKG | Submitted | 2026_ET-01131_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01131_GCPR | 2025-12-08 | Historical | 2026_ET-01131_ACQ | In Progress | 2026_ET-01131_FR |  | Not Started | 2026_ET-01131_RWR | Not Started |  | 2026_ET-01131_CLAZ |  | Not Started |  |  |  | 2026_ET-01131_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01131_WR |  |  | Not Started |  |  |  | 2026_ET-01131_VMLAZ |  | Not Started |  |  |  | 2026_ET-01131_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01131_RR |  | Not Started | [6 empty] | 2026_ET-01131_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LIBERTY-TULARE_ET-01131 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-CANYON-DIEMER | ET-01144 | 2026_ET-01144 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 12.373 | 0.36082 | 3 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-03 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01144_ACQPKG | 2026_ET-01144_GSPKG | Submitted | 2026_ET-01144_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01144_GCPR | 2025-12-08 | Historical | 2026_ET-01144_ACQ | QC Accepted | 2026_ET-01144_FR | 2026-04-02 | Submitted | 2026_ET-01144_RWR | Submitted | 2026-04-02 | 2026_ET-01144_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01144_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01144_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01144_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01144_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01144_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01144_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | VILLA PARK-CANYON-DIEMER_ET-01144 |  |  | No |  |  | FULLERTON | 48 | UNK | 2026-01-30 08:36 PST ¦ 2026-03-02 08:45 PST | 020326 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-HASKELL-SOLEMINT | ET-01180 | 2026_ET-01180 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 16.3322 | 16.3322 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01180_ACQPKG | 2026_ET-01180_GSPKG | Submitted | 2026_ET-01180_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01180_GCPR | 2025-12-08 | Historical | 2026_ET-01180_ACQ | In Progress | 2026_ET-01180_FR |  | Not Started | 2026_ET-01180_RWR | Not Started |  | 2026_ET-01180_CLAZ |  | Not Started |  |  |  | 2026_ET-01180_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01180_WR |  |  | Not Started |  |  |  | 2026_ET-01180_VMLAZ |  | Not Started |  |  |  | 2026_ET-01180_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01180_RR |  | Not Started | [6 empty] | 2026_ET-01180_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SAUGUS-HASKELL-SOLEMINT_ET-01180 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTA ROSA-TAMARISK | ET-01187 | 2026_ET-01187 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.5108 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01187_ACQPKG | 2026_ET-01187_GSPKG | Submitted | 2026_ET-01187_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01187_GCPR | 2025-12-08 | Historical | 2026_ET-01187_ACQ | In Progress | 2026_ET-01187_FR |  | Not Started | 2026_ET-01187_RWR | Not Started |  | 2026_ET-01187_CLAZ |  | Not Started |  |  |  | 2026_ET-01187_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01187_WR |  |  | Not Started |  |  |  | 2026_ET-01187_VMLAZ |  | Not Started |  |  |  | 2026_ET-01187_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01187_RR |  | Not Started | [6 empty] | 2026_ET-01187_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE SANTA ROSA-TAMARISK_ET-01187 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN ONOFRE-SANTIAGO NO.1 | ET-01188 | 2026_ET-01188 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 01-13-2026 | 02-12-2026 | Late | 93 | Transmission | 28.4107 | 20.3004 | 71 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2026-01-12 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | Delay | Variable | SCE | Access | Upload Challenge | Access | Airspace restrictions, waiting on clearance from Camp Pendleton (Working with AirOps) | UploadChallenge | SCE Approved | SCE Approved |  | 14 | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-14-2026 | Flown | 2026-03-12 | 04-29-2026 | 04-29-2026 |  | 2026_ET-01188_ACQPKG | 2026_ET-01188_GSPKG | Submitted | 2026_ET-01188_GS | 2025-11-08 | Field Complete | 2026_ET-01188_GCPR | 2025-12-08 | Historical | 2026_ET-01188_ACQ | QC Accepted | 2026_ET-01188_FR |  | Not Started | 2026_ET-01188_RWR | Submitted | 2026-03-11 | 2026_ET-01188_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-29 | 0 | 2026_ET-01188_PROCPKG | In Progress | All Good - Complete | 2026_ET-01188_WR |  | 06-12-2026 | Not Started |  |  |  | 2026_ET-01188_VMLAZ |  | In Progress |  |  |  | 2026_ET-01188_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01188_RR |  | In Progress | [6 empty] | 2026_ET-01188_VER |  | In Progress | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | SAN ONOFRE-SANTIAGO NO.1_ET-01188 |  |  | Yes |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN ONOFRE-SANTIAGO NO.2 | ET-01189 | 2026_ET-01189 |  | 11 | 2026 | Mar 11, 2026 | 220 | CA_6 | 3 | 12-11-2025 | 12-26-2025 | 01-25-2026 | 02-09-2026 | 10-12-2025 | 11-11-2025 | 01-13-2026 | 02-12-2026 | Late | 93 | Transmission | 28.4062 | 20.2997 | 71 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2026-01-12 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_01 | 2025-12-01 | 2026_Cyient_CWA_01 | 2025-12-01 |  | Delay | Delay | Variable | SCE | Access | Upload Challenge | Access | Airspace restrictions, waiting on clearance from Camp Pendleton (Working with AirOps) | UploadChallenge | SCE Approved | SCE Approved |  | 14 | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 03-14-2026 | Flown | 2026-03-12 | 04-29-2026 | 04-29-2026 |  | 2026_ET-01189_ACQPKG | 2026_ET-01189_GSPKG | Submitted | 2026_ET-01189_GS | 2025-11-08 | Field Complete | 2026_ET-01189_GCPR | 2025-12-08 | Historical | 2026_ET-01189_ACQ | QC Accepted | 2026_ET-01189_FR |  | Not Started | 2026_ET-01189_RWR | Submitted | 2026-03-11 | 2026_ET-01189_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-29 | 0 | 2026_ET-01189_PROCPKG | In Progress | All Good - Complete | 2026_ET-01189_WR |  | 06-12-2026 | Not Started |  |  |  | 2026_ET-01189_VMLAZ |  | In Progress |  |  |  | 2026_ET-01189_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01189_RR |  | In Progress | [6 empty] | 2026_ET-01189_VER |  | In Progress | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | SAN ONOFRE-SANTIAGO NO.2_ET-01189 |  |  | Yes |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRAGE-SANTA ROSA | ET-01197 | 2026_ET-01197 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.0899 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01197_ACQPKG | 2026_ET-01197_GSPKG | Submitted | 2026_ET-01197_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01197_GCPR | 2025-12-08 | Historical | 2026_ET-01197_ACQ | In Progress | 2026_ET-01197_FR |  | Not Started | 2026_ET-01197_RWR | Not Started |  | 2026_ET-01197_CLAZ |  | Not Started |  |  |  | 2026_ET-01197_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01197_WR |  |  | Not Started |  |  |  | 2026_ET-01197_VMLAZ |  | Not Started |  |  |  | 2026_ET-01197_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01197_RR |  | Not Started | [6 empty] | 2026_ET-01197_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MIRAGE-SANTA ROSA_ET-01197 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRAGE-SANTA ROSA-TAMARISK | ET-01198 | 2026_ET-01198 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 7.0599 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01198_ACQPKG | 2026_ET-01198_GSPKG | Submitted | 2026_ET-01198_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01198_GCPR | 2025-12-08 | Historical | 2026_ET-01198_ACQ | In Progress | 2026_ET-01198_FR |  | Not Started | 2026_ET-01198_RWR | Not Started |  | 2026_ET-01198_CLAZ |  | Not Started |  |  |  | 2026_ET-01198_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01198_WR |  |  | Not Started |  |  |  | 2026_ET-01198_VMLAZ |  | Not Started |  |  |  | 2026_ET-01198_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01198_RR |  | Not Started | [6 empty] | 2026_ET-01198_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MIRAGE-SANTA ROSA-TAMARISK_ET-01198 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-GANESHA-PEYTON | ET-01200 | 2026_ET-01200 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 9.0557 | 3.4699 | 38 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-07-2026 |  | 2026_ET-01200_ACQPKG | 2026_ET-01200_GSPKG | Submitted | 2026_ET-01200_GS | 2026-01-31 | Field Complete | 2026_ET-01200_GCPR | 2026-05-03 | Submitted | 2026_ET-01200_ACQ | QC Accepted | 2026_ET-01200_FR | 2026-05-03 | Submitted | 2026_ET-01200_RWR | Submitted | 2026-05-03 | 2026_ET-01200_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01200_PROCPKG | In Progress | SCE | 2026_ET-01200_WR |  |  | In Progress |  |  |  | 2026_ET-01200_VMLAZ |  | In Progress |  |  |  | 2026_ET-01200_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01200_RR |  | In Progress | [6 empty] | 2026_ET-01200_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CHINO-GANESHA-PEYTON_ET-01200 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MORAGA-STADLER-STENT | ET-01208 | 2026_ET-01208 |  | 1 | 2026 | Oct 01, 2026 | 115 | CA_6 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 6.9137 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01208_ACQPKG | 2026_ET-01208_GSPKG | In Progress | 2026_ET-01208_GS |  | Not Started | 2026_ET-01208_GCPR |  | Not Started | 2026_ET-01208_ACQ | In Progress | 2026_ET-01208_FR |  | Not Started | 2026_ET-01208_RWR | Not Started |  | 2026_ET-01208_CLAZ |  | Not Started |  |  |  | 2026_ET-01208_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01208_WR |  |  | Not Started |  |  |  | 2026_ET-01208_VMLAZ |  | Not Started |  |  |  | 2026_ET-01208_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01208_RR |  | Not Started | [6 empty] | 2026_ET-01208_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | MORAGA-STADLER-STENT_ET-01208 |  |  | No |  |  | WILDOMAR | 88 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAUGUS-ELZBTH LKE-HSKELL-MWD FTHILL | ET-01229 | 2026_ET-01229 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.80171 | 0.80171 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-09 | 04-14-2026 | 04-14-2026 |  | 2026_ET-01229_ACQPKG | 2026_ET-01229_GSPKG | Submitted | 2026_ET-01229_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01229_GCPR | 2025-12-08 | Historical | 2026_ET-01229_ACQ | QC Accepted | 2026_ET-01229_FR | 2026-04-02 | Submitted | 2026_ET-01229_RWR | Submitted | 2026-04-02 | 2026_ET-01229_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01229_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01229_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01229_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01229_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01229_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01229_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE SAUGUS-ELZBTH LKE-HSKELL-MWD FTHILL_ET-01229 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:49 PST ¦ 2026-03-09 11:47 PDT | 030926 | 20260309 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-LEWIS | ET-01242 | 2026_ET-01242 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.4277 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-19 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-08-2026 |  | 2026_ET-01242_ACQPKG | 2026_ET-01242_GSPKG | Submitted | 2026_ET-01242_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01242_GCPR | 2025-12-08 | Historical | 2026_ET-01242_ACQ | QC Accepted | 2026_ET-01242_FR | 2026-04-02 | Submitted | 2026_ET-01242_RWR | Submitted | 2026-04-02 | 2026_ET-01242_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01242_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01242_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01242_VMLAZ | 2026-05-01 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01242_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01242_RR | 2026-05-06 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-01242_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-LEWIS_ET-01242 | Done |  | Yes |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO2 | ET-01251 | 2026_ET-01251 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.5254 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-06 | 04-20-2026 | 04-14-2026 |  | 2026_ET-01251_ACQPKG | 2026_ET-01251_GSPKG | Submitted | 2026_ET-01251_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01251_GCPR | 2025-12-08 | Historical | 2026_ET-01251_ACQ | QC Accepted | 2026_ET-01251_FR | 2026-04-02 | Submitted | 2026_ET-01251_RWR | Submitted | 2026-04-02 | 2026_ET-01251_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01251_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01251_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01251_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01251_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01251_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 1 | 2026-05-14 |  | 0 | 2026_ET-01251_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO2_ET-01251 |  |  | No |  |  | SOUTH BAY | 44 | UNK | 2026-03-05 13:03 PST ¦ 2026-03-18 10:24 PDT | 030626 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HIGHWIND-MANDIBLE | ET-01260 | 2026_ET-01260 |  | 1 | 2026 | Jun 01, 2026 | 220 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 0.41517 | 0.41517 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-28 | 03-03-2026 | Flown | 2025-12-19 | 04-28-2026 | 02-18-2026 |  | 2026_ET-01260_ACQPKG | 2026_ET-01260_GSPKG | Submitted | 2026_ET-01260_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01260_GCPR | 2025-12-08 | Historical | 2026_ET-01260_ACQ | QC Accepted | 2026_ET-01260_FR | 2026-01-13 | Submitted | 2026_ET-01260_RWR | Submitted | 2026-01-13 | 2026_ET-01260_CLAZ | 2026-01-13 | QC Accepted | 03-18-2026 | 2026-02-18 |  | 2026_ET-01260_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01260_WR | 2026-04-16 | 05-28-2026 | QC Accepted | 05-02-2026 | 2026-04-20 |  | 2026_ET-01260_VMLAZ | 2026-04-16 | QC Accepted | 05-02-2026 | 2026-04-21 |  | 2026_ET-01260_VMM1 | 2026-04-16 | QC Accepted |  | 05-02-2026 | 2026-04-21 |  | 2026_ET-01260_RR | 2026-04-16 | No Violations | 04-22-2026 |  | 0 |  |  |  | 2026_ET-01260_VER | 2026-04-16 | Uploaded to S123 | 05-02-2026 | 2026-04-22 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | HIGHWIND-MANDIBLE_ET-01260 |  |  | Yes |  | Helicopter | TEHACHAPI | 52 | HC | 2025-12-19 15:36 PST ¦ 2025-12-19 15:40 PST | 121925 | 20251219 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CARDIFF-SANTA ANA RIVER 3 NO.1 | ET-01265 | 2026_ET-01265 |  | 1 | 2026 | Sep 01, 2026 | 33 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.49964 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01265_ACQPKG | 2026_ET-01265_GSPKG | Submitted | 2026_ET-01265_GS | 2025-12-08 | Field Complete | 2026_ET-01265_GCPR | 2026-05-22 | Submitted | 2026_ET-01265_ACQ | Submitted | 2026_ET-01265_FR | 2026-05-22 | Submitted | 2026_ET-01265_RWR | Submitted | 2026-05-22 | 2026_ET-01265_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01265_PROCPKG | In Progress | SCE | 2026_ET-01265_WR |  |  | Not Started |  |  |  | 2026_ET-01265_VMLAZ |  | Not Started |  |  |  | 2026_ET-01265_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01265_RR |  | Not Started | [6 empty] | 2026_ET-01265_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE CARDIFF-SANTA ANA RIVER 3 NO.1_ET-01265 |  |  | No |  | Helicopter | REDLANDS | 31 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARMENITA-GREENING | ET-01268 | 2026_ET-01268 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.6294 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-07-2026 |  | 2026_ET-01268_ACQPKG | 2026_ET-01268_GSPKG | Submitted | 2026_ET-01268_GS | 2026-01-31 | Field Complete | 2026_ET-01268_GCPR | 2026-05-03 | Submitted | 2026_ET-01268_ACQ | QC Accepted | 2026_ET-01268_FR | 2026-05-03 | Submitted | 2026_ET-01268_RWR | Submitted | 2026-05-03 | 2026_ET-01268_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01268_PROCPKG | In Progress | SCE | 2026_ET-01268_WR |  |  | In Progress |  |  |  | 2026_ET-01268_VMLAZ |  | In Progress |  |  |  | 2026_ET-01268_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01268_RR |  | In Progress | [6 empty] | 2026_ET-01268_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CARMENITA-GREENING_ET-01268 | Done |  | No |  |  | WHITTIER | 47 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIMESTONE-SANTIAGO | ET-01273 | 2026_ET-01273 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.0148 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-27 |  | 05-20-2026 |  | 2026_ET-01273_ACQPKG | 2026_ET-01273_GSPKG | Submitted | 2026_ET-01273_GS | 2026-01-31 | Field Complete | 2026_ET-01273_GCPR | 2026-05-03 | Submitted | 2026_ET-01273_ACQ | QC Accepted | 2026_ET-01273_FR | 2026-05-03 | Submitted | 2026_ET-01273_RWR | Submitted | 2026-05-03 | 2026_ET-01273_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01273_PROCPKG | In Progress | SCE | 2026_ET-01273_WR |  |  | Not Started |  |  |  | 2026_ET-01273_VMLAZ |  | Not Started |  |  |  | 2026_ET-01273_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01273_RR |  | Not Started | [6 empty] | 2026_ET-01273_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIMESTONE-SANTIAGO_ET-01273 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BORREGO-CHIQUITA | ET-01275 | 2026_ET-01275 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 13.135 | 6.0967 | 46 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-27 |  | 05-06-2026 |  | 2026_ET-01275_ACQPKG | 2026_ET-01275_GSPKG | Submitted | 2026_ET-01275_GS | 2026-01-31 | Field Complete | 2026_ET-01275_GCPR | 2026-05-03 | Submitted | 2026_ET-01275_ACQ | QC Accepted | 2026_ET-01275_FR | 2026-05-03 | Submitted | 2026_ET-01275_RWR | Submitted | 2026-05-03 | 2026_ET-01275_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-01275_PROCPKG | In Progress | SCE | 2026_ET-01275_WR |  |  | In Progress |  |  |  | 2026_ET-01275_VMLAZ |  | In Progress |  |  |  | 2026_ET-01275_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01275_RR |  | In Progress | [6 empty] | 2026_ET-01275_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BORREGO-CHIQUITA_ET-01275 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAMARILLO-COLONIA | ET-01278 | 2026_ET-01278 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 6.1029 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01278_ACQPKG | 2026_ET-01278_GSPKG | Submitted | 2026_ET-01278_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01278_GCPR | 2025-12-08 | Historical | 2026_ET-01278_ACQ | In Progress | 2026_ET-01278_FR |  | Not Started | 2026_ET-01278_RWR | Not Started |  | 2026_ET-01278_CLAZ |  | Not Started |  |  |  | 2026_ET-01278_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01278_WR |  |  | Not Started |  |  |  | 2026_ET-01278_VMLAZ |  | Not Started |  |  |  | 2026_ET-01278_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01278_RR |  | Not Started | [6 empty] | 2026_ET-01278_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CAMARILLO-COLONIA_ET-01278 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CAMARILLO-SOMIS | ET-01279 | 2026_ET-01279 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.7289 | 2.3688 | 50 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01279_ACQPKG | 2026_ET-01279_GSPKG | Submitted | 2026_ET-01279_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01279_GCPR | 2025-12-08 | Historical | 2026_ET-01279_ACQ | In Progress | 2026_ET-01279_FR |  | Not Started | 2026_ET-01279_RWR | Not Started |  | 2026_ET-01279_CLAZ |  | Not Started |  |  |  | 2026_ET-01279_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01279_WR |  |  | Not Started |  |  |  | 2026_ET-01279_VMLAZ |  | Not Started |  |  |  | 2026_ET-01279_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01279_RR |  | Not Started | [6 empty] | 2026_ET-01279_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CAMARILLO-SOMIS_ET-01279 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLOOMINGTON-COLTON-GLEN AVON | ET-01312 | 2026_ET-01312 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 14.121 | 1.6483 | 12 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-07-2026 |  | 2026_ET-01312_ACQPKG | 2026_ET-01312_GSPKG | Submitted | 2026_ET-01312_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01312_GCPR | 2025-12-08 | Historical | 2026_ET-01312_ACQ | QC Accepted | 2026_ET-01312_FR | 2026-05-03 | Submitted | 2026_ET-01312_RWR | Submitted | 2026-05-03 | 2026_ET-01312_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01312_PROCPKG | In Progress | SCE | 2026_ET-01312_WR |  |  | In Progress |  |  |  | 2026_ET-01312_VMLAZ |  | In Progress |  |  |  | 2026_ET-01312_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01312_RR |  | In Progress | [6 empty] | 2026_ET-01312_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BLOOMINGTON-COLTON-GLEN AVON_ET-01312 | Done |  | No |  |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MALIBU-OAK PARK | ET-01338 | 2026_ET-01338 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.4646 | 3.4646 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-10 |  | 05-20-2026 |  | 2026_ET-01338_ACQPKG | 2026_ET-01338_GSPKG | Submitted | 2026_ET-01338_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01338_GCPR | 2025-12-08 | Historical | 2026_ET-01338_ACQ | QC Accepted | 2026_ET-01338_FR | 2026-05-03 | Submitted | 2026_ET-01338_RWR | Submitted | 2026-05-03 | 2026_ET-01338_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01338_PROCPKG | In Progress | SCE | 2026_ET-01338_WR |  |  | Not Started |  |  |  | 2026_ET-01338_VMLAZ |  | Not Started |  |  |  | 2026_ET-01338_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01338_RR |  | Not Started | [6 empty] | 2026_ET-01338_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MALIBU-OAK PARK_ET-01338 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PARKER-WHIPPLE | ET-01345 | 2026_ET-01345 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.2758 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01345_ACQPKG | 2026_ET-01345_GSPKG | Submitted | 2026_ET-01345_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01345_GCPR | 2025-12-08 | Historical | 2026_ET-01345_ACQ | In Progress | 2026_ET-01345_FR |  | Not Started | 2026_ET-01345_RWR | Not Started |  | 2026_ET-01345_CLAZ |  | Not Started |  |  |  | 2026_ET-01345_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01345_WR |  |  | Not Started |  |  |  | 2026_ET-01345_VMLAZ |  | Not Started |  |  |  | 2026_ET-01345_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01345_RR |  | Not Started | [6 empty] | 2026_ET-01345_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | PARKER-WHIPPLE_ET-01345 |  |  | No |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELIZABETH LAKE-PITCHGEN | ET-01346 | 2026_ET-01346 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.6083 | 2.6083 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01346_ACQPKG | 2026_ET-01346_GSPKG | Submitted | 2026_ET-01346_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01346_GCPR | 2025-12-08 | Historical | 2026_ET-01346_ACQ | In Progress | 2026_ET-01346_FR |  | Not Started | 2026_ET-01346_RWR | Not Started |  | 2026_ET-01346_CLAZ |  | Not Started |  |  |  | 2026_ET-01346_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01346_WR |  |  | Not Started |  |  |  | 2026_ET-01346_VMLAZ |  | Not Started |  |  |  | 2026_ET-01346_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01346_RR |  | Not Started | [6 empty] | 2026_ET-01346_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | ELIZABETH LAKE-PITCHGEN_ET-01346 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HAVASU-LANDING-WHIPPLE | ET-01350 | 2026_ET-01350 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 20.7196 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01350_ACQPKG | 2026_ET-01350_GSPKG | Submitted | 2026_ET-01350_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01350_GCPR | 2025-12-08 | Historical | 2026_ET-01350_ACQ | In Progress | 2026_ET-01350_FR |  | Not Started | 2026_ET-01350_RWR | Not Started |  | 2026_ET-01350_CLAZ |  | Not Started |  |  |  | 2026_ET-01350_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01350_WR |  |  | Not Started |  |  |  | 2026_ET-01350_VMLAZ |  | Not Started |  |  |  | 2026_ET-01350_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01350_RR |  | Not Started | [6 empty] | 2026_ET-01350_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | HAVASU-LANDING-WHIPPLE_ET-01350 |  |  | No |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-P.S.20-P.S.38 | ET-01357 | 2026_ET-01357 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 4.0107 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01357_ACQPKG | 2026_ET-01357_GSPKG | Submitted | 2026_ET-01357_GS | 2025-12-08 | Field Complete | 2026_ET-01357_GCPR | 2026-05-22 | Submitted | 2026_ET-01357_ACQ | Submitted | 2026_ET-01357_FR | 2026-05-22 | Submitted | 2026_ET-01357_RWR | Submitted | 2026-05-22 | 2026_ET-01357_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01357_PROCPKG | In Progress | SCE | 2026_ET-01357_WR |  |  | Not Started |  |  |  | 2026_ET-01357_VMLAZ |  | Not Started |  |  |  | 2026_ET-01357_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01357_RR |  | Not Started | [6 empty] | 2026_ET-01357_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE LAGUNA BELL-P.S.20-P.S.38_ET-01357 |  |  | No |  | Helicopter | DOMINGUEZ HILLS | 32 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OASIS-TORTOISE | ET-01359 | 2026_ET-01359 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.018 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-21 | 04-21-2026 | 04-21-2026 |  | 2026_ET-01359_ACQPKG | 2026_ET-01359_GSPKG | Submitted | 2026_ET-01359_GS | 2025-10-17 | Field Complete | 2026_ET-01359_GCPR | 2025-12-08 | Submitted | 2026_ET-01359_ACQ | QC Accepted | 2026_ET-01359_FR | 2026-03-16 | Submitted | 2026_ET-01359_RWR | Submitted | 2026-03-16 | 2026_ET-01359_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-01359_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01359_WR | 2026-04-29 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01359_VMLAZ | 2026-04-29 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01359_VMM1 | 2026-04-29 | QC Accepted |  | 06-01-2026 | 2026-05-04 |  | 2026_ET-01359_RR |  | No Violations | 05-05-2026 |  | 0 |  |  |  | 2026_ET-01359_VER | 2026-04-29 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | OASIS-TORTOISE_ET-01359 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-21 10:12 PST ¦ 2026-02-21 10:17 PST | 022126 | 20260221 |  | Metadata issue. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
IDLE CHATSWORTH-ROCKETDYNE | ET-01361 | 2026_ET-01361 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.85266 | 0.85266 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-11 | 05-15-2026 | 05-15-2026 |  | 2026_ET-01361_ACQPKG | 2026_ET-01361_GSPKG | Submitted | 2026_ET-01361_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01361_GCPR | 2025-12-08 | Historical | 2026_ET-01361_ACQ | QC Accepted | 2026_ET-01361_FR | 2026-05-03 | Submitted | 2026_ET-01361_RWR | Submitted | 2026-05-03 | 2026_ET-01361_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01361_PROCPKG | In Progress | All Good - Complete | 2026_ET-01361_WR |  | 06-14-2026 | In Progress |  |  |  | 2026_ET-01361_VMLAZ |  | In Progress |  |  |  | 2026_ET-01361_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01361_RR |  | In Progress | [6 empty] | 2026_ET-01361_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE CHATSWORTH-ROCKETDYNE_ET-01361 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VALLEY-NELSON | ET-01383 | 2026_ET-01383 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 11.5877 | 7.9628 | 69 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01383_ACQPKG | 2026_ET-01383_GSPKG | Submitted | 2026_ET-01383_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01383_GCPR | 2025-12-08 | Historical | 2026_ET-01383_ACQ | In Progress | 2026_ET-01383_FR |  | Not Started | 2026_ET-01383_RWR | Not Started |  | 2026_ET-01383_CLAZ |  | Not Started |  |  |  | 2026_ET-01383_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01383_WR |  |  | Not Started |  |  |  | 2026_ET-01383_VMLAZ |  | Not Started |  |  |  | 2026_ET-01383_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01383_RR |  | Not Started | [6 empty] | 2026_ET-01383_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VALLEY-NELSON_ET-01383 |  |  | No |  |  | MENIFEE | 77 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BAILEY-ALAMO-OSO | ET-01388 | 2026_ET-01388 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.0896 | 7.0896 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-23 |  | 04-16-2026 |  | 2026_ET-01388_ACQPKG | 2026_ET-01388_GSPKG | Submitted | 2026_ET-01388_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01388_GCPR | 2025-12-08 | Historical | 2026_ET-01388_ACQ | QC Accepted | 2026_ET-01388_FR | 2026-03-16 | Submitted | 2026_ET-01388_RWR | Submitted | 2026-03-16 | 2026_ET-01388_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-16 |  | 2026_ET-01388_PROCPKG | In Progress | SCE | 2026_ET-01388_WR |  |  | In Progress |  |  |  | 2026_ET-01388_VMLAZ |  | In Progress |  |  |  | 2026_ET-01388_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01388_RR |  | In Progress | [6 empty] | 2026_ET-01388_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BAILEY-ALAMO-OSO_ET-01388 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-23 14:26 PST ¦ 2026-02-23 14:45 PST | 022326 | 20260223 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-ELLIS-FAIRVIEW | ET-01394 | 2026_ET-01394 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.1703 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-26 | 04-02-2026 | Flown | 2026-02-06 | 04-26-2026 | 04-14-2026 |  | 2026_ET-01394_ACQPKG | 2026_ET-01394_GSPKG | Submitted | 2026_ET-01394_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01394_GCPR | 2025-12-08 | Historical | 2026_ET-01394_ACQ | QC Accepted | 2026_ET-01394_FR | 2026-04-02 | Submitted | 2026_ET-01394_RWR | Submitted | 2026-04-02 | 2026_ET-01394_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01394_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01394_WR | 2026-05-14 | 05-26-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01394_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01394_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01394_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01394_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | JOHANNA-ELLIS-FAIRVIEW_ET-01394 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-06 06:48 PST ¦ 2026-03-03 09:05 PST | 020626 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HELIJET-LITTLE ROCK-PALMDALE-ROCKAIR | ET-01402 | 2026_ET-01402 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 15.2192 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 04-17-2026 |  | 2026_ET-01402_ACQPKG | 2026_ET-01402_GSPKG | Submitted | 2026_ET-01402_GS | 2025-10-17 | Field Complete | 2026_ET-01402_GCPR | 2025-12-08 | Submitted | 2026_ET-01402_ACQ | QC Accepted | 2026_ET-01402_FR | 2026-03-16 | Submitted | 2026_ET-01402_RWR | Submitted | 2026-03-16 | 2026_ET-01402_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-01402_PROCPKG | In Progress | SCE | 2026_ET-01402_WR |  |  | In Progress |  |  |  | 2026_ET-01402_VMLAZ |  | In Progress |  |  |  | 2026_ET-01402_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01402_RR |  | In Progress | [6 empty] | 2026_ET-01402_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | HELIJET-LITTLE ROCK-PALMDALE-ROCKAIR_ET-01402 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 14:26 PST ¦ 2026-02-21 10:08 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LANCASTER-LITTLE ROCK-PIUTE | ET-01403 | 2026_ET-01403 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 15.423 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-17 |  | 05-15-2026 |  | 2026_ET-01403_ACQPKG | 2026_ET-01403_GSPKG | Submitted | 2026_ET-01403_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01403_GCPR | 2025-12-08 | Historical | 2026_ET-01403_ACQ | QC Accepted | 2026_ET-01403_FR | 2026-05-08 | Submitted | 2026_ET-01403_RWR | Submitted | 2026-05-08 | 2026_ET-01403_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-01403_PROCPKG | In Progress | SCE | 2026_ET-01403_WR |  |  | Not Started |  |  |  | 2026_ET-01403_VMLAZ |  | Not Started |  |  |  | 2026_ET-01403_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01403_RR |  | Not Started | [6 empty] | 2026_ET-01403_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LANCASTER-LITTLE ROCK-PIUTE_ET-01403 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAN BERNARDINO-CARDIFF-UNIMED-VISTA | ET-01405 | 2026_ET-01405 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 10.4148 | 2.2671 | 22 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01405_ACQPKG | 2026_ET-01405_GSPKG | Submitted | 2026_ET-01405_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01405_GCPR | 2025-12-08 | Historical | 2026_ET-01405_ACQ | In Progress | 2026_ET-01405_FR |  | Not Started | 2026_ET-01405_RWR | Not Started |  | 2026_ET-01405_CLAZ |  | Not Started |  |  |  | 2026_ET-01405_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01405_WR |  |  | Not Started |  |  |  | 2026_ET-01405_VMLAZ |  | Not Started |  |  |  | 2026_ET-01405_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01405_RR |  | Not Started | [6 empty] | 2026_ET-01405_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SAN BERNARDINO-CARDIFF-UNIMED-VISTA_ET-01405 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CRATER-MALIBU-VALDEZ | ET-01406 | 2026_ET-01406 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 13.8611 | 13.8611 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-10 |  | 05-11-2026 |  | 2026_ET-01406_ACQPKG | 2026_ET-01406_GSPKG | Submitted | 2026_ET-01406_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01406_GCPR | 2025-12-08 | Historical | 2026_ET-01406_ACQ | QC Accepted | 2026_ET-01406_FR | 2026-05-03 | Submitted | 2026_ET-01406_RWR | Submitted | 2026-05-03 | 2026_ET-01406_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 1 | 2026_ET-01406_PROCPKG | In Progress | SCE | 2026_ET-01406_WR |  |  | In Progress |  |  |  | 2026_ET-01406_VMLAZ |  | In Progress |  |  |  | 2026_ET-01406_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01406_RR |  | In Progress | [6 empty] | 2026_ET-01406_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CRATER-MALIBU-VALDEZ_ET-01406 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-POTRERO | ET-01407 | 2026_ET-01407 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.8798 | 11.8798 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-10 | 04-20-2026 | 04-15-2026 |  | 2026_ET-01407_ACQPKG | 2026_ET-01407_GSPKG | Submitted | 2026_ET-01407_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01407_GCPR | 2025-12-08 | Historical | 2026_ET-01407_ACQ | QC Accepted | 2026_ET-01407_FR | 2026-04-02 | Submitted | 2026_ET-01407_RWR | Submitted | 2026-04-02 | 2026_ET-01407_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01407_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01407_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01407_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01407_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01407_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01407_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-POTRERO_ET-01407 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-09 14:05 PDT ¦ 2026-03-10 10:54 PDT | 031026 | 20260310 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-CRATER-MALIBU | ET-01408 | 2026_ET-01408 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 22.4527 | 22.4527 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-11 |  | 05-20-2026 |  | 2026_ET-01408_ACQPKG | 2026_ET-01408_GSPKG | Submitted | 2026_ET-01408_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01408_GCPR | 2025-12-08 | Historical | 2026_ET-01408_ACQ | QC Accepted | 2026_ET-01408_FR | 2026-05-03 | Submitted | 2026_ET-01408_RWR | Submitted | 2026-05-03 | 2026_ET-01408_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01408_PROCPKG | In Progress | SCE | 2026_ET-01408_WR |  |  | Not Started |  |  |  | 2026_ET-01408_VMLAZ |  | Not Started |  |  |  | 2026_ET-01408_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01408_RR |  | Not Started | [6 empty] | 2026_ET-01408_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MOORPARK-CRATER-MALIBU_ET-01408 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-SUNGEN | ET-01411 | 2026_ET-01411 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.3096 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01411_ACQPKG | 2026_ET-01411_GSPKG | Submitted | 2026_ET-01411_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01411_GCPR | 2025-12-08 | Historical | 2026_ET-01411_ACQ | In Progress | 2026_ET-01411_FR |  | Not Started | 2026_ET-01411_RWR | Not Started |  | 2026_ET-01411_CLAZ |  | Not Started |  |  |  | 2026_ET-01411_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01411_WR |  |  | Not Started |  |  |  | 2026_ET-01411_VMLAZ |  | Not Started |  |  |  | 2026_ET-01411_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01411_RR |  | Not Started | [6 empty] | 2026_ET-01411_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-SUNGEN_ET-01411 |  |  | No |  | Helicopter | RIDGECREST | 86 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CENTER-GALLATIN-SANTA FE SPRINGS | ET-01414 | 2026_ET-01414 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 7.9366 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01414_ACQPKG | 2026_ET-01414_GSPKG | Submitted | 2026_ET-01414_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01414_GCPR | 2025-12-08 | Historical | 2026_ET-01414_ACQ | In Progress | 2026_ET-01414_FR |  | Not Started | 2026_ET-01414_RWR | Not Started |  | 2026_ET-01414_CLAZ |  | Not Started |  |  |  | 2026_ET-01414_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01414_WR |  |  | Not Started |  |  |  | 2026_ET-01414_VMLAZ |  | Not Started |  |  |  | 2026_ET-01414_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01414_RR |  | Not Started | [6 empty] | 2026_ET-01414_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CENTER-GALLATIN-SANTA FE SPRINGS_ET-01414 |  |  | No |  | Helicopter | WHITTIER | 47 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHERRY-STATE STREET | ET-01418 | 2026_ET-01418 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.54077 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-05 | 04-20-2026 | 04-08-2026 |  | 2026_ET-01418_ACQPKG | 2026_ET-01418_GSPKG | Submitted | 2026_ET-01418_GS | 2025-12-08 | Field Complete | 2026_ET-01418_GCPR | 2026-04-02 | Submitted | 2026_ET-01418_ACQ | QC Accepted | 2026_ET-01418_FR | 2026-04-02 | Submitted | 2026_ET-01418_RWR | Submitted | 2026-04-02 | 2026_ET-01418_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01418_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01418_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01418_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01418_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01418_RR | 2026-05-10 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-01418_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | CHERRY-STATE STREET_ET-01418 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-05 10:13 PST ¦ 2026-03-05 10:20 PST | 030526 | 20260305 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-LUCAS NO. 2 | ET-01427 | 2026_ET-01427 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.1127 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-02 | 04-20-2026 | 04-14-2026 |  | 2026_ET-01427_ACQPKG | 2026_ET-01427_GSPKG | Submitted | 2026_ET-01427_GS | 2025-12-08 | Field Complete | 2026_ET-01427_GCPR | 2026-04-02 | Submitted | 2026_ET-01427_ACQ | QC Accepted | 2026_ET-01427_FR | 2026-04-02 | Submitted | 2026_ET-01427_RWR | Submitted | 2026-04-02 | 2026_ET-01427_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01427_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01427_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01427_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01427_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01427_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01427_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-LUCAS NO. 2_ET-01427 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-02 09:18 PST ¦ 2026-03-17 13:56 PDT | 030226 | 20260317 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-OXBOW | ET-01446 | 2026_ET-01446 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.0789 | 0.0789 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-19 |  | 05-15-2026 |  | 2026_ET-01446_ACQPKG | 2026_ET-01446_GSPKG | Submitted | 2026_ET-01446_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01446_GCPR | 2025-12-08 | Historical | 2026_ET-01446_ACQ | QC Accepted | 2026_ET-01446_FR | 2026-05-08 | Submitted | 2026_ET-01446_RWR | Submitted | 2026-05-08 | 2026_ET-01446_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-01446_PROCPKG | In Progress | SCE | 2026_ET-01446_WR |  |  | Not Started |  |  |  | 2026_ET-01446_VMLAZ |  | Not Started |  |  |  | 2026_ET-01446_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01446_RR |  | Not Started | [6 empty] | 2026_ET-01446_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CONTROL-OXBOW_ET-01446 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVGEN-WESTHILL | ET-01448 | 2026_ET-01448 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 1.4987 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Access Delay |  |  |  |  | 2026_ET-01448_ACQPKG | 2026_ET-01448_GSPKG | In Progress | 2026_ET-01448_GS | 2025-12-08 | Field Complete | 2026_ET-01448_GCPR |  | Not Started | 2026_ET-01448_ACQ | In Progress | 2026_ET-01448_FR |  | Not Started | 2026_ET-01448_RWR | Not Started |  | 2026_ET-01448_CLAZ |  | Not Started |  |  |  | 2026_ET-01448_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01448_WR |  |  | Not Started |  |  |  | 2026_ET-01448_VMLAZ |  | Not Started |  |  |  | 2026_ET-01448_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01448_RR |  | Not Started | [6 empty] | 2026_ET-01448_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CHEVGEN-WESTHILL_ET-01448 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CASA DIABLO-CONTROL-SHERWIN | ET-01449 | 2026_ET-01449 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_3 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 35.5313 | 35.5313 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-19 |  | 05-11-2026 |  | 2026_ET-01449_ACQPKG | 2026_ET-01449_GSPKG | Submitted | 2026_ET-01449_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01449_GCPR | 2025-12-08 | Historical | 2026_ET-01449_ACQ | QC Accepted | 2026_ET-01449_FR | 2026-05-08 | Submitted | 2026_ET-01449_RWR | Submitted | 2026-05-08 | 2026_ET-01449_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-11 | 0 | 2026_ET-01449_PROCPKG | In Progress | SCE | 2026_ET-01449_WR |  |  | Not Started |  |  |  | 2026_ET-01449_VMLAZ |  | Not Started |  |  |  | 2026_ET-01449_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01449_RR |  | Not Started | [6 empty] | 2026_ET-01449_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CASA DIABLO-CONTROL-SHERWIN_ET-01449 | Done |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-DELGEN-JEFFERSON | ET-01454 | 2026_ET-01454 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.5642 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-15 | 05-15-2026 | 05-15-2026 |  | 2026_ET-01454_ACQPKG | 2026_ET-01454_GSPKG | Submitted | 2026_ET-01454_GS | 2026-01-31 | Field Complete | 2026_ET-01454_GCPR | 2026-05-03 | Submitted | 2026_ET-01454_ACQ | QC Accepted | 2026_ET-01454_FR | 2026-05-03 | Submitted | 2026_ET-01454_RWR | Submitted | 2026-05-03 | 2026_ET-01454_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01454_PROCPKG | In Progress | All Good - Complete | 2026_ET-01454_WR |  | 06-14-2026 | In Progress |  |  |  | 2026_ET-01454_VMLAZ |  | In Progress |  |  |  | 2026_ET-01454_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01454_RR |  | In Progress | [6 empty] | 2026_ET-01454_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE CHINO-DELGEN-JEFFERSON_ET-01454 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ANTELOPE-P.S. 74 | ET-01455 | 2026_ET-01455 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 2.7366 | 2.7366 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01455_ACQPKG | 2026_ET-01455_GSPKG | Submitted | 2026_ET-01455_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01455_GCPR | 2025-12-08 | Historical | 2026_ET-01455_ACQ | In Progress | 2026_ET-01455_FR |  | Not Started | 2026_ET-01455_RWR | Not Started |  | 2026_ET-01455_CLAZ |  | Not Started |  |  |  | 2026_ET-01455_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01455_WR |  |  | Not Started |  |  |  | 2026_ET-01455_VMLAZ |  | Not Started |  |  |  | 2026_ET-01455_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01455_RR |  | Not Started | [6 empty] | 2026_ET-01455_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE ANTELOPE-P.S. 74_ET-01455 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-DALTON-LIQUID | ET-01457 | 2026_ET-01457 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.0326 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-28 |  | 05-15-2026 |  | 2026_ET-01457_ACQPKG | 2026_ET-01457_GSPKG | Submitted | 2026_ET-01457_GS | 2026-01-31 | Field Complete | 2026_ET-01457_GCPR | 2026-05-03 | Submitted | 2026_ET-01457_ACQ | QC Accepted | 2026_ET-01457_FR | 2026-05-03 | Submitted | 2026_ET-01457_RWR | Submitted | 2026-05-03 | 2026_ET-01457_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01457_PROCPKG | In Progress | SCE | 2026_ET-01457_WR |  |  | In Progress |  |  |  | 2026_ET-01457_VMLAZ |  | In Progress |  |  |  | 2026_ET-01457_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01457_RR |  | In Progress | [6 empty] | 2026_ET-01457_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RIO HONDO-DALTON-LIQUID_ET-01457 |  |  | No |  |  | MONROVIA | 27 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CAMGEN-COLONIA-NEWBURY-THOUSAND OKS | ET-01458 | 2026_ET-01458 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.6634 | 4.6634 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01458_ACQPKG | 2026_ET-01458_GSPKG | Submitted | 2026_ET-01458_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01458_GCPR | 2025-12-08 | Historical | 2026_ET-01458_ACQ | In Progress | 2026_ET-01458_FR |  | Not Started | 2026_ET-01458_RWR | Not Started |  | 2026_ET-01458_CLAZ |  | Not Started |  |  |  | 2026_ET-01458_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01458_WR |  |  | Not Started |  |  |  | 2026_ET-01458_VMLAZ |  | Not Started |  |  |  | 2026_ET-01458_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01458_RR |  | Not Started | [6 empty] | 2026_ET-01458_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE CAMGEN-COLONIA-NEWBURY-THOUSAND OKS_ET-01458 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EARLIMART-WHEATLAND | ET-01465 | 2026_ET-01465 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 7.1906 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01465_ACQPKG | 2026_ET-01465_GSPKG | Submitted | 2026_ET-01465_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01465_GCPR | 2025-12-08 | Historical | 2026_ET-01465_ACQ | In Progress | 2026_ET-01465_FR |  | Not Started | 2026_ET-01465_RWR | Not Started |  | 2026_ET-01465_CLAZ |  | Not Started |  |  |  | 2026_ET-01465_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01465_WR |  |  | Not Started |  |  |  | 2026_ET-01465_VMLAZ |  | Not Started |  |  |  | 2026_ET-01465_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01465_RR |  | Not Started | [6 empty] | 2026_ET-01465_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | EARLIMART-WHEATLAND_ET-01465 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VESTAL-POPLAR | ET-01467 | 2026_ET-01467 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 17.7269 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01467_ACQPKG | 2026_ET-01467_GSPKG | Submitted | 2026_ET-01467_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01467_GCPR | 2025-12-08 | Historical | 2026_ET-01467_ACQ | In Progress | 2026_ET-01467_FR |  | Not Started | 2026_ET-01467_RWR | Not Started |  | 2026_ET-01467_CLAZ |  | Not Started |  |  |  | 2026_ET-01467_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01467_WR |  |  | Not Started |  |  |  | 2026_ET-01467_VMLAZ |  | Not Started |  |  |  | 2026_ET-01467_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01467_RR |  | Not Started | [6 empty] | 2026_ET-01467_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VESTAL-POPLAR_ET-01467 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEWIS-SERRANO NO.1 | ET-01478 | 2026_ET-01478 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.271 | 2.1812 | 30 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01478_ACQPKG | 2026_ET-01478_GSPKG | Submitted | 2026_ET-01478_GS | 2025-12-08 | Field Complete | 2026_ET-01478_GCPR | 2026-04-02 | Submitted | 2026_ET-01478_ACQ | QC Accepted | 2026_ET-01478_FR | 2026-04-02 | Submitted | 2026_ET-01478_RWR | Submitted | 2026-04-02 | 2026_ET-01478_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01478_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01478_WR | 2026-05-07 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-08 |  | 2026_ET-01478_VMLAZ | 2026-05-01 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01478_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-08 |  | 2026_ET-01478_RR | 2026-05-07 | No Violations | 05-09-2026 | [5 empty] | 2026_ET-01478_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-12 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LEWIS-SERRANO NO.1_ET-01478 |  |  | Yes |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEWIS-SERRANO NO.2 | ET-01479 | 2026_ET-01479 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.2545 | 2.181 | 30 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01479_ACQPKG | 2026_ET-01479_GSPKG | Submitted | 2026_ET-01479_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01479_GCPR | 2025-12-08 | Historical | 2026_ET-01479_ACQ | QC Accepted | 2026_ET-01479_FR | 2026-04-02 | Submitted | 2026_ET-01479_RWR | Submitted | 2026-04-02 | 2026_ET-01479_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01479_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01479_WR | 2026-05-06 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-06 |  | 2026_ET-01479_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01479_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-06 |  | 2026_ET-01479_RR | 2026-05-06 | No Violations | 05-07-2026 |  | 1 | 2026-05-05 |  | 0 | 2026_ET-01479_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LEWIS-SERRANO NO.2_ET-01479 |  |  | Yes |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-VILLA PARK | ET-01480 | 2026_ET-01480 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 9.3356 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-08-2026 |  | 2026_ET-01480_ACQPKG | 2026_ET-01480_GSPKG | Submitted | 2026_ET-01480_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01480_GCPR | 2025-12-08 | Historical | 2026_ET-01480_ACQ | QC Accepted | 2026_ET-01480_FR | 2026-04-02 | Submitted | 2026_ET-01480_RWR | Submitted | 2026-04-02 | 2026_ET-01480_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01480_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01480_WR | 2026-05-07 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01480_VMLAZ | 2026-05-01 | QC Accepted | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01480_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-13 | 0 | 2026_ET-01480_RR | 2026-05-07 | No Violations | 05-14-2026 | [5 empty] | 2026_ET-01480_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-VILLA PARK_ET-01480 | Done |  | Yes |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEWIS-VILLA PARK | ET-01481 | 2026_ET-01481 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.9892 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01481_ACQPKG | 2026_ET-01481_GSPKG | Submitted | 2026_ET-01481_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01481_GCPR | 2025-12-08 | Historical | 2026_ET-01481_ACQ | QC Accepted | 2026_ET-01481_FR | 2026-04-02 | Submitted | 2026_ET-01481_RWR | Submitted | 2026-04-02 | 2026_ET-01481_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01481_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01481_WR | 2026-05-07 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-06 |  | 2026_ET-01481_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01481_VMM1 | 2026-05-06 | QC Accepted |  | 06-01-2026 | 2026-05-06 |  | 2026_ET-01481_RR | 2026-05-06 | No Violations | 05-07-2026 | [5 empty] | 2026_ET-01481_VER | 2026-05-06 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LEWIS-VILLA PARK_ET-01481 |  |  | Yes |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
WALNUT-HILLGEN-INDUSTRY-MESA-RENO | ET-01486 | 2026_ET-01486 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 19.0766 | 0.71167 | 4 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01486_ACQPKG | 2026_ET-01486_GSPKG | Submitted | 2026_ET-01486_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01486_GCPR | 2025-12-08 | Historical | 2026_ET-01486_ACQ | In Progress | 2026_ET-01486_FR |  | Not Started | 2026_ET-01486_RWR | Not Started |  | 2026_ET-01486_CLAZ |  | Not Started |  |  |  | 2026_ET-01486_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01486_WR |  |  | Not Started |  |  |  | 2026_ET-01486_VMLAZ |  | Not Started |  |  |  | 2026_ET-01486_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01486_RR |  | Not Started | [6 empty] | 2026_ET-01486_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | WALNUT-HILLGEN-INDUSTRY-MESA-RENO_ET-01486 |  |  | No |  | Helicopter |  |  | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SANTA SUSANA-TIGE | ET-01488 | 2026_ET-01488 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 1.2658 | 1.2658 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-03 | 04-14-2026 | 04-14-2026 |  | 2026_ET-01488_ACQPKG | 2026_ET-01488_GSPKG | Submitted | 2026_ET-01488_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01488_GCPR | 2025-12-08 | Historical | 2026_ET-01488_ACQ | QC Accepted | 2026_ET-01488_FR | 2026-04-02 | Submitted | 2026_ET-01488_RWR | Submitted | 2026-04-02 | 2026_ET-01488_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01488_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01488_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01488_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01488_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01488_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01488_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE SANTA SUSANA-TIGE_ET-01488 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-11 08:18 PDT ¦ 2026-03-15 10:58 PDT | 031126 | 20260315 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-CHATSWORTH-ROYAL-SANTA SUSANA | ET-01489 | 2026_ET-01489 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 23.4002 | 23.4002 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-11 | 04-21-2026 | 04-15-2026 |  | 2026_ET-01489_ACQPKG | 2026_ET-01489_GSPKG | Submitted | 2026_ET-01489_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01489_GCPR | 2025-12-08 | Historical | 2026_ET-01489_ACQ | QC Accepted | 2026_ET-01489_FR | 2026-04-02 | Submitted | 2026_ET-01489_RWR | Submitted | 2026-04-02 | 2026_ET-01489_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01489_PROCPKG | In Progress | All Good - Complete | 2026_ET-01489_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01489_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-01489_VMM1 | 2026-05-10 | QC Rejected |  |  | 2026-05-21 | 1 | 2026_ET-01489_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-01489_VER | 2026-05-10 | Uploaded to S123 |  | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-CHATSWORTH-ROYAL-SANTA SUSANA_ET-01489 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-09 11:11 PDT ¦ 2026-03-18 09:30 PDT | 031826 | 20260318 | [5 empty] | Subject conductors strung inaccurately. |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-LARK ELLEN-WALNUT | ET-01493 | 2026_ET-01493 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 13.8775 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-28 |  | 05-15-2026 |  | 2026_ET-01493_ACQPKG | 2026_ET-01493_GSPKG | Submitted | 2026_ET-01493_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01493_GCPR | 2025-12-08 | Historical | 2026_ET-01493_ACQ | QC Accepted | 2026_ET-01493_FR | 2026-05-03 | Submitted | 2026_ET-01493_RWR | Submitted | 2026-05-03 | 2026_ET-01493_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01493_PROCPKG | In Progress | SCE | 2026_ET-01493_WR |  |  | In Progress |  |  |  | 2026_ET-01493_VMLAZ |  | In Progress |  |  |  | 2026_ET-01493_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01493_RR |  | In Progress | [6 empty] | 2026_ET-01493_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RIO HONDO-LARK ELLEN-WALNUT_ET-01493 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KAWEAH 1 2 3-KAWGEN-LEMON COVE-THREE RIV | ET-01503 | 2026_ET-01503 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 28.3342 | 17.429 | 62 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-15 |  | 05-15-2026 |  | 2026_ET-01503_ACQPKG | 2026_ET-01503_GSPKG | Submitted | 2026_ET-01503_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01503_GCPR | 2025-12-08 | Historical | 2026_ET-01503_ACQ | QC Accepted | 2026_ET-01503_FR | 2026-05-08 | Submitted | 2026_ET-01503_RWR | Submitted | 2026-05-08 | 2026_ET-01503_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-01503_PROCPKG | In Progress | SCE | 2026_ET-01503_WR |  |  | Not Started |  |  |  | 2026_ET-01503_VMLAZ |  | Not Started |  |  |  | 2026_ET-01503_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01503_RR |  | Not Started | [6 empty] | 2026_ET-01503_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | KAWEAH 1 2 3-KAWGEN-LEMON COVE-THREE RIV_ET-01503 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE MOUNTAIN-KEM NO. 1 | ET-01504 | 2026_ET-01504 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_6 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.993 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01504_ACQPKG | 2026_ET-01504_GSPKG | Submitted | 2026_ET-01504_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01504_GCPR | 2025-12-08 | Historical | 2026_ET-01504_ACQ | In Progress | 2026_ET-01504_FR |  | Not Started | 2026_ET-01504_RWR | Not Started |  | 2026_ET-01504_CLAZ |  | Not Started |  |  |  | 2026_ET-01504_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01504_WR |  |  | Not Started |  |  |  | 2026_ET-01504_VMLAZ |  | Not Started |  |  |  | 2026_ET-01504_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01504_RR |  | Not Started | [6 empty] | 2026_ET-01504_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | EAGLE MOUNTAIN-KEM NO. 1_ET-01504 |  |  | No |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE MOUNTAIN-KEM NO. 2 | ET-01509 | 2026_ET-01509 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_6 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 5.0073 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01509_ACQPKG | 2026_ET-01509_GSPKG | Submitted | 2026_ET-01509_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01509_GCPR | 2025-12-08 | Historical | 2026_ET-01509_ACQ | In Progress | 2026_ET-01509_FR |  | Not Started | 2026_ET-01509_RWR | Not Started |  | 2026_ET-01509_CLAZ |  | Not Started |  |  |  | 2026_ET-01509_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01509_WR |  |  | Not Started |  |  |  | 2026_ET-01509_VMLAZ |  | Not Started |  |  |  | 2026_ET-01509_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01509_RR |  | Not Started | [6 empty] | 2026_ET-01509_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | EAGLE MOUNTAIN-KEM NO. 2_ET-01509 |  |  | No |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CAMDEN-FAIRVIEW | ET-01517 | 2026_ET-01517 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.7495 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-03 |  | 05-06-2026 |  | 2026_ET-01517_ACQPKG | 2026_ET-01517_GSPKG | Submitted | 2026_ET-01517_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01517_GCPR | 2025-12-08 | Historical | 2026_ET-01517_ACQ | QC Accepted | 2026_ET-01517_FR | 2026-05-03 | Submitted | 2026_ET-01517_RWR | Submitted | 2026-05-03 | 2026_ET-01517_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-01517_PROCPKG | In Progress | SCE | 2026_ET-01517_WR |  |  | In Progress |  |  |  | 2026_ET-01517_VMLAZ |  | In Progress |  |  |  | 2026_ET-01517_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01517_RR |  | In Progress | [6 empty] | 2026_ET-01517_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | JOHANNA-CAMDEN-FAIRVIEW_ET-01517 |  |  | No |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
JOHANNA-CHESTNUT-WASHINGTON | ET-01519 | 2026_ET-01519 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.4602 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-02-06 | 04-23-2026 | 04-14-2026 |  | 2026_ET-01519_ACQPKG | 2026_ET-01519_GSPKG | Submitted | 2026_ET-01519_GS | 2025-12-08 | Field Complete | 2026_ET-01519_GCPR | 2026-04-02 | Submitted | 2026_ET-01519_ACQ | QC Accepted | 2026_ET-01519_FR | 2026-04-02 | Submitted | 2026_ET-01519_RWR | Submitted | 2026-04-02 | 2026_ET-01519_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01519_PROCPKG | In Progress | All Good - Complete | 2026_ET-01519_WR | 2026-05-14 | 05-23-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01519_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-01519_VMM1 | 2026-05-10 | QC Rejected |  |  | 2026-05-21 | 1 | 2026_ET-01519_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-01519_VER | 2026-05-10 | Uploaded to S123 |  | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | JOHANNA-CHESTNUT-WASHINGTON_ET-01519 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-06 06:56 PST ¦ 2026-02-06 07:19 PST | 020626 | 20260206 | [5 empty] | Subject conductors strung incorrectly. |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-BURPIT-CANYON-YORBA LINDA | ET-01520 | 2026_ET-01520 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 16.5515 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-24 | 04-02-2026 | Flown | 2026-03-03 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01520_ACQPKG | 2026_ET-01520_GSPKG | Submitted | 2026_ET-01520_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01520_GCPR | 2025-12-08 | Historical | 2026_ET-01520_ACQ | QC Accepted | 2026_ET-01520_FR | 2026-04-02 | Submitted | 2026_ET-01520_RWR | Submitted | 2026-04-02 | 2026_ET-01520_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01520_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01520_WR | 2026-05-14 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01520_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01520_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01520_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 3 | 2026-05-14 |  | 0 | 2026_ET-01520_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | VILLA PARK-BURPIT-CANYON-YORBA LINDA_ET-01520 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-01-30 08:36 PST ¦ 2026-03-03 10:45 PST | 020726 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLM WEST-KRAMER | ET-01528 | 2026_ET-01528 |  | 1 | 2026 | Apr 01, 2026 | 220 | CA_5 | 4 | 01-01-2026 | 01-16-2026 | 02-15-2026 | 03-02-2026 | 11-02-2025 | 12-02-2025 | 11-02-2025 | 12-02-2025 | On Time | 0 | Transmission | 49.4284 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 01-01-2026 | Weather Delay |  |  |  |  | 2026_ET-01528_ACQPKG | 2026_ET-01528_GSPKG | Submitted | 2026_ET-01528_GS | 2026-01-23 | Field Complete | 2026_ET-01528_GCPR | 2026-01-30 | Submitted | 2026_ET-01528_ACQ | In Progress | 2026_ET-01528_FR |  | Not Started | 2026_ET-01528_RWR | Not Started |  | 2026_ET-01528_CLAZ |  | Not Started |  |  |  | 2026_ET-01528_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01528_WR |  |  | Not Started |  |  |  | 2026_ET-01528_VMLAZ |  | Not Started |  |  |  | 2026_ET-01528_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01528_RR |  | Not Started | [6 empty] | 2026_ET-01528_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BLM WEST-KRAMER_ET-01528 |  |  | Yes |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-LSP | ET-01538 | 2026_ET-01538 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 0.20491 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-03-15 | 01-31-2026 | Flown | 2025-12-21 |  |  |  | 2026_ET-01538_ACQPKG | 2026_ET-01538_GSPKG | In Progress | 2026_ET-01538_GS |  | Not Started | 2026_ET-01538_GCPR |  | Not Started | 2026_ET-01538_ACQ | QC Accepted | 2026_ET-01538_FR |  | Not Started | 2026_ET-01538_RWR | Submitted | 2026-05-05 | 2026_ET-01538_CLAZ | 2025-12-21 | QC Accepted |  | 2026-02-12 |  | 2026_ET-01538_PROCPKG | QC Accepted | ACQ Vendor | 2026_ET-01538_WR | 2026-03-15 |  | QC Accepted | 04-01-2026 | 2026-04-29 | 0 | 2026_ET-01538_VMLAZ | 2026-03-12 | QC Accepted | 04-01-2026 | 2026-03-23 | 0 | 2026_ET-01538_VMM1 | 2026-03-15 | QC Accepted |  | 04-01-2026 | 2026-03-27 | 0 | 2026_ET-01538_RR |  | No Violations | 03-28-2026 | [5 empty] | 2026_ET-01538_VER | 2026-03-18 | Uploaded to S123 | 04-01-2026 | 2026-04-13 | [5 empty] | Completed Late - Program | Projected On Time | Completed On Time - Program | KRAMER-LSP_ET-01538 |  |  | Yes |  |  | RIDGECREST | 86 | UNK | 2025-12-21 09:57 PST ¦ 2025-12-21 10:04 PST | 122125 | 20251221 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-SOQUEL | ET-01548 | 2026_ET-01548 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.3661 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-01-29 | 04-15-2026 | 04-08-2026 |  | 2026_ET-01548_ACQPKG | 2026_ET-01548_GSPKG | Submitted | 2026_ET-01548_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01548_GCPR | 2025-12-08 | Historical | 2026_ET-01548_ACQ | QC Accepted | 2026_ET-01548_FR | 2026-04-02 | Submitted | 2026_ET-01548_RWR | Submitted | 2026-04-02 | 2026_ET-01548_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01548_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01548_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01548_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01548_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01548_RR | 2026-05-10 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-01548_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CHINO-SOQUEL_ET-01548 |  |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-29 10:53 PST ¦ 2026-02-15 10:05 PST | 012926 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE IVY GLEN-NEWCOMB-SKYLARK | ET-01552 | 2026_ET-01552 |  | 1 | 2026 | Nov 01, 2026 | 115 | CA_6 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 1.0559 | 1.0409 | 99 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01552_ACQPKG | 2026_ET-01552_GSPKG | Submitted | 2026_ET-01552_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01552_GCPR | 2025-12-08 | Historical | 2026_ET-01552_ACQ | In Progress | 2026_ET-01552_FR |  | Not Started | 2026_ET-01552_RWR | Not Started |  | 2026_ET-01552_CLAZ |  | Not Started |  |  |  | 2026_ET-01552_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01552_WR |  |  | Not Started |  |  |  | 2026_ET-01552_VMLAZ |  | Not Started |  |  |  | 2026_ET-01552_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01552_RR |  | Not Started | [6 empty] | 2026_ET-01552_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE IVY GLEN-NEWCOMB-SKYLARK_ET-01552 |  |  | No |  |  | WILDOMAR | 88 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-HOLGATE | ET-01554 | 2026_ET-01554 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 11.1695 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Removed From Scope |  |  |  |  | 2026_ET-01554_ACQPKG | 2026_ET-01554_GSPKG | In Progress | 2026_ET-01554_GS |  | Not Started | 2026_ET-01554_GCPR |  | Not Started | 2026_ET-01554_ACQ | In Progress | 2026_ET-01554_FR |  | Not Started | 2026_ET-01554_RWR | Not Started |  | 2026_ET-01554_CLAZ |  | Not Started |  |  |  | 2026_ET-01554_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01554_WR |  |  | Not Started |  |  |  | 2026_ET-01554_VMLAZ |  | Not Started |  |  |  | 2026_ET-01554_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01554_RR |  | Not Started | [6 empty] | 2026_ET-01554_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-HOLGATE_ET-01554 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CLARK-COLLEGE-DEL AMO-HATHAWAY | ET-01562 | 2026_ET-01562 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.7959 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-02 | 04-21-2026 | 04-09-2026 |  | 2026_ET-01562_ACQPKG | 2026_ET-01562_GSPKG | Submitted | 2026_ET-01562_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01562_GCPR | 2025-12-08 | Historical | 2026_ET-01562_ACQ | QC Accepted | 2026_ET-01562_FR | 2026-04-02 | Submitted | 2026_ET-01562_RWR | Submitted | 2026-04-02 | 2026_ET-01562_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-01562_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01562_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01562_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01562_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-19 | 0 | 2026_ET-01562_RR | 2026-05-10 | No Violations | 05-20-2026 |  | 0 |  |  |  | 2026_ET-01562_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CLARK-COLLEGE-DEL AMO-HATHAWAY_ET-01562 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-02 09:32 PST ¦ 2026-03-02 12:17 PST | 030226 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
APOLLO-BOLSA-TEAM | ET-01563 | 2026_ET-01563 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.5372 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-06 | 04-22-2026 | 04-08-2026 |  | 2026_ET-01563_ACQPKG | 2026_ET-01563_GSPKG | Submitted | 2026_ET-01563_GS | 2025-12-08 | Field Complete | 2026_ET-01563_GCPR | 2026-04-02 | Submitted | 2026_ET-01563_ACQ | QC Accepted | 2026_ET-01563_FR | 2026-04-02 | Submitted | 2026_ET-01563_RWR | Submitted | 2026-04-02 | 2026_ET-01563_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01563_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01563_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01563_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01563_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01563_RR | 2026-05-07 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-01563_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | APOLLO-BOLSA-TEAM_ET-01563 | Done |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | 2026-02-06 11:23 PST ¦ 2026-02-06 11:43 PST | 020626 | 20260206 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MACNEIL-STUDIO-UNIVERSAL | ET-01588 | 2026_ET-01588 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.6375 | 0.19125 | 5 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 04-17-2026 |  | 2026_ET-01588_ACQPKG | 2026_ET-01588_GSPKG | Submitted | 2026_ET-01588_GS | 2025-10-15 | Field Complete | 2026_ET-01588_GCPR | 2025-12-08 | Submitted | 2026_ET-01588_ACQ | QC Accepted | 2026_ET-01588_FR | 2026-03-16 | Submitted | 2026_ET-01588_RWR | Submitted | 2026-03-16 | 2026_ET-01588_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-01588_PROCPKG | In Progress | SCE | 2026_ET-01588_WR |  |  | In Progress |  |  |  | 2026_ET-01588_VMLAZ |  | In Progress |  |  |  | 2026_ET-01588_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01588_RR |  | In Progress | [6 empty] | 2026_ET-01588_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MACNEIL-STUDIO-UNIVERSAL_ET-01588 |  |  | No |  | Helicopter | SANTA MONICA | 42 | HC | 2026-02-21 10:55 PST ¦ 2026-02-21 10:59 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-LANCASTER-LANPRI-SHUTTLE | ET-01590 | 2026_ET-01590 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 13.2322 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-13-2026 |  | 2026_ET-01590_ACQPKG | 2026_ET-01590_GSPKG | Submitted | 2026_ET-01590_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01590_GCPR | 2025-12-08 | Historical | 2026_ET-01590_ACQ | QC Accepted | 2026_ET-01590_FR | 2026-05-08 | Submitted | 2026_ET-01590_RWR | Submitted | 2026-05-08 | 2026_ET-01590_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-13 | 0 | 2026_ET-01590_PROCPKG | In Progress | SCE | 2026_ET-01590_WR |  |  | Not Started |  |  |  | 2026_ET-01590_VMLAZ |  | Not Started |  |  |  | 2026_ET-01590_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01590_RR |  | Not Started | [6 empty] | 2026_ET-01590_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ANTELOPE-LANCASTER-LANPRI-SHUTTLE_ET-01590 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-CORNERS-SUNNYSIDE-TOYOTA | ET-01592 | 2026_ET-01592 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.2721 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-01 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01592_ACQPKG | 2026_ET-01592_GSPKG | Submitted | 2026_ET-01592_GS | 2025-12-08 | Field Complete | 2026_ET-01592_GCPR | 2026-04-02 | Submitted | 2026_ET-01592_ACQ | QC Accepted | 2026_ET-01592_FR | 2026-04-02 | Submitted | 2026_ET-01592_RWR | Submitted | 2026-04-02 | 2026_ET-01592_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01592_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01592_WR | 2026-05-10 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01592_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01592_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01592_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01592_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-CORNERS-SUNNYSIDE-TOYOTA_ET-01592 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-01 12:06 PST ¦ 2026-03-01 12:51 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-AMADOR-JOSE-MESA | ET-01604 | 2026_ET-01604 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 12.7477 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-28 |  | 05-21-2026 |  | 2026_ET-01604_ACQPKG | 2026_ET-01604_GSPKG | Submitted | 2026_ET-01604_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01604_GCPR | 2025-12-08 | Historical | 2026_ET-01604_ACQ | QC Accepted | 2026_ET-01604_FR | 2026-05-03 | Submitted | 2026_ET-01604_RWR | Submitted | 2026-05-03 | 2026_ET-01604_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-21 |  | 2026_ET-01604_PROCPKG | In Progress | SCE | 2026_ET-01604_WR |  |  | Not Started |  |  |  | 2026_ET-01604_VMLAZ |  | Not Started |  |  |  | 2026_ET-01604_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01604_RR |  | Not Started | [6 empty] | 2026_ET-01604_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RIO HONDO-AMADOR-JOSE-MESA_ET-01604 |  |  | No |  |  | MONTEBELLO | 22 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-REVITAL-SUNNYSIDE | ET-01623 | 2026_ET-01623 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.8133 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-15-2026 |  | 2026_ET-01623_ACQPKG | 2026_ET-01623_GSPKG | Submitted | 2026_ET-01623_GS | 2026-01-31 | Field Complete | 2026_ET-01623_GCPR | 2026-05-03 | Submitted | 2026_ET-01623_ACQ | QC Accepted | 2026_ET-01623_FR | 2026-05-03 | Submitted | 2026_ET-01623_RWR | Submitted | 2026-05-03 | 2026_ET-01623_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-01623_PROCPKG | In Progress | SCE | 2026_ET-01623_WR |  |  | In Progress |  |  |  | 2026_ET-01623_VMLAZ |  | In Progress |  |  |  | 2026_ET-01623_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01623_RR |  | In Progress | [6 empty] | 2026_ET-01623_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIGHTHIPE-REVITAL-SUNNYSIDE_ET-01623 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHASE-CORONA-DATABANK | ET-01631 | 2026_ET-01631 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.2136 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 05-14-2026 |  | 2026_ET-01631_ACQPKG | 2026_ET-01631_GSPKG | Submitted | 2026_ET-01631_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01631_GCPR | 2025-12-08 | Historical | 2026_ET-01631_ACQ | QC Accepted | 2026_ET-01631_FR | 2026-05-03 | Submitted | 2026_ET-01631_RWR | Submitted | 2026-05-03 | 2026_ET-01631_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-14 | 1 | 2026_ET-01631_PROCPKG | In Progress | SCE | 2026_ET-01631_WR |  |  | In Progress |  |  |  | 2026_ET-01631_VMLAZ |  | In Progress |  |  |  | 2026_ET-01631_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01631_RR |  | In Progress | [6 empty] | 2026_ET-01631_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CHASE-CORONA-DATABANK_ET-01631 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-LAMPSON | ET-01635 | 2026_ET-01635 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.9447 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-18 | 04-02-2026 | Flown | 2026-03-03 | 04-18-2026 | 04-08-2026 |  | 2026_ET-01635_ACQPKG | 2026_ET-01635_GSPKG | Submitted | 2026_ET-01635_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01635_GCPR | 2025-12-08 | Historical | 2026_ET-01635_ACQ | QC Accepted | 2026_ET-01635_FR | 2026-04-02 | Submitted | 2026_ET-01635_RWR | Submitted | 2026-04-02 | 2026_ET-01635_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01635_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01635_WR | 2026-05-14 | 05-18-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01635_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01635_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01635_RR | 2026-05-07 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-01635_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-LAMPSON_ET-01635 | Done |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-07 06:52 PST ¦ 2026-03-03 10:10 PST | 020726 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-KINDER-LAMPSON | ET-01636 | 2026_ET-01636 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 8.1697 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-03 | 04-20-2026 | 04-09-2026 |  | 2026_ET-01636_ACQPKG | 2026_ET-01636_GSPKG | Submitted | 2026_ET-01636_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01636_GCPR | 2025-12-08 | Historical | 2026_ET-01636_ACQ | QC Accepted | 2026_ET-01636_FR | 2026-04-02 | Submitted | 2026_ET-01636_RWR | Submitted | 2026-04-02 | 2026_ET-01636_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-01636_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01636_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01636_VMLAZ | 2026-05-11 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01636_VMM1 | 2026-05-11 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01636_RR | 2026-05-11 | Violations QC Confirmed | 05-21-2026 | 05-21-2026 | 2 | 2026-05-12 | 0 | 2 | 2026_ET-01636_VER | 2026-05-11 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-KINDER-LAMPSON_ET-01636 | Done |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-07 06:51 PST ¦ 2026-03-03 10:41 PST | 020726 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALESSANDRO-HIGHGROVE-MAXWELL-TANKER | ET-01643 | 2026_ET-01643 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 16.4416 | 4.1776 | 25 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-01-29 | 04-22-2026 | 04-08-2026 |  | 2026_ET-01643_ACQPKG | 2026_ET-01643_GSPKG | Submitted | 2026_ET-01643_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01643_GCPR | 2025-12-08 | Historical | 2026_ET-01643_ACQ | QC Accepted | 2026_ET-01643_FR | 2026-04-02 | Submitted | 2026_ET-01643_RWR | Submitted | 2026-04-02 | 2026_ET-01643_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01643_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01643_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01643_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01643_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01643_RR | 2026-05-07 | No Violations | 05-19-2026 |  | 0 |  |  |  | 2026_ET-01643_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ALESSANDRO-HIGHGROVE-MAXWELL-TANKER_ET-01643 | Done |  | No |  |  | MENIFEE | 77 | UNK | 2026-01-29 12:32 PST ¦ 2026-01-29 14:28 PST | 012926 | 20260129 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-FAIRFAX-WABASH | ET-01651 | 2026_ET-01651 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 19.8292 | 4.9884 | 25 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-01651_ACQPKG | 2026_ET-01651_GSPKG | Submitted | 2026_ET-01651_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01651_GCPR | 2025-12-08 | Historical | 2026_ET-01651_ACQ | QC Accepted | 2026_ET-01651_FR | 2026-03-16 | Submitted | 2026_ET-01651_RWR | Submitted | 2026-03-16 | 2026_ET-01651_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-01651_PROCPKG | In Progress | SCE | 2026_ET-01651_WR |  |  | In Progress |  |  |  | 2026_ET-01651_VMLAZ |  | In Progress |  |  |  | 2026_ET-01651_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01651_RR |  | In Progress | [6 empty] | 2026_ET-01651_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | EAGLE ROCK-FAIRFAX-WABASH_ET-01651 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-21 13:41 PST ¦ 2026-02-22 10:18 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-LIMESTONE-MOULTON | ET-01652 | 2026_ET-01652 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 6.4416 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-27 |  | 05-20-2026 |  | 2026_ET-01652_ACQPKG | 2026_ET-01652_GSPKG | Submitted | 2026_ET-01652_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01652_GCPR | 2025-12-08 | Historical | 2026_ET-01652_ACQ | QC Accepted | 2026_ET-01652_FR | 2026-05-03 | Submitted | 2026_ET-01652_RWR | Submitted | 2026-05-03 | 2026_ET-01652_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01652_PROCPKG | In Progress | SCE | 2026_ET-01652_WR |  |  | Not Started |  |  |  | 2026_ET-01652_VMLAZ |  | Not Started |  |  |  | 2026_ET-01652_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01652_RR |  | Not Started | [6 empty] | 2026_ET-01652_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | SANTIAGO-LIMESTONE-MOULTON_ET-01652 |  |  | No |  |  | SADDLEBACK | 43 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CLAREMONT-LIVE OAK-SAN ANTONIO | ET-01656 | 2026_ET-01656 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 4.5887 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01656_ACQPKG | 2026_ET-01656_GSPKG | Submitted | 2026_ET-01656_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01656_GCPR | 2025-12-08 | Historical | 2026_ET-01656_ACQ | In Progress | 2026_ET-01656_FR |  | Not Started | 2026_ET-01656_RWR | Not Started |  | 2026_ET-01656_CLAZ |  | Not Started |  |  |  | 2026_ET-01656_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01656_WR |  |  | Not Started |  |  |  | 2026_ET-01656_VMLAZ |  | Not Started |  |  |  | 2026_ET-01656_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01656_RR |  | Not Started | [6 empty] | 2026_ET-01656_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CLAREMONT-LIVE OAK-SAN ANTONIO_ET-01656 |  |  | No |  |  | COVINA | 26 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VICTOR-BLACK MOUNTAIN-SOPORT-SOUTHCAP-SO | ET-01661 | 2026_ET-01661 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 21.6192 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-23 | 04-24-2026 | 04-24-2026 |  | 2026_ET-01661_ACQPKG | 2026_ET-01661_GSPKG | Submitted | 2026_ET-01661_GS | 2025-10-17 | Field Complete | 2026_ET-01661_GCPR | 2025-12-08 | Submitted | 2026_ET-01661_ACQ | QC Accepted | 2026_ET-01661_FR | 2026-03-16 | Submitted | 2026_ET-01661_RWR | Submitted | 2026-03-16 | 2026_ET-01661_CLAZ | 2026-04-17 | QC Accepted | 05-01-2026 | 2026-04-24 | 1 | 2026_ET-01661_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01661_WR | 2026-05-10 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01661_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-01661_VMM1 | 2026-05-10 | QC Accepted |  |  | 2026-05-20 |  | 2026_ET-01661_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01661_VER | 2026-05-10 | QC Rejected |  | 2026-05-21 | 1 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed Late - Program | VICTOR-BLACK MOUNTAIN-SOPORT-SOUTHCAP-SO_ET-01661 |  |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2026-02-23 09:25 PST ¦ 2026-02-23 11:26 PST | 022326 | 20260223 |  | Data voids are present., Metadata issue. |  |  | Analysis Error - False Negative Vegetation Point |  |  | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
ANTELOPE-ANAVERDE-HELIJET | ET-01671 | 2026_ET-01671 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 20.2171 | 4.7783 | 24 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-21 | 04-20-2026 | 04-16-2026 |  | 2026_ET-01671_ACQPKG | 2026_ET-01671_GSPKG | Submitted | 2026_ET-01671_GS | 2025-10-17 | Field Complete | 2026_ET-01671_GCPR | 2025-12-08 | Submitted | 2026_ET-01671_ACQ | QC Accepted | 2026_ET-01671_FR | 2026-03-16 | Submitted | 2026_ET-01671_RWR | Submitted | 2026-03-16 | 2026_ET-01671_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01671_PROCPKG | Submitted | All Good - Complete | 2026_ET-01671_WR | 2026-05-10 | 05-20-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01671_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01671_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01671_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-01671_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | ANTELOPE-ANAVERDE-HELIJET_ET-01671 | Done |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 10:56 PST ¦ 2026-02-21 10:02 PST | 022126 | 20260221 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MORAGA-PECHANGA | ET-01677 | 2026_ET-01677 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.5462 | 1.851 | 33 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-06 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01677_ACQPKG | 2026_ET-01677_GSPKG | Submitted | 2026_ET-01677_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01677_GCPR | 2025-12-08 | Historical | 2026_ET-01677_ACQ | QC Accepted | 2026_ET-01677_FR | 2026-04-02 | Submitted | 2026_ET-01677_RWR | Submitted | 2026-04-02 | 2026_ET-01677_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01677_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01677_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01677_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01677_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01677_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01677_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MORAGA-PECHANGA_ET-01677 |  |  | No |  |  | WILDOMAR | 88 | UNK | 2026-02-06 12:39 PST ¦ 2026-02-06 13:20 PST | 020626 | 20260206 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PAUBA-PECHANGA | ET-01678 | 2026_ET-01678 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.4824 | 7.4824 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-02-06 | 04-14-2026 | 04-14-2026 |  | 2026_ET-01678_ACQPKG | 2026_ET-01678_GSPKG | Submitted | 2026_ET-01678_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01678_GCPR | 2025-12-08 | Historical | 2026_ET-01678_ACQ | QC Accepted | 2026_ET-01678_FR | 2026-04-02 | Submitted | 2026_ET-01678_RWR | Submitted | 2026-04-02 | 2026_ET-01678_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01678_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01678_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01678_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01678_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01678_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01678_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | PAUBA-PECHANGA_ET-01678 |  |  | No |  |  | WILDOMAR | 88 | UNK | 2026-02-06 12:49 PST ¦ 2026-02-06 13:14 PST | 020626 | 20260206 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GOLETA-ELLWOOD-ISLAVISTA-ONSHORE | ET-01683 | 2026_ET-01683 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.0842 | 3.091 | 61 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-14 |  | 05-06-2026 |  | 2026_ET-01683_ACQPKG | 2026_ET-01683_GSPKG | Submitted | 2026_ET-01683_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01683_GCPR | 2025-12-08 | Historical | 2026_ET-01683_ACQ | QC Accepted | 2026_ET-01683_FR | 2026-05-03 | Submitted | 2026_ET-01683_RWR | Submitted | 2026-05-03 | 2026_ET-01683_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-01683_PROCPKG | In Progress | SCE | 2026_ET-01683_WR |  |  | In Progress |  |  |  | 2026_ET-01683_VMLAZ |  | In Progress |  |  |  | 2026_ET-01683_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01683_RR |  | In Progress | [6 empty] | 2026_ET-01683_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | GOLETA-ELLWOOD-ISLAVISTA-ONSHORE_ET-01683 |  |  | No |  |  | SANTA BARBARA | 49 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-ARCHLINE-CUCAMONGA-GENAMIC | ET-01688 | 2026_ET-01688 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 12.5366 | 0.23699 | 2 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-07-2026 |  | 2026_ET-01688_ACQPKG | 2026_ET-01688_GSPKG | Submitted | 2026_ET-01688_GS | 2026-01-31 | Field Complete | 2026_ET-01688_GCPR | 2026-05-03 | Submitted | 2026_ET-01688_ACQ | QC Accepted | 2026_ET-01688_FR | 2026-05-03 | Submitted | 2026_ET-01688_RWR | Submitted | 2026-05-03 | 2026_ET-01688_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01688_PROCPKG | In Progress | SCE | 2026_ET-01688_WR |  |  | In Progress |  |  |  | 2026_ET-01688_VMLAZ |  | In Progress |  |  |  | 2026_ET-01688_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01688_RR |  | In Progress | [6 empty] | 2026_ET-01688_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ETIWANDA-ARCHLINE-CUCAMONGA-GENAMIC_ET-01688 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ELLIS-BAYSIDE | ET-01691 | 2026_ET-01691 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.8887 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-06 | 04-20-2026 | 04-14-2026 |  | 2026_ET-01691_ACQPKG | 2026_ET-01691_GSPKG | Submitted | 2026_ET-01691_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01691_GCPR | 2025-12-08 | Historical | 2026_ET-01691_ACQ | QC Accepted | 2026_ET-01691_FR | 2026-04-02 | Submitted | 2026_ET-01691_RWR | Submitted | 2026-04-02 | 2026_ET-01691_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01691_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01691_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01691_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01691_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01691_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01691_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | ELLIS-BAYSIDE_ET-01691 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | 2026-02-06 06:43 PST ¦ 2026-03-02 13:00 PST | 020626 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-CAROLINA-PLACENTIA-TITANS | ET-01694 | 2026_ET-01694 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.5738 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-03 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01694_ACQPKG | 2026_ET-01694_GSPKG | Submitted | 2026_ET-01694_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01694_GCPR | 2025-12-08 | Historical | 2026_ET-01694_ACQ | QC Accepted | 2026_ET-01694_FR | 2026-04-02 | Submitted | 2026_ET-01694_RWR | Submitted | 2026-04-02 | 2026_ET-01694_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01694_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01694_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01694_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01694_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01694_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 11 | 2026-05-14 |  | 0 | 2026_ET-01694_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | VILLA PARK-CAROLINA-PLACENTIA-TITANS_ET-01694 |  |  | No |  |  | FULLERTON | 48 | UNK | 2026-02-02 13:30 PST ¦ 2026-02-02 14:01 PST | 020226 | 20260202 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-BRIDGE-NORTHROP-YUKON NO. 1 | ET-01699 | 2026_ET-01699 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.5562 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-06 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01699_ACQPKG | 2026_ET-01699_GSPKG | Submitted | 2026_ET-01699_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01699_GCPR | 2025-12-08 | Historical | 2026_ET-01699_ACQ | QC Accepted | 2026_ET-01699_FR | 2026-04-02 | Submitted | 2026_ET-01699_RWR | Submitted | 2026-04-02 | 2026_ET-01699_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01699_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01699_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01699_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01699_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01699_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 10 | 2026-05-14 |  | 0 | 2026_ET-01699_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LA FRESA-BRIDGE-NORTHROP-YUKON NO. 1_ET-01699 |  |  | No |  |  | SOUTH BAY | 44 | UNK | 2026-03-06 10:15 PST ¦ 2026-03-06 12:30 PST | 030626 | 20260306 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-BRIDGE-NORTHROP-YUKON NO. 2 | ET-01700 | 2026_ET-01700 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.815 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-28 | 04-02-2026 | Flown | 2026-03-06 | 04-28-2026 | 04-14-2026 |  | 2026_ET-01700_ACQPKG | 2026_ET-01700_GSPKG | Submitted | 2026_ET-01700_GS | 2025-12-08 | Field Complete | 2026_ET-01700_GCPR | 2026-04-02 | Submitted | 2026_ET-01700_ACQ | QC Accepted | 2026_ET-01700_FR | 2026-04-02 | Submitted | 2026_ET-01700_RWR | Submitted | 2026-04-02 | 2026_ET-01700_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01700_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01700_WR | 2026-05-14 | 05-28-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01700_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01700_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01700_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01700_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LA FRESA-BRIDGE-NORTHROP-YUKON NO. 2_ET-01700 |  |  | No |  |  | SOUTH BAY | 44 | UNK | 2026-03-06 10:17 PST ¦ 2026-03-06 12:26 PST | 030626 | 20260306 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARROWHEAD-DEVIL CANYON-MOJAVE SIPHON-SHA | ET-01716 | 2026_ET-01716 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 20.1476 | 19.6938 | 98 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01716_ACQPKG | 2026_ET-01716_GSPKG | Submitted | 2026_ET-01716_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01716_GCPR | 2025-12-08 | Historical | 2026_ET-01716_ACQ | Submitted | 2026_ET-01716_FR | 2026-05-22 | Submitted | 2026_ET-01716_RWR | Submitted | 2026-05-22 | 2026_ET-01716_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01716_PROCPKG | In Progress | SCE | 2026_ET-01716_WR |  |  | Not Started |  |  |  | 2026_ET-01716_VMLAZ |  | Not Started |  |  |  | 2026_ET-01716_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01716_RR |  | Not Started | [6 empty] | 2026_ET-01716_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | ARROWHEAD-DEVIL CANYON-MOJAVE SIPHON-SHA_ET-01716 | Done |  | No |  |  | ARROWHEAD | 40 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
APPLE VALLEY-COTTONWOOD-PLUESS-SAVAGE | ET-01720 | 2026_ET-01720 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 31.8122 | 1.8269 | 6 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-02-23 | 04-23-2026 | 04-16-2026 |  | 2026_ET-01720_ACQPKG | 2026_ET-01720_GSPKG | Submitted | 2026_ET-01720_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01720_GCPR | 2025-12-08 | Historical | 2026_ET-01720_ACQ | QC Accepted | 2026_ET-01720_FR | 2026-03-16 | Submitted | 2026_ET-01720_RWR | Submitted | 2026-03-16 | 2026_ET-01720_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01720_PROCPKG | Submitted | All Good - Complete | 2026_ET-01720_WR | 2026-05-10 | 05-23-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01720_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01720_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01720_RR | 2026-05-10 | Ready for QC |  |  | 3 |  |  |  | 2026_ET-01720_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | APPLE VALLEY-COTTONWOOD-PLUESS-SAVAGE_ET-01720 | Done |  | No |  | Helicopter | VICTORVILLE | 73 | HC | 2026-02-23 09:44 PST ¦ 2026-02-23 10:37 PST | 022326 | 20260223 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVMAIN-WESTHILL | ET-01722 | 2026_ET-01722 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 05-02-2026 | On Time | 0 | Transmission | 1.4549 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-01-2026 | Access Delay |  |  |  |  | 2026_ET-01722_ACQPKG | 2026_ET-01722_GSPKG | In Progress | 2026_ET-01722_GS | 2025-12-08 | Field Complete | 2026_ET-01722_GCPR |  | Not Started | 2026_ET-01722_ACQ | In Progress | 2026_ET-01722_FR |  | Not Started | 2026_ET-01722_RWR | Not Started |  | 2026_ET-01722_CLAZ |  | Not Started |  |  |  | 2026_ET-01722_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01722_WR |  |  | Not Started |  |  |  | 2026_ET-01722_VMLAZ |  | Not Started |  |  |  | 2026_ET-01722_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01722_RR |  | Not Started | [6 empty] | 2026_ET-01722_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | CHEVMAIN-WESTHILL_ET-01722 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHINO-GANESHA-PLASTIC | ET-01728 | 2026_ET-01728 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 7.026 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-05-2026 |  | 2026_ET-01728_ACQPKG | 2026_ET-01728_GSPKG | Submitted | 2026_ET-01728_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01728_GCPR | 2025-12-08 | Historical | 2026_ET-01728_ACQ | QC Accepted | 2026_ET-01728_FR | 2026-05-03 | Submitted | 2026_ET-01728_RWR | Submitted | 2026-05-03 | 2026_ET-01728_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-05 |  | 2026_ET-01728_PROCPKG | In Progress | SCE | 2026_ET-01728_WR |  |  | In Progress |  |  |  | 2026_ET-01728_VMLAZ |  | In Progress |  |  |  | 2026_ET-01728_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01728_RR |  | In Progress | [6 empty] | 2026_ET-01728_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CHINO-GANESHA-PLASTIC_ET-01728 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVMAIN-CHEVCENTRAL | ET-01734 | 2026_ET-01734 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 1.0534 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Access Delay |  |  |  |  | 2026_ET-01734_ACQPKG | 2026_ET-01734_GSPKG | In Progress | 2026_ET-01734_GS | 2025-12-08 | Field Complete | 2026_ET-01734_GCPR |  | Not Started | 2026_ET-01734_ACQ | In Progress | 2026_ET-01734_FR |  | Not Started | 2026_ET-01734_RWR | Not Started |  | 2026_ET-01734_CLAZ |  | Not Started |  |  |  | 2026_ET-01734_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01734_WR |  |  | Not Started |  |  |  | 2026_ET-01734_VMLAZ |  | Not Started |  |  |  | 2026_ET-01734_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01734_RR |  | Not Started | [6 empty] | 2026_ET-01734_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CHEVMAIN-CHEVCENTRAL_ET-01734 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-AMCO-MOOG | ET-01736 | 2026_ET-01736 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.7838 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-28 | 04-02-2026 | Flown | 2026-03-06 | 04-28-2026 | 04-14-2026 |  | 2026_ET-01736_ACQPKG | 2026_ET-01736_GSPKG | Submitted | 2026_ET-01736_GS | 2025-12-08 | Field Complete | 2026_ET-01736_GCPR | 2026-04-02 | Submitted | 2026_ET-01736_ACQ | QC Accepted | 2026_ET-01736_FR | 2026-04-02 | Submitted | 2026_ET-01736_RWR | Submitted | 2026-04-02 | 2026_ET-01736_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01736_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01736_WR | 2026-05-14 | 05-28-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01736_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01736_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01736_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01736_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | LA FRESA-AMCO-MOOG_ET-01736 |  |  | No |  |  | SOUTH BAY | 44 | UNK | 2026-03-06 11:02 PST ¦ 2026-03-18 10:24 PDT | 030626 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVCENTRAL-CHEVGEN | ET-01737 | 2026_ET-01737 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.41033 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Access Delay |  |  |  |  | 2026_ET-01737_ACQPKG | 2026_ET-01737_GSPKG | In Progress | 2026_ET-01737_GS | 2025-12-08 | Field Complete | 2026_ET-01737_GCPR |  | Not Started | 2026_ET-01737_ACQ | In Progress | 2026_ET-01737_FR |  | Not Started | 2026_ET-01737_RWR | Not Started |  | 2026_ET-01737_CLAZ |  | Not Started |  |  |  | 2026_ET-01737_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01737_WR |  |  | Not Started |  |  |  | 2026_ET-01737_VMLAZ |  | Not Started |  |  |  | 2026_ET-01737_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01737_RR |  | Not Started | [6 empty] | 2026_ET-01737_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CHEVCENTRAL-CHEVGEN_ET-01737 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVMAIN-DEL MAR-LOSULFUR | ET-01747 | 2026_ET-01747 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 1.4117 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Access Delay |  |  |  |  | 2026_ET-01747_ACQPKG | 2026_ET-01747_GSPKG | In Progress | 2026_ET-01747_GS | 2025-12-08 | Field Complete | 2026_ET-01747_GCPR |  | Not Started | 2026_ET-01747_ACQ | In Progress | 2026_ET-01747_FR |  | Not Started | 2026_ET-01747_RWR | Not Started |  | 2026_ET-01747_CLAZ |  | Not Started |  |  |  | 2026_ET-01747_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01747_WR |  |  | Not Started |  |  |  | 2026_ET-01747_VMLAZ |  | Not Started |  |  |  | 2026_ET-01747_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01747_RR |  | Not Started | [6 empty] | 2026_ET-01747_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CHEVMAIN-DEL MAR-LOSULFUR_ET-01747 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHEVGEN-DEL MAR-LOSULFUR | ET-01749 | 2026_ET-01749 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.58993 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Access Delay |  |  |  |  | 2026_ET-01749_ACQPKG | 2026_ET-01749_GSPKG | In Progress | 2026_ET-01749_GS | 2025-12-08 | Field Complete | 2026_ET-01749_GCPR |  | Not Started | 2026_ET-01749_ACQ | In Progress | 2026_ET-01749_FR |  | Not Started | 2026_ET-01749_RWR | Not Started |  | 2026_ET-01749_CLAZ |  | Not Started |  |  |  | 2026_ET-01749_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01749_WR |  |  | Not Started |  |  |  | 2026_ET-01749_VMLAZ |  | Not Started |  |  |  | 2026_ET-01749_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01749_RR |  | Not Started | [6 empty] | 2026_ET-01749_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CHEVGEN-DEL MAR-LOSULFUR_ET-01749 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARCHIBALD-FIREHOUSE-MILLIKEN | ET-01759 | 2026_ET-01759 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.5833 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-01-29 | 04-21-2026 | 04-17-2026 |  | 2026_ET-01759_ACQPKG | 2026_ET-01759_GSPKG | Submitted | 2026_ET-01759_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01759_GCPR | 2025-12-08 | Historical | 2026_ET-01759_ACQ | QC Accepted | 2026_ET-01759_FR | 2026-04-02 | Submitted | 2026_ET-01759_RWR | Submitted | 2026-04-02 | 2026_ET-01759_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-17 | 0 | 2026_ET-01759_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01759_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01759_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01759_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01759_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01759_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ARCHIBALD-FIREHOUSE-MILLIKEN_ET-01759 | Done |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-29 09:56 PST ¦ 2026-02-15 10:47 PST | 012926 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE EL NIDO-CULVER #6 | ET-01769 | 2026_ET-01769 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.6068 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01769_ACQPKG | 2026_ET-01769_GSPKG | In Progress | 2026_ET-01769_GS |  | Not Started | 2026_ET-01769_GCPR |  | Not Started | 2026_ET-01769_ACQ | In Progress | 2026_ET-01769_FR |  | Not Started | 2026_ET-01769_RWR | Not Started |  | 2026_ET-01769_CLAZ |  | Not Started |  |  |  | 2026_ET-01769_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01769_WR |  |  | Not Started |  |  |  | 2026_ET-01769_VMLAZ |  | Not Started |  |  |  | 2026_ET-01769_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01769_RR |  | Not Started | [6 empty] | 2026_ET-01769_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE EL NIDO-CULVER #6_ET-01769 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE EL NIDO-CULVER #7 | ET-01770 | 2026_ET-01770 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 06-02-2026 | On Time | 0 | Transmission | 4.6063 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Airspace issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-02-2026 | Access Delay |  |  |  |  | 2026_ET-01770_ACQPKG | 2026_ET-01770_GSPKG | Submitted | 2026_ET-01770_GS | 2026-01-31 | Field Complete | 2026_ET-01770_GCPR | 2026-05-03 | Submitted | 2026_ET-01770_ACQ | In Progress | 2026_ET-01770_FR |  | Not Started | 2026_ET-01770_RWR | Not Started |  | 2026_ET-01770_CLAZ |  | Not Started |  |  |  | 2026_ET-01770_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01770_WR |  |  | Not Started |  |  |  | 2026_ET-01770_VMLAZ |  | Not Started |  |  |  | 2026_ET-01770_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01770_RR |  | Not Started | [6 empty] | 2026_ET-01770_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | IDLE EL NIDO-CULVER #7_ET-01770 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-COLOSSUS-LOCKHEED-PITCHGEN | ET-01772 | 2026_ET-01772 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 6.7216 | 6.7216 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-03-09 | 04-23-2026 | 04-15-2026 |  | 2026_ET-01772_ACQPKG | 2026_ET-01772_GSPKG | Submitted | 2026_ET-01772_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01772_GCPR | 2025-12-08 | Historical | 2026_ET-01772_ACQ | QC Accepted | 2026_ET-01772_FR | 2026-04-02 | Submitted | 2026_ET-01772_RWR | Submitted | 2026-04-02 | 2026_ET-01772_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01772_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01772_WR | 2026-05-14 | 05-23-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01772_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01772_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01772_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01772_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-COLOSSUS-LOCKHEED-PITCHGEN_ET-01772 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:49 PST ¦ 2026-03-18 09:20 PDT | 030926 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEE VINING-LUNDY NO.1 | ET-01774 | 2026_ET-01774 |  | 1 | 2026 | Nov 01, 2026 | 55 | CA_3 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 7.2652 | 7.2652 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01774_ACQPKG | 2026_ET-01774_GSPKG | Submitted | 2026_ET-01774_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01774_GCPR | 2025-12-08 | Historical | 2026_ET-01774_ACQ | In Progress | 2026_ET-01774_FR |  | Not Started | 2026_ET-01774_RWR | Not Started |  | 2026_ET-01774_CLAZ |  | Not Started |  |  |  | 2026_ET-01774_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01774_WR |  |  | Not Started |  |  |  | 2026_ET-01774_VMLAZ |  | Not Started |  |  |  | 2026_ET-01774_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01774_RR |  | Not Started | [6 empty] | 2026_ET-01774_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LEE VINING-LUNDY NO.1_ET-01774 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-LENNOX-POLARIS-YUKON | ET-01775 | 2026_ET-01775 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 05-02-2026 | On Time | 0 | Transmission | 7.2985 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Issues - Trying to find a resolution |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-01-2026 | Access Delay |  |  |  |  | 2026_ET-01775_ACQPKG | 2026_ET-01775_GSPKG | Submitted | 2026_ET-01775_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01775_GCPR |  | Historical | 2026_ET-01775_ACQ | In Progress | 2026_ET-01775_FR |  | Not Started | 2026_ET-01775_RWR | Not Started |  | 2026_ET-01775_CLAZ |  | Not Started |  |  |  | 2026_ET-01775_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01775_WR |  |  | Not Started |  |  |  | 2026_ET-01775_VMLAZ |  | Not Started |  |  |  | 2026_ET-01775_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01775_RR |  | Not Started | [6 empty] | 2026_ET-01775_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | EL NIDO-LENNOX-POLARIS-YUKON_ET-01775 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-INGLEWOOD | ET-01778 | 2026_ET-01778 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 06-02-2026 | On Time | 0 | Transmission | 6.0884 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Airspace issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-02-2026 | Access Delay |  |  |  |  | 2026_ET-01778_ACQPKG | 2026_ET-01778_GSPKG | Submitted | 2026_ET-01778_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01778_GCPR | 2025-12-08 | Historical | 2026_ET-01778_ACQ | In Progress | 2026_ET-01778_FR |  | Not Started | 2026_ET-01778_RWR | Not Started |  | 2026_ET-01778_CLAZ |  | Not Started |  |  |  | 2026_ET-01778_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01778_WR |  |  | Not Started |  |  |  | 2026_ET-01778_VMLAZ |  | Not Started |  |  |  | 2026_ET-01778_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01778_RR |  | Not Started | [6 empty] | 2026_ET-01778_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | EL NIDO-INGLEWOOD_ET-01778 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BURRO FLATS-CHATSWORTH-THRUST | ET-01780 | 2026_ET-01780 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.40477 | 0.40477 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-11 | 04-14-2026 | 04-14-2026 |  | 2026_ET-01780_ACQPKG | 2026_ET-01780_GSPKG | Submitted | 2026_ET-01780_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01780_GCPR | 2025-12-08 | Historical | 2026_ET-01780_ACQ | QC Accepted | 2026_ET-01780_FR | 2026-04-02 | Submitted | 2026_ET-01780_RWR | Submitted | 2026-04-02 | 2026_ET-01780_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01780_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01780_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01780_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01780_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01780_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01780_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | IDLE BURRO FLATS-CHATSWORTH-THRUST_ET-01780 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-11 08:49 PDT ¦ 2026-03-15 10:42 PDT | 031126 | 20260315 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-GARFIELD-WABASH | ET-01792 | 2026_ET-01792 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.9839 | 6.6821 | 48 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-22 | 04-21-2026 | 04-16-2026 |  | 2026_ET-01792_ACQPKG | 2026_ET-01792_GSPKG | Submitted | 2026_ET-01792_GS | 2025-10-15 | Field Complete | 2026_ET-01792_GCPR | 2025-12-08 | Submitted | 2026_ET-01792_ACQ | QC Accepted | 2026_ET-01792_FR | 2026-03-16 | Submitted | 2026_ET-01792_RWR | Submitted | 2026-03-16 | 2026_ET-01792_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01792_PROCPKG | Submitted | All Good - Complete | 2026_ET-01792_WR | 2026-05-10 | 05-21-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01792_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01792_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01792_RR | 2026-05-10 | Ready for QC |  |  | 1 |  |  |  | 2026_ET-01792_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | EAGLE ROCK-GARFIELD-WABASH_ET-01792 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2026-02-22 09:16 PST ¦ 2026-02-22 10:10 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE ROCK-ALHAMBRA NO. 3 | ET-01793 | 2026_ET-01793 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 8.2421 | 5.4087 | 66 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-25 | 04-02-2026 | Flown | 2026-02-22 | 04-25-2026 | 04-16-2026 |  | 2026_ET-01793_ACQPKG | 2026_ET-01793_GSPKG | Submitted | 2026_ET-01793_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01793_GCPR | 2025-12-08 | Historical | 2026_ET-01793_ACQ | QC Accepted | 2026_ET-01793_FR | 2026-03-16 | Submitted | 2026_ET-01793_RWR | Submitted | 2026-03-16 | 2026_ET-01793_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01793_PROCPKG | Submitted | All Good - Complete | 2026_ET-01793_WR | 2026-05-10 | 05-25-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01793_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01793_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01793_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-01793_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | EAGLE ROCK-ALHAMBRA NO. 3_ET-01793 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 09:35 PST ¦ 2026-02-22 09:50 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-NEWMARK-RAMONA | ET-01794 | 2026_ET-01794 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.7878 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-22 | 04-22-2026 | 04-21-2026 |  | 2026_ET-01794_ACQPKG | 2026_ET-01794_GSPKG | Submitted | 2026_ET-01794_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01794_GCPR | 2025-12-08 | Historical | 2026_ET-01794_ACQ | QC Accepted | 2026_ET-01794_FR | 2026-03-16 | Submitted | 2026_ET-01794_RWR | Submitted | 2026-03-16 | 2026_ET-01794_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-01794_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01794_WR | 2026-04-29 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01794_VMLAZ | 2026-04-29 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01794_VMM1 | 2026-04-29 | QC Accepted |  | 06-01-2026 | 2026-05-04 |  | 2026_ET-01794_RR |  | No Violations | 05-05-2026 |  | 0 |  |  |  | 2026_ET-01794_VER | 2026-04-29 | Uploaded to S123 | 06-01-2026 | 2026-05-06 | [5 empty] | Completed On Time - Program | Completed On Time | Completed Late - Program | MESA-NEWMARK-RAMONA_ET-01794 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 09:54 PST ¦ 2026-02-22 11:09 PST | 022226 | 20260222 |  | Metadata issue. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
LEE VINING-LUNDY NO.2 | ET-01797 | 2026_ET-01797 |  | 1 | 2026 | Nov 01, 2026 | 55 | CA_3 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 7.2329 | 7.2329 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01797_ACQPKG | 2026_ET-01797_GSPKG | Submitted | 2026_ET-01797_GS | 2023-12-12 | Field Complete | 2026_ET-01797_GCPR | 2025-12-08 | Submitted | 2026_ET-01797_ACQ | In Progress | 2026_ET-01797_FR |  | Not Started | 2026_ET-01797_RWR | Not Started |  | 2026_ET-01797_CLAZ |  | Not Started |  |  |  | 2026_ET-01797_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01797_WR |  |  | Not Started |  |  |  | 2026_ET-01797_VMLAZ |  | Not Started |  |  |  | 2026_ET-01797_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01797_RR |  | Not Started | [6 empty] | 2026_ET-01797_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LEE VINING-LUNDY NO.2_ET-01797 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE ETIWANDA-DECLEZ-RANDALL | ET-01802 | 2026_ET-01802 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.10659 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-01-31 | 04-15-2026 | 04-15-2026 |  | 2026_ET-01802_ACQPKG | 2026_ET-01802_GSPKG | Submitted | 2026_ET-01802_GS | 2025-12-08 | Field Complete | 2026_ET-01802_GCPR | 2026-04-02 | Submitted | 2026_ET-01802_ACQ | QC Accepted | 2026_ET-01802_FR | 2026-04-02 | Submitted | 2026_ET-01802_RWR | Submitted | 2026-04-02 | 2026_ET-01802_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01802_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01802_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01802_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01802_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01802_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01802_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE ETIWANDA-DECLEZ-RANDALL_ET-01802 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-31 12:54 PST ¦ 2026-01-31 13:28 PST | 013126 | 20260131 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-ARCHIBALD | ET-01803 | 2026_ET-01803 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.2252 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-15 | 04-20-2026 | 04-14-2026 |  | 2026_ET-01803_ACQPKG | 2026_ET-01803_GSPKG | Submitted | 2026_ET-01803_GS | 2025-12-08 | Field Complete | 2026_ET-01803_GCPR | 2026-04-02 | Submitted | 2026_ET-01803_ACQ | QC Accepted | 2026_ET-01803_FR | 2026-04-02 | Submitted | 2026_ET-01803_RWR | Submitted | 2026-04-02 | 2026_ET-01803_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01803_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01803_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01803_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01803_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01803_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01803_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MIRA LOMA-ARCHIBALD_ET-01803 |  |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-29 09:39 PST ¦ 2026-02-15 10:55 PST | 012926 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
GALLATIN-LAGUNA BELL-SPONGE | ET-01806 | 2026_ET-01806 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.0584 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Proceed with Wire Temp at Ambient | Daniel |  | 2026-04-28 | 04-02-2026 | Flown | 2026-03-01 | 04-28-2026 | 04-14-2026 |  | 2026_ET-01806_ACQPKG | 2026_ET-01806_GSPKG | Submitted | 2026_ET-01806_GS | 2025-12-08 | Field Complete | 2026_ET-01806_GCPR | 2026-04-02 | Submitted | 2026_ET-01806_ACQ | QC Accepted | 2026_ET-01806_FR | 2026-04-02 | Submitted | 2026_ET-01806_RWR | Submitted | 2026-04-02 | 2026_ET-01806_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01806_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01806_WR | 2026-05-14 | 05-28-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01806_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01806_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01806_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01806_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | GALLATIN-LAGUNA BELL-SPONGE_ET-01806 |  |  | No |  |  | WHITTIER | 47 | UNK | 2026-03-01 08:56 PST ¦ 2026-03-18 10:04 PDT | 030126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-ARCHIBALD-BAIN-METALCAN | ET-01808 | 2026_ET-01808 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 11.398 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-20-2026 |  | 2026_ET-01808_ACQPKG | 2026_ET-01808_GSPKG | Submitted | 2026_ET-01808_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01808_GCPR | 2025-12-08 | Historical | 2026_ET-01808_ACQ | QC Accepted | 2026_ET-01808_FR | 2026-05-03 | Submitted | 2026_ET-01808_RWR | Submitted | 2026-05-03 | 2026_ET-01808_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01808_PROCPKG | In Progress | SCE | 2026_ET-01808_WR |  |  | Not Started |  |  |  | 2026_ET-01808_VMLAZ |  | Not Started |  |  |  | 2026_ET-01808_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01808_RR |  | Not Started | [6 empty] | 2026_ET-01808_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MIRA LOMA-ARCHIBALD-BAIN-METALCAN_ET-01808 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-GARNET-INDIGO | ET-01810 | 2026_ET-01810 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 4.1209 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01810_ACQPKG | 2026_ET-01810_GSPKG | Submitted | 2026_ET-01810_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01810_GCPR | 2025-12-08 | Historical | 2026_ET-01810_ACQ | Submitted | 2026_ET-01810_FR | 2026-05-22 | Submitted | 2026_ET-01810_RWR | Submitted | 2026-05-22 | 2026_ET-01810_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-01810_PROCPKG | In Progress | SCE | 2026_ET-01810_WR |  |  | Not Started |  |  |  | 2026_ET-01810_VMLAZ |  | Not Started |  |  |  | 2026_ET-01810_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01810_RR |  | Not Started | [6 empty] | 2026_ET-01810_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | DEVERS-GARNET-INDIGO_ET-01810 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRAGE-RAMON (IID KS) | ET-01813 | 2026_ET-01813 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.080499 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-07 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01813_ACQPKG | 2026_ET-01813_GSPKG | Submitted | 2026_ET-01813_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01813_GCPR | 2025-12-08 | Historical | 2026_ET-01813_ACQ | QC Accepted | 2026_ET-01813_FR | 2026-04-02 | Submitted | 2026_ET-01813_RWR | Submitted | 2026-04-02 | 2026_ET-01813_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01813_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01813_WR | 2026-05-13 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-14 | 0 | 2026_ET-01813_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-01813_VMM1 | 2026-05-13 | QC Accepted |  | 06-01-2026 | 2026-05-14 |  | 2026_ET-01813_RR | 2026-05-13 | No Violations | 05-15-2026 | [5 empty] | 2026_ET-01813_VER | 2026-05-13 | Uploaded to S123 | 06-01-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MIRAGE-RAMON (IID KS)_ET-01813 |  |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-WAKEFIELD NO. 1 | ET-01819 | 2026_ET-01819 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 10.9465 | 10.0642 | 92 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01819_ACQPKG | 2026_ET-01819_GSPKG | Submitted | 2026_ET-01819_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01819_GCPR | 2025-12-08 | Historical | 2026_ET-01819_ACQ | In Progress | 2026_ET-01819_FR |  | Not Started | 2026_ET-01819_RWR | Not Started |  | 2026_ET-01819_CLAZ |  | Not Started |  |  |  | 2026_ET-01819_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01819_WR |  |  | Not Started |  |  |  | 2026_ET-01819_VMLAZ |  | Not Started |  |  |  | 2026_ET-01819_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01819_RR |  | Not Started | [6 empty] | 2026_ET-01819_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-WAKEFIELD NO. 1_ET-01819 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-WAKEFIELD NO. 2 | ET-01820 | 2026_ET-01820 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 20.8599 | 19.5394 | 94 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-01820_ACQPKG | 2026_ET-01820_GSPKG | Submitted | 2026_ET-01820_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01820_GCPR | 2025-12-08 | Historical | 2026_ET-01820_ACQ | In Progress | 2026_ET-01820_FR |  | Not Started | 2026_ET-01820_RWR | Not Started |  | 2026_ET-01820_CLAZ |  | Not Started |  |  |  | 2026_ET-01820_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01820_WR |  |  | Not Started |  |  |  | 2026_ET-01820_VMLAZ |  | Not Started |  |  |  | 2026_ET-01820_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01820_RR |  | Not Started | [6 empty] | 2026_ET-01820_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-WAKEFIELD NO. 2_ET-01820 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-FILLMORE NO.1 | ET-01821 | 2026_ET-01821 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 22.8868 | 20.5469 | 90 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-03-10 | 04-16-2026 | 04-15-2026 |  | 2026_ET-01821_ACQPKG | 2026_ET-01821_GSPKG | Submitted | 2026_ET-01821_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01821_GCPR | 2025-12-08 | Historical | 2026_ET-01821_ACQ | QC Accepted | 2026_ET-01821_FR | 2026-04-02 | Submitted | 2026_ET-01821_RWR | Submitted | 2026-04-02 | 2026_ET-01821_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01821_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01821_WR | 2026-05-14 | 05-16-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01821_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01821_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01821_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01821_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-FILLMORE NO.1_ET-01821 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-09 10:50 PDT ¦ 2026-03-18 09:25 PDT | 031826 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-FILLMORE NO. 2 | ET-01822 | 2026_ET-01822 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 22.6025 | 22.6025 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-03-09 | 04-15-2026 | 04-15-2026 |  | 2026_ET-01822_ACQPKG | 2026_ET-01822_GSPKG | Submitted | 2026_ET-01822_GS | 2025-12-08 | Field Complete | 2026_ET-01822_GCPR | 2026-04-02 | Submitted | 2026_ET-01822_ACQ | QC Accepted | 2026_ET-01822_FR | 2026-04-02 | Submitted | 2026_ET-01822_RWR | Submitted | 2026-04-02 | 2026_ET-01822_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01822_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01822_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01822_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01822_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01822_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01822_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | SAUGUS-FILLMORE NO. 2_ET-01822 |  |  | No |  |  | VALENCIA | 59 | UNK | 2026-03-04 09:49 PST ¦ 2026-03-18 09:25 PDT | 031326 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
APL-DOCK-LONG BEACH | ET-01826 | 2026_ET-01826 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 2.4116 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_01 | 2025-12-01 | 2026_GSI_QC_CWA_05 | 2026-05-08 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available |  |  | 2026-05-18 | 03-03-2026 | Flown | 2026-01-10 | 05-18-2026 | 03-09-2026 |  | 2026_ET-01826_ACQPKG | 2026_ET-01826_GSPKG | Submitted | 2026_ET-01826_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01826_GCPR | 2025-12-08 | Historical | 2026_ET-01826_ACQ | QC Accepted | 2026_ET-01826_FR | 2026-03-02 | Submitted | 2026_ET-01826_RWR | Submitted | 2026-03-02 | 2026_ET-01826_CLAZ | 2026-03-02 | QC Accepted | 03-18-2026 | 2026-03-09 | 0 | 2026_ET-01826_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01826_WR | 2026-04-13 | 06-17-2026 | QC Accepted | 05-02-2026 | 2026-05-15 |  | 2026_ET-01826_VMLAZ | 2026-04-13 | QC Accepted | 05-22-2026 | 2026-05-18 |  | 2026_ET-01826_VMM1 | 2026-04-13 | QC Accepted |  | 05-22-2026 | 2026-05-14 |  | 2026_ET-01826_RR | 2026-04-13 | No Violations | 05-15-2026 |  | 0 |  |  |  | 2026_ET-01826_VER | 2026-04-13 | Uploaded to S123 | 05-22-2026 | 2026-05-13 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | APL-DOCK-LONG BEACH_ET-01826 | Done |  | No | 17:50 |  | LONG BEACH | 46 | UNK | 2026-01-10 11:17 PST ¦ 2026-01-10 12:09 PST | 011026 | 20260110 | [6 empty] | Yes | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOCK-SERRFGEN | ET-01828 | 2026_ET-01828 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.36789 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01828_ACQPKG | 2026_ET-01828_GSPKG | Submitted | 2026_ET-01828_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01828_GCPR | 2025-12-08 | Historical | 2026_ET-01828_ACQ | In Progress | 2026_ET-01828_FR |  | Not Started | 2026_ET-01828_RWR | Not Started |  | 2026_ET-01828_CLAZ |  | Not Started |  |  |  | 2026_ET-01828_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01828_WR |  |  | Not Started |  |  |  | 2026_ET-01828_VMLAZ |  | Not Started |  |  |  | 2026_ET-01828_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01828_RR |  | Not Started | [6 empty] | 2026_ET-01828_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | DOCK-SERRFGEN_ET-01828 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARDIFF-GREENSPOT-SANTA ANA RIVER 3 | ET-01834 | 2026_ET-01834 |  | 1 | 2026 | Jul 01, 2026 | 33 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.6993 | 3.6968 | 27 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-23 | 04-02-2026 | Flown | 2026-02-01 | 04-23-2026 | 04-09-2026 |  | 2026_ET-01834_ACQPKG | 2026_ET-01834_GSPKG | Submitted | 2026_ET-01834_GS | 2025-12-08 | Field Complete | 2026_ET-01834_GCPR | 2026-04-02 | Submitted | 2026_ET-01834_ACQ | QC Accepted | 2026_ET-01834_FR | 2026-04-02 | Submitted | 2026_ET-01834_RWR | Submitted | 2026-04-02 | 2026_ET-01834_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-01834_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01834_WR | 2026-05-14 | 05-23-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01834_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01834_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01834_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01834_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CARDIFF-GREENSPOT-SANTA ANA RIVER 3_ET-01834 | Done |  | No |  |  | REDLANDS | 31 | UNK | 2026-01-31 09:18 PST ¦ 2026-03-18 12:09 PDT | 020126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARDIFF-SANTA ANA RIVER 3 | ET-01835 | 2026_ET-01835 |  | 1 | 2026 | Sep 01, 2026 | 33 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 11.1789 | 5.6168 | 50 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-01835_ACQPKG | 2026_ET-01835_GSPKG | Submitted | 2026_ET-01835_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01835_GCPR | 2025-12-08 | Historical | 2026_ET-01835_ACQ | In Progress | 2026_ET-01835_FR |  | Not Started | 2026_ET-01835_RWR | Not Started |  | 2026_ET-01835_CLAZ |  | Not Started |  |  |  | 2026_ET-01835_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01835_WR |  |  | Not Started |  |  |  | 2026_ET-01835_VMLAZ |  | Not Started |  |  |  | 2026_ET-01835_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01835_RR |  | Not Started | [6 empty] | 2026_ET-01835_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CARDIFF-SANTA ANA RIVER 3_ET-01835 | Done |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RECTOR-LOURICH-OCTOL-TIPTON-TULARE | ET-01836 | 2026_ET-01836 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 32.6642 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01836_ACQPKG | 2026_ET-01836_GSPKG | Submitted | 2026_ET-01836_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01836_GCPR | 2025-12-08 | Historical | 2026_ET-01836_ACQ | In Progress | 2026_ET-01836_FR |  | Not Started | 2026_ET-01836_RWR | Not Started |  | 2026_ET-01836_CLAZ |  | Not Started |  |  |  | 2026_ET-01836_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01836_WR |  |  | Not Started |  |  |  | 2026_ET-01836_VMLAZ |  | Not Started |  |  |  | 2026_ET-01836_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01836_RR |  | Not Started | [6 empty] | 2026_ET-01836_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | RECTOR-LOURICH-OCTOL-TIPTON-TULARE_ET-01836 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EL NIDO-EL SEGUNDO-LA FRESA-ROSECRANS | ET-01842 | 2026_ET-01842 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 06-02-2026 | On Time | 0 | Transmission | 7.8879 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Airspace issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-02-2026 | Access Delay |  |  |  |  | 2026_ET-01842_ACQPKG | 2026_ET-01842_GSPKG | Submitted | 2026_ET-01842_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01842_GCPR | 2025-12-08 | Historical | 2026_ET-01842_ACQ | In Progress | 2026_ET-01842_FR |  | Not Started | 2026_ET-01842_RWR | Not Started |  | 2026_ET-01842_CLAZ |  | Not Started |  |  |  | 2026_ET-01842_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01842_WR |  |  | Not Started |  |  |  | 2026_ET-01842_VMLAZ |  | Not Started |  |  |  | 2026_ET-01842_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01842_RR |  | Not Started | [6 empty] | 2026_ET-01842_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | EL NIDO-EL SEGUNDO-LA FRESA-ROSECRANS_ET-01842 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-DECLEZ NO.1 | ET-01857 | 2026_ET-01857 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.0851 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-31 | 04-20-2026 | 04-15-2026 |  | 2026_ET-01857_ACQPKG | 2026_ET-01857_GSPKG | Submitted | 2026_ET-01857_GS | 2025-12-08 | Field Complete | 2026_ET-01857_GCPR | 2026-04-02 | Submitted | 2026_ET-01857_ACQ | QC Accepted | 2026_ET-01857_FR | 2026-04-02 | Submitted | 2026_ET-01857_RWR | Submitted | 2026-04-02 | 2026_ET-01857_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01857_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01857_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01857_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01857_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01857_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01857_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | ETIWANDA-DECLEZ NO.1_ET-01857 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-30 09:58 PST ¦ 2026-02-15 13:11 PST | 021526 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-DECLEZ NO.2 | ET-01858 | 2026_ET-01858 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.8766 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-30 | 04-20-2026 | 04-15-2026 |  | 2026_ET-01858_ACQPKG | 2026_ET-01858_GSPKG | Submitted | 2026_ET-01858_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01858_GCPR | 2025-12-08 | Historical | 2026_ET-01858_ACQ | QC Accepted | 2026_ET-01858_FR | 2026-04-02 | Submitted | 2026_ET-01858_RWR | Submitted | 2026-04-02 | 2026_ET-01858_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01858_PROCPKG | In Progress | All Good - Complete | 2026_ET-01858_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01858_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-01858_VMM1 | 2026-05-10 | QC Accepted |  |  | 2026-05-20 |  | 2026_ET-01858_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01858_VER | 2026-05-10 | QC Rejected |  | 2026-05-21 | 1 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ETIWANDA-DECLEZ NO.2_ET-01858 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-30 09:44 PST ¦ 2026-02-15 13:01 PST | 021526 | 20260215 |  |  |  |  | Analysis Error - False Negative Vegetation Point |  |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-RANDALL | ET-01860 | 2026_ET-01860 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.9458 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-31 | 04-20-2026 | 04-15-2026 |  | 2026_ET-01860_ACQPKG | 2026_ET-01860_GSPKG | Submitted | 2026_ET-01860_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01860_GCPR | 2025-12-08 | Historical | 2026_ET-01860_ACQ | QC Accepted | 2026_ET-01860_FR | 2026-04-02 | Submitted | 2026_ET-01860_RWR | Submitted | 2026-04-02 | 2026_ET-01860_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-01860_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01860_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01860_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01860_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01860_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01860_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | ETIWANDA-RANDALL_ET-01860 |  |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-30 09:44 PST ¦ 2026-02-15 13:01 PST | 021526 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEBEC-PASTORIA | ET-01867 | 2026_ET-01867 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.25094 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-23 | 04-24-2026 | 04-16-2026 |  | 2026_ET-01867_ACQPKG | 2026_ET-01867_GSPKG | Submitted | 2026_ET-01867_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01867_GCPR | 2025-12-08 | Historical | 2026_ET-01867_ACQ | QC Accepted | 2026_ET-01867_FR | 2026-03-16 | Submitted | 2026_ET-01867_RWR | Submitted | 2026-03-16 | 2026_ET-01867_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01867_PROCPKG | Submitted | All Good - Complete | 2026_ET-01867_WR | 2026-05-13 | 05-24-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01867_VMLAZ | 2026-04-30 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01867_VMM1 | 2026-05-13 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01867_RR | 2026-05-13 | No Violations | [6 empty] | 2026_ET-01867_VER | 2026-05-13 | Ready for QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | LEBEC-PASTORIA_ET-01867 |  |  | Yes |  | Helicopter |  |  | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BARRE-FULLERTON-VILLA PARK | ET-01868 | 2026_ET-01868 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.9537 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-03 | 04-20-2026 | 04-10-2026 |  | 2026_ET-01868_ACQPKG | 2026_ET-01868_GSPKG | Submitted | 2026_ET-01868_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01868_GCPR | 2025-12-08 | Historical | 2026_ET-01868_ACQ | QC Accepted | 2026_ET-01868_FR | 2026-04-02 | Submitted | 2026_ET-01868_RWR | Submitted | 2026-04-02 | 2026_ET-01868_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-01868_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01868_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01868_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01868_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-18 | 0 | 2026_ET-01868_RR | 2026-05-07 | Violations QC Confirmed | 05-19-2026 | 05-19-2026 | 2 | 2026-05-08 | 0 | 2 | 2026_ET-01868_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-18 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BARRE-FULLERTON-VILLA PARK_ET-01868 | Done |  | No |  |  | SANTA ANA | 29 | UNK | 2026-01-30 08:57 PST ¦ 2026-03-03 10:56 PST | 030226 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SOMIS-RTS 87 | ET-01872 | 2026_ET-01872 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 4.4165 | 2.1965 | 50 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-01872_ACQPKG | 2026_ET-01872_GSPKG | Submitted | 2026_ET-01872_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01872_GCPR | 2025-12-08 | Historical | 2026_ET-01872_ACQ | In Progress | 2026_ET-01872_FR |  | Not Started | 2026_ET-01872_RWR | Not Started |  | 2026_ET-01872_CLAZ |  | Not Started |  |  |  | 2026_ET-01872_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01872_WR |  |  | Not Started |  |  |  | 2026_ET-01872_VMLAZ |  | Not Started |  |  |  | 2026_ET-01872_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01872_RR |  | Not Started | [6 empty] | 2026_ET-01872_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SOMIS-RTS 87_ET-01872 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-NEWBURY-PHARMACY | ET-01873 | 2026_ET-01873 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 9.361 | 9.361 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-24 | 04-02-2026 | Flown | 2026-03-10 | 04-24-2026 | 04-14-2026 |  | 2026_ET-01873_ACQPKG | 2026_ET-01873_GSPKG | Submitted | 2026_ET-01873_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01873_GCPR | 2025-12-08 | Historical | 2026_ET-01873_ACQ | QC Accepted | 2026_ET-01873_FR | 2026-04-02 | Submitted | 2026_ET-01873_RWR | Submitted | 2026-04-02 | 2026_ET-01873_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01873_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01873_WR | 2026-05-14 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01873_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01873_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01873_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01873_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-NEWBURY-PHARMACY_ET-01873 |  |  | No |  |  | VENTURA | 39 | UNK | 2026-03-09 14:00 PDT ¦ 2026-03-10 09:36 PDT | 031026 | 20260310 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-HATHAWAY-LAKEWOOD | ET-01875 | 2026_ET-01875 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.6907 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-02 | 04-21-2026 | 04-14-2026 |  | 2026_ET-01875_ACQPKG | 2026_ET-01875_GSPKG | Submitted | 2026_ET-01875_GS | 2025-12-08 | Field Complete | 2026_ET-01875_GCPR | 2026-04-02 | Submitted | 2026_ET-01875_ACQ | QC Accepted | 2026_ET-01875_FR | 2026-04-02 | Submitted | 2026_ET-01875_RWR | Submitted | 2026-04-02 | 2026_ET-01875_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01875_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01875_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01875_VMLAZ | 2026-05-11 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01875_VMM1 | 2026-05-11 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01875_RR | 2026-05-11 | No Violations | 05-21-2026 |  | 4 | 2026-05-14 |  | 0 | 2026_ET-01875_VER | 2026-05-11 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-HATHAWAY-LAKEWOOD_ET-01875 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-02 09:48 PST ¦ 2026-03-02 12:31 PST | 030226 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL AMO-LAKEWOOD | ET-01876 | 2026_ET-01876 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.9269 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-03-02 | 04-17-2026 | 04-14-2026 |  | 2026_ET-01876_ACQPKG | 2026_ET-01876_GSPKG | Submitted | 2026_ET-01876_GS | 2025-12-08 | Field Complete | 2026_ET-01876_GCPR | 2026-04-02 | Submitted | 2026_ET-01876_ACQ | QC Accepted | 2026_ET-01876_FR | 2026-04-02 | Submitted | 2026_ET-01876_RWR | Submitted | 2026-04-02 | 2026_ET-01876_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01876_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01876_WR | 2026-05-14 | 05-17-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01876_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01876_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01876_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01876_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | DEL AMO-LAKEWOOD_ET-01876 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-02 09:19 PST ¦ 2026-03-17 13:56 PDT | 030226 | 20260317 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ARBORS-ARCHLINE | ET-01880 | 2026_ET-01880 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.9231 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-01-30 | 04-16-2026 | 04-08-2026 |  | 2026_ET-01880_ACQPKG | 2026_ET-01880_GSPKG | Submitted | 2026_ET-01880_GS | 2025-12-08 | Field Complete | 2026_ET-01880_GCPR | 2026-04-02 | Submitted | 2026_ET-01880_ACQ | QC Accepted | 2026_ET-01880_FR | 2026-04-02 | Submitted | 2026_ET-01880_RWR | Submitted | 2026-04-02 | 2026_ET-01880_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01880_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01880_WR | 2026-05-14 | 05-16-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01880_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01880_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01880_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01880_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | ARBORS-ARCHLINE_ET-01880 | Done |  | No |  |  | FOOTHILL | 30 | UNK | 2026-01-30 09:20 PST ¦ 2026-02-15 13:15 PST | 021526 | 20260215 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AZUSA-KIRKWALL | ET-01882 | 2026_ET-01882 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.6939 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-22 | 04-16-2026 | 04-16-2026 |  | 2026_ET-01882_ACQPKG | 2026_ET-01882_GSPKG | Submitted | 2026_ET-01882_GS | 2025-10-15 | Field Complete | 2026_ET-01882_GCPR | 2025-12-08 | Submitted | 2026_ET-01882_ACQ | QC Accepted | 2026_ET-01882_FR | 2026-03-16 | Submitted | 2026_ET-01882_RWR | Submitted | 2026-03-16 | 2026_ET-01882_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01882_PROCPKG | Submitted | All Good - Complete | 2026_ET-01882_WR | 2026-05-10 | 05-16-2026 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01882_VMLAZ | 2026-05-10 | Ready for QC | 06-01-2026 |  |  | 2026_ET-01882_VMM1 | 2026-05-10 | Ready for QC |  | 06-01-2026 |  |  | 2026_ET-01882_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-01882_VER | 2026-05-10 | Ready for QC | 06-01-2026 | [6 empty] | Projected On Time | Completed On Time | Completed Late - Program | AZUSA-KIRKWALL_ET-01882 | Done |  | No |  | Helicopter | MONROVIA | 27 | HC | 2026-02-22 13:18 PST ¦ 2026-02-22 13:23 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CITRUS-DALTON-KIRKWALL | ET-01883 | 2026_ET-01883 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.8859 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-28 | 04-22-2026 | 04-08-2026 |  | 2026_ET-01883_ACQPKG | 2026_ET-01883_GSPKG | Submitted | 2026_ET-01883_GS | 2025-12-08 | Field Complete | 2026_ET-01883_GCPR | 2026-04-02 | Submitted | 2026_ET-01883_ACQ | QC Accepted | 2026_ET-01883_FR | 2026-04-02 | Submitted | 2026_ET-01883_RWR | Submitted | 2026-04-02 | 2026_ET-01883_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01883_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01883_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01883_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01883_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01883_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01883_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CITRUS-DALTON-KIRKWALL_ET-01883 |  |  | No |  |  | COVINA | 26 | UNK | 2026-02-28 09:25 PST ¦ 2026-03-17 13:03 PDT | 022826 | 20260317 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CLEARGEN-JEFFERSON | ET-01888 | 2026_ET-01888 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 2.7815 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-01-31 | 04-20-2026 | 04-14-2026 |  | 2026_ET-01888_ACQPKG | 2026_ET-01888_GSPKG | Submitted | 2026_ET-01888_GS | 2025-12-08 | Field Complete | 2026_ET-01888_GCPR | 2026-04-02 | Submitted | 2026_ET-01888_ACQ | QC Accepted | 2026_ET-01888_FR | 2026-04-02 | Submitted | 2026_ET-01888_RWR | Submitted | 2026-04-02 | 2026_ET-01888_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-01888_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01888_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01888_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-01888_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-01888_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01888_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | CLEARGEN-JEFFERSON_ET-01888 |  |  | No |  |  | ONTARIO | 34 | UNK | 2026-01-31 14:10 PST ¦ 2026-02-22 08:41 PST | 013126 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARBOGEN-WATSON | ET-01892 | 2026_ET-01892 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.4313 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-26 | 04-02-2026 | Flown | 2026-03-05 | 04-26-2026 | 04-08-2026 |  | 2026_ET-01892_ACQPKG | 2026_ET-01892_GSPKG | Submitted | 2026_ET-01892_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01892_GCPR | 2025-12-08 | Historical | 2026_ET-01892_ACQ | QC Accepted | 2026_ET-01892_FR | 2026-04-02 | Submitted | 2026_ET-01892_RWR | Submitted | 2026-04-02 | 2026_ET-01892_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-08 | 0 | 2026_ET-01892_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01892_WR | 2026-05-14 | 05-26-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01892_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01892_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01892_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-01892_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Projected On Time | Completed On Time - Program | CARBOGEN-WATSON_ET-01892 | Done |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | 2026-03-05 09:59 PST ¦ 2026-03-05 11:02 PST | 030526 | 20260305 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BANNING-ZANJA | ET-01912 | 2026_ET-01912 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 18.1896 | 16.3834 | 90 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-16 | 04-02-2026 | Flown | 2026-02-02 | 04-16-2026 | 04-09-2026 |  | 2026_ET-01912_ACQPKG | 2026_ET-01912_GSPKG | Submitted | 2026_ET-01912_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01912_GCPR | 2025-12-08 | Historical | 2026_ET-01912_ACQ | QC Accepted | 2026_ET-01912_FR | 2026-04-02 | Submitted | 2026_ET-01912_RWR | Submitted | 2026-04-02 | 2026_ET-01912_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-09 | 0 | 2026_ET-01912_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01912_WR | 2026-05-14 | 05-16-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01912_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01912_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01912_RR | 2026-05-07 | Violations QC Confirmed | 05-21-2026 | 05-21-2026 | 36 | 2026-05-08 | 0 | 36 | 2026_ET-01912_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | BANNING-ZANJA_ET-01912 | Done |  | No |  |  | REDLANDS | 31 | UNK | 2026-02-01 14:11 PST ¦ 2026-02-02 09:27 PST | 020226 | 20260202 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLACK RANCH-RED BLUFF | ET-01930 | 2026_ET-01930 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.11632 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-08-2026 |  | 2026_ET-01930_ACQPKG | 2026_ET-01930_GSPKG | Submitted | 2026_ET-01930_GS | 2026-01-31 | Field Complete | 2026_ET-01930_GCPR | 2026-05-03 | Submitted | 2026_ET-01930_ACQ | QC Accepted | 2026_ET-01930_FR | 2026-05-03 | Submitted | 2026_ET-01930_RWR | Submitted | 2026-05-03 | 2026_ET-01930_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-08 |  | 2026_ET-01930_PROCPKG | In Progress | SCE | 2026_ET-01930_WR |  |  | In Progress |  |  |  | 2026_ET-01930_VMLAZ |  | In Progress |  |  |  | 2026_ET-01930_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01930_RR |  | In Progress | [6 empty] | 2026_ET-01930_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BLACK RANCH-RED BLUFF_ET-01930 | Done |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-YUCCA | ET-01933 | 2026_ET-01933 |  | 1 | 2026 | Aug 01, 2026 | 115 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 19.8854 | 13.672 | 69 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 05-05-2026 |  | 2026_ET-01933_ACQPKG | 2026_ET-01933_GSPKG | Submitted | 2026_ET-01933_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01933_GCPR | 2025-12-08 | Historical | 2026_ET-01933_ACQ | QC Accepted | 2026_ET-01933_FR | 2026-05-03 | Submitted | 2026_ET-01933_RWR | Submitted | 2026-05-03 | 2026_ET-01933_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-05 |  | 2026_ET-01933_PROCPKG | In Progress | SCE | 2026_ET-01933_WR |  |  | In Progress |  |  |  | 2026_ET-01933_VMLAZ |  | In Progress |  |  |  | 2026_ET-01933_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01933_RR |  | In Progress | [6 empty] | 2026_ET-01933_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEVERS-YUCCA_ET-01933 |  |  | No |  |  | YUCCA VALLEY | 84 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BANDUCCI-KERN RIVER 1 | ET-01936 | 2026_ET-01936 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 34.782 | 20.566 | 59 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01936_ACQPKG | 2026_ET-01936_GSPKG | Submitted | 2026_ET-01936_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01936_GCPR | 2025-12-08 | Historical | 2026_ET-01936_ACQ | In Progress | 2026_ET-01936_FR |  | Not Started | 2026_ET-01936_RWR | Not Started |  | 2026_ET-01936_CLAZ |  | Not Started |  |  |  | 2026_ET-01936_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01936_WR |  |  | Not Started |  |  |  | 2026_ET-01936_VMLAZ |  | Not Started |  |  |  | 2026_ET-01936_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01936_RR |  | Not Started | [6 empty] | 2026_ET-01936_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BANDUCCI-KERN RIVER 1_ET-01936 | Done |  | No |  | Helicopter | TEHACHAPI | 52 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BOREL-ISABELLA | ET-01939 | 2026_ET-01939 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 4.486 | 4.486 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Flown | 2026-04-20 |  | 05-13-2026 |  | 2026_ET-01939_ACQPKG | 2026_ET-01939_GSPKG | Submitted | 2026_ET-01939_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01939_GCPR | 2025-12-08 | Historical | 2026_ET-01939_ACQ | QC Accepted | 2026_ET-01939_FR | 2026-05-08 | Submitted | 2026_ET-01939_RWR | Submitted | 2026-05-08 | 2026_ET-01939_CLAZ | 2026-05-08 | QC Accepted | 07-18-2026 | 2026-05-13 | 0 | 2026_ET-01939_PROCPKG | In Progress | SCE | 2026_ET-01939_WR |  |  | Not Started |  |  |  | 2026_ET-01939_VMLAZ |  | Not Started |  |  |  | 2026_ET-01939_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01939_RR |  | Not Started | [6 empty] | 2026_ET-01939_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BOREL-ISABELLA_ET-01939 | Done |  | No |  | Helicopter | KERNVILLE | 53 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ISABELLA-KERN RIVER 3-LAKEGEN-WELDON | ET-01941 | 2026_ET-01941 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 27.0953 | 27.0953 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Flown | 2026-04-20 |  | 05-13-2026 |  | 2026_ET-01941_ACQPKG | 2026_ET-01941_GSPKG | Submitted | 2026_ET-01941_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01941_GCPR | 2025-12-08 | Historical | 2026_ET-01941_ACQ | QC Accepted | 2026_ET-01941_FR | 2026-05-08 | Submitted | 2026_ET-01941_RWR | Submitted | 2026-05-08 | 2026_ET-01941_CLAZ | 2026-05-08 | QC Accepted | 07-18-2026 | 2026-05-13 | 0 | 2026_ET-01941_PROCPKG | In Progress | SCE | 2026_ET-01941_WR |  |  | Not Started |  |  |  | 2026_ET-01941_VMLAZ |  | Not Started |  |  |  | 2026_ET-01941_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01941_RR |  | Not Started | [6 empty] | 2026_ET-01941_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ISABELLA-KERN RIVER 3-LAKEGEN-WELDON_ET-01941 |  |  | No |  | Helicopter | KERNVILLE | 53 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CARNIVAL-PICO-STEVEDORE | ET-01954 | 2026_ET-01954 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.1991 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-01954_ACQPKG | 2026_ET-01954_GSPKG | Submitted | 2026_ET-01954_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01954_GCPR | 2025-12-08 | Historical | 2026_ET-01954_ACQ | In Progress | 2026_ET-01954_FR |  | Not Started | 2026_ET-01954_RWR | Not Started |  | 2026_ET-01954_CLAZ |  | Not Started |  |  |  | 2026_ET-01954_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01954_WR |  |  | Not Started |  |  |  | 2026_ET-01954_VMLAZ |  | Not Started |  |  |  | 2026_ET-01954_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01954_RR |  | Not Started | [6 empty] | 2026_ET-01954_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | CARNIVAL-PICO-STEVEDORE_ET-01954 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AQUA-PEAR BLOSSOM-VINCENT | ET-01963 | 2026_ET-01963 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 13.0077 | 9.4998 | 73 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-20 | 04-02-2026 | Flown | 2026-02-20 | 05-20-2026 | 04-16-2026 |  | 2026_ET-01963_ACQPKG | 2026_ET-01963_GSPKG | Submitted | 2026_ET-01963_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01963_GCPR | 2025-12-08 | Historical | 2026_ET-01963_ACQ | QC Accepted | 2026_ET-01963_FR | 2026-03-16 | Submitted | 2026_ET-01963_RWR | Submitted | 2026-03-16 | 2026_ET-01963_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-16 |  | 2026_ET-01963_PROCPKG | Submitted | All Good - Complete | 2026_ET-01963_WR | 2026-05-21 | 06-19-2026 | Ready for QC | 06-04-2026 |  |  | 2026_ET-01963_VMLAZ | 2026-04-30 | Ready for QC | 06-04-2026 |  |  | 2026_ET-01963_VMM1 | 2026-05-21 | Ready for QC |  | 06-04-2026 |  |  | 2026_ET-01963_RR | 2026-05-21 | No Violations | [6 empty] | 2026_ET-01963_VER | 2026-05-21 | Ready for QC | 06-04-2026 | [6 empty] | Projected Late | Completed On Time | Completed Late - Program | AQUA-PEAR BLOSSOM-VINCENT_ET-01963 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ETIWANDA-GRAPELAND-PIPE | ET-01965 | 2026_ET-01965 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.58934 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-07-2026 |  | 2026_ET-01965_ACQPKG | 2026_ET-01965_GSPKG | Submitted | 2026_ET-01965_GS | 2026-01-31 | Field Complete | 2026_ET-01965_GCPR | 2026-05-03 | Submitted | 2026_ET-01965_ACQ | QC Accepted | 2026_ET-01965_FR | 2026-05-03 | Submitted | 2026_ET-01965_RWR | Submitted | 2026-05-03 | 2026_ET-01965_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-01965_PROCPKG | In Progress | SCE | 2026_ET-01965_WR |  |  | In Progress |  |  |  | 2026_ET-01965_VMLAZ |  | In Progress |  |  |  | 2026_ET-01965_VMM1 |  | In Progress |  |  |  |  | 2026_ET-01965_RR |  | In Progress | [6 empty] | 2026_ET-01965_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ETIWANDA-GRAPELAND-PIPE_ET-01965 |  |  | No |  |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-RIO HONDO NO.2 | ET-01969 | 2026_ET-01969 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 11.0085 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-28 |  | 05-20-2026 |  | 2026_ET-01969_ACQPKG | 2026_ET-01969_GSPKG | Submitted | 2026_ET-01969_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01969_GCPR | 2025-12-08 | Historical | 2026_ET-01969_ACQ | QC Accepted | 2026_ET-01969_FR | 2026-05-03 | Submitted | 2026_ET-01969_RWR | Submitted | 2026-05-03 | 2026_ET-01969_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-01969_PROCPKG | In Progress | SCE | 2026_ET-01969_WR |  |  | Not Started |  |  |  | 2026_ET-01969_VMLAZ |  | Not Started |  |  |  | 2026_ET-01969_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01969_RR |  | Not Started | [6 empty] | 2026_ET-01969_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MESA-RIO HONDO NO.2_ET-01969 |  |  | Yes |  |  | MONTEBELLO | 22 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VESTAL-BROWNING-QUINN | ET-01990 | 2026_ET-01990 |  | 1 | 2026 | Jun 01, 2026 | 66 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-02-2026 | 02-01-2026 | On Time | 0 | Transmission | 18.0229 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-28 | 03-03-2026 | Flown | 2025-12-19 | 04-28-2026 | 04-09-2026 |  | 2026_ET-01990_ACQPKG | 2026_ET-01990_GSPKG | Submitted | 2026_ET-01990_GS | 2025-10-15 | Field Complete | 2026_ET-01990_GCPR | 2025-12-08 | Submitted | 2026_ET-01990_ACQ | QC Accepted | 2026_ET-01990_FR | 2026-01-13 | Submitted | 2026_ET-01990_RWR | Submitted | 2026-01-13 | 2026_ET-01990_CLAZ | 2026-03-18 | QC Accepted | 04-01-2026 | 2026-04-09 | 2 | 2026_ET-01990_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-01990_WR | 2026-04-27 | 05-28-2026 | QC Accepted | 05-11-2026 | 2026-04-30 |  | 2026_ET-01990_VMLAZ | 2026-04-27 | QC Accepted | 05-11-2026 | 2026-04-30 | 0 | 2026_ET-01990_VMM1 | 2026-04-27 | QC Accepted |  | 05-11-2026 | 2026-05-04 |  | 2026_ET-01990_RR | 2026-04-27 | No Violations | 05-05-2026 |  | 0 |  |  |  | 2026_ET-01990_VER | 2026-04-27 | Uploaded to S123 | 05-11-2026 | 2026-05-04 | [5 empty] | Completed Late - Program | Projected On Time | Completed Late - Program | VESTAL-BROWNING-QUINN_ET-01990 |  |  | No |  | Helicopter | TULARE | 51 | HC | 2025-12-19 09:56 PST ¦ 2025-12-19 10:26 PST | 121925 | 20251219 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CALECTRIC-HOMART-MENTONE | ET-01998 | 2026_ET-01998 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 16.0312 | 0.89511 | 6 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-24 | 04-02-2026 | Flown | 2026-01-31 | 04-24-2026 | 04-10-2026 |  | 2026_ET-01998_ACQPKG | 2026_ET-01998_GSPKG | Submitted | 2026_ET-01998_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01998_GCPR | 2025-12-08 | Historical | 2026_ET-01998_ACQ | QC Accepted | 2026_ET-01998_FR | 2026-04-02 | Submitted | 2026_ET-01998_RWR | Submitted | 2026-04-02 | 2026_ET-01998_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-10 | 0 | 2026_ET-01998_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-01998_WR | 2026-05-14 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01998_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01998_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 | 0 | 2026_ET-01998_RR | 2026-05-10 | Violations QC Confirmed | 05-21-2026 | 05-21-2026 | 2 | 2026-05-11 | 0 | 2 | 2026_ET-01998_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | 0 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed On Time - Program | CALECTRIC-HOMART-MENTONE_ET-01998 | Done |  | No |  |  | REDLANDS | 31 | UNK | 2026-01-31 09:18 PST ¦ 2026-03-18 12:09 PDT | 013126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-CALDEN-CUDAHY | ET-02002 | 2026_ET-02002 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 9.4336 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-01 | 04-20-2026 | 04-14-2026 |  | 2026_ET-02002_ACQPKG | 2026_ET-02002_GSPKG | Submitted | 2026_ET-02002_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02002_GCPR | 2025-12-08 | Historical | 2026_ET-02002_ACQ | QC Accepted | 2026_ET-02002_FR | 2026-04-02 | Submitted | 2026_ET-02002_RWR | Submitted | 2026-04-02 | 2026_ET-02002_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-02002_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02002_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02002_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02002_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-02002_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-02002_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-CALDEN-CUDAHY_ET-02002 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | 2026-03-01 09:04 PST ¦ 2026-03-01 10:24 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MIRA LOMA-CLEARGEN | ET-02006 | 2026_ET-02006 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 10.4624 | 1.5436 | 15 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 05-20-2026 |  | 2026_ET-02006_ACQPKG | 2026_ET-02006_GSPKG | Submitted | 2026_ET-02006_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02006_GCPR | 2025-12-08 | Historical | 2026_ET-02006_ACQ | QC Accepted | 2026_ET-02006_FR | 2026-05-03 | Submitted | 2026_ET-02006_RWR | Submitted | 2026-05-03 | 2026_ET-02006_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-02006_PROCPKG | In Progress | SCE | 2026_ET-02006_WR |  |  | Not Started |  |  |  | 2026_ET-02006_VMLAZ |  | Not Started |  |  |  | 2026_ET-02006_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02006_RR |  | Not Started | [6 empty] | 2026_ET-02006_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MIRA LOMA-CLEARGEN_ET-02006 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALAMITOS-UNIT 2 | ET-02009 | 2026_ET-02009 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.040055 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-07-2026 |  | 2026_ET-02009_ACQPKG | 2026_ET-02009_GSPKG | Submitted | 2026_ET-02009_GS | 2026-01-31 | Field Complete | 2026_ET-02009_GCPR | 2026-05-03 | Submitted | 2026_ET-02009_ACQ | QC Accepted | 2026_ET-02009_FR | 2026-05-03 | Submitted | 2026_ET-02009_RWR | Submitted | 2026-05-03 | 2026_ET-02009_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-02009_PROCPKG | In Progress | SCE | 2026_ET-02009_WR |  |  | In Progress |  |  |  | 2026_ET-02009_VMLAZ |  | In Progress |  |  |  | 2026_ET-02009_VMM1 |  | In Progress |  |  |  |  | 2026_ET-02009_RR |  | In Progress | [6 empty] | 2026_ET-02009_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ALAMITOS-UNIT 2_ET-02009 | Done |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE DEL AMO-CORNUTA | ET-02016 | 2026_ET-02016 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 0.96762 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-01 | 04-14-2026 | 04-14-2026 |  | 2026_ET-02016_ACQPKG | 2026_ET-02016_GSPKG | Submitted | 2026_ET-02016_GS | 2025-12-08 | Field Complete | 2026_ET-02016_GCPR | 2026-04-02 | Submitted | 2026_ET-02016_ACQ | QC Accepted | 2026_ET-02016_FR | 2026-04-02 | Submitted | 2026_ET-02016_RWR | Submitted | 2026-04-02 | 2026_ET-02016_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-02016_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02016_WR | 2026-05-10 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02016_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02016_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-02016_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-02016_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE DEL AMO-CORNUTA_ET-02016 |  |  | No |  |  | LONG BEACH | 46 | UNK | 2026-03-01 13:13 PST ¦ 2026-03-02 09:29 PST | 030226 | 20260302 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
INYOKERN-SEARLES | ET-02043 | 2026_ET-02043 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 28.7164 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02043_ACQPKG | 2026_ET-02043_GSPKG | Submitted | 2026_ET-02043_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02043_GCPR | 2025-12-08 | Historical | 2026_ET-02043_ACQ | In Progress | 2026_ET-02043_FR |  | Not Started | 2026_ET-02043_RWR | Not Started |  | 2026_ET-02043_CLAZ |  | Not Started |  |  |  | 2026_ET-02043_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02043_WR |  |  | Not Started |  |  |  | 2026_ET-02043_VMLAZ |  | Not Started |  |  |  | 2026_ET-02043_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02043_RR |  | Not Started | [6 empty] | 2026_ET-02043_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | INYOKERN-SEARLES_ET-02043 |  |  | No |  | Helicopter | RIDGECREST | 86 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DOWNS-SEARLES | ET-02044 | 2026_ET-02044 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 18.8549 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02044_ACQPKG | 2026_ET-02044_GSPKG | Submitted | 2026_ET-02044_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02044_GCPR | 2025-12-08 | Historical | 2026_ET-02044_ACQ | In Progress | 2026_ET-02044_FR |  | Not Started | 2026_ET-02044_RWR | Not Started |  | 2026_ET-02044_CLAZ |  | Not Started |  |  |  | 2026_ET-02044_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02044_WR |  |  | Not Started |  |  |  | 2026_ET-02044_VMLAZ |  | Not Started |  |  |  | 2026_ET-02044_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02044_RR |  | Not Started | [6 empty] | 2026_ET-02044_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | DOWNS-SEARLES_ET-02044 |  |  | No |  | Helicopter | RIDGECREST | 86 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEE VINING-POOLE | ET-02046 | 2026_ET-02046 |  | 1 | 2026 |  | 115 | CA_3 | 0 | [9 empty] | NaN | Transmission | 6.4032 | 6.4032 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repatitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | N/A | N/A | 55 |  | Vegetation Management |  | N/A | Not Started |  |  |  |  | Removed From Scope |  |  |  |  | 2026_ET-02046_ACQPKG | 2026_ET-02046_GSPKG | Submitted | 2026_ET-02046_GS | 2023-12-12 | Field Complete | 2026_ET-02046_GCPR | 2025-12-08 | Submitted | 2026_ET-02046_ACQ | In Progress | 2026_ET-02046_FR |  | N/A | 2026_ET-02046_RWR | N/A |  | 2026_ET-02046_CLAZ |  | N/A |  |  |  | 2026_ET-02046_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02046_WR |  |  | N/A |  |  |  | 2026_ET-02046_VMLAZ |  | N/A |  |  |  | 2026_ET-02046_VMM1 |  | N/A |  |  |  |  | 2026_ET-02046_RR |  | N/A | [6 empty] | 2026_ET-02046_VER |  | N/A | [7 empty] | TBD - Pending Completion of ACQ Deliverables |  |  | LEE VINING-POOLE_ET-02046 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LEE VINING-RUSH CREEK | ET-02047 | 2026_ET-02047 |  | 1 | 2026 |  | 115 | CA_3 | 0 | [9 empty] | NaN | Transmission | 15.4333 | 14.8858 | 96 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | Delay | No Delay | Variable | N/A | Weather | N/A | weather | Repetitive bad weather for access to area. Wind, rain and snow delaying access to area. |  | N/A | N/A | 30 |  | Vegetation Management |  | N/A | Not Started |  |  |  |  | Removed From Scope |  |  |  |  | 2026_ET-02047_ACQPKG | 2026_ET-02047_GSPKG | Submitted | 2026_ET-02047_GS | 2023-12-12 | Field Complete | 2026_ET-02047_GCPR | 2025-12-08 | Submitted | 2026_ET-02047_ACQ | In Progress | 2026_ET-02047_FR |  | N/A | 2026_ET-02047_RWR | N/A |  | 2026_ET-02047_CLAZ |  | N/A |  |  |  | 2026_ET-02047_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02047_WR |  |  | N/A |  |  |  | 2026_ET-02047_VMLAZ |  | N/A |  |  |  | 2026_ET-02047_VMM1 |  | N/A |  |  |  |  | 2026_ET-02047_RR |  | N/A | [6 empty] | 2026_ET-02047_VER |  | N/A | [7 empty] | TBD - Pending Completion of ACQ Deliverables |  |  | LEE VINING-RUSH CREEK_ET-02047 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-ALISA-GONZALES | ET-02058 | 2026_ET-02058 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 8.965 | 1.9792 | 22 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02058_ACQPKG | 2026_ET-02058_GSPKG | Submitted | 2026_ET-02058_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02058_GCPR | 2025-12-08 | Historical | 2026_ET-02058_ACQ | In Progress | 2026_ET-02058_FR |  | Not Started | 2026_ET-02058_RWR | Not Started |  | 2026_ET-02058_CLAZ |  | Not Started |  |  |  | 2026_ET-02058_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02058_WR |  |  | Not Started |  |  |  | 2026_ET-02058_VMLAZ |  | Not Started |  |  |  | 2026_ET-02058_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02058_RR |  | Not Started | [6 empty] | 2026_ET-02058_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-ALISA-GONZALES_ET-02058 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BARRE-GILBERT | ET-02060 | 2026_ET-02060 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.45107 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-02 | 05-11-2026 | 05-11-2026 |  | 2026_ET-02060_ACQPKG | 2026_ET-02060_GSPKG | Submitted | 2026_ET-02060_GS | 2026-01-31 | Field Complete | 2026_ET-02060_GCPR | 2026-05-03 | Submitted | 2026_ET-02060_ACQ | QC Accepted | 2026_ET-02060_FR | 2026-05-03 | Submitted | 2026_ET-02060_RWR | Submitted | 2026-05-03 | 2026_ET-02060_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-02060_PROCPKG | In Progress | All Good - Complete | 2026_ET-02060_WR |  | 06-10-2026 | In Progress |  |  |  | 2026_ET-02060_VMLAZ |  | In Progress |  |  |  | 2026_ET-02060_VMM1 |  | In Progress |  |  |  |  | 2026_ET-02060_RR |  | In Progress | [6 empty] | 2026_ET-02060_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE BARRE-GILBERT_ET-02060 |  |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEVERS-HI DESERT-YUCCA | ET-02068 | 2026_ET-02068 |  | 1 | 2026 | Aug 01, 2026 | 115 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 38.3631 | 18.3743 | 48 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 05-05-2026 |  | 2026_ET-02068_ACQPKG | 2026_ET-02068_GSPKG | Submitted | 2026_ET-02068_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02068_GCPR | 2025-12-08 | Historical | 2026_ET-02068_ACQ | QC Accepted | 2026_ET-02068_FR | 2026-05-03 | Submitted | 2026_ET-02068_RWR | Submitted | 2026-05-03 | 2026_ET-02068_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-05 |  | 2026_ET-02068_PROCPKG | In Progress | SCE | 2026_ET-02068_WR |  |  | In Progress |  |  |  | 2026_ET-02068_VMLAZ |  | In Progress |  |  |  | 2026_ET-02068_VMM1 |  | In Progress |  |  |  |  | 2026_ET-02068_RR |  | In Progress | [6 empty] | 2026_ET-02068_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEVERS-HI DESERT-YUCCA_ET-02068 |  |  | No |  |  | YUCCA VALLEY | 84 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SALLY-WAKEFIELD | ET-02074 | 2026_ET-02074 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 0.02451 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-02074_ACQPKG | 2026_ET-02074_GSPKG | Submitted | 2026_ET-02074_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02074_GCPR | 2025-12-08 | Historical | 2026_ET-02074_ACQ | In Progress | 2026_ET-02074_FR |  | Not Started | 2026_ET-02074_RWR | Not Started |  | 2026_ET-02074_CLAZ |  | Not Started |  |  |  | 2026_ET-02074_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02074_WR |  |  | Not Started |  |  |  | 2026_ET-02074_VMLAZ |  | Not Started |  |  |  | 2026_ET-02074_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02074_RR |  | Not Started | [6 empty] | 2026_ET-02074_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SALLY-WAKEFIELD_ET-02074 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ALISA-MANITEE | ET-02076 | 2026_ET-02076 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.018009 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-03-15 |  |  |  | 2026_ET-02076_ACQPKG | 2026_ET-02076_GSPKG | Submitted | 2026_ET-02076_GS | 2025-12-08 | Field Complete | 2026_ET-02076_GCPR | 2026-05-22 | Submitted | 2026_ET-02076_ACQ | Submitted | 2026_ET-02076_FR | 2026-05-22 | Submitted | 2026_ET-02076_RWR | Submitted | 2026-05-22 | 2026_ET-02076_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-02076_PROCPKG | In Progress | SCE | 2026_ET-02076_WR |  |  | Not Started |  |  |  | 2026_ET-02076_VMLAZ |  | Not Started |  |  |  | 2026_ET-02076_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02076_RR |  | Not Started | [6 empty] | 2026_ET-02076_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ALISA-MANITEE_ET-02076 | Done |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-RANDOLPH NO.6 | ET-02084 | 2026_ET-02084 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 0.84753 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02084_ACQPKG | 2026_ET-02084_GSPKG | Submitted | 2026_ET-02084_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02084_GCPR | 2025-12-08 | Historical | 2026_ET-02084_ACQ | In Progress | 2026_ET-02084_FR |  | Not Started | 2026_ET-02084_RWR | Not Started |  | 2026_ET-02084_CLAZ |  | Not Started |  |  |  | 2026_ET-02084_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02084_WR |  |  | Not Started |  |  |  | 2026_ET-02084_VMLAZ |  | Not Started |  |  |  | 2026_ET-02084_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02084_RR |  | Not Started | [6 empty] | 2026_ET-02084_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE LAGUNA BELL-RANDOLPH NO.6_ET-02084 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-AREA | ET-02087 | 2026_ET-02087 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.44376 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02087_ACQPKG | 2026_ET-02087_GSPKG | Submitted | 2026_ET-02087_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02087_GCPR | 2025-12-08 | Historical | 2026_ET-02087_ACQ | In Progress | 2026_ET-02087_FR |  | Not Started | 2026_ET-02087_RWR | Not Started |  | 2026_ET-02087_CLAZ |  | Not Started |  |  |  | 2026_ET-02087_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02087_WR |  |  | Not Started |  |  |  | 2026_ET-02087_VMLAZ |  | Not Started |  |  |  | 2026_ET-02087_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02087_RR |  | Not Started | [6 empty] | 2026_ET-02087_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE LAGUNA BELL-AREA_ET-02087 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE RECTOR-OAKGROVE (SECTION 1) | ET-02090 | 2026_ET-02090 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.13735 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02090_ACQPKG | 2026_ET-02090_GSPKG | Submitted | 2026_ET-02090_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02090_GCPR | 2025-12-08 | Historical | 2026_ET-02090_ACQ | In Progress | 2026_ET-02090_FR |  | Not Started | 2026_ET-02090_RWR | Not Started |  | 2026_ET-02090_CLAZ |  | Not Started |  |  |  | 2026_ET-02090_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02090_WR |  |  | Not Started |  |  |  | 2026_ET-02090_VMLAZ |  | Not Started |  |  |  | 2026_ET-02090_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02090_RR |  | Not Started | [6 empty] | 2026_ET-02090_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE RECTOR-OAKGROVE (SECTION 1)_ET-02090 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OLINDA-PARKWOOD | ET-02092 | 2026_ET-02092 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_6 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 5.4171 | 0.53939 | 10 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-02092_ACQPKG | 2026_ET-02092_GSPKG | Submitted | 2026_ET-02092_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02092_GCPR | 2025-12-08 | Historical | 2026_ET-02092_ACQ | In Progress | 2026_ET-02092_FR |  | Not Started | 2026_ET-02092_RWR | Not Started |  | 2026_ET-02092_CLAZ |  | Not Started |  |  |  | 2026_ET-02092_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02092_WR |  |  | Not Started |  |  |  | 2026_ET-02092_VMLAZ |  | Not Started |  |  |  | 2026_ET-02092_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02092_RR |  | Not Started | [6 empty] | 2026_ET-02092_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | OLINDA-PARKWOOD_ET-02092 |  |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-PLACENTIA | ET-02093 | 2026_ET-02093 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 11.747 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-03-03 | 04-29-2026 | 04-29-2026 |  | 2026_ET-02093_ACQPKG | 2026_ET-02093_GSPKG | Submitted | 2026_ET-02093_GS | 2025-12-08 | Field Complete | 2026_ET-02093_GCPR | 2026-04-02 | Submitted | 2026_ET-02093_ACQ | QC Accepted | 2026_ET-02093_FR | 2026-04-02 | Submitted | 2026_ET-02093_RWR | Submitted | 2026-04-29 | 2026_ET-02093_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-02093_PROCPKG | In Progress | All Good - Complete | 2026_ET-02093_WR | 2026-05-14 | 05-29-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02093_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-02093_VMM1 | 2026-05-10 | QC Rejected |  |  | 2026-05-21 | 1 | 2026_ET-02093_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-02093_VER | 2026-05-10 | Uploaded to S123 |  | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | VILLA PARK-PLACENTIA_ET-02093 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-02 13:30 PST ¦ 2026-03-03 10:14 PST | 020726 | 20260303 | [5 empty] | Subject conductors strung inaccurately. |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RED BLUFF-VICTORY PASS | ET-02105 | 2026_ET-02105 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.14443 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-21-2026 |  | 2026_ET-02105_ACQPKG | 2026_ET-02105_GSPKG | Submitted | 2026_ET-02105_GS | 2026-01-31 | Field Complete | 2026_ET-02105_GCPR | 2026-05-03 | Submitted | 2026_ET-02105_ACQ | QC Accepted | 2026_ET-02105_FR | 2026-05-03 | Submitted | 2026_ET-02105_RWR | Submitted | 2026-05-03 | 2026_ET-02105_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-21 |  | 2026_ET-02105_PROCPKG | In Progress | SCE | 2026_ET-02105_WR |  |  | Not Started |  |  |  | 2026_ET-02105_VMLAZ |  | Not Started |  |  |  | 2026_ET-02105_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02105_RR |  | Not Started | [6 empty] | 2026_ET-02105_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RED BLUFF-VICTORY PASS_ET-02105 |  |  | Yes |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BANNING-DYLAN-MARASCHINO | ET-02106 | 2026_ET-02106 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 8.5902 | 5.824 | 68 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-02106_ACQPKG | 2026_ET-02106_GSPKG | Submitted | 2026_ET-02106_GS | 2025-12-08 | Field Complete | 2026_ET-02106_GCPR | 2026-05-22 | Submitted | 2026_ET-02106_ACQ | Submitted | 2026_ET-02106_FR | 2026-05-22 | Submitted | 2026_ET-02106_RWR | Submitted | 2026-05-22 | 2026_ET-02106_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-02106_PROCPKG | In Progress | SCE | 2026_ET-02106_WR |  |  | Not Started |  |  |  | 2026_ET-02106_VMLAZ |  | Not Started |  |  |  | 2026_ET-02106_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02106_RR |  | Not Started | [6 empty] | 2026_ET-02106_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | BANNING-DYLAN-MARASCHINO_ET-02106 | Done |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE RECTOR-OAKGROVE (SECTION 2) | ET-02107 | 2026_ET-02107 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.82549 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02107_ACQPKG | 2026_ET-02107_GSPKG | Submitted | 2026_ET-02107_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02107_GCPR | 2025-12-08 | Historical | 2026_ET-02107_ACQ | In Progress | 2026_ET-02107_FR |  | Not Started | 2026_ET-02107_RWR | Not Started |  | 2026_ET-02107_CLAZ |  | Not Started |  |  |  | 2026_ET-02107_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02107_WR |  |  | Not Started |  |  |  | 2026_ET-02107_VMLAZ |  | Not Started |  |  |  | 2026_ET-02107_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02107_RR |  | Not Started | [6 empty] | 2026_ET-02107_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE RECTOR-OAKGROVE (SECTION 2)_ET-02107 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LA FRESA-INGLEWOOD NO.2 | ET-02118 | 2026_ET-02118 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.1772 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-06 | 05-15-2026 | 05-15-2026 |  | 2026_ET-02118_ACQPKG | 2026_ET-02118_GSPKG | Submitted | 2026_ET-02118_GS | 2026-01-31 | Field Complete | 2026_ET-02118_GCPR | 2026-05-03 | Submitted | 2026_ET-02118_ACQ | QC Accepted | 2026_ET-02118_FR | 2026-05-03 | Submitted | 2026_ET-02118_RWR | Submitted | 2026-05-03 | 2026_ET-02118_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-02118_PROCPKG | In Progress | All Good - Complete | 2026_ET-02118_WR |  | 06-14-2026 | In Progress |  |  |  | 2026_ET-02118_VMLAZ |  | In Progress |  |  |  | 2026_ET-02118_VMM1 |  | In Progress |  |  |  |  | 2026_ET-02118_RR |  | In Progress | [6 empty] | 2026_ET-02118_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE LA FRESA-INGLEWOOD NO.2_ET-02118 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTIAGO-CROWN | ET-02150 | 2026_ET-02150 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.3763 | 2.1683 | 64 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-15 | 04-02-2026 | Flown | 2026-02-06 | 04-15-2026 | 04-14-2026 |  | 2026_ET-02150_ACQPKG | 2026_ET-02150_GSPKG | Submitted | 2026_ET-02150_GS | 2025-12-08 | Field Complete | 2026_ET-02150_GCPR | 2026-04-02 | Submitted | 2026_ET-02150_ACQ | QC Accepted | 2026_ET-02150_FR | 2026-04-02 | Submitted | 2026_ET-02150_RWR | Submitted | 2026-04-02 | 2026_ET-02150_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-02150_PROCPKG | In Progress | All Good - Complete | 2026_ET-02150_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-02150_VMLAZ | 2026-05-10 | QC Accepted |  | 2026-05-20 |  | 2026_ET-02150_VMM1 | 2026-05-10 | QC Rejected |  |  | 2026-05-21 | 1 | 2026_ET-02150_RR | 2026-05-10 | No Violations |  |  | 0 |  |  |  | 2026_ET-02150_VER | 2026-05-10 | Uploaded to S123 |  | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTIAGO-CROWN_ET-02150 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | 2026-02-06 08:05 PST ¦ 2026-02-27 13:51 PST | 020626 | 20260227 | [5 empty] | Subject conductors strung incorrectly. |  | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SPRINGVILLE-TULE | ET-02158 | 2026_ET-02158 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 9.8777 | 9.8777 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02158_ACQPKG | 2026_ET-02158_GSPKG | Submitted | 2026_ET-02158_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02158_GCPR | 2025-12-08 | Historical | 2026_ET-02158_ACQ | In Progress | 2026_ET-02158_FR |  | Not Started | 2026_ET-02158_RWR | Not Started |  | 2026_ET-02158_CLAZ |  | Not Started |  |  |  | 2026_ET-02158_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02158_WR |  |  | Not Started |  |  |  | 2026_ET-02158_VMLAZ |  | Not Started |  |  |  | 2026_ET-02158_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02158_RR |  | Not Started | [6 empty] | 2026_ET-02158_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SPRINGVILLE-TULE_ET-02158 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE SAN BERNARDINO-REDLANDS-TENNESSEE | ET-02161 | 2026_ET-02161 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 1.7006 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02161_ACQPKG | 2026_ET-02161_GSPKG | In Progress | 2026_ET-02161_GS |  | Not Started | 2026_ET-02161_GCPR |  | Not Started | 2026_ET-02161_ACQ | In Progress | 2026_ET-02161_FR |  | Not Started | 2026_ET-02161_RWR | Not Started |  | 2026_ET-02161_CLAZ |  | Not Started |  |  |  | 2026_ET-02161_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02161_WR |  |  | Not Started |  |  |  | 2026_ET-02161_VMLAZ |  | Not Started |  |  |  | 2026_ET-02161_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02161_RR |  | Not Started | [6 empty] | 2026_ET-02161_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE SAN BERNARDINO-REDLANDS-TENNESSEE_ET-02161 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-BANDINI-VAIL | ET-02167 | 2026_ET-02167 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 4.6179 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02167_ACQPKG | 2026_ET-02167_GSPKG | Submitted | 2026_ET-02167_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02167_GCPR | 2025-12-08 | Historical | 2026_ET-02167_ACQ | In Progress | 2026_ET-02167_FR |  | Not Started | 2026_ET-02167_RWR | Not Started |  | 2026_ET-02167_CLAZ |  | Not Started |  |  |  | 2026_ET-02167_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02167_WR |  |  | Not Started |  |  |  | 2026_ET-02167_VMLAZ |  | Not Started |  |  |  | 2026_ET-02167_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02167_RR |  | Not Started | [6 empty] | 2026_ET-02167_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LAGUNA BELL-BANDINI-VAIL_ET-02167 |  |  | No |  | Helicopter | DOMINGUEZ HILLS | 32 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE RIO HONDO-AMADOR | ET-02176 | 2026_ET-02176 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 1.4606 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-15-2026 |  | 2026_ET-02176_ACQPKG | 2026_ET-02176_GSPKG | Submitted | 2026_ET-02176_GS | 2025-10-15 | Field Complete | 2026_ET-02176_GCPR | 2025-12-08 | Submitted | 2026_ET-02176_ACQ | QC Accepted | 2026_ET-02176_FR | 2026-05-08 | Submitted | 2026_ET-02176_RWR | Submitted | 2026-05-08 | 2026_ET-02176_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-02176_PROCPKG | In Progress | SCE | 2026_ET-02176_WR |  |  | Not Started |  |  |  | 2026_ET-02176_VMLAZ |  | Not Started |  |  |  | 2026_ET-02176_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02176_RR |  | Not Started | [6 empty] | 2026_ET-02176_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | IDLE RIO HONDO-AMADOR_ET-02176 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE CHINO-MIRA LOMA NO.1 | ET-02197 | 2026_ET-02197 |  | 1 | 2026 | Jul 01, 2026 | 220 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.0181 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_GSI_CWA_05_r0 | 2026-04-24 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-01-29 | 04-24-2026 | 04-14-2026 |  | 2026_ET-02197_ACQPKG | 2026_ET-02197_GSPKG | Submitted | 2026_ET-02197_GS | 2025-12-08 | Field Complete | 2026_ET-02197_GCPR | 2026-04-02 | Submitted | 2026_ET-02197_ACQ | QC Accepted | 2026_ET-02197_FR | 2026-04-02 | Submitted | 2026_ET-02197_RWR | Submitted | 2026-04-02 | 2026_ET-02197_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-02197_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-02197_WR | 2026-05-07 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-08 |  | 2026_ET-02197_VMLAZ | 2026-04-30 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-02197_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-08 |  | 2026_ET-02197_RR | 2026-05-07 | No Violations | 05-09-2026 | [5 empty] | 2026_ET-02197_VER | 2026-05-07 | Uploaded to S123 | 06-01-2026 | 2026-05-12 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE CHINO-MIRA LOMA NO.1_ET-02197 |  |  | No |  |  | ONTARIO | 34 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CORUM-GOLDTOWN | ET-02503 | 2026_ET-02503 |  | 1 | 2026 | May 01, 2026 | 66 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 12-02-2025 | 01-01-2026 | On Time | 0 | Transmission | 18.7664 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-21 | 01-31-2026 | Flown | 2026-01-31 | 05-21-2026 | 05-12-2026 |  | 2026_ET-02503_ACQPKG | 2026_ET-02503_GSPKG | Submitted | 2026_ET-02503_GS | 2026-01-23 | Field Complete | 2026_ET-02503_GCPR | 2026-01-30 | Submitted | 2026_ET-02503_ACQ | QC Accepted | 2026_ET-02503_FR |  | Not Started | 2026_ET-02503_RWR | Submitted | 2026-04-29 | 2026_ET-02503_CLAZ | 2026-05-18 | QC Accepted | 06-01-2026 | 2026-05-12 |  | 2026_ET-02503_PROCPKG | In Progress | All Good - Complete | 2026_ET-02503_WR |  | 06-20-2026 | Not Started |  |  |  | 2026_ET-02503_VMLAZ |  | Not Started |  |  |  | 2026_ET-02503_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02503_RR |  | Not Started | [6 empty] | 2026_ET-02503_VER |  | Not Started | [7 empty] | Projected Late | Projected On Time | Completed Late - Program | CORUM-GOLDTOWN_ET-02503 |  |  | No |  |  | TEHACHAPI | 52 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BAYSIDE-HAMILTON | ET-02716 | 2026_ET-02716 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 3.1714 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02716_ACQPKG | 2026_ET-02716_GSPKG | Submitted | 2026_ET-02716_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02716_GCPR | 2025-12-08 | Historical | 2026_ET-02716_ACQ | In Progress | 2026_ET-02716_FR |  | Not Started | 2026_ET-02716_RWR | Not Started |  | 2026_ET-02716_CLAZ |  | Not Started |  |  |  | 2026_ET-02716_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02716_WR |  |  | Not Started |  |  |  | 2026_ET-02716_VMLAZ |  | Not Started |  |  |  | 2026_ET-02716_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02716_RR |  | Not Started | [6 empty] | 2026_ET-02716_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BAYSIDE-HAMILTON_ET-02716 | Done |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HAMILTON-HUNTINGTON BEACH | ET-02731 | 2026_ET-02731 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_6 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 1.9732 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02731_ACQPKG | 2026_ET-02731_GSPKG | Submitted | 2026_ET-02731_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02731_GCPR | 2025-12-08 | Historical | 2026_ET-02731_ACQ | In Progress | 2026_ET-02731_FR |  | Not Started | 2026_ET-02731_RWR | Not Started |  | 2026_ET-02731_CLAZ |  | Not Started |  |  |  | 2026_ET-02731_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02731_WR |  |  | Not Started |  |  |  | 2026_ET-02731_VMLAZ |  | Not Started |  |  |  | 2026_ET-02731_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02731_RR |  | Not Started | [6 empty] | 2026_ET-02731_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | HAMILTON-HUNTINGTON BEACH_ET-02731 |  |  | No |  |  | HUNTINGTON BEACH | 33 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-COLTON NO. 1 | ET-02871 | 2026_ET-02871 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 1.5973 | 0.29926 | 19 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02871_ACQPKG | 2026_ET-02871_GSPKG | Submitted | 2026_ET-02871_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02871_GCPR | 2025-12-08 | Historical | 2026_ET-02871_ACQ | In Progress | 2026_ET-02871_FR |  | Not Started | 2026_ET-02871_RWR | Not Started |  | 2026_ET-02871_CLAZ |  | Not Started |  |  |  | 2026_ET-02871_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02871_WR |  |  | Not Started |  |  |  | 2026_ET-02871_VMLAZ |  | Not Started |  |  |  | 2026_ET-02871_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02871_RR |  | Not Started | [6 empty] | 2026_ET-02871_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-COLTON NO. 1_ET-02871 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-COLTON NO. 2 | ET-02872 | 2026_ET-02872 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 1.7004 | 0.29785 | 18 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02872_ACQPKG | 2026_ET-02872_GSPKG | Submitted | 2026_ET-02872_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02872_GCPR | 2025-12-08 | Historical | 2026_ET-02872_ACQ | In Progress | 2026_ET-02872_FR |  | Not Started | 2026_ET-02872_RWR | Not Started |  | 2026_ET-02872_CLAZ |  | Not Started |  |  |  | 2026_ET-02872_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02872_WR |  |  | Not Started |  |  |  | 2026_ET-02872_VMLAZ |  | Not Started |  |  |  | 2026_ET-02872_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02872_RR |  | Not Started | [6 empty] | 2026_ET-02872_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-COLTON NO. 2_ET-02872 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-COLTON NO. 3 | ET-02873 | 2026_ET-02873 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.8175 | 0.51609 | 18 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02873_ACQPKG | 2026_ET-02873_GSPKG | Submitted | 2026_ET-02873_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02873_GCPR | 2025-12-08 | Historical | 2026_ET-02873_ACQ | In Progress | 2026_ET-02873_FR |  | Not Started | 2026_ET-02873_RWR | Not Started |  | 2026_ET-02873_CLAZ |  | Not Started |  |  |  | 2026_ET-02873_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02873_WR |  |  | Not Started |  |  |  | 2026_ET-02873_VMLAZ |  | Not Started |  |  |  | 2026_ET-02873_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02873_RR |  | Not Started | [6 empty] | 2026_ET-02873_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-COLTON NO. 3_ET-02873 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VISTA-DEL ROSA | ET-02944 | 2026_ET-02944 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 3.2905 | 0.36631 | 11 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02944_ACQPKG | 2026_ET-02944_GSPKG | Submitted | 2026_ET-02944_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02944_GCPR | 2025-12-08 | Historical | 2026_ET-02944_ACQ | In Progress | 2026_ET-02944_FR |  | Not Started | 2026_ET-02944_RWR | Not Started |  | 2026_ET-02944_CLAZ |  | Not Started |  |  |  | 2026_ET-02944_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02944_WR |  |  | Not Started |  |  |  | 2026_ET-02944_VMLAZ |  | Not Started |  |  |  | 2026_ET-02944_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02944_RR |  | Not Started | [6 empty] | 2026_ET-02944_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE VISTA-DEL ROSA_ET-02944 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-HUNTER | ET-02945 | 2026_ET-02945 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.8684 | 1.3103 | 46 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-02945_ACQPKG | 2026_ET-02945_GSPKG | Submitted | 2026_ET-02945_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02945_GCPR | 2025-12-08 | Historical | 2026_ET-02945_ACQ | In Progress | 2026_ET-02945_FR |  | Not Started | 2026_ET-02945_RWR | Not Started |  | 2026_ET-02945_CLAZ |  | Not Started |  |  |  | 2026_ET-02945_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02945_WR |  |  | Not Started |  |  |  | 2026_ET-02945_VMLAZ |  | Not Started |  |  |  | 2026_ET-02945_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02945_RR |  | Not Started | [6 empty] | 2026_ET-02945_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-HUNTER_ET-02945 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-MT. VIEW | ET-02955 | 2026_ET-02955 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 3.9292 | 3.805 | 97 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-02955_ACQPKG | 2026_ET-02955_GSPKG | Submitted | 2026_ET-02955_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02955_GCPR | 2025-12-08 | Historical | 2026_ET-02955_ACQ | In Progress | 2026_ET-02955_FR |  | Not Started | 2026_ET-02955_RWR | Not Started |  | 2026_ET-02955_CLAZ |  | Not Started |  |  |  | 2026_ET-02955_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02955_WR |  |  | Not Started |  |  |  | 2026_ET-02955_VMLAZ |  | Not Started |  |  |  | 2026_ET-02955_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02955_RR |  | Not Started | [6 empty] | 2026_ET-02955_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-MT. VIEW_ET-02955 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VISTA-TIMOTEO-REDLANDS NO.2 | ET-02984 | 2026_ET-02984 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.59101 | 0.34221 | 58 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-02984_ACQPKG | 2026_ET-02984_GSPKG | Submitted | 2026_ET-02984_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-02984_GCPR | 2025-12-08 | Historical | 2026_ET-02984_ACQ | In Progress | 2026_ET-02984_FR |  | Not Started | 2026_ET-02984_RWR | Not Started |  | 2026_ET-02984_CLAZ |  | Not Started |  |  |  | 2026_ET-02984_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-02984_WR |  |  | Not Started |  |  |  | 2026_ET-02984_VMLAZ |  | Not Started |  |  |  | 2026_ET-02984_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02984_RR |  | Not Started | [6 empty] | 2026_ET-02984_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE VISTA-TIMOTEO-REDLANDS NO.2_ET-02984 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-RIVERSIDE NO. 1 | ET-03021 | 2026_ET-03021 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 3.7334 | 3.2051 | 86 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-03021_ACQPKG | 2026_ET-03021_GSPKG | Submitted | 2026_ET-03021_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-03021_GCPR | 2025-12-08 | Historical | 2026_ET-03021_ACQ | In Progress | 2026_ET-03021_FR |  | Not Started | 2026_ET-03021_RWR | Not Started |  | 2026_ET-03021_CLAZ |  | Not Started |  |  |  | 2026_ET-03021_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-03021_WR |  |  | Not Started |  |  |  | 2026_ET-03021_VMLAZ |  | Not Started |  |  |  | 2026_ET-03021_VMM1 |  | Not Started |  |  |  |  | 2026_ET-03021_RR |  | Not Started | [6 empty] | 2026_ET-03021_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-RIVERSIDE NO. 1_ET-03021 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-RIVERSIDE NO. 2 | ET-03022 | 2026_ET-03022 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 3.7335 | 3.2042 | 86 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-03022_ACQPKG | 2026_ET-03022_GSPKG | Submitted | 2026_ET-03022_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-03022_GCPR | 2025-12-08 | Historical | 2026_ET-03022_ACQ | In Progress | 2026_ET-03022_FR |  | Not Started | 2026_ET-03022_RWR | Not Started |  | 2026_ET-03022_CLAZ |  | Not Started |  |  |  | 2026_ET-03022_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-03022_WR |  |  | Not Started |  |  |  | 2026_ET-03022_VMLAZ |  | Not Started |  |  |  | 2026_ET-03022_VMM1 |  | Not Started |  |  |  |  | 2026_ET-03022_RR |  | Not Started | [6 empty] | 2026_ET-03022_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-RIVERSIDE NO. 2_ET-03022 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
AGUA MANZA-COLTON-DREWS | ET-03031 | 2026_ET-03031 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.017792 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-08-2026 |  | 2026_ET-03031_ACQPKG | 2026_ET-03031_GSPKG | Submitted | 2026_ET-03031_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-03031_GCPR | 2025-12-08 | Historical | 2026_ET-03031_ACQ | QC Accepted | 2026_ET-03031_FR | 2026-05-03 | Submitted | 2026_ET-03031_RWR | Submitted | 2026-05-03 | 2026_ET-03031_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-08 |  | 2026_ET-03031_PROCPKG | In Progress | SCE | 2026_ET-03031_WR |  |  | In Progress |  |  |  | 2026_ET-03031_VMLAZ |  | In Progress |  |  |  | 2026_ET-03031_VMM1 |  | In Progress |  |  |  |  | 2026_ET-03031_RR |  | In Progress | [6 empty] | 2026_ET-03031_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | AGUA MANZA-COLTON-DREWS_ET-03031 | Done |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-SEABRIGHT | ET-03180 | 2026_ET-03180 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.7468 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-05 |  | 05-07-2026 |  | 2026_ET-03180_ACQPKG | 2026_ET-03180_GSPKG | Submitted | 2026_ET-03180_GS | 2026-01-31 | Field Complete | 2026_ET-03180_GCPR | 2026-05-03 | Submitted | 2026_ET-03180_ACQ | QC Accepted | 2026_ET-03180_FR | 2026-05-03 | Submitted | 2026_ET-03180_RWR | Submitted | 2026-05-03 | 2026_ET-03180_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-03180_PROCPKG | In Progress | SCE | 2026_ET-03180_WR |  |  | In Progress |  |  |  | 2026_ET-03180_VMLAZ |  | In Progress |  |  |  | 2026_ET-03180_VMM1 |  | In Progress |  |  |  |  | 2026_ET-03180_RR |  | In Progress | [6 empty] | 2026_ET-03180_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | HINSON-SEABRIGHT_ET-03180 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HINSON-STATE STREET | ET-03184 | 2026_ET-03184 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.5463 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-05 |  | 05-11-2026 |  | 2026_ET-03184_ACQPKG | 2026_ET-03184_GSPKG | Submitted | 2026_ET-03184_GS | 2026-01-31 | Field Complete | 2026_ET-03184_GCPR | 2026-05-03 | Submitted | 2026_ET-03184_ACQ | QC Accepted | 2026_ET-03184_FR | 2026-05-03 | Submitted | 2026_ET-03184_RWR | Submitted | 2026-05-03 | 2026_ET-03184_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-03184_PROCPKG | In Progress | SCE | 2026_ET-03184_WR |  |  | In Progress |  |  |  | 2026_ET-03184_VMLAZ |  | In Progress |  |  |  | 2026_ET-03184_VMM1 |  | In Progress |  |  |  |  | 2026_ET-03184_RR |  | In Progress | [6 empty] | 2026_ET-03184_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | HINSON-STATE STREET_ET-03184 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE FULLERTON-KATELLA-MODULE | ET-03911 | 2026_ET-03911 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.99332 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-03911_ACQPKG | 2026_ET-03911_GSPKG | Submitted | 2026_ET-03911_GS | 2025-12-08 | Field Complete | 2026_ET-03911_GCPR | 2026-05-22 | Submitted | 2026_ET-03911_ACQ | Submitted | 2026_ET-03911_FR | 2026-05-22 | Submitted | 2026_ET-03911_RWR | Submitted | 2026-05-22 | 2026_ET-03911_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-03911_PROCPKG | In Progress | SCE | 2026_ET-03911_WR |  |  | Not Started |  |  |  | 2026_ET-03911_VMLAZ |  | Not Started |  |  |  | 2026_ET-03911_VMM1 |  | Not Started |  |  |  |  | 2026_ET-03911_RR |  | Not Started | [6 empty] | 2026_ET-03911_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE FULLERTON-KATELLA-MODULE_ET-03911 |  |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VESTAL-GLENNVILLE-GREENHORN-KERN RIVER 3 | ET-04107 | 2026_ET-04107 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 44.6936 | 35.267 | 79 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-04107_ACQPKG | 2026_ET-04107_GSPKG | Submitted | 2026_ET-04107_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04107_GCPR | 2025-12-08 | Historical | 2026_ET-04107_ACQ | In Progress | 2026_ET-04107_FR |  | Not Started | 2026_ET-04107_RWR | Not Started |  | 2026_ET-04107_CLAZ |  | Not Started |  |  |  | 2026_ET-04107_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04107_WR |  |  | Not Started |  |  |  | 2026_ET-04107_VMLAZ |  | Not Started |  |  |  | 2026_ET-04107_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04107_RR |  | Not Started | [6 empty] | 2026_ET-04107_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VESTAL-GLENNVILLE-GREENHORN-KERN RIVER 3_ET-04107 |  |  | No |  | Helicopter | KERNVILLE | 53 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KERN RIVER 3-KERNVILLE | ET-04204 | 2026_ET-04204 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 0.40049 | 0.40049 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Flown | 2026-04-20 |  | 05-11-2026 |  | 2026_ET-04204_ACQPKG | 2026_ET-04204_GSPKG | Submitted | 2026_ET-04204_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04204_GCPR | 2025-12-08 | Historical | 2026_ET-04204_ACQ | QC Accepted | 2026_ET-04204_FR | 2026-05-08 | Submitted | 2026_ET-04204_RWR | Submitted | 2026-05-08 | 2026_ET-04204_CLAZ | 2026-05-08 | QC Accepted | 07-18-2026 | 2026-05-11 | 0 | 2026_ET-04204_PROCPKG | In Progress | SCE | 2026_ET-04204_WR |  |  | Not Started |  |  |  | 2026_ET-04204_VMLAZ |  | Not Started |  |  |  | 2026_ET-04204_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04204_RR |  | Not Started | [6 empty] | 2026_ET-04204_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | KERN RIVER 3-KERNVILLE_ET-04204 |  |  | No |  | Helicopter | KERNVILLE | 53 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-BRIGHTON NO. 1 | ET-04242 | 2026_ET-04242 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.8031 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-06 |  | 05-06-2026 |  | 2026_ET-04242_ACQPKG | 2026_ET-04242_GSPKG | Submitted | 2026_ET-04242_GS | 2026-01-31 | Field Complete | 2026_ET-04242_GCPR | 2026-05-03 | Submitted | 2026_ET-04242_ACQ | QC Accepted | 2026_ET-04242_FR | 2026-05-03 | Submitted | 2026_ET-04242_RWR | Submitted | 2026-05-03 | 2026_ET-04242_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-04242_PROCPKG | In Progress | SCE | 2026_ET-04242_WR |  |  | In Progress |  |  |  | 2026_ET-04242_VMLAZ |  | In Progress |  |  |  | 2026_ET-04242_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04242_RR |  | In Progress | [6 empty] | 2026_ET-04242_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LA FRESA-BRIGHTON NO. 1_ET-04242 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-BRIGHTON NO. 2 | ET-04243 | 2026_ET-04243 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.7337 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-06 |  | 05-07-2026 |  | 2026_ET-04243_ACQPKG | 2026_ET-04243_GSPKG | Submitted | 2026_ET-04243_GS | 2026-01-31 | Field Complete | 2026_ET-04243_GCPR | 2026-05-03 | Submitted | 2026_ET-04243_ACQ | QC Accepted | 2026_ET-04243_FR | 2026-05-03 | Submitted | 2026_ET-04243_RWR | Submitted | 2026-05-03 | 2026_ET-04243_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-07 |  | 2026_ET-04243_PROCPKG | In Progress | SCE | 2026_ET-04243_WR |  |  | In Progress |  |  |  | 2026_ET-04243_VMLAZ |  | In Progress |  |  |  | 2026_ET-04243_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04243_RR |  | In Progress | [6 empty] | 2026_ET-04243_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LA FRESA-BRIGHTON NO. 2_ET-04243 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LA FRESA-CARBIDE | ET-04247 | 2026_ET-04247 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 1.2814 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-03-06 | 05-15-2026 | 05-15-2026 |  | 2026_ET-04247_ACQPKG | 2026_ET-04247_GSPKG | Submitted | 2026_ET-04247_GS | 2026-01-31 | Field Complete | 2026_ET-04247_GCPR | 2026-05-03 | Submitted | 2026_ET-04247_ACQ | QC Accepted | 2026_ET-04247_FR | 2026-05-03 | Submitted | 2026_ET-04247_RWR | Submitted | 2026-05-03 | 2026_ET-04247_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-04247_PROCPKG | In Progress | All Good - Complete | 2026_ET-04247_WR |  | 06-14-2026 | In Progress |  |  |  | 2026_ET-04247_VMLAZ |  | In Progress |  |  |  | 2026_ET-04247_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04247_RR |  | In Progress | [6 empty] | 2026_ET-04247_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | IDLE LA FRESA-CARBIDE_ET-04247 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-MOBILOIL NO. 1 | ET-04272 | 2026_ET-04272 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.77724 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-06 |  | 05-11-2026 |  | 2026_ET-04272_ACQPKG | 2026_ET-04272_GSPKG | Submitted | 2026_ET-04272_GS | 2026-01-31 | Field Complete | 2026_ET-04272_GCPR | 2026-05-03 | Submitted | 2026_ET-04272_ACQ | QC Accepted | 2026_ET-04272_FR | 2026-05-03 | Submitted | 2026_ET-04272_RWR | Submitted | 2026-05-03 | 2026_ET-04272_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-04272_PROCPKG | In Progress | SCE | 2026_ET-04272_WR |  |  | In Progress |  |  |  | 2026_ET-04272_VMLAZ |  | In Progress |  |  |  | 2026_ET-04272_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04272_RR |  | In Progress | [6 empty] | 2026_ET-04272_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LA FRESA-MOBILOIL NO. 1_ET-04272 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-MOBILOIL NO. 2 | ET-04273 | 2026_ET-04273 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.77092 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-06 |  | 05-11-2026 |  | 2026_ET-04273_ACQPKG | 2026_ET-04273_GSPKG | Submitted | 2026_ET-04273_GS | 2026-01-31 | Field Complete | 2026_ET-04273_GCPR | 2026-05-03 | Submitted | 2026_ET-04273_ACQ | QC Accepted | 2026_ET-04273_FR | 2026-05-03 | Submitted | 2026_ET-04273_RWR | Submitted | 2026-05-03 | 2026_ET-04273_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-04273_PROCPKG | In Progress | SCE | 2026_ET-04273_WR |  |  | In Progress |  |  |  | 2026_ET-04273_VMLAZ |  | In Progress |  |  |  | 2026_ET-04273_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04273_RR |  | In Progress | [6 empty] | 2026_ET-04273_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LA FRESA-MOBILOIL NO. 2_ET-04273 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE LAGUNA BELL-P.S.33 | ET-04333 | 2026_ET-04333 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.3358 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-03-01 | 04-14-2026 | 04-14-2026 |  | 2026_ET-04333_ACQPKG | 2026_ET-04333_GSPKG | Submitted | 2026_ET-04333_GS | 2025-12-08 | Field Complete | 2026_ET-04333_GCPR | 2026-04-02 | Submitted | 2026_ET-04333_ACQ | QC Accepted | 2026_ET-04333_FR | 2026-04-02 | Submitted | 2026_ET-04333_RWR | Submitted | 2026-04-02 | 2026_ET-04333_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-04333_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04333_WR | 2026-05-14 | 05-14-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04333_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04333_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04333_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-04333_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE LAGUNA BELL-P.S.33_ET-04333 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | 2026-03-01 09:20 PST ¦ 2026-03-18 10:07 PDT | 031826 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-CUDAHY | ET-04339 | 2026_ET-04339 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.9994 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-19 | 04-02-2026 | Flown | 2026-03-01 | 04-19-2026 | 04-14-2026 |  | 2026_ET-04339_ACQPKG | 2026_ET-04339_GSPKG | Submitted | 2026_ET-04339_GS | 2025-12-08 | Field Complete | 2026_ET-04339_GCPR | 2026-04-02 | Submitted | 2026_ET-04339_ACQ | QC Accepted | 2026_ET-04339_FR | 2026-04-02 | Submitted | 2026_ET-04339_RWR | Submitted | 2026-04-02 | 2026_ET-04339_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-04339_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04339_WR | 2026-05-14 | 05-19-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04339_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04339_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04339_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 1 | 2026-05-14 |  | 0 | 2026_ET-04339_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LAGUNA BELL-CUDAHY_ET-04339 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | 2026-03-01 09:04 PST ¦ 2026-03-18 10:03 PDT | 030126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-RANDOLPH NO. 1 | ET-04364 | 2026_ET-04364 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.9625 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-14-2026 |  | 2026_ET-04364_ACQPKG | 2026_ET-04364_GSPKG | Submitted | 2026_ET-04364_GS | 2026-01-31 | Field Complete | 2026_ET-04364_GCPR | 2026-05-03 | Submitted | 2026_ET-04364_ACQ | QC Accepted | 2026_ET-04364_FR | 2026-05-03 | Submitted | 2026_ET-04364_RWR | Submitted | 2026-05-03 | 2026_ET-04364_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-14 | 0 | 2026_ET-04364_PROCPKG | In Progress | SCE | 2026_ET-04364_WR |  |  | In Progress |  |  |  | 2026_ET-04364_VMLAZ |  | In Progress |  |  |  | 2026_ET-04364_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04364_RR |  | In Progress | [6 empty] | 2026_ET-04364_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LAGUNA BELL-RANDOLPH NO. 1_ET-04364 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-RANDOLPH NO. 4 | ET-04366 | 2026_ET-04366 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.4582 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-14-2026 |  | 2026_ET-04366_ACQPKG | 2026_ET-04366_GSPKG | Submitted | 2026_ET-04366_GS | 2026-01-31 | Field Complete | 2026_ET-04366_GCPR | 2026-05-03 | Submitted | 2026_ET-04366_ACQ | QC Accepted | 2026_ET-04366_FR | 2026-05-03 | Submitted | 2026_ET-04366_RWR | Submitted | 2026-05-03 | 2026_ET-04366_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-14 | 0 | 2026_ET-04366_PROCPKG | In Progress | SCE | 2026_ET-04366_WR |  |  | In Progress |  |  |  | 2026_ET-04366_VMLAZ |  | In Progress |  |  |  | 2026_ET-04366_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04366_RR |  | In Progress | [6 empty] | 2026_ET-04366_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LAGUNA BELL-RANDOLPH NO. 4_ET-04366 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LA FRESA-REDONDO | ET-04392 | 2026_ET-04392 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.57 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-06 |  | 05-11-2026 |  | 2026_ET-04392_ACQPKG | 2026_ET-04392_GSPKG | Submitted | 2026_ET-04392_GS | 2026-01-31 | Field Complete | 2026_ET-04392_GCPR | 2026-05-03 | Submitted | 2026_ET-04392_ACQ | QC Accepted | 2026_ET-04392_FR | 2026-05-03 | Submitted | 2026_ET-04392_RWR | Submitted | 2026-05-03 | 2026_ET-04392_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-04392_PROCPKG | In Progress | SCE | 2026_ET-04392_WR |  |  | In Progress |  |  |  | 2026_ET-04392_VMLAZ |  | In Progress |  |  |  | 2026_ET-04392_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04392_RR |  | In Progress | [6 empty] | 2026_ET-04392_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LA FRESA-REDONDO_ET-04392 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
DEL SUR-LANCASTER-RITEAID | ET-04424 | 2026_ET-04424 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 9.5077 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-17 |  | 05-15-2026 |  | 2026_ET-04424_ACQPKG | 2026_ET-04424_GSPKG | Submitted | 2026_ET-04424_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04424_GCPR | 2025-12-08 | Historical | 2026_ET-04424_ACQ | QC Accepted | 2026_ET-04424_FR | 2026-05-08 | Submitted | 2026_ET-04424_RWR | Submitted | 2026-05-08 | 2026_ET-04424_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-04424_PROCPKG | In Progress | SCE | 2026_ET-04424_WR |  |  | Not Started |  |  |  | 2026_ET-04424_VMLAZ |  | Not Started |  |  |  | 2026_ET-04424_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04424_RR |  | Not Started | [6 empty] | 2026_ET-04424_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | DEL SUR-LANCASTER-RITEAID_ET-04424 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LANCASTER-PURIFY-REDMAN | ET-04436 | 2026_ET-04436 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 16.9288 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 04-17-2026 |  | 2026_ET-04436_ACQPKG | 2026_ET-04436_GSPKG | Submitted | 2026_ET-04436_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04436_GCPR | 2025-12-08 | Historical | 2026_ET-04436_ACQ | QC Accepted | 2026_ET-04436_FR | 2026-03-16 | Submitted | 2026_ET-04436_RWR | Submitted | 2026-03-16 | 2026_ET-04436_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04436_PROCPKG | In Progress | SCE | 2026_ET-04436_WR |  |  | In Progress |  |  |  | 2026_ET-04436_VMLAZ |  | In Progress |  |  |  | 2026_ET-04436_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04436_RR |  | In Progress | [6 empty] | 2026_ET-04436_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LANCASTER-PURIFY-REDMAN_ET-04436 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 10:19 PST ¦ 2026-02-20 10:48 PST | 022026 | 20260220 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
FULLERTON-LA PALMA | ET-04440 | 2026_ET-04440 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.2219 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-06-2026 |  | 2026_ET-04440_ACQPKG | 2026_ET-04440_GSPKG | Submitted | 2026_ET-04440_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04440_GCPR | 2025-12-08 | Historical | 2026_ET-04440_ACQ | QC Accepted | 2026_ET-04440_FR | 2026-05-03 | Submitted | 2026_ET-04440_RWR | Submitted | 2026-05-03 | 2026_ET-04440_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-04440_PROCPKG | In Progress | SCE | 2026_ET-04440_WR |  |  | In Progress |  |  |  | 2026_ET-04440_VMLAZ |  | In Progress |  |  |  | 2026_ET-04440_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04440_RR |  | In Progress | [6 empty] | 2026_ET-04440_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | FULLERTON-LA PALMA_ET-04440 |  |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-BULLIS-FERNWOOD | ET-04466 | 2026_ET-04466 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 6.6592 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-18 | 04-02-2026 | Flown | 2026-03-01 | 04-18-2026 | 04-14-2026 |  | 2026_ET-04466_ACQPKG | 2026_ET-04466_GSPKG | Submitted | 2026_ET-04466_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04466_GCPR | 2025-12-08 | Historical | 2026_ET-04466_ACQ | QC Accepted | 2026_ET-04466_FR | 2026-04-02 | Submitted | 2026_ET-04466_RWR | Submitted | 2026-04-02 | 2026_ET-04466_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-04466_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04466_WR | 2026-05-10 | 05-18-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04466_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04466_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04466_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-04466_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | LIGHTHIPE-BULLIS-FERNWOOD_ET-04466 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | 2026-03-01 10:26 PST ¦ 2026-03-01 12:20 PST | 030126 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-BULLIS | ET-04467 | 2026_ET-04467 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.2886 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-15-2026 |  | 2026_ET-04467_ACQPKG | 2026_ET-04467_GSPKG | Submitted | 2026_ET-04467_GS | 2026-01-31 | Field Complete | 2026_ET-04467_GCPR | 2026-05-03 | Submitted | 2026_ET-04467_ACQ | QC Accepted | 2026_ET-04467_FR | 2026-05-03 | Submitted | 2026_ET-04467_RWR | Submitted | 2026-05-03 | 2026_ET-04467_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-04467_PROCPKG | In Progress | SCE | 2026_ET-04467_WR |  |  | In Progress |  |  |  | 2026_ET-04467_VMLAZ |  | In Progress |  |  |  | 2026_ET-04467_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04467_RR |  | In Progress | [6 empty] | 2026_ET-04467_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIGHTHIPE-BULLIS_ET-04467 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-FREMONT | ET-04480 | 2026_ET-04480 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 6.3276 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-15-2026 |  | 2026_ET-04480_ACQPKG | 2026_ET-04480_GSPKG | Submitted | 2026_ET-04480_GS | 2026-01-31 | Field Complete | 2026_ET-04480_GCPR | 2026-05-03 | Submitted | 2026_ET-04480_ACQ | QC Accepted | 2026_ET-04480_FR | 2026-05-03 | Submitted | 2026_ET-04480_RWR | Submitted | 2026-05-03 | 2026_ET-04480_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-04480_PROCPKG | In Progress | SCE | 2026_ET-04480_WR |  |  | In Progress |  |  |  | 2026_ET-04480_VMLAZ |  | In Progress |  |  |  | 2026_ET-04480_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04480_RR |  | In Progress | [6 empty] | 2026_ET-04480_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIGHTHIPE-FREMONT_ET-04480 |  |  | No |  |  | DOMINGUEZ HILLS | 32 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-MESA NO.1 | ET-04488 | 2026_ET-04488 |  | 1 | 2026 | Sep 01, 2026 | 220 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 4.9065 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-04-18 |  | 05-15-2026 |  | 2026_ET-04488_ACQPKG | 2026_ET-04488_GSPKG | Submitted | 2026_ET-04488_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04488_GCPR | 2025-12-08 | Historical | 2026_ET-04488_ACQ | QC Accepted | 2026_ET-04488_FR | 2026-05-08 | Submitted | 2026_ET-04488_RWR | Submitted | 2026-05-08 | 2026_ET-04488_CLAZ | 2026-05-08 | QC Accepted | 06-18-2026 | 2026-05-15 |  | 2026_ET-04488_PROCPKG | In Progress | SCE | 2026_ET-04488_WR |  |  | Not Started |  |  |  | 2026_ET-04488_VMLAZ |  | Not Started |  |  |  | 2026_ET-04488_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04488_RR |  | Not Started | [6 empty] | 2026_ET-04488_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LAGUNA BELL-MESA NO.1_ET-04488 |  |  | Yes |  | Helicopter | DOMINGUEZ HILLS | 32 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAGUNA BELL-MESA NO.2 | ET-04489 | 2026_ET-04489 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.0595 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-04489_ACQPKG | 2026_ET-04489_GSPKG | Submitted | 2026_ET-04489_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04489_GCPR | 2025-12-08 | Historical | 2026_ET-04489_ACQ | QC Accepted | 2026_ET-04489_FR | 2026-03-16 | Submitted | 2026_ET-04489_RWR | Submitted | 2026-03-16 | 2026_ET-04489_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04489_PROCPKG | In Progress | SCE | 2026_ET-04489_WR |  |  | In Progress |  |  |  | 2026_ET-04489_VMLAZ |  | In Progress |  |  |  | 2026_ET-04489_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04489_RR |  | In Progress | [6 empty] | 2026_ET-04489_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LAGUNA BELL-MESA NO.2_ET-04489 |  |  | Yes |  | Helicopter | DOMINGUEZ HILLS | 32 | HC | 2026-02-22 10:46 PST ¦ 2026-02-22 11:09 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LIGHTHIPE-SIGNAL HILL | ET-04515 | 2026_ET-04515 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.7168 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-01 |  | 05-20-2026 |  | 2026_ET-04515_ACQPKG | 2026_ET-04515_GSPKG | Submitted | 2026_ET-04515_GS | 2026-01-31 | Field Complete | 2026_ET-04515_GCPR | 2026-05-03 | Submitted | 2026_ET-04515_ACQ | QC Accepted | 2026_ET-04515_FR | 2026-05-03 | Submitted | 2026_ET-04515_RWR | Submitted | 2026-05-03 | 2026_ET-04515_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-04515_PROCPKG | In Progress | SCE | 2026_ET-04515_WR |  |  | Not Started |  |  |  | 2026_ET-04515_VMLAZ |  | Not Started |  |  |  | 2026_ET-04515_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04515_RR |  | Not Started | [6 empty] | 2026_ET-04515_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | LIGHTHIPE-SIGNAL HILL_ET-04515 |  |  | No |  |  | LONG BEACH | 46 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
HYGEN-LINDE | ET-04549 | 2026_ET-04549 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 0.67931 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-15 |  | 05-11-2026 |  | 2026_ET-04549_ACQPKG | 2026_ET-04549_GSPKG | Submitted | 2026_ET-04549_GS | 2026-01-31 | Field Complete | 2026_ET-04549_GCPR | 2026-05-03 | Submitted | 2026_ET-04549_ACQ | QC Accepted | 2026_ET-04549_FR | 2026-05-03 | Submitted | 2026_ET-04549_RWR | Submitted | 2026-05-03 | 2026_ET-04549_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-11 | 0 | 2026_ET-04549_PROCPKG | In Progress | SCE | 2026_ET-04549_WR |  |  | In Progress |  |  |  | 2026_ET-04549_VMLAZ |  | In Progress |  |  |  | 2026_ET-04549_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04549_RR |  | In Progress | [6 empty] | 2026_ET-04549_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | HYGEN-LINDE_ET-04549 |  |  | No |  |  | FOOTHILL | 30 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLISS-LINDSAY | ET-04551 | 2026_ET-04551 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 10.7674 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-04551_ACQPKG | 2026_ET-04551_GSPKG | Submitted | 2026_ET-04551_GS | 2025-10-15 | Field Complete | 2026_ET-04551_GCPR | 2025-12-08 | Submitted | 2026_ET-04551_ACQ | In Progress | 2026_ET-04551_FR |  | Not Started | 2026_ET-04551_RWR | Not Started |  | 2026_ET-04551_CLAZ |  | Not Started |  |  |  | 2026_ET-04551_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04551_WR |  |  | Not Started |  |  |  | 2026_ET-04551_VMLAZ |  | Not Started |  |  |  | 2026_ET-04551_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04551_RR |  | Not Started | [6 empty] | 2026_ET-04551_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BLISS-LINDSAY_ET-04551 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE BEVERLY-MACNEIL-UNIVERSAL | ET-04635 | 2026_ET-04635 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 0.49139 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-04635_ACQPKG | 2026_ET-04635_GSPKG | Submitted | 2026_ET-04635_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04635_GCPR | 2025-12-08 | Historical | 2026_ET-04635_ACQ | In Progress | 2026_ET-04635_FR |  | Not Started | 2026_ET-04635_RWR | Not Started |  | 2026_ET-04635_CLAZ |  | Not Started |  |  |  | 2026_ET-04635_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04635_WR |  |  | Not Started |  |  |  | 2026_ET-04635_VMLAZ |  | Not Started |  |  |  | 2026_ET-04635_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04635_RR |  | Not Started | [6 empty] | 2026_ET-04635_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE BEVERLY-MACNEIL-UNIVERSAL_ET-04635 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BEVERLY-MACNEIL | ET-04637 | 2026_ET-04637 |  | 1 | 2026 | Oct 01, 2026 | 66 | CA_5 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 7.4133 | 3.5149 | 47 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Not Started |  |  |  |  | 2026_ET-04637_ACQPKG | 2026_ET-04637_GSPKG | Submitted | 2026_ET-04637_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04637_GCPR | 2025-12-08 | Historical | 2026_ET-04637_ACQ | In Progress | 2026_ET-04637_FR |  | Not Started | 2026_ET-04637_RWR | Not Started |  | 2026_ET-04637_CLAZ |  | Not Started |  |  |  | 2026_ET-04637_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04637_WR |  |  | Not Started |  |  |  | 2026_ET-04637_VMLAZ |  | Not Started |  |  |  | 2026_ET-04637_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04637_RR |  | Not Started | [6 empty] | 2026_ET-04637_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BEVERLY-MACNEIL_ET-04637 |  |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-MAGUNDEN NO.1 | ET-04676 | 2026_ET-04676 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 59.3873 | 28.8957 | 49 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-25 | 05-07-2026 | 04-16-2026 |  | 2026_ET-04676_ACQPKG | 2026_ET-04676_GSPKG | Submitted | 2026_ET-04676_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04676_GCPR | 2025-12-08 | Historical | 2026_ET-04676_ACQ | QC Accepted | 2026_ET-04676_FR | 2026-03-16 | Submitted | 2026_ET-04676_RWR | Submitted | 2026-03-16 | 2026_ET-04676_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-16 |  | 2026_ET-04676_PROCPKG | In Progress | All Good - Complete | 2026_ET-04676_WR |  | 06-06-2026 | In Progress |  |  |  | 2026_ET-04676_VMLAZ |  | In Progress |  |  |  | 2026_ET-04676_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04676_RR |  | In Progress | [6 empty] | 2026_ET-04676_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ANTELOPE-MAGUNDEN NO.1_ET-04676 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-23 13:37 PST ¦ 2026-02-25 09:40 PST | 022526 | 20260225 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ANTELOPE-MAGUNDEN NO.2 | ET-04677 | 2026_ET-04677 |  | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 59.4418 | 28.8969 | 49 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-05-07 | 05-03-2026 | Flown | 2026-02-25 | 05-07-2026 | 04-16-2026 |  | 2026_ET-04677_ACQPKG | 2026_ET-04677_GSPKG | Submitted | 2026_ET-04677_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04677_GCPR | 2025-12-08 | Historical | 2026_ET-04677_ACQ | QC Accepted | 2026_ET-04677_FR | 2026-03-16 | Submitted | 2026_ET-04677_RWR | Submitted | 2026-03-16 | 2026_ET-04677_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-16 |  | 2026_ET-04677_PROCPKG | In Progress | All Good - Complete | 2026_ET-04677_WR |  | 06-06-2026 | In Progress |  |  |  | 2026_ET-04677_VMLAZ |  | In Progress |  |  |  | 2026_ET-04677_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04677_RR |  | In Progress | [6 empty] | 2026_ET-04677_VER |  | In Progress | [7 empty] | Projected On Time | Completed On Time | Completed On Time - Program | ANTELOPE-MAGUNDEN NO.2_ET-04677 | Done |  | Yes |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-23 13:37 PST ¦ 2026-02-25 09:42 PST | 022526 | 20260225 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-NARROWS | ET-04863 | 2026_ET-04863 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 8.4996 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | No Load | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-02-28 | 04-20-2026 | 04-14-2026 |  | 2026_ET-04863_ACQPKG | 2026_ET-04863_GSPKG | Submitted | 2026_ET-04863_GS | 2025-12-08 | Field Complete | 2026_ET-04863_GCPR | 2026-04-02 | Submitted | 2026_ET-04863_ACQ | QC Accepted | 2026_ET-04863_FR | 2026-04-02 | Submitted | 2026_ET-04863_RWR | Submitted | 2026-04-02 | 2026_ET-04863_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-04863_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04863_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04863_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04863_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04863_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-04863_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | MESA-NARROWS_ET-04863 |  |  | No |  |  | MONTEBELLO | 22 | UNK | 2026-02-28 12:43 PST ¦ 2026-02-28 13:26 PST | 022826 | 20260228 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE MANDALAY-SANTA CLARA NO. 1 | ET-04896 | 2026_ET-04896 |  | 1 | 2026 | Nov 01, 2026 | 220 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.9902 | 2.346 | 26 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-04896_ACQPKG | 2026_ET-04896_GSPKG | Submitted | 2026_ET-04896_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04896_GCPR | 2025-12-08 | Historical | 2026_ET-04896_ACQ | In Progress | 2026_ET-04896_FR |  | Not Started | 2026_ET-04896_RWR | Not Started |  | 2026_ET-04896_CLAZ |  | Not Started |  |  |  | 2026_ET-04896_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04896_WR |  |  | Not Started |  |  |  | 2026_ET-04896_VMLAZ |  | Not Started |  |  |  | 2026_ET-04896_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04896_RR |  | Not Started | [6 empty] | 2026_ET-04896_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE MANDALAY-SANTA CLARA NO. 1_ET-04896 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE MANDALAY-SANTA CLARA NO. 2 | ET-04897 | 2026_ET-04897 |  | 1 | 2026 | Nov 01, 2026 | 220 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 8.8057 | 2.3515 | 27 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-04897_ACQPKG | 2026_ET-04897_GSPKG | Submitted | 2026_ET-04897_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04897_GCPR | 2025-12-08 | Historical | 2026_ET-04897_ACQ | In Progress | 2026_ET-04897_FR |  | Not Started | 2026_ET-04897_RWR | Not Started |  | 2026_ET-04897_CLAZ |  | Not Started |  |  |  | 2026_ET-04897_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-04897_WR |  |  | Not Started |  |  |  | 2026_ET-04897_VMLAZ |  | Not Started |  |  |  | 2026_ET-04897_VMM1 |  | Not Started |  |  |  |  | 2026_ET-04897_RR |  | Not Started | [6 empty] | 2026_ET-04897_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE MANDALAY-SANTA CLARA NO. 2_ET-04897 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-REPETTO-WABASH | ET-04906 | 2026_ET-04906 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 4.8312 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-24 | 04-02-2026 | Flown | 2026-02-22 | 04-24-2026 | 04-21-2026 |  | 2026_ET-04906_ACQPKG | 2026_ET-04906_GSPKG | Submitted | 2026_ET-04906_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04906_GCPR | 2025-12-08 | Historical | 2026_ET-04906_ACQ | QC Accepted | 2026_ET-04906_FR | 2026-03-16 | Submitted | 2026_ET-04906_RWR | Submitted | 2026-03-16 | 2026_ET-04906_CLAZ | 2026-04-15 | QC Accepted | 04-29-2026 | 2026-04-21 | 1 | 2026_ET-04906_PROCPKG | In Progress | All Good - Complete | 2026_ET-04906_WR | 2026-04-29 | 05-24-2026 | QC Accepted | 06-01-2026 | 2026-05-04 |  | 2026_ET-04906_VMLAZ | 2026-04-29 | QC Accepted |  | 2026-05-04 |  | 2026_ET-04906_VMM1 | 2026-04-29 | QC Accepted |  |  | 2026-05-04 |  | 2026_ET-04906_RR |  | No Violations | 05-05-2026 |  | 0 |  |  |  | 2026_ET-04906_VER | 2026-04-29 | QC Rejected |  | 2026-05-12 | 1 |  |  |  |  | Completed On Time - Program | Completed On Time | Completed Late - Program | MESA-REPETTO-WABASH_ET-04906 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 09:55 PST ¦ 2026-02-22 11:09 PST | 022226 | 20260222 |  | Metadata issue. |  |  | Analysis Error - False Negative Vegetation Point, Attribute - Survey Date |  |  | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
MESA-ROSEMEAD NO. 1 | ET-04921 | 2026_ET-04921 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.8914 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-04921_ACQPKG | 2026_ET-04921_GSPKG | Submitted | 2026_ET-04921_GS | 2025-10-15 | Field Complete | 2026_ET-04921_GCPR | 2025-12-08 | Submitted | 2026_ET-04921_ACQ | QC Accepted | 2026_ET-04921_FR | 2026-03-16 | Submitted | 2026_ET-04921_RWR | Submitted | 2026-03-16 | 2026_ET-04921_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04921_PROCPKG | In Progress | SCE | 2026_ET-04921_WR |  |  | In Progress |  |  |  | 2026_ET-04921_VMLAZ |  | In Progress |  |  |  | 2026_ET-04921_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04921_RR |  | In Progress | [6 empty] | 2026_ET-04921_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MESA-ROSEMEAD NO. 1_ET-04921 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 11:03 PST ¦ 2026-02-22 12:57 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-ROSEMEAD NO. 2 | ET-04922 | 2026_ET-04922 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 8.5852 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-04922_ACQPKG | 2026_ET-04922_GSPKG | Submitted | 2026_ET-04922_GS | 2025-10-15 | Field Complete | 2026_ET-04922_GCPR | 2025-12-08 | Submitted | 2026_ET-04922_ACQ | QC Accepted | 2026_ET-04922_FR | 2026-03-16 | Submitted | 2026_ET-04922_RWR | Submitted | 2026-03-16 | 2026_ET-04922_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04922_PROCPKG | In Progress | SCE | 2026_ET-04922_WR |  |  | In Progress |  |  |  | 2026_ET-04922_VMLAZ |  | In Progress |  |  |  | 2026_ET-04922_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04922_RR |  | In Progress | [6 empty] | 2026_ET-04922_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MESA-ROSEMEAD NO. 2_ET-04922 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 10:57 PST ¦ 2026-02-22 12:56 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-RUSH NO. 2 | ET-04926 | 2026_ET-04926 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.8728 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-04926_ACQPKG | 2026_ET-04926_GSPKG | Submitted | 2026_ET-04926_GS | 2025-10-15 | Field Complete | 2026_ET-04926_GCPR | 2025-12-08 | Submitted | 2026_ET-04926_ACQ | QC Accepted | 2026_ET-04926_FR | 2026-03-16 | Submitted | 2026_ET-04926_RWR | Submitted | 2026-03-16 | 2026_ET-04926_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04926_PROCPKG | In Progress | SCE | 2026_ET-04926_WR |  |  | In Progress |  |  |  | 2026_ET-04926_VMLAZ |  | In Progress |  |  |  | 2026_ET-04926_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04926_RR |  | In Progress | [6 empty] | 2026_ET-04926_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MESA-RUSH NO. 2_ET-04926 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 10:57 PST ¦ 2026-02-22 11:14 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MESA-SAN GABRIEL | ET-04930 | 2026_ET-04930 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.5169 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-04930_ACQPKG | 2026_ET-04930_GSPKG | Submitted | 2026_ET-04930_GS | 2025-10-15 | Field Complete | 2026_ET-04930_GCPR | 2025-12-08 | Submitted | 2026_ET-04930_ACQ | QC Accepted | 2026_ET-04930_FR | 2026-03-16 | Submitted | 2026_ET-04930_RWR | Submitted | 2026-03-16 | 2026_ET-04930_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-04930_PROCPKG | In Progress | SCE | 2026_ET-04930_WR |  |  | In Progress |  |  |  | 2026_ET-04930_VMLAZ |  | In Progress |  |  |  | 2026_ET-04930_VMM1 |  | In Progress |  |  |  |  | 2026_ET-04930_RR |  | In Progress | [6 empty] | 2026_ET-04930_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | MESA-SAN GABRIEL_ET-04930 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 11:03 PST ¦ 2026-02-22 12:50 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-THOUSAND OAKS NO. 1 | ET-04990 | 2026_ET-04990 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 7.7719 | 7.7719 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-20 | 04-02-2026 | Flown | 2026-03-10 | 04-20-2026 | 04-15-2026 |  | 2026_ET-04990_ACQPKG | 2026_ET-04990_GSPKG | Submitted | 2026_ET-04990_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04990_GCPR | 2025-12-08 | Historical | 2026_ET-04990_ACQ | QC Accepted | 2026_ET-04990_FR | 2026-04-02 | Submitted | 2026_ET-04990_RWR | Submitted | 2026-04-02 | 2026_ET-04990_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-04990_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04990_WR | 2026-05-14 | 05-20-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04990_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04990_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04990_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-04990_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-THOUSAND OAKS NO. 1_ET-04990 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-09 14:02 PDT ¦ 2026-03-10 10:00 PDT | 031026 | 20260310 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
MOORPARK-THOUSAND OAKS NO. 2 | ET-04991 | 2026_ET-04991 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 10.0768 | 10.0768 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-17 | 04-02-2026 | Flown | 2026-03-10 | 04-17-2026 | 04-15-2026 |  | 2026_ET-04991_ACQPKG | 2026_ET-04991_GSPKG | Submitted | 2026_ET-04991_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-04991_GCPR | 2025-12-08 | Historical | 2026_ET-04991_ACQ | QC Accepted | 2026_ET-04991_FR | 2026-04-02 | Submitted | 2026_ET-04991_RWR | Submitted | 2026-04-02 | 2026_ET-04991_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-04991_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-04991_WR | 2026-05-14 | 05-17-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04991_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-04991_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-04991_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 5 | 2026-05-14 |  | 0 | 2026_ET-04991_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Projected On Time | Completed On Time - Program | MOORPARK-THOUSAND OAKS NO. 2_ET-04991 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | 2026-03-09 14:05 PDT ¦ 2026-03-10 10:59 PDT | 031026 | 20260310 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
NEWMARK-REPETTO-WABASH | ET-05198 | 2026_ET-05198 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 3.525 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-05198_ACQPKG | 2026_ET-05198_GSPKG | Submitted | 2026_ET-05198_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-05198_GCPR | 2025-12-08 | Historical | 2026_ET-05198_ACQ | In Progress | 2026_ET-05198_FR |  | Not Started | 2026_ET-05198_RWR | Not Started |  | 2026_ET-05198_CLAZ |  | Not Started |  |  |  | 2026_ET-05198_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-05198_WR |  |  | Not Started |  |  |  | 2026_ET-05198_VMLAZ |  | Not Started |  |  |  | 2026_ET-05198_VMM1 |  | Not Started |  |  |  |  | 2026_ET-05198_RR |  | Not Started | [6 empty] | 2026_ET-05198_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | NEWMARK-REPETTO-WABASH_ET-05198 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
LAUREL-OCTOL | ET-05585 | 2026_ET-05585 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 12.6564 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-05585_ACQPKG | 2026_ET-05585_GSPKG | Submitted | 2026_ET-05585_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-05585_GCPR | 2025-12-08 | Historical | 2026_ET-05585_ACQ | In Progress | 2026_ET-05585_FR |  | Not Started | 2026_ET-05585_RWR | Not Started |  | 2026_ET-05585_CLAZ |  | Not Started |  |  |  | 2026_ET-05585_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-05585_WR |  |  | Not Started |  |  |  | 2026_ET-05585_VMLAZ |  | Not Started |  |  |  | 2026_ET-05585_VMM1 |  | Not Started |  |  |  |  | 2026_ET-05585_RR |  | Not Started | [6 empty] | 2026_ET-05585_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | LAUREL-OCTOL_ET-05585 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
ATWOOD-PLACENTIA | ET-05780 | 2026_ET-05780 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 4.1289 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-02 |  | 05-06-2026 |  | 2026_ET-05780_ACQPKG | 2026_ET-05780_GSPKG | Submitted | 2026_ET-05780_GS | 2026-01-31 | Field Complete | 2026_ET-05780_GCPR | 2026-05-03 | Submitted | 2026_ET-05780_ACQ | QC Accepted | 2026_ET-05780_FR | 2026-05-03 | Submitted | 2026_ET-05780_RWR | Submitted | 2026-05-03 | 2026_ET-05780_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-05780_PROCPKG | In Progress | SCE | 2026_ET-05780_WR |  |  | In Progress |  |  |  | 2026_ET-05780_VMLAZ |  | In Progress |  |  |  | 2026_ET-05780_VMM1 |  | In Progress |  |  |  |  | 2026_ET-05780_RR |  | In Progress | [6 empty] | 2026_ET-05780_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | ATWOOD-PLACENTIA_ET-05780 | Done |  | No |  |  | FULLERTON | 48 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EATON-RAVENDALE | ET-06594 | 2026_ET-06594 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.967 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-06594_ACQPKG | 2026_ET-06594_GSPKG | Submitted | 2026_ET-06594_GS | 2025-10-15 | Field Complete | 2026_ET-06594_GCPR | 2025-12-08 | Submitted | 2026_ET-06594_ACQ | QC Accepted | 2026_ET-06594_FR | 2026-03-16 | Submitted | 2026_ET-06594_RWR | Submitted | 2026-03-16 | 2026_ET-06594_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-06594_PROCPKG | In Progress | SCE | 2026_ET-06594_WR |  |  | In Progress |  |  |  | 2026_ET-06594_VMLAZ |  | In Progress |  |  |  | 2026_ET-06594_VMM1 |  | In Progress |  |  |  |  | 2026_ET-06594_RR |  | In Progress | [6 empty] | 2026_ET-06594_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | EATON-RAVENDALE_ET-06594 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | 2026-02-22 13:08 PST ¦ 2026-02-22 13:10 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RAVENDALE-SAN GABRIEL | ET-06595 | 2026_ET-06595 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.6446 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-22 |  | 04-17-2026 |  | 2026_ET-06595_ACQPKG | 2026_ET-06595_GSPKG | Submitted | 2026_ET-06595_GS | 2025-10-15 | Field Complete | 2026_ET-06595_GCPR | 2025-12-08 | Submitted | 2026_ET-06595_ACQ | QC Accepted | 2026_ET-06595_FR | 2026-03-16 | Submitted | 2026_ET-06595_RWR | Submitted | 2026-03-16 | 2026_ET-06595_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-06595_PROCPKG | In Progress | SCE | 2026_ET-06595_WR |  |  | In Progress |  |  |  | 2026_ET-06595_VMLAZ |  | In Progress |  |  |  | 2026_ET-06595_VMM1 |  | In Progress |  |  |  |  | 2026_ET-06595_RR |  | In Progress | [6 empty] | 2026_ET-06595_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RAVENDALE-SAN GABRIEL_ET-06595 |  |  | No |  | Helicopter | MONTEBELLO | 22 | HC | 2026-02-22 12:37 PST ¦ 2026-02-22 13:00 PST | 022226 | 20260222 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE REDLANDS-YUCAIPA | ET-06738 | 2026_ET-06738 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 0.45338 | 0.13516 | 30 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-06738_ACQPKG | 2026_ET-06738_GSPKG | Submitted | 2026_ET-06738_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06738_GCPR | 2025-12-08 | Historical | 2026_ET-06738_ACQ | In Progress | 2026_ET-06738_FR |  | Not Started | 2026_ET-06738_RWR | Not Started |  | 2026_ET-06738_CLAZ |  | Not Started |  |  |  | 2026_ET-06738_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-06738_WR |  |  | Not Started |  |  |  | 2026_ET-06738_VMLAZ |  | Not Started |  |  |  | 2026_ET-06738_VMM1 |  | Not Started |  |  |  |  | 2026_ET-06738_RR |  | Not Started | [6 empty] | 2026_ET-06738_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE REDLANDS-YUCAIPA_ET-06738 |  |  | No |  |  | REDLANDS | 31 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
PIUTE-REDMAN | ET-06762 | 2026_ET-06762 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 5.0876 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-20 |  | 04-17-2026 |  | 2026_ET-06762_ACQPKG | 2026_ET-06762_GSPKG | Submitted | 2026_ET-06762_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06762_GCPR | 2025-12-08 | Historical | 2026_ET-06762_ACQ | QC Accepted | 2026_ET-06762_FR | 2026-03-16 | Submitted | 2026_ET-06762_RWR | Submitted | 2026-03-16 | 2026_ET-06762_CLAZ | 2026-04-15 | QC Accepted | 05-18-2026 | 2026-04-17 | 0 | 2026_ET-06762_PROCPKG | In Progress | SCE | 2026_ET-06762_WR |  |  | In Progress |  |  |  | 2026_ET-06762_VMLAZ |  | In Progress |  |  |  | 2026_ET-06762_VMM1 |  | In Progress |  |  |  |  | 2026_ET-06762_RR |  | In Progress | [6 empty] | 2026_ET-06762_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | PIUTE-REDMAN_ET-06762 |  |  | No |  | Helicopter | ANTELOPE VALLEY | 36 | HC | 2026-02-20 10:13 PST ¦ 2026-02-20 10:13 PST | 022026 | 20260220 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
RIO HONDO-CITRUS | ET-06827 | 2026_ET-06827 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 9.0609 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-28 |  | 05-15-2026 |  | 2026_ET-06827_ACQPKG | 2026_ET-06827_GSPKG | Submitted | 2026_ET-06827_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-06827_GCPR | 2025-12-08 | Historical | 2026_ET-06827_ACQ | QC Accepted | 2026_ET-06827_FR | 2026-05-03 | Submitted | 2026_ET-06827_RWR | Submitted | 2026-05-03 | 2026_ET-06827_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-15 |  | 2026_ET-06827_PROCPKG | In Progress | SCE | 2026_ET-06827_WR |  |  | In Progress |  |  |  | 2026_ET-06827_VMLAZ |  | In Progress |  |  |  | 2026_ET-06827_VMM1 |  | In Progress |  |  |  |  | 2026_ET-06827_RR |  | In Progress | [6 empty] | 2026_ET-06827_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | RIO HONDO-CITRUS_ET-06827 |  |  | No |  |  | MONROVIA | 27 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE EAGLE ROCK-SAUGUS | ET-07008 | 2026_ET-07008 |  | 1 | 2026 | Nov 01, 2026 | 220 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 1.1501 | 1.1501 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-07008_ACQPKG | 2026_ET-07008_GSPKG | Submitted | 2026_ET-07008_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07008_GCPR | 2025-12-08 | Historical | 2026_ET-07008_ACQ | In Progress | 2026_ET-07008_FR |  | Not Started | 2026_ET-07008_RWR | Not Started |  | 2026_ET-07008_CLAZ |  | Not Started |  |  |  | 2026_ET-07008_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07008_WR |  |  | Not Started |  |  |  | 2026_ET-07008_VMLAZ |  | Not Started |  |  |  | 2026_ET-07008_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07008_RR |  | Not Started | [6 empty] | 2026_ET-07008_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE EAGLE ROCK-SAUGUS_ET-07008 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-COLONIA | ET-07024 | 2026_ET-07024 |  | 1 | 2026 | Dec 01, 2026 | 66 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 12.8325 | 2.5121 | 20 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-07024_ACQPKG | 2026_ET-07024_GSPKG | In Progress | 2026_ET-07024_GS |  | Not Started | 2026_ET-07024_GCPR |  | Not Started | 2026_ET-07024_ACQ | In Progress | 2026_ET-07024_FR |  | Not Started | 2026_ET-07024_RWR | Not Started |  | 2026_ET-07024_CLAZ |  | Not Started |  |  |  | 2026_ET-07024_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07024_WR |  |  | Not Started |  |  |  | 2026_ET-07024_VMLAZ |  | Not Started |  |  |  | 2026_ET-07024_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07024_RR |  | Not Started | [6 empty] | 2026_ET-07024_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SANTA CLARA-COLONIA_ET-07024 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA CLARA-SAN MIGUEL | ET-07090 | 2026_ET-07090 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 4.8171 | 1.271 | 26 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-07090_ACQPKG | 2026_ET-07090_GSPKG | Submitted | 2026_ET-07090_GS | 2025-12-08 | Field Complete | 2026_ET-07090_GCPR | 2026-05-22 | Submitted | 2026_ET-07090_ACQ | Submitted | 2026_ET-07090_FR | 2026-05-22 | Submitted | 2026_ET-07090_RWR | Submitted | 2026-05-22 | 2026_ET-07090_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-07090_PROCPKG | In Progress | SCE | 2026_ET-07090_WR |  |  | Not Started |  |  |  | 2026_ET-07090_VMLAZ |  | Not Started |  |  |  | 2026_ET-07090_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07090_RR |  | Not Started | [6 empty] | 2026_ET-07090_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | SANTA CLARA-SAN MIGUEL_ET-07090 |  |  | No |  |  | VENTURA | 39 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CHATSWORTH-SANTA SUSANA | ET-07108 | 2026_ET-07108 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 5.3326 | 5.3326 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-07108_ACQPKG | 2026_ET-07108_GSPKG | Submitted | 2026_ET-07108_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07108_GCPR | 2025-12-08 | Historical | 2026_ET-07108_ACQ | Submitted | 2026_ET-07108_FR | 2026-05-22 | Submitted | 2026_ET-07108_RWR | Submitted | 2026-05-22 | 2026_ET-07108_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-07108_PROCPKG | In Progress | SCE | 2026_ET-07108_WR |  |  | Not Started |  |  |  | 2026_ET-07108_VMLAZ |  | Not Started |  |  |  | 2026_ET-07108_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07108_RR |  | Not Started | [6 empty] | 2026_ET-07108_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | CHATSWORTH-SANTA SUSANA_ET-07108 |  |  | No |  |  | THOUSAND OAKS | 35 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SAUGUS-SANTA SUSANA | ET-07164 | 2026_ET-07164 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 14.7154 | 14.7154 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-07164_ACQPKG | 2026_ET-07164_GSPKG | Submitted | 2026_ET-07164_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07164_GCPR | 2025-12-08 | Historical | 2026_ET-07164_ACQ | Submitted | 2026_ET-07164_FR | 2026-05-22 | Submitted | 2026_ET-07164_RWR | Submitted | 2026-05-22 | 2026_ET-07164_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-07164_PROCPKG | In Progress | SCE | 2026_ET-07164_WR |  |  | Not Started |  |  |  | 2026_ET-07164_VMLAZ |  | Not Started |  |  |  | 2026_ET-07164_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07164_RR |  | Not Started | [6 empty] | 2026_ET-07164_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | SAUGUS-SANTA SUSANA_ET-07164 |  |  | No |  |  | VALENCIA | 59 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
POLARIS-SEPULVEDA | ET-07189 | 2026_ET-07189 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 05-02-2026 | On Time | 0 | Transmission | 1.6278 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | Variable | N/A | Restricted Air Space | N/A |  | LAX Issues |  | SCE Approved | N/A | 60 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-01-2026 | Access Delay |  |  |  |  | 2026_ET-07189_ACQPKG | 2026_ET-07189_GSPKG | In Progress | 2026_ET-07189_GS | 2025-12-08 | Field Complete | 2026_ET-07189_GCPR |  | Not Started | 2026_ET-07189_ACQ | In Progress | 2026_ET-07189_FR |  | Not Started | 2026_ET-07189_RWR | Submitted |  | 2026_ET-07189_CLAZ |  | Not Started |  |  |  | 2026_ET-07189_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07189_WR |  |  | Not Started |  |  |  | 2026_ET-07189_VMLAZ |  | Not Started |  |  |  | 2026_ET-07189_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07189_RR |  | Not Started | [6 empty] | 2026_ET-07189_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | POLARIS-SEPULVEDA_ET-07189 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SANTA ANA RIVER NO. 1-NO. 3 | ET-07216 | 2026_ET-07216 |  | 1 | 2026 | Jul 01, 2026 | 33 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.9801 | 3.9801 | 100 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Available | Daniel |  | 2026-04-22 | 04-02-2026 | Flown | 2026-02-01 | 04-22-2026 | 04-15-2026 |  | 2026_ET-07216_ACQPKG | 2026_ET-07216_GSPKG | Submitted | 2026_ET-07216_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07216_GCPR | 2025-12-08 | Historical | 2026_ET-07216_ACQ | QC Accepted | 2026_ET-07216_FR | 2026-04-02 | Submitted | 2026_ET-07216_RWR | Submitted | 2026-04-02 | 2026_ET-07216_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-07216_PROCPKG | QC Accepted | ACQ Vendor and SCE | 2026_ET-07216_WR | 2026-05-14 | 05-22-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-07216_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-07216_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-07216_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 5 | 2026-05-14 |  | 0 | 2026_ET-07216_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-20 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | SANTA ANA RIVER NO. 1-NO. 3_ET-07216 |  |  | No |  |  | REDLANDS | 31 | UNK | 2026-02-01 13:26 PST ¦ 2026-03-18 12:21 PDT | 020126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SPRINGVILLE-LINDSAY-VENIDA | ET-07230 | 2026_ET-07230 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 27.4826 | 4.8357 | 18 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-07230_ACQPKG | 2026_ET-07230_GSPKG | Submitted | 2026_ET-07230_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07230_GCPR | 2025-12-08 | Historical | 2026_ET-07230_ACQ | In Progress | 2026_ET-07230_FR |  | Not Started | 2026_ET-07230_RWR | Not Started |  | 2026_ET-07230_CLAZ |  | Not Started |  |  |  | 2026_ET-07230_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07230_WR |  |  | Not Started |  |  |  | 2026_ET-07230_VMLAZ |  | Not Started |  |  |  | 2026_ET-07230_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07230_RR |  | Not Started | [6 empty] | 2026_ET-07230_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SPRINGVILLE-LINDSAY-VENIDA_ET-07230 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BIG CREEK 4-SPRINGVILLE | ET-07241 | 2026_ET-07241 |  | 1 | 2026 | Sep 01, 2026 | 220 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 81.6132 | 73.6482 | 90 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown | 2026-03-01 |  | 04-22-2026 |  | 2026_ET-07241_ACQPKG | 2026_ET-07241_GSPKG | Submitted | 2026_ET-07241_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07241_GCPR | 2025-12-08 | Historical | 2026_ET-07241_ACQ | QC Accepted | 2026_ET-07241_FR | 2026-03-16 | Submitted | 2026_ET-07241_RWR | Submitted | 2026-03-16 | 2026_ET-07241_CLAZ | 2026-04-15 | QC Accepted | 06-18-2026 | 2026-04-22 | 0 | 2026_ET-07241_PROCPKG | In Progress | SCE | 2026_ET-07241_WR |  |  | Not Started |  |  |  | 2026_ET-07241_VMLAZ |  | In Progress |  |  |  | 2026_ET-07241_VMM1 |  | In Progress |  |  |  |  | 2026_ET-07241_RR |  | In Progress | [6 empty] | 2026_ET-07241_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | BIG CREEK 4-SPRINGVILLE_ET-07241 | Done |  | Yes |  | Helicopter | TULARE | 51 | HC | 2026-02-25 11:36 PST ¦ 2026-03-01 08:58 PST | 022626 | 20260301 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SPRINGVILLE-PORTERVILLE | ET-07243 | 2026_ET-07243 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 7.6745 | 3.4056 | 44 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-07243_ACQPKG | 2026_ET-07243_GSPKG | Submitted | 2026_ET-07243_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07243_GCPR | 2025-12-08 | Historical | 2026_ET-07243_ACQ | In Progress | 2026_ET-07243_FR |  | Not Started | 2026_ET-07243_RWR | Not Started |  | 2026_ET-07243_CLAZ |  | Not Started |  |  |  | 2026_ET-07243_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07243_WR |  |  | Not Started |  |  |  | 2026_ET-07243_VMLAZ |  | Not Started |  |  |  | 2026_ET-07243_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07243_RR |  | Not Started | [6 empty] | 2026_ET-07243_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SPRINGVILLE-PORTERVILLE_ET-07243 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SPRINGVILLE-PORTERVILLE-STRATHMORE | ET-07300 | 2026_ET-07300 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 14.2472 | 3.3757 | 24 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-07300_ACQPKG | 2026_ET-07300_GSPKG | Submitted | 2026_ET-07300_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-07300_GCPR | 2025-12-08 | Historical | 2026_ET-07300_ACQ | In Progress | 2026_ET-07300_FR |  | Not Started | 2026_ET-07300_RWR | Not Started |  | 2026_ET-07300_CLAZ |  | Not Started |  |  |  | 2026_ET-07300_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-07300_WR |  |  | Not Started |  |  |  | 2026_ET-07300_VMLAZ |  | Not Started |  |  |  | 2026_ET-07300_VMM1 |  | Not Started |  |  |  |  | 2026_ET-07300_RR |  | Not Started | [6 empty] | 2026_ET-07300_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | SPRINGVILLE-PORTERVILLE-STRATHMORE_ET-07300 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
SULLIVAN-VERA | ET-07315 | 2026_ET-07315 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 3.6045 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-06 | 04-21-2026 | 04-14-2026 |  | 2026_ET-07315_ACQPKG | 2026_ET-07315_GSPKG | Submitted | 2026_ET-07315_GS | 2025-12-08 | Field Complete | 2026_ET-07315_GCPR | 2026-04-02 | Submitted | 2026_ET-07315_ACQ | QC Accepted | 2026_ET-07315_FR | 2026-04-02 | Submitted | 2026_ET-07315_RWR | Submitted | 2026-04-02 | 2026_ET-07315_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-07315_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-07315_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-07315_VMLAZ | 2026-05-10 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-07315_VMM1 | 2026-05-10 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-07315_RR | 2026-05-10 | No Violations | 05-21-2026 |  | 0 |  |  |  | 2026_ET-07315_VER | 2026-05-10 | Uploaded to S123 | 06-01-2026 | 2026-05-19 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | SULLIVAN-VERA_ET-07315 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-02-06 08:41 PST ¦ 2026-02-06 08:55 PST | 020626 | 20260206 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VESTAL-WHEATLAND | ET-08427 | 2026_ET-08427 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_4 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 8.1307 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-25 | 05-20-2026 | 05-20-2026 |  | 2026_ET-08427_ACQPKG | 2026_ET-08427_GSPKG | Submitted | 2026_ET-08427_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08427_GCPR | 2025-12-08 | Historical | 2026_ET-08427_ACQ | QC Accepted | 2026_ET-08427_FR | 2026-03-16 | Submitted | 2026_ET-08427_RWR | Submitted | 2026-03-16 | 2026_ET-08427_CLAZ | 2026-05-11 | QC Accepted | 05-25-2026 | 2026-05-20 | 2 | 2026_ET-08427_PROCPKG | In Progress | All Good - Complete | 2026_ET-08427_WR |  | 06-19-2026 | Not Started |  |  |  | 2026_ET-08427_VMLAZ |  | Not Started |  |  |  | 2026_ET-08427_VMM1 |  | Not Started |  |  |  |  | 2026_ET-08427_RR |  | Not Started | [6 empty] | 2026_ET-08427_VER |  | Not Started | [7 empty] | Projected Late | Completed On Time | Completed Late - Program | VESTAL-WHEATLAND_ET-08427 |  |  | No |  | Helicopter | TULARE | 51 | HC |  |  |  |  | Relative accuracy is not within 3 inches RMSE or a single instance over 6 inches. | [5 empty] | Delay | No Delay | Variable | N/A |  |  | BulkRedelivery |  |  |  | N/A | N/A | 1
VILLA PARK-ATWOOD | ET-08440 | 2026_ET-08440 |  | 1 | 2026 | Jul 01, 2026 | 66 | CA_6 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 5.3504 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Complete | Daniel |  | 2026-04-21 | 04-02-2026 | Flown | 2026-02-03 | 04-21-2026 | 04-14-2026 |  | 2026_ET-08440_ACQPKG | 2026_ET-08440_GSPKG | Submitted | 2026_ET-08440_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08440_GCPR | 2025-12-08 | Historical | 2026_ET-08440_ACQ | QC Accepted | 2026_ET-08440_FR | 2026-04-02 | Submitted | 2026_ET-08440_RWR | Submitted | 2026-04-02 | 2026_ET-08440_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-14 | 0 | 2026_ET-08440_PROCPKG | Submitted | All Good - Complete | 2026_ET-08440_WR | 2026-05-14 | 05-21-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-08440_VMLAZ | 2026-05-07 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-08440_VMM1 | 2026-05-07 | QC Accepted |  | 06-01-2026 | 2026-05-22 |  | 2026_ET-08440_RR | 2026-05-07 | No Violations | 05-23-2026 |  | 0 |  |  |  | 2026_ET-08440_VER | 2026-05-07 | Under QC | 06-01-2026 | [6 empty] | Projected Late | Completed On Time | Completed On Time - Program | VILLA PARK-ATWOOD_ET-08440 |  |  | No |  |  | SANTA ANA | 29 | UNK | 2026-01-30 08:57 PST ¦ 2026-03-03 10:52 PST | 020326 | 20260303 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VILLA PARK-MODENA NO. 1 | ET-08477 | 2026_ET-08477 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 3.3271 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-03 |  | 05-20-2026 |  | 2026_ET-08477_ACQPKG | 2026_ET-08477_GSPKG | Submitted | 2026_ET-08477_GS | 2026-01-31 | Field Complete | 2026_ET-08477_GCPR | 2026-05-03 | Submitted | 2026_ET-08477_ACQ | QC Accepted | 2026_ET-08477_FR | 2026-05-03 | Submitted | 2026_ET-08477_RWR | Submitted | 2026-05-03 | 2026_ET-08477_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-20 |  | 2026_ET-08477_PROCPKG | In Progress | SCE | 2026_ET-08477_WR |  |  | Not Started |  |  |  | 2026_ET-08477_VMLAZ |  | Not Started |  |  |  | 2026_ET-08477_VMM1 |  | Not Started |  |  |  |  | 2026_ET-08477_RR |  | Not Started | [6 empty] | 2026_ET-08477_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | VILLA PARK-MODENA NO. 1_ET-08477 |  |  | No |  |  | SANTA ANA | 29 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE WALNUT-DALTON-LARK ELLEN | ET-08563 | 2026_ET-08563 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_5 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 1.4385 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-08563_ACQPKG | 2026_ET-08563_GSPKG | Submitted | 2026_ET-08563_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08563_GCPR | 2025-12-08 | Historical | 2026_ET-08563_ACQ | In Progress | 2026_ET-08563_FR |  | Not Started | 2026_ET-08563_RWR | Not Started |  | 2026_ET-08563_CLAZ |  | Not Started |  |  |  | 2026_ET-08563_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-08563_WR |  |  | Not Started |  |  |  | 2026_ET-08563_VMLAZ |  | Not Started |  |  |  | 2026_ET-08563_VMM1 |  | Not Started |  |  |  |  | 2026_ET-08563_RR |  | Not Started | [6 empty] | 2026_ET-08563_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | IDLE WALNUT-DALTON-LARK ELLEN_ET-08563 |  |  | No |  | Helicopter | MONROVIA | 27 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CREST-WALTERIA | ET-08710 | 2026_ET-08710 |  | 1 | 2026 | Aug 01, 2026 | 66 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 2.9876 | 1.318 | 44 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-03-05 |  | 05-08-2026 |  | 2026_ET-08710_ACQPKG | 2026_ET-08710_GSPKG | Submitted | 2026_ET-08710_GS | 2026-01-31 | Field Complete | 2026_ET-08710_GCPR | 2026-05-03 | Submitted | 2026_ET-08710_ACQ | QC Accepted | 2026_ET-08710_FR | 2026-05-03 | Submitted | 2026_ET-08710_RWR | Submitted | 2026-05-03 | 2026_ET-08710_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-08 |  | 2026_ET-08710_PROCPKG | In Progress | SCE | 2026_ET-08710_WR |  |  | In Progress |  |  |  | 2026_ET-08710_VMLAZ |  | In Progress |  |  |  | 2026_ET-08710_VMM1 |  | In Progress |  |  |  |  | 2026_ET-08710_RR |  | In Progress | [6 empty] | 2026_ET-08710_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CREST-WALTERIA_ET-08710 |  |  | No |  |  | SOUTH BAY | 44 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BLISS-WOODVILLE | ET-08768 | 2026_ET-08768 |  | 1 | 2026 | Nov 01, 2026 | 66 | CA_4 | 11 | 08-03-2026 | 08-18-2026 | 09-17-2026 | 10-02-2026 | 06-04-2026 | 07-04-2026 | 06-04-2026 | 07-04-2026 | On Time | 0 | Transmission | 7.6169 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 08-03-2026 | Not Started |  |  |  |  | 2026_ET-08768_ACQPKG | 2026_ET-08768_GSPKG | Submitted | 2026_ET-08768_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-08768_GCPR | 2025-12-08 | Historical | 2026_ET-08768_ACQ | In Progress | 2026_ET-08768_FR |  | Not Started | 2026_ET-08768_RWR | Not Started |  | 2026_ET-08768_CLAZ |  | Not Started |  |  |  | 2026_ET-08768_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-08768_WR |  |  | Not Started |  |  |  | 2026_ET-08768_VMLAZ |  | Not Started |  |  |  | 2026_ET-08768_VMM1 |  | Not Started |  |  |  |  | 2026_ET-08768_RR |  | Not Started | [6 empty] | 2026_ET-08768_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | BLISS-WOODVILLE_ET-08768 |  |  | No |  | Helicopter | TULARE | 51 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE EL NIDO-CULVER-MARINE | ET-47112 | 2026_ET-47112 |  | 1 | 2026 | Sep 01, 2026 | 66 | CA_5 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 3.0894 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-47112_ACQPKG | 2026_ET-47112_GSPKG | Submitted | 2026_ET-47112_GS | 2025-12-08 | Field Complete | 2026_ET-47112_GCPR | 2026-05-22 | Submitted | 2026_ET-47112_ACQ | Submitted | 2026_ET-47112_FR | 2026-05-22 | Submitted | 2026_ET-47112_RWR | Submitted | 2026-05-22 | 2026_ET-47112_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-47112_PROCPKG | In Progress | SCE | 2026_ET-47112_WR |  |  | Not Started |  |  |  | 2026_ET-47112_VMLAZ |  | Not Started |  |  |  | 2026_ET-47112_VMM1 |  | Not Started |  |  |  |  | 2026_ET-47112_RR |  | Not Started | [6 empty] | 2026_ET-47112_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE EL NIDO-CULVER-MARINE_ET-47112 |  |  | No |  |  | SANTA MONICA | 42 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
EAGLE MOUNTAIN-BLYTHE | ET-75165 | 2026_ET-75165 |  | 1 | 2026 | Aug 01, 2026 | 161 | CA_6 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-04-2026 | 04-03-2026 | On Time | 0 | Transmission | 52.4268 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 05-03-2026 | Flown | 2026-02-21 |  | 05-06-2026 |  | 2026_ET-75165_ACQPKG | 2026_ET-75165_GSPKG | Submitted | 2026_ET-75165_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-75165_GCPR | 2025-12-08 | Historical | 2026_ET-75165_ACQ | QC Accepted | 2026_ET-75165_FR | 2026-05-03 | Submitted | 2026_ET-75165_RWR | Submitted | 2026-05-03 | 2026_ET-75165_CLAZ | 2026-05-03 | QC Accepted | 05-18-2026 | 2026-05-06 |  | 2026_ET-75165_PROCPKG | In Progress | SCE | 2026_ET-75165_WR |  |  | In Progress |  |  |  | 2026_ET-75165_VMLAZ |  | In Progress |  |  |  | 2026_ET-75165_VMM1 |  | In Progress |  |  |  |  | 2026_ET-75165_RR |  | In Progress | [6 empty] | 2026_ET-75165_VER |  | In Progress | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | EAGLE MOUNTAIN-BLYTHE_ET-75165 |  |  | No |  |  | BLYTHE | 87 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-PLANT 5-PLANT 6 | ET-75435 | 2026_ET-75435 |  | 1 | 2026 | Oct 01, 2026 | 55 | CA_4 | 10 | 07-03-2026 | 07-18-2026 | 08-17-2026 | 09-01-2026 | 05-04-2026 | 06-03-2026 | 05-04-2026 | 06-03-2026 | On Time | 0 | Transmission | 1.8357 | 1.8357 | 100 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 07-03-2026 | Flown | 2026-04-19 |  | 05-11-2026 |  | 2026_ET-75435_ACQPKG | 2026_ET-75435_GSPKG | Submitted | 2026_ET-75435_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-75435_GCPR | 2025-12-08 | Historical | 2026_ET-75435_ACQ | QC Accepted | 2026_ET-75435_FR | 2026-05-08 | Submitted | 2026_ET-75435_RWR | Submitted | 2026-05-08 | 2026_ET-75435_CLAZ | 2026-05-08 | QC Accepted | 07-18-2026 | 2026-05-11 | 0 | 2026_ET-75435_PROCPKG | In Progress | SCE | 2026_ET-75435_WR |  |  | Not Started |  |  |  | 2026_ET-75435_VMLAZ |  | Not Started |  |  |  | 2026_ET-75435_VMM1 |  | Not Started |  |  |  |  | 2026_ET-75435_RR |  | Not Started | [6 empty] | 2026_ET-75435_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed On Time - Program | CONTROL-PLANT 5-PLANT 6_ET-75435 |  |  | No |  | Helicopter | BISHOP/MAMMOTH | 85 | HC | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE GARNET-HI DESERT NO.1 | ET-75858 | 2026_ET-75858 |  | 1 | 2026 | Sep 01, 2026 | 115 | CA_6 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 05-04-2026 | On Time | 0 | Transmission | 0.81173 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_TCS_CWA_02 | 2026-04-02 | 2026_TCS_CWA_02 | 2026-04-02 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 06-03-2026 | Flown |  |  |  |  | 2026_ET-75858_ACQPKG | 2026_ET-75858_GSPKG | Submitted | 2026_ET-75858_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-75858_GCPR | 2026-05-22 | Submitted | 2026_ET-75858_ACQ | Submitted | 2026_ET-75858_FR | 2026-05-22 | Submitted | 2026_ET-75858_RWR | Submitted | 2026-05-22 | 2026_ET-75858_CLAZ | 2026-05-22 | Ready for QC | 06-18-2026 |  |  | 2026_ET-75858_PROCPKG | In Progress | SCE | 2026_ET-75858_WR |  |  | Not Started |  |  |  | 2026_ET-75858_VMLAZ |  | Not Started |  |  |  | 2026_ET-75858_VMM1 |  | Not Started |  |  |  |  | 2026_ET-75858_RR |  | Not Started | [6 empty] | 2026_ET-75858_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Completed On Time - Program | IDLE GARNET-HI DESERT NO.1_ET-75858 |  |  | No |  |  | PALM SPRINGS | 79 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
KRAMER-ROCKET TEST | ET-76043 | 2026_ET-76043 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 11.1829 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-76043_ACQPKG | 2026_ET-76043_GSPKG | Submitted | 2026_ET-76043_GS | 2026-01-23 | Field Complete | 2026_ET-76043_GCPR | 2026-01-30 | Submitted | 2026_ET-76043_ACQ | In Progress | 2026_ET-76043_FR |  | Not Started | 2026_ET-76043_RWR | Not Started |  | 2026_ET-76043_CLAZ |  | Not Started |  |  |  | 2026_ET-76043_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-76043_WR |  |  | Not Started |  |  |  | 2026_ET-76043_VMLAZ |  | Not Started |  |  |  | 2026_ET-76043_VMM1 |  | Not Started |  |  |  |  | 2026_ET-76043_RR |  | Not Started | [6 empty] | 2026_ET-76043_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | KRAMER-ROCKET TEST_ET-76043 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CNTRL-DEPSPRGS-FSHLKEVLY-WHT MT-SLVRPEAK | ET-76337 | 2026_ET-76337 |  | 1 | 2026 | Sep 01, 2026 | 55 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 09-01-2026 | On Time | 0 | Transmission | 45.2061 | 3.3439 | 7 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_Cyient_CWA_04 | 2026-04-02 | 2026_Cyient_CWA_04 | 2026-04-02 |  | Delay | No Delay | SCE | N/A | Air Ops Rejection | N/A | Environmental, Access, AirOps | Advised via D. Bloomer that CKT has a section that is off limits to Air Ops (environmental) until ~August 2026. Per Air Ops on 5/13 there are Big Horn Sheep in the area and therefore it is off limits until August 2026. SCE has added a 120 day delay to the SLA date to account for this. These are staying in scope despite the delay |  | SCE Approved | N/A | 120 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 10-01-2026 | Access Delay |  |  |  |  | 2026_ET-76337_ACQPKG | 2026_ET-76337_GSPKG | Submitted | 2026_ET-76337_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-76337_GCPR | 2025-12-08 | Historical | 2026_ET-76337_ACQ | In Progress | 2026_ET-76337_FR |  | Not Started | 2026_ET-76337_RWR | Not Started |  | 2026_ET-76337_CLAZ |  | Not Started |  |  |  | 2026_ET-76337_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-76337_WR |  |  | Not Started |  |  |  | 2026_ET-76337_VMLAZ |  | Not Started |  |  |  | 2026_ET-76337_VMM1 |  | Not Started |  |  |  |  | 2026_ET-76337_RR |  | Not Started | [6 empty] | 2026_ET-76337_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | CNTRL-DEPSPRGS-FSHLKEVLY-WHT MT-SLVRPEAK_ET-76337 |  |  | No |  |  | BISHOP/MAMMOTH | 85 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-SILVER PEAK-ZACK | ET-76438 | 2026_ET-76438 |  | 1 | 2026 | Sep 01, 2026 | 55 | CA_4 | 9 | 06-03-2026 | 06-18-2026 | 07-18-2026 | 08-02-2026 | 04-04-2026 | 05-04-2026 | 04-04-2026 | 09-01-2026 | On Time | 0 | Transmission | 58.2948 | 3.3814 | 6 | 2026 Vegetation Management Transmission | 2026_SS_CWA_01 | 2025-10-08 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | SCE | N/A | Air Ops Rejection | N/A | Environmental, Access, AirOps | Advised via D. Bloomer that CKT has a section that is off limits to Air Ops (environmental) until ~August 2026. Per Air Ops on 5/13 there are Big Horn Sheep in the area and therefore it is off limits until August 2026. SCE has added a 120 day delay to the SLA date to account for this. These are staying in scope despite the delay |  | SCE Approved | N/A | 120 |  | Vegetation Management |  | N/A | Not Started |  |  |  | 10-01-2026 | Access Delay |  |  |  |  | 2026_ET-76438_ACQPKG | 2026_ET-76438_GSPKG | Submitted | 2026_ET-76438_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-76438_GCPR | 2025-12-08 | Historical | 2026_ET-76438_ACQ | In Progress | 2026_ET-76438_FR |  | Not Started | 2026_ET-76438_RWR | Not Started |  | 2026_ET-76438_CLAZ |  | Not Started |  |  |  | 2026_ET-76438_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-76438_WR |  |  | Not Started |  |  |  | 2026_ET-76438_VMLAZ |  | Not Started |  |  |  | 2026_ET-76438_VMM1 |  | Not Started |  |  |  |  | 2026_ET-76438_RR |  | Not Started | [6 empty] | 2026_ET-76438_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | CONTROL-SILVER PEAK-ZACK_ET-76438 |  |  | No |  |  | BISHOP/MAMMOTH | 85 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
IDLE VICTOR-CALECTRIC NO. 2 | ET-76847 | 2026_ET-76847 |  | 1 | 2026 | Jul 01, 2026 | 115 | CA_5 | 7 | 04-02-2026 | 04-17-2026 | 05-17-2026 | 06-01-2026 | 02-01-2026 | 03-03-2026 | 02-01-2026 | 03-03-2026 | On Time | 0 | Transmission | 17.6565 | 14.5328 | 82 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Idle Circuit | Daniel |  | 2026-04-14 | 04-02-2026 | Flown | 2026-02-01 | 04-15-2026 | 04-15-2026 |  | 2026_ET-76847_ACQPKG | 2026_ET-76847_GSPKG | Submitted | 2026_ET-76847_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-76847_GCPR | 2025-12-08 | Historical | 2026_ET-76847_ACQ | QC Accepted | 2026_ET-76847_FR | 2026-04-02 | Submitted | 2026_ET-76847_RWR | Submitted | 2026-04-02 | 2026_ET-76847_CLAZ | 2026-04-02 | QC Accepted | 04-17-2026 | 2026-04-15 | 0 | 2026_ET-76847_PROCPKG | QC Accepted | All Good - Complete | 2026_ET-76847_WR | 2026-05-14 | 05-15-2026 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-76847_VMLAZ | 2026-05-11 | QC Accepted | 06-01-2026 | 2026-05-20 |  | 2026_ET-76847_VMM1 | 2026-05-11 | QC Accepted |  | 06-01-2026 | 2026-05-20 |  | 2026_ET-76847_RR | 2026-05-11 | No Violations | 05-21-2026 |  | 98 | 2026-05-14 |  | 0 | 2026_ET-76847_VER | 2026-05-11 | Uploaded to S123 | 06-01-2026 | 2026-05-21 | [5 empty] | Completed On Time - Program | Completed On Time | Completed On Time - Program | IDLE VICTOR-CALECTRIC NO. 2_ET-76847 |  |  | No |  |  | VICTORVILLE | 73 | UNK | 2026-02-01 08:26 PST ¦ 2026-03-18 13:13 PDT | 020126 | 20260318 | [7 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-CALECTRIC | ET-77750 | 2026_ET-77750 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 5.0327 | 0.87522 | 17 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-77750_ACQPKG | 2026_ET-77750_GSPKG | Submitted | 2026_ET-77750_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-77750_GCPR | 2025-12-08 | Historical | 2026_ET-77750_ACQ | In Progress | 2026_ET-77750_FR |  | Not Started | 2026_ET-77750_RWR | Not Started |  | 2026_ET-77750_CLAZ |  | Not Started |  |  |  | 2026_ET-77750_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-77750_WR |  |  | Not Started |  |  |  | 2026_ET-77750_VMLAZ |  | Not Started |  |  |  | 2026_ET-77750_VMM1 |  | Not Started |  |  |  |  | 2026_ET-77750_RR |  | Not Started | [6 empty] | 2026_ET-77750_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-CALECTRIC_ET-77750 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-HIGHGROVE NO. 1 | ET-77753 | 2026_ET-77753 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.0061 | 0.71894 | 36 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-77753_ACQPKG | 2026_ET-77753_GSPKG | Submitted | 2026_ET-77753_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-77753_GCPR | 2025-12-08 | Historical | 2026_ET-77753_ACQ | In Progress | 2026_ET-77753_FR |  | Not Started | 2026_ET-77753_RWR | Not Started |  | 2026_ET-77753_CLAZ |  | Not Started |  |  |  | 2026_ET-77753_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-77753_WR |  |  | Not Started |  |  |  | 2026_ET-77753_VMLAZ |  | Not Started |  |  |  | 2026_ET-77753_VMM1 |  | Not Started |  |  |  |  | 2026_ET-77753_RR |  | Not Started | [6 empty] | 2026_ET-77753_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-HIGHGROVE NO. 1_ET-77753 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
VISTA-HIGHGROVE NO. 2 | ET-77754 | 2026_ET-77754 |  | 1 | 2026 | Dec 01, 2026 | 115 | CA_5 | 12 | 09-02-2026 | 09-17-2026 | 10-17-2026 | 11-01-2026 | 07-04-2026 | 08-03-2026 | 07-04-2026 | 08-03-2026 | On Time | 0 | Transmission | 2.0466 | 0.77963 | 38 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_01 | 2025-10-09 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 09-02-2026 | Not Started |  |  |  |  | 2026_ET-77754_ACQPKG | 2026_ET-77754_GSPKG | Submitted | 2026_ET-77754_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-77754_GCPR | 2025-12-08 | Historical | 2026_ET-77754_ACQ | In Progress | 2026_ET-77754_FR |  | Not Started | 2026_ET-77754_RWR | Not Started |  | 2026_ET-77754_CLAZ |  | Not Started |  |  |  | 2026_ET-77754_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-77754_WR |  |  | Not Started |  |  |  | 2026_ET-77754_VMLAZ |  | Not Started |  |  |  | 2026_ET-77754_VMM1 |  | Not Started |  |  |  |  | 2026_ET-77754_RR |  | Not Started | [6 empty] | 2026_ET-77754_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected On Time | Projected On Time | VISTA-HIGHGROVE NO. 2_ET-77754 |  |  | No |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
OCASO-SANDLOT | ET-00322 | 2026_ET-00322 |  | 1 | 2026 | May 01, 2026 | 220 | CA_5 | 5 | 01-31-2026 | 02-15-2026 | 03-17-2026 | 04-01-2026 | 12-02-2025 | 01-01-2026 | 01-13-2026 | 02-12-2026 | Late | 42 | Transmission | 0.052487 | 0 | 0 | 2025 Vegetation Management Transmission | 2026_Air Ops | 2026-01-12 | 2026_Neara_CWA_01 |  | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 03-14-2026 | Flown | 2025-12-21 |  | 05-11-2026 |  | 2026_ET-00322_ACQPKG | 2026_ET-00322_GSPKG | Submitted | 2026_ET-00322_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-00322_GCPR | 2025-12-08 | Historical | 2026_ET-00322_ACQ | QC Accepted | 2026_ET-00322_FR |  | Not Started | 2026_ET-00322_RWR | Submitted | 2026-05-09 | 2026_ET-00322_CLAZ | 2026-05-09 | QC Accepted | 05-23-2026 | 2026-05-11 |  | 2026_ET-00322_PROCPKG | In Progress | SCE | 2026_ET-00322_WR |  |  | Not Started |  |  |  | 2026_ET-00322_VMLAZ |  | Not Started |  |  |  | 2026_ET-00322_VMM1 |  | Not Started |  |  |  |  | 2026_ET-00322_RR |  | Not Started | [6 empty] | 2026_ET-00322_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Completed Late - Program | OCASO-SANDLOT_ET-00322 |  |  | Yes |  |  | BARSTOW | 72 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
BORAX-HOLGATE | ET-01871 | 2026_ET-01871 |  | 1 | 2026 | Jun 01, 2026 | 115 | CA_5 | 6 | 03-03-2026 | 03-18-2026 | 04-17-2026 | 05-02-2026 | 01-02-2026 | 02-01-2026 | 01-13-2026 | 02-12-2026 | Late | 11 | Transmission | 0.04497 | 0 | 0 | 2025 Vegetation Management Transmission | 2026_Air Ops | 2026-01-12 | 2026_Neara_CWA_01 |  | 2026_TCS_CWA_01 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  | 03-14-2026 | Access Delay |  |  |  |  | 2026_ET-01871_ACQPKG | 2026_ET-01871_GSPKG | Submitted | 2026_ET-01871_GS | 2025-12-08 | Historical Data Leveraged | 2026_ET-01871_GCPR | 2025-12-08 | Historical | 2026_ET-01871_ACQ | In Progress | 2026_ET-01871_FR |  | Not Started | 2026_ET-01871_RWR | Not Started |  | 2026_ET-01871_CLAZ |  | Not Started |  |  |  | 2026_ET-01871_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-01871_WR |  |  | Not Started |  |  |  | 2026_ET-01871_VMLAZ |  | Not Started |  |  |  | 2026_ET-01871_VMM1 |  | Not Started |  |  |  |  | 2026_ET-01871_RR |  | Not Started | [6 empty] | 2026_ET-01871_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Projected Late | BORAX-HOLGATE_ET-01871 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
Bellefield-Windhub | ET-02062 | 2026_ET-02062 | [NORTH VALLEY] | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-19-2026 | 04-23-2026 | Late | 15 | Transmission | 0.13721 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_03 | 2026-03-18 | 2026_SAM_CWA_03 | 2026-03-18 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | SCE | N/A | GCP | N/A | Access | Folders not available in GCP when SAM attempted to upload. |  | SCE Approved | N/A | 5 |  |  |  | N/A | Not Started |  |  |  | 05-23-2026 | Flown | 2026-04-22 |  | 05-21-2026 |  | 2026_ET-02062_ACQPKG | 2026_ET-02062_GSPKG | Submitted | 2026_ET-02062_GS | 2026-04-25 | Field Complete | 2026_ET-02062_GCPR | 2026-05-05 | Submitted | 2026_ET-02062_ACQ | QC Accepted | 2026_ET-02062_FR | 2026-05-05 | Submitted | 2026_ET-02062_RWR | Submitted | 2026-05-05 | 2026_ET-02062_CLAZ | 2026-05-05 | QC Accepted | 05-19-2026 | 2026-05-21 |  | 2026_ET-02062_PROCPKG | In Progress | SCE | 2026_ET-02062_WR |  |  | Not Started |  |  |  | 2026_ET-02062_VMLAZ |  | Not Started |  |  |  | 2026_ET-02062_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02062_RR |  | Not Started | [6 empty] | 2026_ET-02062_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Completed Late - Program |  |  |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
Eldorado-Poleta Springs | ET-02166 | 2026_ET-02166 | [RURALS] | 1 | 2026 | Aug 01, 2026 | 220 | NV_E | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-19-2026 | 04-23-2026 | Late | 15 | Transmission | 0.26226 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_03 | 2026-03-18 | 2026_SAM_CWA_03 | 2026-03-18 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | SCE | N/A | GCP | N/A | Access | Folders not available in GCP when SAM attempted to upload. |  | SCE Approved | N/A | 5 |  |  |  | N/A | Not Started |  |  |  | 05-23-2026 | Flown | 2026-04-26 |  | 05-20-2026 |  | 2026_ET-02166_ACQPKG | 2026_ET-02166_GSPKG | Submitted | 2026_ET-02166_GS | 2026-04-25 | Field Complete | 2026_ET-02166_GCPR | 2026-05-05 | Submitted | 2026_ET-02166_ACQ | QC Accepted | 2026_ET-02166_FR | 2026-05-05 | Submitted | 2026_ET-02166_RWR | Submitted | 2026-05-05 | 2026_ET-02166_CLAZ | 2026-05-05 | QC Accepted | 05-19-2026 | 2026-05-20 |  | 2026_ET-02166_PROCPKG | In Progress | SCE | 2026_ET-02166_WR |  |  | Not Started |  |  |  | 2026_ET-02166_VMLAZ |  | Not Started |  |  |  | 2026_ET-02166_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02166_RR |  | Not Started | [6 empty] | 2026_ET-02166_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Projected Late | Completed Late - Program |  |  |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
La Fresa-Lighthipe | ET-02265 | 2026_ET-02265 | [METRO WEST] | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-19-2026 | 04-23-2026 | Late | 15 | Transmission | 18.7249 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_03 | 2026-03-18 | 2026_SAM_CWA_03 | 2026-03-18 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | SCE | N/A | GCP | N/A | Access | Folders not available in GCP when SAM attempted to upload. |  | SCE Approved | N/A | 5 |  |  |  | N/A | Not Started |  |  |  | 05-23-2026 | Flown | 2026-03-24 |  | 05-21-2026 |  | 2026_ET-02265_ACQPKG | 2026_ET-02265_GSPKG | Submitted | 2026_ET-02265_GS | 2026-04-25 | Field Complete | 2026_ET-02265_GCPR | 2026-05-05 | Submitted | 2026_ET-02265_ACQ | QC Accepted | 2026_ET-02265_FR | 2026-05-05 | Submitted | 2026_ET-02265_RWR | Submitted | 2026-05-05 | 2026_ET-02265_CLAZ | 2026-05-05 | QC Accepted | 05-19-2026 | 2026-05-21 |  | 2026_ET-02265_PROCPKG | In Progress | SCE | 2026_ET-02265_WR |  |  | Not Started |  |  |  | 2026_ET-02265_VMLAZ |  | Not Started |  |  |  | 2026_ET-02265_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02265_RR |  | Not Started | [6 empty] | 2026_ET-02265_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed Late - Program |  |  |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
La Fresa-Mesa | ET-02264 | 2026_ET-02264 | [METRO WEST] | 1 | 2026 | Aug 01, 2026 | 220 | CA_5 | 8 | 05-03-2026 | 05-18-2026 | 06-17-2026 | 07-02-2026 | 03-04-2026 | 04-03-2026 | 03-19-2026 | 04-23-2026 | Late | 15 | Transmission | 30.6811 | 0 | 0 | 2026 Vegetation Management Transmission | 2026_SAM_CWA_03 | 2026-03-18 | 2026_SAM_CWA_03 | 2026-03-18 | 2026_GSI_QC_CWA_04 | 2026-03-26 | 2026_GSI_QC_CWA_04 | 2026-03-26 |  | Delay | No Delay | SCE | N/A | GCP | N/A | Access | Folders not available in GCP when SAM attempted to upload. |  | SCE Approved | N/A | 5 |  |  |  | N/A | Not Started |  |  |  | 05-23-2026 | Flown | 2026-03-24 |  | 05-22-2026 |  | 2026_ET-02264_ACQPKG | 2026_ET-02264_GSPKG | Submitted | 2026_ET-02264_GS | 2026-04-25 | Field Complete | 2026_ET-02264_GCPR | 2026-05-05 | Submitted | 2026_ET-02264_ACQ | QC Accepted | 2026_ET-02264_FR | 2026-05-05 | Submitted | 2026_ET-02264_RWR | Submitted | 2026-05-05 | 2026_ET-02264_CLAZ | 2026-05-05 | QC Accepted | 05-19-2026 | 2026-05-22 |  | 2026_ET-02264_PROCPKG | In Progress | SCE | 2026_ET-02264_WR |  |  | Not Started |  |  |  | 2026_ET-02264_VMLAZ |  | Not Started |  |  |  | 2026_ET-02264_VMM1 |  | Not Started |  |  |  |  | 2026_ET-02264_RR |  | Not Started | [6 empty] | 2026_ET-02264_VER |  | Not Started | [7 empty] | TBD - Pending Completion of ACQ Deliverables | Completed On Time | Completed Late - Program |  |  |  | Yes |  |  |  |  | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-HAIWEE-INYOKERN | ET-77245 | 2026_ET-77245 |  | 11 | 2026 |  | 115 | CA_4 | 0 | [9 empty] | NaN | Transmission | 127.066 | 17.4268 | 14 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_03 | 2026-01-09 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  |  | Removed From Scope | 2026-03-17 |  |  |  | 2026_ET-77245_ACQPKG | 2026_ET-77245_GSPKG | Submitted | 2026_ET-77245_GS | 2026-01-23 | Field Complete | 2026_ET-77245_GCPR | 2026-01-30 | Submitted | 2026_ET-77245_ACQ | In Progress | 2026_ET-77245_FR |  | N/A | 2026_ET-77245_RWR | N/A |  | 2026_ET-77245_CLAZ |  | N/A |  |  |  | 2026_ET-77245_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-77245_WR |  |  | N/A |  |  |  | 2026_ET-77245_VMLAZ |  | N/A |  |  |  | 2026_ET-77245_VMM1 |  | N/A |  |  |  |  | 2026_ET-77245_RR |  | N/A | [6 empty] | 2026_ET-77245_VER |  | N/A | [7 empty] | TBD - Pending Completion of ACQ Deliverables |  |  | CONTROL-HAIWEE-INYOKERN_ET-77245 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
CONTROL-COSO-HAIWEE-INYOKERN | ET-77246 | 2026_ET-77246 |  | 11 | 2026 |  | 115 | CA_4 | 0 | [9 empty] | NaN | Transmission | 127.0875 | 17.4493 | 14 | 2026 Vegetation Management Transmission | 2026_Air Ops | 2025-10-29 | 2026_Neara_CWA_01 | 2025-12-20 | 2026_GSI_QC_CWA_03 | 2026-01-09 | 2026_GSI_QC_CWA_01 | 2025-12-01 |  | No Delay | No Delay | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A |  |  | Vegetation Management |  | N/A | Not Started |  |  |  |  | Removed From Scope | 2026-03-17 |  |  |  | 2026_ET-77246_ACQPKG | 2026_ET-77246_GSPKG | Submitted | 2026_ET-77246_GS | 2026-01-23 | Field Complete | 2026_ET-77246_GCPR | 2026-01-30 | Submitted | 2026_ET-77246_ACQ | In Progress | 2026_ET-77246_FR |  | N/A | 2026_ET-77246_RWR | N/A |  | 2026_ET-77246_CLAZ |  | N/A |  |  |  | 2026_ET-77246_PROCPKG | In Progress | ACQ Vendor and SCE | 2026_ET-77246_WR |  |  | N/A |  |  |  | 2026_ET-77246_VMLAZ |  | N/A |  |  |  | 2026_ET-77246_VMM1 |  | N/A |  |  |  |  | 2026_ET-77246_RR |  | N/A | [6 empty] | 2026_ET-77246_VER |  | N/A | [7 empty] | TBD - Pending Completion of ACQ Deliverables |  |  | CONTROL-COSO-HAIWEE-INYOKERN_ET-77246 |  |  | No |  |  | RIDGECREST | 86 | UNK | [10 empty] | No Delay | No Delay | N/A | N/A | [6 empty] | N/A | N/A
|  |  |  | 1019 | 2064494 | 0 | 123478 |  | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | null |  | 11048.4561 | 4105.3148 | 26637 |  |  | 2025-10-08 to 2026-03-18 |  | 2025-12-20 to 2026-04-24 |  | 2025-12-01 to 2026-04-02 |  | 2025-12-01 to 2026-05-08 | [12 empty] | 1005 | 56 | [6 empty] | 2025-11-30 to 2026-05-21 | 0 |  | 2025-10-13 to 2026-05-09 | 0 | 0 |  | 0 | 0 | 0 | 0 | 2023-12-12 to 2026-04-25 |  | 0 | 2025-11-20 to 2026-05-22 |  | 0 | 0 | 0 | 2025-11-13 to 2026-05-22 |  | 0 |  | 2025-11-13 to 2026-05-22 | 0 | 2025-11-13 to 2026-05-22 |  | 0 | 2025-12-08 to 2026-05-22 | 41 | 0 | 0 | 0 | 0 | 2026-02-01 to 2026-05-21 | 0 |  | 0 | 2026-02-11 to 2026-05-25 | 44 | 0 | 2026-02-01 to 2026-05-12 |  | 0 | 2026-02-11 to 2026-05-25 | 41 | 0 | 2026-02-01 to 2026-05-21 |  |  | 0 | 2026-02-11 to 2026-05-25 | 44 | 0 | 2026-02-01 to 2026-05-21 |  | 0 | 0 | 1160 | 2026-02-02 to 2026-05-14 | 117 | 331 | 0 | 2026-02-01 to 2026-05-22 |  | 0 | 2026-02-17 to 2026-05-25 | 304 |  |  |  |  | 0 | 0 | 0 | [8 empty] | 0 | [22 empty] | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 91