## Cumulative Progress Summary
Type | Scope Month | Total circuits | Ready circuits | GIS 100% circuits | PC QA circuits | Scope Month miles (MB) | Actionable miles | Ready miles | GIS 100% miles | PC QA miles | Actionable % of Scope | % Ready (of Actionable) | % GIS 100% (of Actionable) | % PC QA (of Actionable)
Distribution | March | 335 | 317 | 334 | 0 | 2799.917 | 3688.85 | 3460.95 | 3681.11 | 0 | 131.7% | 93.82% | 99.79% | 0%
Transmission | March | 171 | 165 | 163 | 0 | 2378.775 | 2334.66 | 2114.15 | 2057.33 | 0 | 98.15% | 90.55% | 88.12% | 0%
Combined | March | 506 | 482 | 497 | 0 | 5178.692 | 6023.51 | 5575.1 | 5738.44 | 0 | 116.3% | 92.56% | 95.27% | 0%
Distribution | April | 239 | 239 | 239 | 0 | 2005.909 | 2005.9 | 2005.9 | 2005.9 | 0 | 100% | 100% | 100% | 0%
Transmission | April | 122 | 120 | 118 | 0 | 1386.59 | 1135.64 | 1068.92 | 1005.55 | 0 | 81.9% | 94.12% | 88.54% | 0%
Combined | April | 361 | 359 | 357 | 0 | 3392.499 | 3141.54 | 3074.82 | 3011.45 | 0 | 92.6% | 97.88% | 95.86% | 0%
Distribution | May | 246 | 246 | 246 | 0 | 2146.215 | 1859.58 | 1859.58 | 1859.58 | 0 | 86.64% | 100% | 100% | 0%
Transmission | May | 98 | 89 | 88 | 0 | 789.539 | 753.56 | 662.53 | 634.45 | 0 | 95.44% | 87.92% | 84.19% | 0%
Combined | May | 344 | 335 | 334 | 0 | 2935.754 | 2613.14 | 2522.11 | 2494.03 | 0 | 89.01% | 96.52% | 95.44% | 0%
Distribution | June | 202 | 202 | 202 | 0 | 2034.447 | 2034.48 | 2034.48 | 2034.48 | 0 | 100% | 100% | 100% | 0%
Transmission | June | 109 | 107 | 106 | 0 | 879.169 | 879.15 | 878.53 | 838.34 | 0 | 100% | 99.93% | 95.36% | 0%
Combined | June | 311 | 309 | 308 | 0 | 2913.617 | 2913.63 | 2913.01 | 2872.82 | 0 | 100% | 99.98% | 98.6% | 0%
Distribution | July | 282 | 281 | 282 | 0 | 3195.982 | 3103.28 | 3099.26 | 3103.28 | 0 | 97.1% | 99.87% | 100% | 0%
Transmission | July | 98 | 97 | 97 | 0 | 780.397 | 770.03 | 761.9 | 761.9 | 0 | 98.67% | 98.94% | 98.94% | 0%
Combined | July | 380 | 378 | 379 | 0 | 3976.38 | 3873.31 | 3861.16 | 3865.18 | 0 | 97.41% | 99.69% | 99.79% | 0%
Distribution | August | 285 | 57 | 44 | 0 | 2775.427 | 2693.11 | 750.83 | 570.56 | 0 | 97.03% | 27.88% | 21.19% | 0%
Transmission | August | 116 | 31 | 25 | 0 | 1229.994 | 1189.65 | 547.41 | 524.69 | 0 | 96.72% | 46.01% | 44.1% | 0%
Combined | August | 401 | 88 | 69 | 0 | 4005.421 | 3882.76 | 1298.24 | 1095.25 | 0 | 96.94% | 33.44% | 28.21% | 0%
Distribution | September | 0 | 0 | 0 | 0 | 1473.177 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0%
Transmission | September | 16 | 1 | 0 | 0 | 576.213 | 320.05 | 81.61 | 0 | 0 | 55.54% | 25.5% | 0% | 0%
Combined | September | 16 | 1 | 0 | 0 | 2049.389 | 320.05 | 81.61 | 0 | 0 | 15.62% | 25.5% | 0% | 0%
Distribution | October | 0 | 0 | 0 | 0 | 1148.129 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0%
Transmission | October | 4 | 0 | 0 | 0 | 159.987 | 33.83 | 0 | 0 | 0 | 21.15% | 0% | 0% | 0%
Combined | October | 4 | 0 | 0 | 0 | 1308.116 | 33.83 | 0 | 0 | 0 | 2.586% | 0% | 0% | 0%

## Daily Rate
Date | Type | Scope Month | Bucket | Miles | Circuits | Cumulative Miles
2026-01-01 | Distribution | March | Final review done | 102.28 | 2 | 102.28
2026-01-01 | Distribution | March | MB Check done | 45.15 | 3 | 45.15
2026-01-02 | Distribution | March | MB Check done | 71 | 2 | 116.15
2026-01-04 | Distribution | March | Final review done | 46.14 | 6 | 148.42
2026-01-04 | Distribution | March | MB Check done | 34.5 | 5 | 150.65
2026-01-05 | Distribution | March | Final review done | 112.04 | 10 | 260.46
2026-01-05 | Distribution | March | MB Check done | 149.91 | 16 | 300.56
2026-01-06 | Distribution | March | Final review done | 132.87 | 10 | 393.33
2026-01-06 | Distribution | March | MB Check done | 31.43 | 3 | 331.99
2026-01-06 | Transmission | March | MB Check done | 21.85 | 2 | 21.85
2026-01-07 | Distribution | March | Final review done | 174.54 | 15 | 567.87
2026-01-07 | Distribution | March | MB Check done | 113.55 | 8 | 445.54
2026-01-07 | Transmission | March | Final review done | 20.11 | 2 | 20.11
2026-01-07 | Transmission | March | MB Check done | 70.17 | 12 | 92.02
2026-01-08 | Distribution | March | Final review done | 92.54 | 11 | 660.41
2026-01-08 | Distribution | March | MB Check done | 13.56 | 2 | 459.1
2026-01-08 | Transmission | March | Final review done | 46.21 | 1 | 66.32
2026-01-08 | Transmission | March | MB Check done | 84.15 | 11 | 176.17
2026-01-09 | Transmission | March | MB Check done | 31.56 | 1 | 207.73
2026-01-10 | Transmission | March | MB Check done | 31.55 | 1 | 239.28
2026-01-11 | Distribution | March | Final review done | 21.45 | 2 | 681.86
2026-01-11 | Distribution | March | MB Check done | 12.33 | 1 | 471.43
2026-01-11 | Transmission | March | Final review done | 40.33 | 4 | 106.65
2026-01-11 | Transmission | March | MB Check done | 82.71 | 4 | 321.99
2026-01-12 | Transmission | March | Final review done | 13.66 | 3 | 120.31
2026-01-12 | Transmission | March | MB Check done | 41.54 | 5 | 363.53
2026-01-13 | Distribution | March | Final review done | 12.33 | 1 | 694.19
2026-01-13 | Transmission | March | Final review done | 42.6 | 9 | 162.91
2026-01-13 | Transmission | March | MB Check done | 14.08 | 1 | 377.61
2026-01-14 | Transmission | March | Final review done | 194.67 | 16 | 357.58
2026-01-14 | Transmission | March | MB Check done | 101.24 | 10 | 478.85
2026-01-15 | Transmission | March | Final review done | 114.77 | 15 | 472.35
2026-01-15 | Transmission | March | MB Check done | 150.71 | 27 | 629.56
2026-01-16 | Transmission | March | MB Check done | 9.98 | 1 | 639.54
2026-01-17 | Transmission | March | MB Check done | 88.39 | 11 | 727.93
2026-01-18 | Transmission | March | Final review done | 50.05 | 9 | 522.4
2026-01-18 | Transmission | March | MB Check done | 39.41 | 14 | 767.34
2026-01-19 | Transmission | March | Final review done | 69.71 | 31 | 592.11
2026-01-19 | Transmission | March | MB Check done | 10.4 | 2 | 777.74
2026-01-20 | Distribution | March | Final review done | 5.14 | 1 | 699.33
2026-01-21 | Distribution | March | Final review done | 28.09 | 1 | 727.42
2026-01-21 | Distribution | March | MB Check done | 170.68 | 7 | 642.11
2026-01-22 | Distribution | March | Final review done | 143.3 | 5 | 870.72
2026-01-22 | Distribution | March | MB Check done | 103.95 | 2 | 746.06
2026-01-22 | Transmission | March | Final review done | 18.95 | 2 | 611.06
2026-01-25 | Distribution | March | Final review done | 43.43 | 2 | 914.15
2026-01-25 | Distribution | March | MB Check done | 71.38 | 2 | 817.44
2026-01-25 | Transmission | March | Final review done | 26.19 | 1 | 637.25
2026-01-25 | Transmission | March | MB Check done | 0.13 | 1 | 777.87
2026-01-26 | Distribution | March | Final review done | 37.11 | 1 | 951.26
2026-01-26 | Distribution | March | MB Check done | 75.81 | 3 | 893.25
2026-01-26 | Transmission | March | Final review done | 70.22 | 3 | 707.47
2026-01-26 | Transmission | March | MB Check done | 16.86 | 3 | 794.73
2026-01-27 | Distribution | March | Final review done | 84.67 | 2 | 1035.93
2026-01-27 | Distribution | March | MB Check done | 90.48 | 5 | 983.73
2026-01-27 | Transmission | March | Final review done | 39.97 | 4 | 747.44
2026-01-28 | Distribution | March | Final review done | 61.35 | 4 | 1097.28
2026-01-28 | Distribution | March | MB Check done | 145.64 | 9 | 1129.37
2026-01-28 | Transmission | March | Final review done | 13.75 | 1 | 761.19
2026-01-29 | Distribution | March | Final review done | 177.55 | 5 | 1274.83
2026-01-29 | Distribution | March | MB Check done | 51.88 | 5 | 1181.25
2026-01-29 | Transmission | March | MB Check done | 1.72 | 1 | 796.45
2026-01-31 | Transmission | March | Final review done | 12.21 | 2 | 773.4
2026-01-31 | Transmission | March | MB Check done | 121.35 | 19 | 917.8
2026-02-01 | Distribution | March | MB Check done | 174.45 | 47 | 1355.7
2026-02-01 | Transmission | March | Final review done | 128.31 | 22 | 901.71
2026-02-02 | Distribution | March | Final review done | 263.73 | 54 | 1538.56
2026-02-02 | Distribution | March | MB Check done | 11.34 | 4 | 1367.04
2026-02-02 | Transmission | March | MB Check done | 709.72 | 16 | 1627.52
2026-02-03 | Distribution | March | Final review done | 56.38 | 10 | 1594.94
2026-02-03 | Distribution | March | MB Check done | 51.51 | 11 | 1418.55
2026-02-03 | Transmission | March | Final review done | 475.51 | 10 | 1377.22
2026-02-03 | Transmission | March | MB Check done | 198.35 | 11 | 1825.87
2026-02-04 | Distribution | March | Final review done | 48.01 | 2 | 1642.95
2026-02-04 | Distribution | March | MB Check done | 467.92 | 71 | 1886.47
2026-02-04 | Transmission | March | Final review done | 448.65 | 18 | 1825.87
2026-02-05 | Distribution | March | Final review done | 218.83 | 33 | 1861.78
2026-02-05 | Distribution | March | MB Check done | 227.74 | 42 | 2114.21
2026-02-05 | Transmission | March | MB Check done | 59.49 | 4 | 1885.36
2026-02-06 | Distribution | March | Final review done | 57.8 | 6 | 1919.58
2026-02-06 | Distribution | March | MB Check done | 51.68 | 25 | 2165.89
2026-02-06 | Transmission | March | Final review done | 59.49 | 4 | 1885.36
2026-02-08 | Distribution | March | Final review done | 446.26 | 98 | 2365.84
2026-02-08 | Distribution | March | MB Check done | 30.77 | 3 | 2196.66
2026-02-08 | Transmission | April | MB Check done | 6.67 | 1 | 6.67
2026-02-09 | Distribution | March | Final review done | 50.98 | 12 | 2416.82
2026-02-09 | Transmission | April | MB Check done | 7.24 | 1 | 13.91
2026-02-10 | Distribution | March | Final review done | 166.05 | 1 | 2582.87
2026-02-10 | Distribution | March | MB Check done | 166.05 | 1 | 2362.71
2026-02-10 | Transmission | April | Final review done | 43.87 | 9 | 43.87
2026-02-10 | Transmission | April | MB Check done | 49.59 | 14 | 63.5
2026-02-11 | Distribution | April | Final review done | 86.32 | 5 | 86.32
2026-02-11 | Distribution | April | MB Check done | 86.32 | 5 | 86.32
2026-02-11 | Transmission | April | Final review done | 110.88 | 16 | 154.75
2026-02-11 | Transmission | April | MB Check done | 161.28 | 11 | 224.78
2026-02-12 | Transmission | April | Final review done | 193.16 | 13 | 347.91
2026-02-12 | Transmission | April | MB Check done | 172.88 | 13 | 397.66
2026-02-13 | Transmission | April | MB Check done | 135.18 | 7 | 532.84
2026-02-14 | Transmission | April | MB Check done | 0.92 | 1 | 533.76
2026-02-15 | Distribution | April | MB Check done | 19.53 | 1 | 105.85
2026-02-15 | Transmission | April | MB Check done | 59.05 | 15 | 592.81
2026-02-16 | Distribution | April | Final review done | 147.36 | 5 | 233.68
2026-02-16 | Distribution | April | MB Check done | 187.92 | 16 | 293.77
2026-02-16 | Transmission | April | Final review done | 36.91 | 4 | 384.82
2026-02-16 | Transmission | April | MB Check done | 175.09 | 19 | 767.9
2026-02-17 | Distribution | April | Final review done | 216.31 | 17 | 449.99
2026-02-17 | Distribution | April | MB Check done | 250.19 | 18 | 543.96
2026-02-17 | Transmission | April | Final review done | 225.76 | 24 | 610.58
2026-02-17 | Transmission | April | MB Check done | 92.29 | 17 | 860.19
2026-02-18 | Distribution | April | Final review done | 195 | 29 | 644.99
2026-02-18 | Distribution | April | MB Check done | 122.45 | 20 | 666.41
2026-02-18 | Transmission | April | Final review done | 173.12 | 23 | 783.7
2026-02-18 | Transmission | April | MB Check done | 12.23 | 1 | 872.42
2026-02-19 | Distribution | April | Final review done | 254.52 | 21 | 899.51
2026-02-19 | Distribution | April | MB Check done | 245.17 | 18 | 911.58
2026-02-19 | Transmission | April | Final review done | 92.37 | 12 | 876.07
2026-02-19 | Transmission | April | MB Check done | 3.65 | 1 | 876.07
2026-02-20 | Distribution | April | MB Check done | 40.15 | 9 | 951.73
2026-02-20 | Transmission | April | MB Check done | 5.08 | 1 | 881.15
2026-02-21 | Distribution | April | MB Check done | 25.02 | 10 | 976.75
2026-02-22 | Distribution | April | Final review done | 260.54 | 48 | 1160.05
2026-02-22 | Distribution | April | MB Check done | 231.97 | 35 | 1208.72
2026-02-23 | Distribution | April | Final review done | 140.43 | 27 | 1300.48
2026-02-23 | Distribution | April | MB Check done | 239.6 | 41 | 1448.32
2026-02-24 | Distribution | April | Final review done | 192.32 | 28 | 1492.8
2026-02-24 | Distribution | April | MB Check done | 245.52 | 39 | 1693.84
2026-02-24 | Transmission | April | Final review done | 5.08 | 1 | 881.15
2026-02-25 | Distribution | April | Final review done | 229.53 | 35 | 1722.33
2026-02-25 | Distribution | April | MB Check done | 149.83 | 14 | 1843.67
2026-02-25 | Transmission | April | Final review done | 61.31 | 7 | 942.46
2026-02-25 | Transmission | April | MB Check done | 61.31 | 7 | 942.46
2026-02-25 | Transmission | June | Final review done | 20.54 | 3 | 20.54
2026-02-26 | Distribution | April | Final review done | 160.23 | 18 | 1882.56
2026-02-26 | Distribution | April | MB Check done | 157.86 | 12 | 2001.53
2026-02-26 | Transmission | April | Final review done | 13.09 | 1 | 955.55
2026-02-26 | Transmission | April | MB Check done | 13.09 | 1 | 955.55
2026-02-27 | Transmission | April | MB Check done | 17.39 | 2 | 972.94
2026-03-01 | Distribution | April | Final review done | 123.34 | 6 | 2005.9
2026-03-01 | Distribution | April | MB Check done | 4.37 | 1 | 2005.9
2026-03-01 | Transmission | April | Final review done | 17.91 | 3 | 973.46
2026-03-01 | Transmission | April | MB Check done | 0.52 | 1 | 973.46
2026-03-01 | Transmission | May | Final review done | 194.56 | 12 | 194.56
2026-03-01 | Transmission | May | MB Check done | 311.8 | 16 | 311.8
2026-03-02 | Distribution | May | Final review done | 105.88 | 4 | 105.88
2026-03-02 | Distribution | May | MB Check done | 142.89 | 6 | 142.89
2026-03-02 | Transmission | May | Final review done | 170.74 | 23 | 365.3
2026-03-02 | Transmission | May | MB Check done | 114.94 | 27 | 426.74
2026-03-03 | Distribution | May | Final review done | 188.06 | 17 | 293.94
2026-03-03 | Distribution | May | MB Check done | 151.05 | 15 | 293.94
2026-03-03 | Transmission | May | Final review done | 11.87 | 4 | 377.17
2026-03-03 | Transmission | May | MB Check done | 66.38 | 15 | 493.12
2026-03-04 | Distribution | May | Final review done | 69.9 | 11 | 363.84
2026-03-04 | Distribution | May | MB Check done | 69.9 | 11 | 363.84
2026-03-04 | Transmission | May | Final review done | 92.45 | 14 | 469.62
2026-03-04 | Transmission | May | MB Check done | 85.53 | 16 | 578.65
2026-03-05 | Distribution | May | Final review done | 4.56 | 1 | 368.4
2026-03-05 | Distribution | May | MB Check done | 210.58 | 9 | 574.42
2026-03-05 | Transmission | May | Final review done | 33.26 | 13 | 502.88
2026-03-05 | Transmission | May | MB Check done | 41.44 | 9 | 620.09
2026-03-06 | Transmission | May | Final review done | 22.26 | 3 | 525.14
2026-03-06 | Transmission | May | MB Check done | 9.45 | 1 | 629.54
2026-03-07 | Transmission | May | Final review done | 2.98 | 1 | 528.12
2026-03-07 | Transmission | May | MB Check done | 21.29 | 2 | 650.83
2026-03-08 | Distribution | May | Final review done | 302.56 | 12 | 670.96
2026-03-08 | Distribution | May | MB Check done | 179.78 | 10 | 754.2
2026-03-08 | Transmission | May | Final review done | 81.16 | 12 | 609.28
2026-03-08 | Transmission | May | MB Check done | 6.62 | 2 | 657.45
2026-03-09 | Distribution | May | Final review done | 129.67 | 10 | 800.63
2026-03-09 | Distribution | May | MB Check done | 149.92 | 18 | 904.12
2026-03-09 | Transmission | April | Final review done | 4.28 | 1 | 977.74
2026-03-09 | Transmission | May | Final review done | 11.3 | 4 | 620.58
2026-03-10 | Distribution | May | MB Check done | 128.56 | 23 | 1032.68
2026-03-10 | Transmission | May | Final review done | 8.79 | 1 | 629.37
2026-03-11 | Distribution | May | Final review done | 202.65 | 30 | 1003.28
2026-03-11 | Distribution | May | MB Check done | 270.47 | 35 | 1303.15
2026-03-12 | Distribution | May | Final review done | 210.39 | 39 | 1213.67
2026-03-12 | Distribution | May | MB Check done | 137.4 | 23 | 1440.55
2026-03-14 | Distribution | May | MB Check done | 19.84 | 1 | 1460.39
2026-03-15 | Distribution | May | Final review done | 205.96 | 14 | 1419.63
2026-03-15 | Distribution | May | MB Check done | 237.74 | 46 | 1698.13
2026-03-16 | Distribution | May | Final review done | 168.37 | 28 | 1588
2026-03-16 | Distribution | May | MB Check done | 40.13 | 13 | 1738.26
2026-03-17 | Distribution | May | Final review done | 16.07 | 26 | 1604.07
2026-03-17 | Distribution | May | MB Check done | 85.19 | 28 | 1823.45
2026-03-17 | Transmission | June | MB Check done | 79.47 | 6 | 79.47
2026-03-18 | Distribution | May | Final review done | 79.77 | 17 | 1683.84
2026-03-18 | Distribution | May | MB Check done | 36.13 | 8 | 1859.58
2026-03-18 | Transmission | June | MB Check done | 14.9 | 11 | 94.37
2026-03-19 | Distribution | June | MB Check done | 63.89 | 1 | 63.89
2026-03-19 | Distribution | May | Final review done | 136.89 | 23 | 1820.73
2026-03-19 | Transmission | April | Final review done | 0.19 | 1 | 977.93
2026-03-19 | Transmission | June | Final review done | 93.85 | 16 | 114.39
2026-03-19 | Transmission | June | MB Check done | 125.16 | 8 | 219.53
2026-03-20 | Distribution | May | Final review done | 22.61 | 10 | 1843.34
2026-03-21 | Transmission | June | Final review done | 11.71 | 3 | 126.1
2026-03-21 | Transmission | June | MB Check done | 16.59 | 4 | 236.12
2026-03-22 | Distribution | June | MB Check done | 112.96 | 5 | 176.85
2026-03-22 | Distribution | May | Final review done | 16.24 | 4 | 1859.58
2026-03-22 | Transmission | April | Final review done | 0.23 | 1 | 978.16
2026-03-22 | Transmission | April | MB Check done | 0.23 | 1 | 973.69
2026-03-22 | Transmission | June | Final review done | 135.55 | 13 | 261.65
2026-03-22 | Transmission | June | MB Check done | 288.26 | 20 | 524.38
2026-03-23 | Distribution | June | Final review done | 196.71 | 6 | 196.71
2026-03-23 | Distribution | June | MB Check done | 176.02 | 20 | 352.87
2026-03-23 | Distribution | March | Final review done | 1098.24 | 40 | 3681.11
2026-03-23 | Distribution | March | MB Check done | 1098.24 | 40 | 3460.95
2026-03-23 | Transmission | April | Final review done | 9.75 | 1 | 987.91
2026-03-23 | Transmission | April | MB Check done | 9.75 | 1 | 983.44
2026-03-23 | Transmission | June | Final review done | 234 | 15 | 495.65
2026-03-23 | Transmission | June | MB Check done | 86.93 | 24 | 611.31
2026-03-24 | Distribution | June | Final review done | 156.16 | 20 | 352.87
2026-03-24 | Distribution | June | MB Check done | 239.95 | 8 | 592.82
2026-03-24 | Transmission | June | Final review done | 121.4 | 28 | 617.05
2026-03-24 | Transmission | June | MB Check done | 92.59 | 17 | 703.9
2026-03-25 | Distribution | June | Final review done | 245.54 | 9 | 598.41
2026-03-25 | Distribution | June | MB Check done | 199.75 | 10 | 792.57
2026-03-25 | Transmission | June | Final review done | 36.55 | 9 | 653.6
2026-03-25 | Transmission | June | MB Check done | 5.98 | 2 | 709.88
2026-03-26 | Distribution | June | Final review done | 281.02 | 16 | 879.43
2026-03-26 | Distribution | June | MB Check done | 177.97 | 11 | 970.54
2026-03-26 | Transmission | April | MB Check done | 17.64 | 1 | 1001.08
2026-03-26 | Transmission | June | Final review done | 35.42 | 6 | 689.02
2026-03-26 | Transmission | June | MB Check done | 63.04 | 4 | 772.92
2026-03-29 | Distribution | June | Final review done | 254.69 | 31 | 1134.12
2026-03-29 | Distribution | June | MB Check done | 214.26 | 33 | 1184.8
2026-03-29 | Transmission | April | Final review done | 17.64 | 1 | 1005.55
2026-03-29 | Transmission | April | MB Check done | 4.47 | 2 | 1005.55
2026-03-29 | Transmission | June | Final review done | 17.97 | 7 | 706.99
2026-03-29 | Transmission | June | MB Check done | 17.97 | 7 | 790.89
2026-03-30 | Distribution | June | Final review done | 124.26 | 19 | 1258.38
2026-03-30 | Distribution | June | MB Check done | 137.98 | 24 | 1322.78
2026-03-31 | Distribution | June | Final review done | 132.15 | 21 | 1390.53
2026-03-31 | Distribution | June | MB Check done | 122.31 | 21 | 1445.09
2026-04-01 | Distribution | June | Final review done | 145.95 | 26 | 1536.48
2026-04-01 | Distribution | June | MB Check done | 114.48 | 25 | 1559.57
2026-04-02 | Distribution | June | Final review done | 57.44 | 14 | 1593.92
2026-04-02 | Distribution | June | MB Check done | 34.35 | 4 | 1593.92
2026-04-05 | Distribution | June | MB Check done | 45.2 | 4 | 1639.12
2026-04-06 | Distribution | June | MB Check done | 198.92 | 16 | 1838.04
2026-04-06 | Transmission | June | MB Check done | 25.72 | 1 | 816.61
2026-04-06 | Transmission | May | Final review done | 5.08 | 1 | 634.45
2026-04-06 | Transmission | May | MB Check done | 5.08 | 1 | 662.53
2026-04-07 | Distribution | June | Final review done | 171.02 | 10 | 1764.94
2026-04-07 | Distribution | June | MB Check done | 81.49 | 10 | 1919.53
2026-04-07 | Transmission | June | Final review done | 25.72 | 1 | 732.71
2026-04-08 | Distribution | June | Final review done | 109.39 | 16 | 1874.33
2026-04-09 | Distribution | June | Final review done | 45.2 | 4 | 1919.53
2026-04-09 | Distribution | June | MB Check done | 12.29 | 1 | 1931.82
2026-04-12 | Distribution | June | Final review done | 20.19 | 2 | 1939.72
2026-04-12 | Distribution | June | MB Check done | 7.9 | 1 | 1939.72
2026-04-13 | Distribution | June | Final review done | 68.53 | 1 | 2008.25
2026-04-13 | Distribution | June | MB Check done | 68.53 | 1 | 2008.25
2026-04-15 | Transmission | June | Final review done | 87.61 | 4 | 820.32
2026-04-15 | Transmission | June | MB Check done | 43.9 | 2 | 860.51
2026-04-19 | Distribution | July | MB Check done | 164.8 | 8 | 164.8
2026-04-20 | Distribution | July | Final review done | 190.03 | 10 | 190.03
2026-04-20 | Distribution | July | MB Check done | 375.93 | 23 | 540.73
2026-04-20 | Transmission | June | Final review done | 18.02 | 1 | 838.34
2026-04-20 | Transmission | June | MB Check done | 18.02 | 1 | 878.53
2026-04-21 | Distribution | July | Final review done | 386.1 | 23 | 576.13
2026-04-21 | Distribution | July | MB Check done | 189.14 | 11 | 729.87
2026-04-22 | Distribution | July | Final review done | 315.48 | 14 | 891.61
2026-04-22 | Distribution | July | MB Check done | 165.51 | 6 | 895.38
2026-04-22 | Transmission | July | Final review done | 9.75 | 4 | 9.75
2026-04-22 | Transmission | July | MB Check done | 9.75 | 4 | 9.75
2026-04-23 | Distribution | June | MB Check done | 26.23 | 7 | 2034.48
2026-04-23 | Transmission | July | MB Check done | 3.36 | 3 | 13.11
2026-04-26 | Distribution | July | MB Check done | 132.36 | 7 | 1027.74
2026-04-26 | Distribution | June | Final review done | 10.83 | 1 | 2019.08
2026-04-26 | Transmission | July | Final review done | 13.14 | 5 | 22.89
2026-04-26 | Transmission | July | MB Check done | 34.17 | 4 | 47.28
2026-04-27 | Distribution | July | Final review done | 104.95 | 4 | 996.56
2026-04-27 | Distribution | July | MB Check done | 111.84 | 7 | 1139.58
2026-04-27 | Distribution | June | Final review done | 8.7 | 5 | 2027.78
2026-04-27 | Transmission | July | Final review done | 24.39 | 2 | 47.28
2026-04-27 | Transmission | July | MB Check done | 96.71 | 14 | 143.99
2026-04-28 | Distribution | July | Final review done | 23.74 | 2 | 1020.3
2026-04-28 | Distribution | July | MB Check done | 86.48 | 16 | 1226.06
2026-04-28 | Distribution | June | Final review done | 6.7 | 1 | 2034.48
2026-04-28 | Transmission | July | Final review done | 36.95 | 8 | 84.23
2026-04-28 | Transmission | July | MB Check done | 27.35 | 4 | 171.34
2026-04-29 | Distribution | July | MB Check done | 106.41 | 20 | 1332.47
2026-04-29 | Transmission | July | Final review done | 141.15 | 15 | 225.38
2026-04-29 | Transmission | July | MB Check done | 90.29 | 8 | 261.63
2026-04-30 | Transmission | July | Final review done | 31.36 | 2 | 256.74
2026-05-03 | Distribution | July | Final review done | 140.23 | 12 | 1160.53
2026-05-03 | Distribution | July | MB Check done | 105.55 | 12 | 1438.02
2026-05-03 | Transmission | July | Final review done | 22.59 | 5 | 279.33
2026-05-03 | Transmission | July | MB Check done | 186.78 | 20 | 448.41
2026-05-04 | Distribution | July | Final review done | 161.72 | 39 | 1322.25
2026-05-04 | Distribution | July | MB Check done | 200.55 | 16 | 1638.57
2026-05-04 | Transmission | July | Final review done | 261.35 | 25 | 540.68
2026-05-04 | Transmission | July | MB Check done | 120.93 | 15 | 569.34
2026-05-05 | Distribution | July | Final review done | 305.2 | 21 | 1627.45
2026-05-05 | Distribution | July | MB Check done | 323.36 | 25 | 1961.93
2026-05-05 | Transmission | July | Final review done | 124.1 | 17 | 664.78
2026-05-05 | Transmission | July | MB Check done | 130.9 | 17 | 700.24
2026-05-05 | Transmission | September | MB Check done | 81.61 | 1 | 81.61
2026-05-06 | Distribution | July | Final review done | 315.53 | 29 | 1942.98
2026-05-06 | Distribution | July | MB Check done | 293.38 | 23 | 2255.31
2026-05-06 | Transmission | July | Final review done | 53.82 | 9 | 718.6
2026-05-06 | Transmission | July | MB Check done | 61.66 | 8 | 761.9
2026-05-07 | Distribution | July | Final review done | 143.75 | 21 | 2086.73
2026-05-07 | Distribution | July | MB Check done | 117.32 | 17 | 2372.63
2026-05-07 | Transmission | July | Final review done | 23.66 | 4 | 742.26
2026-05-09 | Distribution | July | MB Check done | 1.88 | 1 | 2374.51
2026-05-10 | Distribution | July | Final review done | 150.92 | 7 | 2237.65
2026-05-10 | Distribution | July | MB Check done | 254.61 | 25 | 2629.12
2026-05-10 | Transmission | July | Final review done | 19.64 | 1 | 761.9
2026-05-11 | Distribution | July | Final review done | 160.73 | 22 | 2398.38
2026-05-11 | Distribution | July | MB Check done | 260.74 | 37 | 2889.86
2026-05-12 | Distribution | July | Final review done | 178.05 | 25 | 2576.43
2026-05-12 | Distribution | July | MB Check done | 118.19 | 18 | 3008.05
2026-05-13 | Distribution | July | Final review done | 427.76 | 41 | 3004.19
2026-05-13 | Distribution | July | MB Check done | 52.66 | 8 | 3060.71
2026-05-14 | Distribution | July | Final review done | 99.09 | 12 | 3103.28
2026-05-14 | Distribution | July | MB Check done | 38.55 | 1 | 3099.26
2026-05-14 | Transmission | April | MB Check done | 63.37 | 2 | 1068.92
2026-05-18 | Distribution | August | MB Check done | 235.7 | 8 | 235.7
2026-05-18 | Transmission | August | Final review done | 186.85 | 3 | 186.85
2026-05-18 | Transmission | August | MB Check done | 283.2 | 12 | 283.2
2026-05-18 | Transmission | March | MB Check done | 56.82 | 2 | 1942.18
2026-05-19 | Distribution | August | Final review done | 99.29 | 3 | 99.29
2026-05-19 | Distribution | August | MB Check done | 212.54 | 24 | 448.24
2026-05-19 | Transmission | August | Final review done | 105.48 | 12 | 292.33
2026-05-19 | Transmission | August | MB Check done | 160.74 | 9 | 443.94
2026-05-20 | Distribution | August | Final review done | 248.77 | 25 | 348.06
2026-05-20 | Distribution | August | MB Check done | 17.12 | 3 | 465.36
2026-05-20 | Transmission | August | Final review done | 151.61 | 6 | 443.94
2026-05-20 | Transmission | August | MB Check done | 58.25 | 2 | 502.19
2026-05-21 | Distribution | August | Final review done | 222.5 | 16 | 570.56
2026-05-21 | Distribution | August | MB Check done | 281.46 | 21 | 746.82
2026-05-21 | Transmission | August | Final review done | 80.75 | 4 | 524.69
2026-05-21 | Transmission | August | MB Check done | 45.22 | 8 | 547.41
2026-05-22 | Distribution | August | MB Check done | 4.01 | 1 | 750.83
2026-09-01 | Transmission | March | Final review done | 171.97 | 6 | 2057.33
2026-09-01 | Transmission | March | MB Check done | 171.97 | 6 | 2114.15

## Per Circuit
Type | Scope Month | Circuit Name | Circuit ID | Mileage | MB Check done date | Final review done date | PC QA done date
Distribution | March | JORDAN | ED-09320 | 166.05 | 2026-02-10 | 2026-02-10
Distribution | March | RNOLES | ED-15221 | 11.53 |  | 2026-01-06
Distribution | March | CARATAN | ED-02950 | 41.48 | 2026-01-01 | 2026-01-01
Distribution | March | CASCADA | ED-03090 | 1.93 |  | 2026-01-05
Distribution | March | WELCH | ED-19140 | 60.8 |  | 2026-01-01
Distribution | March | BEAVER | ED-01360 | 34.27 | 2026-01-25 | 2026-01-29
Distribution | March | BURR | ED-02490 | 28.38 | 2026-01-28 | 2026-01-29
Distribution | March | CAIRNS | ED-02640 | 35.56 | 2026-01-26 | 2026-01-28
Distribution | March | CURTIS | ED-04510 | 44.36 | 2026-01-27 | 2026-01-29
Distribution | March | CUTLER | ED-04530 | 16.55 | 2026-01-21 | 2026-01-22
Distribution | March | DEER | ED-04770 | 59.81 | 2026-01-21 | 2026-01-27
Distribution | March | DORAN | ED-05210 | 24.86 | 2026-01-27 | 2026-01-27
Distribution | March | DUCOR | ED-05360 | 39.72 | 2026-01-21 | 2026-01-22
Distribution | March | GOPHER | ED-07445 | 33.42 | 2026-01-28 | 2026-01-29
Distribution | March | HATFIELD | ED-08161 | 11.26 | 2026-01-21 | 2026-01-22
Distribution | March | LINNELL | ED-10510 | 37.11 | 2026-01-25 | 2026-01-26
Distribution | March | OAKLAND | ED-12980 | 28.09 | 2026-01-21 | 2026-01-21
Distribution | March | TEAPOT | ED-17604 | 5.68 | 2026-01-21 | 2026-01-22
Distribution | March | VANDALIA | ED-18610 | 37.12 | 2026-01-29 | 2026-01-29
Distribution | March | ZION | ED-19830 | 9.57 | 2026-01-21 | 2026-01-25
Distribution | March | AMBERSKY | ED-00437 | 2.81 | 2026-01-05 | 2026-01-06
Distribution | March | ARMOUR | ED-00750 | 6.72 | 2026-01-07 | 2026-01-11
Distribution | March | AVANTI | ED-00888 | 3.79 | 2026-01-07 | 2026-01-07
Distribution | March | BRAKEMAN | ED-02136 | 8.55 | 2026-01-04 | 2026-01-05
Distribution | March | CHAMPION | ED-03319 | 1.04 | 2026-01-04 | 2026-01-06
Distribution | March | CHANTRY | ED-03335 | 14.24 | 2026-01-06 | 2026-01-07
Distribution | March | CIENIGITAS | ED-03510 | 12.33 | 2026-01-11 | 2026-01-13
Distribution | March | CORNWALL | ED-04075 | 6.86 | 2026-01-05 | 2026-01-07
Distribution | March | DEL CARBON | ED-04795 | 9.94 | 2026-01-08 | 2026-01-08
Distribution | March | ESTABAN | ED-06065 | 48.68 | 2026-01-02 | 2026-01-06
Distribution | March | GALAHAD | ED-06924 | 53.94 |  | 2026-01-05
Distribution | March | GARDEN | ED-07010 | 5.14 | 2026-01-07 | 2026-01-20
Distribution | March | GOLDSMITH | ED-07415 | 10.87 | 2026-01-06 | 2026-01-07
Distribution | March | GRANDAD | ED-07480 | 13.43 | 2026-01-05 | 2026-01-07
Distribution | March | GRIDLOCK | ED-07664 | 3.18 | 2026-01-05 | 2026-01-07
Distribution | March | GUTIERREZ | ED-07800 | 6.32 | 2026-01-06 | 2026-01-08
Distribution | March | HAMPSHIRE | ED-07928 | 21.53 | 2026-01-07 | 2026-01-07
Distribution | March | HELENA | ED-08300 | 7.11 | 2026-01-07 | 2026-01-08
Distribution | March | HOT SPRINGS | ED-08730 | 14.73 | 2026-01-07 | 2026-01-11
Distribution | March | INDEPENDENCE | ED-08912 | 2.28 | 2026-01-07 | 2026-01-08
Distribution | March | KWIS | ED-09885 | 12.2 | 2026-01-05 | 2026-01-07
Distribution | March | LA GRANDE | ED-09972 | 4.92 | 2026-01-05 | 2026-01-07
Distribution | March | LOPEZ | ED-10705 | 34.4 | 2026-01-05 | 2026-01-07
Distribution | March | MACIEL | ED-10871 | 1.46 | 2026-01-04 | 2026-01-08
Distribution | March | MAIZE | ED-10951 | 3.18 | 2026-01-05 | 2026-01-07
Distribution | March | MILLENNIUM | ED-11907 | 3.62 | 2026-01-08 | 2026-01-08
Distribution | March | MORGANSTEIN | ED-01354 | 22.32 | 2026-01-02 | 2026-01-06
Distribution | March | RACER | ED-14603 | 1.65 | 2026-01-04 | 2026-01-07
Distribution | March | RED MOUNTAIN | ED-14810 | 15.08 | 2026-01-05 | 2026-01-06
Distribution | March | ROCKHILL | ED-15307 | 24.5 | 2026-01-05 | 2026-01-07
Distribution | March | SAN NICHOLAS | ED-15828 | 13.18 | 2026-01-05 | 2026-01-07
Distribution | March | SEACLIFF | ED-16040 | 52.25 | 2026-01-07 | 2026-01-08
Distribution | March | SHORELINE | ED-12161 | 6.13 | 2026-01-05 | 2026-01-08
Distribution | March | TIN MINE | ED-17903 | 21.8 | 2026-01-04 | 2026-01-06
Distribution | March | VANDERLIP | ED-18613 | 1.43 | 2026-01-05 | 2026-01-08
Distribution | March | VASQUEZ | ED-18631 | 0.61 | 2026-01-05 | 2026-01-08
Distribution | March | WIGWAG | ED-19354 | 1.39 | 2026-01-05 | 2026-01-08
Distribution | March | WINTHROP | ED-19573 | 6.61 | 2026-01-05 | 2026-01-07
Distribution | March | MORITZ | ED-12190 | 22.39 | 2026-02-08 | 2026-02-08
Distribution | March | ABIGAIL | ED-00022 | 9.54 | 2026-02-04 | 2026-02-08
Distribution | March | ALAMEDA | ED-00220 | 8.05 | 2026-02-06 | 2026-02-08
Distribution | March | ALCOA | ED-00250 | 5.3 | 2026-02-04 | 2026-02-08
Distribution | March | ALLEGRA | ED-00324 | 70.09 | 2026-01-22 | 2026-01-22
Distribution | March | AMHERST | ED-00457 | 8.19 | 2026-02-05 | 2026-02-05
Distribution | March | ARBORVITAE | ED-00670 | 5.42 | 2026-02-06 | 2026-02-08
Distribution | March | ASTON | ED-00812 | 8.12 | 2026-02-04 | 2026-02-08
Distribution | March | AZURE | ED-00915 | 6.73 | 2026-02-05 | 2026-02-08
Distribution | March | BAMBOO | ED-01057 | 5.36 | 2026-02-04 | 2026-02-05
Distribution | March | BEARDSLEY | ED-01330 | 2.91 | 2026-02-04 | 2026-02-05
Distribution | March | BEONE | ED-01532 | 21.4 | 2026-02-04 | 2026-02-04
Distribution | March | BESSEMER | ED-01586 | 14.61 | 2026-02-04 | 2026-02-05
Distribution | March | BILL | ED-01656 | 3.88 | 2026-02-04 | 2026-02-05
Distribution | March | BITTERN | ED-01733 | 0.58 | 2026-02-04 | 2026-02-05
Distribution | March | BLUEWATER | ED-21056 | 0.01 | 2026-02-05 | 2026-02-08
Distribution | March | BOLAND | ED-01880 | 9.89 | 2026-02-04 | 2026-02-08
Distribution | March | BOSTON | ED-02020 | 4.64 | 2026-02-05 | 2026-02-08
Distribution | March | BOYALTA | ED-02064 | 2.05 | 2026-02-04 | 2026-02-05
Distribution | March | BRACKETT | ED-02100 | 5.59 | 2026-02-04 | 2026-02-05
Distribution | March | BUCK | ED-02358 | 0.13 | 2026-02-04 | 2026-02-08
Distribution | March | CEDAR | ED-03220 | 3.37 | 2026-02-08 | 2026-02-08
Distribution | March | CENTINELA | ED-03270 | 0.66 | 2026-02-05 | 2026-02-08
Distribution | March | CHANGE | ED-03328 | 17.06 | 2026-02-04 | 2026-02-05
Distribution | March | CLOVERFIELD | ED-03690 | 3.75 | 2026-02-05 | 2026-02-09
Distribution | March | COLBURN | ED-03763 | 5.09 | 2026-02-04 | 2026-02-05
Distribution | March | COLLEGE PARK | ED-03800 | 4.43 | 2026-02-04 | 2026-02-05
Distribution | March | CORBY | ED-04037 | 1.09 | 2026-02-04 | 2026-02-08
Distribution | March | CORVETTE | ED-04130 | 11.4 | 2026-02-05 | 2026-02-08
Distribution | March | COURSON | ED-04207 | 3.19 | 2026-02-05 | 2026-02-05
Distribution | March | CYRUS | ED-04561 | 0.63 | 2026-02-05 | 2026-02-08
Distribution | March | DEAUVILLE | ED-04730 | 0.08 | 2026-02-06 | 2026-02-08
Distribution | March | DIAMOND | ED-05060 | 4.34 | 2026-02-04 | 2026-02-08
Distribution | March | DIXON | ED-05130 | 8.11 | 2026-02-04 | 2026-02-05
Distribution | March | DROID | ED-05334 | 1.5 | 2026-02-04 | 2026-02-08
Distribution | March | DURWARD | ED-05466 | 1.05 | 2026-02-04 | 2026-02-05
Distribution | March | ELKO | ED-05730 | 1.7 | 2026-02-04 | 2026-02-08
Distribution | March | ENGLAND | ED-05950 | 1.36 | 2026-02-06 | 2026-02-08
Distribution | March | ENSIGN | ED-05980 | 3.42 | 2026-02-05 | 2026-02-08
Distribution | March | ESCALONA | ED-06042 | 2.49 | 2026-02-04 | 2026-02-08
Distribution | March | FAIRHAVEN | ED-06210 | 6.87 | 2026-02-04 | 2026-02-08
Distribution | March | FALLON | ED-06271 | 3.93 | 2026-02-05 | 2026-02-06
Distribution | March | FANWOOD | ED-06275 | 8.1 | 2026-02-04 | 2026-02-08
Distribution | March | FAUST | ED-06300 | 5.6 | 2026-02-04 | 2026-02-09
Distribution | March | FIFTH ST. | ED-06390 | 6.27 | 2026-02-04 | 2026-02-05
Distribution | March | FILLY | ED-06427 | 1.47 | 2026-02-05 | 2026-02-08
Distribution | March | FISHBURN | ED-06470 | 0.03 | 2026-02-05 | 2026-02-09
Distribution | March | FLASK | ED-06506 | 12.12 | 2026-02-05 | 2026-02-08
Distribution | March | FLEMING | ED-06520 | 4.76 | 2026-02-04 | 2026-02-08
Distribution | March | FORBID | ED-06636 | 11.66 | 2026-02-04 | 2026-02-08
Distribution | March | FORD | ED-06640 | 0.52 | 2026-02-05 | 2026-02-08
Distribution | March | GARD | ED-06992 | 2.36 | 2026-02-05 | 2026-02-08
Distribution | March | GEARLINE | ED-07134 | 1.9 | 2026-02-04 | 2026-02-08
Distribution | March | GEORGIAN | ED-07170 | 0.14 | 2026-02-06 | 2026-02-08
Distribution | March | GIZMO | ED-07269 | 3.51 | 2026-02-05 | 2026-02-05
Distribution | March | GLASGOW | ED-07290 | 3.84 | 2026-02-06 | 2026-02-08
Distribution | March | GRAYDON | ED-07520 | 17.61 | 2026-02-04 | 2026-02-08
Distribution | March | GUIRADO | ED-07740 | 0.13 | 2026-02-04 | 2026-02-08
Distribution | March | HALE | ED-07850 | 0.71 | 2026-02-05 | 2026-02-08
Distribution | March | HALLET | ED-07870 | 4.45 | 2026-02-05 | 2026-02-09
Distribution | March | HANDCAR | ED-07947 | 0.76 | 2026-02-04 | 2026-02-08
Distribution | March | HIMO | ED-08497 | 14.55 | 2026-02-04 | 2026-02-05
Distribution | March | HINDRY | ED-08460 | 3.33 | 2026-02-05 | 2026-02-09
Distribution | March | HOBART | ED-08500 | 14.61 | 2026-02-04 | 2026-02-06
Distribution | March | HOBO | ED-08507 | 1.21 | 2026-02-06 | 2026-02-08
Distribution | March | HONDO | ED-08660 | 3.6 | 2026-02-05 | 2026-02-08
Distribution | March | HOTPOINT | ED-08720 | 11.77 | 2026-02-04 | 2026-02-05
Distribution | March | IRISH | ED-08986 | 3.77 | 2026-02-05 | 2026-02-06
Distribution | March | IRWIN HTS | ED-09000 | 2.66 | 2026-02-06 | 2026-02-08
Distribution | March | JOJO | ED-09300 | 3.3 | 2026-02-04 | 2026-02-08
Distribution | March | JONES | ED-09310 | 3.74 | 2026-02-05 | 2026-02-09
Distribution | March | JUDAH | ED-09370 | 6.67 | 2026-02-04 | 2026-02-08
Distribution | March | JULEP | ED-09390 | 12.33 | 2026-02-05 | 2026-02-08
Distribution | March | KATHLEEN | ED-09474 | 5.59 | 2026-02-04 | 2026-02-08
Distribution | March | KELSEY | ED-09558 | 11.81 | 2026-02-05 | 2026-02-08
Distribution | March | KONOBIE | ED-09443 | 11.65 | 2026-02-04 | 2026-02-05
Distribution | March | KORNBLUM | ED-09840 | 5.01 | 2026-02-08 | 2026-02-08
Distribution | March | LA CUMBRE | ED-09960 | 5.08 | 2026-02-04 | 2026-02-05
Distribution | March | LASSEN | ED-10160 | 0.92 | 2026-02-06 | 2026-02-08
Distribution | March | LAWSON | ED-10251 | 0.09 | 2026-02-04 | 2026-02-08
Distribution | March | LEETUM | ED-10300 | 7.14 | 2026-02-04 | 2026-02-08
Distribution | March | LEONARD | ED-10380 | 1.86 | 2026-02-05 | 2026-02-08
Distribution | March | LIDUMS | ED-10453 | 6.43 | 2026-02-04 | 2026-02-08
Distribution | March | LIMING | ED-15702 | 8.36 | 2026-02-03 | 2026-02-05
Distribution | March | LUCIA | ED-10774 | 9.42 | 2026-02-04 | 2026-02-09
Distribution | March | MADISON | ED-10890 | 3.62 | 2026-02-05 | 2026-02-08
Distribution | March | MANUEL | ED-11110 | 3.16 | 2026-02-06 | 2026-02-08
Distribution | March | MARSHALL | ED-11280 | 6.56 | 2026-02-04 | 2026-02-09
Distribution | March | MCEWAN | ED-11480 | 1.72 | 2026-02-05 | 2026-02-08
Distribution | March | MEDICAL | ED-11580 | 4.37 | 2026-02-04 | 2026-02-09
Distribution | March | MIDGE | ED-11843 | 33.86 | 2026-01-22 | 2026-01-25
Distribution | March | MILER | ED-11888 | 3.32 | 2026-02-04 | 2026-02-05
Distribution | March | MINNOW | ED-11935 | 1.66 | 2026-02-06 | 2026-02-08
Distribution | March | MOLINO | ED-12070 | 4.63 | 2026-02-04 | 2026-02-08
Distribution | March | MYSTIC | ED-12460 | 2.7 | 2026-02-06 | 2026-02-08
Distribution | March | NAVY | ED-12560 | 5.9 | 2026-02-04 | 2026-02-09
Distribution | March | NINTH ST | ED-12720 | 0.2 | 2026-02-06 | 2026-02-08
Distribution | March | NISLEY | ED-12730 | 4.49 | 2026-02-05 | 2026-02-08
Distribution | March | NOGAL | ED-12772 | 3.17 | 2026-02-05 | 2026-02-05
Distribution | March | NORTHSIDE | ED-12870 | 3.12 | 2026-02-06 | 2026-02-08
Distribution | March | OPPORTUNITY | ED-13194 | 7.25 | 2026-02-04 | 2026-02-08
Distribution | March | PARKWAY | ED-13720 | 0.25 | 2026-02-04 | 2026-02-05
Distribution | March | PARMA | ED-13727 | 0.38 | 2026-02-06 | 2026-02-08
Distribution | March | PENGUIN | ED-13930 | 1.23 | 2026-02-06 | 2026-02-08
Distribution | March | PLYMOUTH | ED-14250 | 4.7 | 2026-02-04 | 2026-02-08
Distribution | March | QUAKER | ED-14550 | 4.36 | 2026-02-04 | 2026-02-05
Distribution | March | QUEBEC | ED-14570 | 6.8 | 2026-02-04 | 2026-02-08
Distribution | March | RANSOM | ED-14710 | 3.44 | 2026-02-05 | 2026-02-08
Distribution | March | RAYBORN | ED-14720 | 6.11 | 2026-02-04 | 2026-02-08
Distribution | March | REASONER | ED-14747 | 7.67 | 2026-02-04 | 2026-02-08
Distribution | March | RELISH | ED-14895 | 8.55 | 2026-02-05 | 2026-02-08
Distribution | March | RICHGROVE | ED-15010 | 26.61 | 2026-02-04 | 2026-02-04
Distribution | March | RICKO | ED-06364 | 7.74 | 2026-02-06
Distribution | March | SAGO | ED-15646 | 15.84 | 2026-02-05 | 2026-02-06
Distribution | March | SATELLITE | ED-15908 | 10.43 | 2026-02-05 | 2026-02-05
Distribution | March | SAYBROOK | ED-15972 | 4.28 | 2026-02-04 | 2026-02-08
Distribution | March | SEABASS | ED-16030 | 1.21 | 2026-02-06 | 2026-02-08
Distribution | March | SEAMAN | ED-16050 | 0.28 | 2026-02-06 | 2026-02-08
Distribution | March | SECURITY | ED-16090 | 0 | 2026-02-06 | 2026-02-09
Distribution | March | SEMORA | ED-16127 | 3.91 | 2026-02-05 | 2026-02-06
Distribution | March | SILVERSIDE | ED-16443 | 15.74 | 2026-02-05 | 2026-02-06
Distribution | March | SIXTEENTH ST. | ED-16470 | 0.95 | 2026-02-06 | 2026-02-08
Distribution | March | SMITH | ED-16558 | 2.41 | 2026-02-04 | 2026-02-08
Distribution | March | SPLENDORA | ED-16793 | 15.02 | 2026-02-05 | 2026-02-05
Distribution | March | SUNLIGHT | ED-17274 | 0 | 2026-02-06 | 2026-02-08
Distribution | March | SURFRIDER | ED-17353 | 0.6 | 2026-02-06 | 2026-02-08
Distribution | March | TAFT | ED-17471 | 1.6 | 2026-02-06 | 2026-02-08
Distribution | March | TEAK | ED-17601 | 2.5 | 2026-02-03 | 2026-02-08
Distribution | March | TEMPLE | ED-17660 | 3.1 | 2026-02-03 | 2026-02-08
Distribution | March | TERM | ED-17669 | 8.86 | 2026-02-03 | 2026-02-08
Distribution | March | TERMINAL | ED-17670 | 1.06 | 2026-02-04 | 2026-02-08
Distribution | March | TERRADELL | ED-17676 | 16.47 | 2026-01-28 | 2026-02-02
Distribution | March | TEVIS | ED-17701 | 3.27 | 2026-02-03 | 2026-02-08
Distribution | March | TICHENOR | ED-17817 | 10.26 | 2026-02-03 | 2026-02-08
Distribution | March | TICKET | ED-10653 | 6.94 | 2026-02-04 | 2026-02-08
Distribution | March | TIPPERARY | ED-17907 | 3.76 | 2026-02-03 | 2026-02-08
Distribution | March | TIROS | ED-17913 | 20.04 | 2026-02-04 | 2026-02-05
Distribution | March | TORCHLIGHT | ED-17980 | 12.81 | 2026-02-04 | 2026-02-08
Distribution | March | TRACTOR | ED-18073 | 5.43 | 2026-02-03 | 2026-02-05
Distribution | March | TROY | ED-18200 | 3.98 | 2026-02-04 | 2026-02-08
Distribution | March | TUBE | ED-18245 | 3.1 | 2026-02-03 | 2026-02-08
Distribution | March | TURNOUT | ED-07109 | 7.45 | 2026-02-04 | 2026-02-05
Distribution | March | TWENTY SIX ST | ED-18360 | 0.58 | 2026-02-03 | 2026-02-08
Distribution | March | TYHARD | ED-18386 | 2.61 | 2026-02-04 | 2026-02-08
Distribution | March | VALNETT | ED-18560 | 5.54 | 2026-02-05 | 2026-02-08
Distribution | March | VANGUARD | ED-18614 | 3.17 | 2026-02-05 | 2026-02-05
Distribution | March | VIA HUERTO | ED-18718 | 0.61 | 2026-02-04 | 2026-02-05
Distribution | March | VICKI | ED-18727 | 10.3 | 2026-02-04 | 2026-02-08
Distribution | March | WADSWORTH | ED-18900 | 3.17 | 2026-02-06 | 2026-02-08
Distribution | March | WALNUT PARK | ED-18970 | 3.83 | 2026-02-05 | 2026-02-09
Distribution | March | WARD | ED-19000 | 5.53 | 2026-02-04 | 2026-02-08
Distribution | March | WILDCAT | ED-19373 | 13.45 | 2026-02-05 | 2026-02-08
Distribution | March | WINNER | ED-19545 | 2.29 | 2026-02-03 | 2026-02-05
Distribution | March | WOODROW | ED-19610 | 3.66 | 2026-02-05 | 2026-02-08
Distribution | March | WYOMING | ED-19696 | 5.19 | 2026-02-04 | 2026-02-08
Distribution | March | ACAPULCO | ED-00041 | 5.71 |  | 2026-01-04
Distribution | March | ARIEL | ED-00699 | 0.36 | 2026-01-01 | 2026-01-05
Distribution | March | BABYLON | ED-00921 | 4.29 |  | 2026-01-06
Distribution | March | BECKER | ED-01371 | 0.97 |  | 2026-01-05
Distribution | March | BLACKBURN | ED-01741 | 3.31 | 2026-01-01 | 2026-01-06
Distribution | March | BLACKFOOT | ED-01737 | 13.16 |  | 2026-01-05
Distribution | March | CANTINA | ED-02876 | 2.8 |  | 2026-01-05
Distribution | March | DEACON | ED-04723 | 14.35 |  | 2026-01-04
Distribution | March | ERIN | ED-06014 | 12.72 |  | 2026-01-04
Distribution | March | FACEMASK | ED-06173 | 0.59 |  | 2026-01-05
Distribution | March | FULLBACK | ED-06867 | 4.7 |  | 2026-01-05
Distribution | March | GRENADE | ED-07637 | 3.81 |  | 2026-01-04
Distribution | March | HELENKA | ED-08302 | 25.04 |  | 2026-01-05
Distribution | March | JADE | ED-11430 | 1 |  | 2026-01-04
Distribution | March | SAXOPHONE | ED-15971 | 2.01 |  | 2026-01-06
Distribution | March | TYPHOON | ED-18395 | 8.55 |  | 2026-01-04
Distribution | March | AGENA | ED-00118 | 0.84 | 2026-02-02 | 2026-02-02
Distribution | March | ALMOND | ED-00353 | 13.41 | 2026-01-28 | 2026-02-02
Distribution | March | ANGELA | ED-00548 | 0.05 | 2026-02-01 | 2026-02-03
Distribution | March | APACHE | ED-00625 | 2.44 | 2026-02-01 | 2026-02-03
Distribution | March | BAJA | ED-00978 | 7.19 | 2026-02-01 | 2026-02-03
Distribution | March | BEECHNUT | ED-01375 | 6.97 | 2026-02-01 | 2026-02-02
Distribution | March | BEERNUT | ED-01376 | 4.95 | 2026-01-29 | 2026-02-02
Distribution | March | BLACKHAWK | ED-01743 | 17.85 | 2026-01-26 | 2026-02-02
Distribution | March | CANOE | ED-02874 | 7.23 | 2026-02-01 | 2026-02-03
Distribution | March | CARRIBEAN | ED-03011 | 3.47 | 2026-01-29 | 2026-02-03
Distribution | March | CHARGERS | ED-03356 | 11.44 | 2026-02-01 | 2026-02-02
Distribution | March | CHEROKEE | ED-03403 | 22.4 | 2026-01-26 | 2026-01-28
Distribution | March | CHOCTAW | ED-03493 | 1.82 | 2026-02-01 | 2026-02-02
Distribution | March | CLAIR | ED-03580 | 2.47 | 2026-02-01 | 2026-02-02
Distribution | March | CLAUDIA | ED-03607 | 8.81 | 2026-02-01 | 2026-02-02
Distribution | March | CORNNUT | ED-04072 | 0.43 | 2026-02-01 | 2026-02-02
Distribution | March | CUBBON | ED-04490 | 0.72 | 2026-02-01 | 2026-02-02
Distribution | March | DANDELION | ED-04719 | 14.25 | 2026-01-28 | 2026-02-02
Distribution | March | DARWIN | ED-04695 | 3.11 | 2026-02-01 | 2026-02-02
Distribution | March | DINGY | ED-05083 | 4.59 | 2026-02-01 | 2026-02-02
Distribution | March | EAGLE | ED-05485 | 2.23 | 2026-01-29 | 2026-02-02
Distribution | March | EL CAMINO | ED-05638 | 0.36 | 2026-02-01 | 2026-02-02
Distribution | March | EXPLORER | ED-06171 | 0.41 | 2026-02-01 | 2026-02-02
Distribution | March | FILBERT | ED-06423 | 2.03 | 2026-02-01 | 2026-02-02
Distribution | March | FLINT | ED-06539 | 9.83 | 2026-02-01 | 2026-02-02
Distribution | March | GIRARD | ED-07266 | 11.94 | 2026-02-01 | 2026-02-02
Distribution | March | HAZELNUT | ED-08252 | 1.92 | 2026-02-01 | 2026-02-02
Distribution | March | HEWITT | ED-08368 | 0.03 | 2026-02-01 | 2026-02-02
Distribution | March | HOPI | ED-08691 | 1.94 | 2026-02-01 | 2026-02-02
Distribution | March | HUDSON | ED-08800 | 0.73 | 2026-02-01 | 2026-02-02
Distribution | March | KADICE | ED-09429 | 3.26 | 2026-02-01 | 2026-02-02
Distribution | March | KETCH | ED-09655 | 6.14 | 2026-02-01 | 2026-02-02
Distribution | March | LEAD | ED-10262 | 0.26 | 2026-02-01 | 2026-02-02
Distribution | March | MACADAMIA | ED-10866 | 1.51 | 2026-02-02 | 2026-02-02
Distribution | March | MAIN ST. | ED-10960 | 3.46 | 2026-02-01 | 2026-02-02
Distribution | March | MARDA | ED-11183 | 6.82 | 2026-02-01 | 2026-02-03
Distribution | March | MASSACHUSETTS | ED-11326 | 2.8 | 2026-02-01 | 2026-02-02
Distribution | March | MCKEEVER | ED-11496 | 16.75 | 2026-01-27 | 2026-02-02
Distribution | March | MONSOON | ED-12105 | 4.8 | 2026-02-01 | 2026-02-02
Distribution | March | OKLAHOMA | ED-13064 | 6.05 | 2026-02-01 | 2026-02-02
Distribution | March | ORBITER | ED-13249 | 8.3 | 2026-02-02 | 2026-02-03
Distribution | March | ORIOLE | ED-13252 | 11.04 | 2026-02-01 | 2026-02-02
Distribution | March | OUTRIGGER | ED-13358 | 6.77 | 2026-02-01 | 2026-02-02
Distribution | March | PARROT | ED-13734 | 0.72 | 2026-02-01 | 2026-02-02
Distribution | March | PECAN | ED-13875 | 2.38 | 2026-02-01 | 2026-02-02
Distribution | March | PISTACHIO | ED-14162 | 4.11 | 2026-01-29 | 2026-02-03
Distribution | March | PLUMOSA | ED-14245 | 6.07 | 2026-02-01 | 2026-02-03
Distribution | March | POKER | ED-14258 | 10.7 | 2026-02-01 | 2026-02-03
Distribution | March | QUARTER | ED-14567 | 0.69 | 2026-02-02 | 2026-02-02
Distribution | March | RAVEN | ED-14717 | 3.28 | 2026-02-01 | 2026-02-02
Distribution | March | RUMMY | ED-15545 | 1.87 | 2026-02-01 | 2026-02-02
Distribution | March | SEGERSTROM | ED-16105 | 0.3 | 2026-02-01 | 2026-02-02
Distribution | March | SIDNEY | ED-16420 | 1.02 | 2026-02-01 | 2026-02-02
Distribution | March | SIOUX | ED-16457 | 15.27 | 2026-01-28 | 2026-02-02
Distribution | March | SKIFF | ED-16485 | 1.88 | 2026-02-01 | 2026-02-02
Distribution | March | SNAPDRAGON | ED-16578 | 0.54 | 2026-02-01 | 2026-02-02
Distribution | March | SPARROW | ED-16739 | 0.07 | 2026-02-01 | 2026-02-02
Distribution | March | STUDENT | ED-17125 | 4.26 | 2026-02-01 | 2026-02-02
Distribution | March | TACOMA | ED-17470 | 0 | 2026-02-01 | 2026-02-02
Distribution | March | TETRIS | ED-17698 | 0.75 | 2026-02-01 | 2026-02-02
Distribution | March | TITANIUM | ED-17916 | 2.24 | 2026-01-27 | 2026-02-02
Distribution | March | TITTLE | ED-17914 | 9.93 | 2026-01-28 | 2026-02-02
Distribution | March | TUITION | ED-18255 | 2.27 | 2026-01-27 | 2026-01-28
Distribution | March | URANIUM | ED-18494 | 2.75 | 2026-02-01 | 2026-02-02
Distribution | March | VAN BROCKLIN | ED-18586 | 1.12 | 2026-01-28 | 2026-01-28
Distribution | March | YOUNGER | ED-19781 | 13.39 | 2026-01-28 | 2026-02-02
Distribution | March | KIRBY | ED-09782 | 8.57 | 2026-03-23 | 2026-03-23
Distribution | March | OVERLOOK | ED-13383 | 3.68 | 2026-03-23 | 2026-03-23
Distribution | March | STANFORD | ED-16926 | 6.13 | 2026-03-23 | 2026-03-23
Distribution | March | TRUMBLE | ED-18229 | 7.12 | 2026-03-23 | 2026-03-23
Distribution | March | WAITE | ED-18929 | 11.93 | 2026-03-23 | 2026-03-23
Distribution | March | AMETHYST | ED-00452 | 2.31 | 2026-03-23 | 2026-03-23
Distribution | March | BOOTLEGGER | ED-01954 | 83.05 | 2026-03-23 | 2026-03-23
Distribution | March | CALSTATE | ED-02751 | 3.82 | 2026-03-23 | 2026-03-23
Distribution | March | CRESTLINE | ED-04360 | 10.84 | 2026-03-23 | 2026-03-23
Distribution | March | JENKS LAKE | ED-09205 | 14.89 | 2026-03-23 | 2026-03-23
Distribution | March | SHASTA | ED-16281 | 15.04 | 2026-03-23 | 2026-03-23
Distribution | March | SPUR | ED-16825 | 0.96 | 2026-03-23 | 2026-03-23
Distribution | March | SWEETWATER | ED-17405 | 3.16 | 2026-03-23 | 2026-03-23
Distribution | March | WEESHA | ED-19132 | 3.76 | 2026-03-23 | 2026-03-23
Distribution | March | WHIP | ED-19243 | 11.66 | 2026-03-23 | 2026-03-23
Distribution | March | ZENDA | ED-19820 | 45.86 | 2026-03-23 | 2026-03-23
Distribution | March | MELVERE | ED-11627 | 10.3 | 2026-03-23 | 2026-03-23
Distribution | March | MINOR | ED-11938 | 11.18 | 2026-03-23 | 2026-03-23
Distribution | March | MURRAY | ED-12383 | 0.39 | 2026-03-23 | 2026-03-23
Distribution | March | QUARTERBACK | ED-14569 | 1.47 | 2026-03-23 | 2026-03-23
Distribution | March | CIMARRON | ED-03515 | 12.36 | 2026-03-23 | 2026-03-23
Distribution | March | HYDE PARK | ED-08860 | 5.6 | 2026-03-23 | 2026-03-23
Distribution | March | KNOLLS | ED-09828 | 17.83 | 2026-03-23 | 2026-03-23
Distribution | March | LAKOTA | ED-10005 | 16.68 | 2026-03-23 | 2026-03-23
Distribution | March | LARREA | ED-10124 | 21.82 | 2026-03-23 | 2026-03-23
Distribution | March | MARIANNA | ED-11211 | 28.02 | 2026-03-23 | 2026-03-23
Distribution | March | MARK | ED-11216 | 2.58 | 2026-03-23 | 2026-03-23
Distribution | March | MELODY | ED-11625 | 320.78 | 2026-03-23 | 2026-03-23
Distribution | March | NORTH ADOBE | ED-12815 | 25.63 | 2026-03-23 | 2026-03-23
Distribution | March | OLD DALE | ED-13083 | 0.1 | 2026-03-23 | 2026-03-23
Distribution | March | PEARLAND | ED-13870 | 3.27 | 2026-03-23 | 2026-03-23
Distribution | March | RABBIT | ED-14598 | 87.21 | 2026-03-23 | 2026-03-23
Distribution | March | SLUICE | ED-16554 | 5.48 | 2026-03-23 | 2026-03-23
Distribution | March | SMOKE TREE | ED-16575 | 20.37 | 2026-03-23 | 2026-03-23
Distribution | March | STING | ED-16997 | 0.35 | 2026-03-23 | 2026-03-23
Distribution | March | SUNFAIR | ED-10040 | 79.56 | 2026-03-23 | 2026-03-23
Distribution | March | SUNNYVALE | ED-17282 | 61.51 | 2026-03-23 | 2026-03-23
Distribution | March | SYMERON | ED-17437 | 18.07 | 2026-03-23 | 2026-03-23
Distribution | March | TIMCO | ED-17885 | 72.83 | 2026-03-23 | 2026-03-23
Distribution | March | UTAH | ED-18496 | 42.07 | 2026-03-23 | 2026-03-23
Distribution | April | MCGEE | ED-11493 | 18.71 | 2026-02-11 | 2026-02-11
Distribution | April | NORDIC | ED-12798 | 0.13 | 2026-02-11 | 2026-02-11
Distribution | April | SAGEHEN | ED-15634 | 42.93 | 2026-02-11 | 2026-02-11
Distribution | April | STEVENSON | ED-17010 | 24.08 | 2026-02-11 | 2026-02-11
Distribution | April | VULCAN | ED-18874 | 0.47 | 2026-02-11 | 2026-02-11
Distribution | April | BANYAN | ED-01078 | 4.37 | 2026-03-01 | 2026-03-01
Distribution | April | BURTON | ED-02510 | 19.53 | 2026-02-15 | 2026-02-16
Distribution | April | DRAG | ED-05307 | 3.86 | 2026-02-16 | 2026-02-16
Distribution | April | ELSTER | ED-05850 | 56.34 | 2026-02-16 | 2026-02-16
Distribution | April | MCCLENNY | ED-11448 | 2.34 | 2026-02-16 | 2026-02-16
Distribution | April | SKINKLE | ED-16490 | 65.29 | 2026-02-16 | 2026-02-16
Distribution | April | SODA SPRINGS | ED-16600 | 135.94 | 2026-02-17 | 2026-02-17
Distribution | April | DE CAMP | ED-04735 | 2.48 | 2026-02-26 | 2026-02-26
Distribution | April | DELTA | ED-04890 | 18.13 | 2026-02-25 | 2026-02-26
Distribution | April | DEMAREE | ED-04905 | 2.78 | 2026-02-26 | 2026-02-26
Distribution | April | DIAMANTE | ED-05063 | 1 | 2026-02-25 | 2026-02-26
Distribution | April | DRAKE | ED-05310 | 29.99 | 2026-02-26 | 2026-03-01
Distribution | April | DUNGAN | ED-05400 | 9.47 | 2026-02-26 | 2026-03-01
Distribution | April | EDENDALE | ED-05600 | 11.12 | 2026-02-26 | 2026-02-26
Distribution | April | FAIRLAWN | ED-06220 | 0.12 | 2026-02-26 | 2026-02-26
Distribution | April | KINSMAN | ED-09778 | 0.16 | 2026-02-26 | 2026-02-26
Distribution | April | MCDERMONT | ED-11476 | 24.08 | 2026-02-25 | 2026-02-26
Distribution | April | ORANGE BLOSSOM | ED-13201 | 38.99 | 2026-02-25 | 2026-02-26
Distribution | April | ROUND VALLEY | ED-15470 | 6.99 | 2026-02-25 | 2026-02-26
Distribution | April | TARUSA | ED-17560 | 21.75 | 2026-02-26 | 2026-02-26
Distribution | April | TWIN BUTTE | ED-18366 | 73.11 | 2026-02-26 | 2026-03-01
Distribution | April | ANTONE | ED-00580 | 8.17 | 2026-02-21 | 2026-02-22
Distribution | April | BAHAMA | ED-00977 | 9.83 | 2026-02-22 | 2026-02-22
Distribution | April | BASS | ED-01203 | 4.08 | 2026-02-22 | 2026-02-22
Distribution | April | BILLINGS | ED-01660 | 0.54 | 2026-02-21 | 2026-02-22
Distribution | April | BLUEMOON | ED-01841 | 2.19 | 2026-02-22 | 2026-02-22
Distribution | April | BOHEMIA | ED-01873 | 0.96 | 2026-02-22 | 2026-02-22
Distribution | April | BORDER | ED-01974 | 4.82 | 2026-02-22 | 2026-02-22
Distribution | April | BRAVES | ED-02155 | 0.04 | 2026-02-21 | 2026-02-22
Distribution | April | BULLDOG | ED-02409 | 1.35 | 2026-02-22 | 2026-02-22
Distribution | April | BUSHARD | ED-02531 | 12.52 | 2026-02-22 | 2026-02-22
Distribution | April | CADDY | ED-02615 | 2.85 | 2026-02-22 | 2026-02-22
Distribution | April | CALICO | ED-02676 | 17.36 | 2026-02-22 | 2026-02-22
Distribution | April | CHEYENNE | ED-03442 | 7.85 | 2026-02-22 | 2026-02-22
Distribution | April | CHIPPER | ED-03486 | 1.43 | 2026-02-22 | 2026-02-22
Distribution | April | CLOVER | ED-03688 | 22.94 | 2026-02-22 | 2026-02-22
Distribution | April | DALLAS | ED-04620 | 13.88 | 2026-02-20 | 2026-02-22
Distribution | April | DANA | ED-04633 | 1.06 | 2026-02-22 | 2026-02-22
Distribution | April | DE MARI | ED-04895 | 3.81 | 2026-02-21 | 2026-02-22
Distribution | April | DOVER | ED-05270 | 3.91 | 2026-02-21 | 2026-02-22
Distribution | April | FOXGLOVE | ED-06701 | 1.65 | 2026-02-22 | 2026-02-22
Distribution | April | GOLDWATER | ED-07418 | 0.4 | 2026-02-20 | 2026-02-22
Distribution | April | GREENBAY | ED-07576 | 2.22 | 2026-02-22 | 2026-02-22
Distribution | April | GUINNESS | ED-07738 | 2.85 | 2026-02-22 | 2026-02-22
Distribution | April | HUSKIE | ED-08855 | 0.09 | 2026-02-20 | 2026-02-22
Distribution | April | INDIANAPOLIS | ED-08911 | 11.55 | 2026-02-22 | 2026-02-22
Distribution | April | JOAQUIN | ED-09270 | 0.86 | 2026-02-21 | 2026-02-22
Distribution | April | LECHE | ED-10276 | 0.57 | 2026-02-20 | 2026-02-22
Distribution | April | LORNA | ED-10719 | 4.15 | 2026-02-22 | 2026-02-22
Distribution | April | OILWELL | ED-13080 | 0.15 | 2026-02-21 | 2026-02-22
Distribution | April | OMAHA | ED-13160 | 15.14 | 2026-02-22 | 2026-02-22
Distribution | April | PACIFICA | ED-13469 | 6 | 2026-02-22 | 2026-02-22
Distribution | April | PLATINUM | ED-14191 | 0.29 | 2026-02-20 | 2026-02-22
Distribution | April | POLLARD | ED-14290 | 2.66 | 2026-02-22 | 2026-02-22
Distribution | April | RAIDERS | ED-14641 | 14.76 | 2026-02-22 | 2026-02-22
Distribution | April | RAMSGATE | ED-14661 | 1.33 | 2026-02-20 | 2026-02-22
Distribution | April | ROUGH | ED-15465 | 2.07 | 2026-02-22 | 2026-02-22
Distribution | April | SAINTS | ED-15645 | 3.26 | 2026-02-20 | 2026-02-22
Distribution | April | SIAM | ED-16408 | 2.06 | 2026-02-22 | 2026-02-22
Distribution | April | STAR ROCK | ED-16936 | 3.18 | 2026-02-22 | 2026-02-22
Distribution | April | SUGAR | ED-17180 | 10.31 | 2026-02-22 | 2026-02-22
Distribution | April | SUNFLOWER | ED-17260 | 0.08 | 2026-02-21 | 2026-02-22
Distribution | April | VERA CRUZ | ED-18650 | 11.11 | 2026-02-20 | 2026-02-22
Distribution | April | WACO | ED-18880 | 5.12 | 2026-02-21 | 2026-02-22
Distribution | April | WAINWRIGHT | ED-18927 | 2.41 | 2026-02-22 | 2026-02-22
Distribution | April | WARRIORS | ED-19028 | 12.7 | 2026-02-22 | 2026-02-22
Distribution | April | WILLETS | ED-19410 | 15.47 | 2026-02-22 | 2026-02-22
Distribution | April | WISCONSIN | ED-19576 | 6.17 | 2026-02-22 | 2026-02-22
Distribution | April | YORBA | ED-19751 | 2.34 | 2026-02-21 | 2026-02-22
Distribution | April | ANTON | ED-01344 | 29.92 | 2026-02-19 | 2026-02-19
Distribution | April | CARVER | ED-03060 | 48.65 | 2026-02-19 | 2026-02-19
Distribution | April | CASPER | ED-03100 | 3.78 | 2026-02-19 | 2026-02-19
Distribution | April | CODE | ED-03720 | 5.52 | 2026-02-19 | 2026-02-19
Distribution | April | DEL REY | ED-04875 | 6.91 | 2026-02-19 | 2026-02-19
Distribution | April | DIABLO | ED-05055 | 11.02 | 2026-02-19 | 2026-02-19
Distribution | April | EAST CITY | ED-05500 | 2.54 | 2026-02-19 | 2026-02-19
Distribution | April | FELLOWSHIP | ED-06315 | 5.39 | 2026-02-19 | 2026-02-19
Distribution | April | GABBERT | ED-06888 | 9.22 | 2026-02-20 | 2026-02-19
Distribution | April | HOSPITAL | ED-08700 | 5.02 | 2026-02-19 | 2026-02-19
Distribution | April | LEXINGTON | ED-10410 | 3.09 | 2026-02-19 | 2026-02-19
Distribution | April | LOMA VISTA | ED-10662 | 0.01 | 2026-02-18 | 2026-02-19
Distribution | April | MALOY | ED-11015 | 9.66 | 2026-02-19 | 2026-02-19
Distribution | April | MILPAS | ED-11915 | 18.19 | 2026-02-19 | 2026-02-19
Distribution | April | PEARCE | ED-13866 | 7.08 | 2026-02-19 | 2026-02-19
Distribution | April | RAMAC | ED-14652 | 26.83 | 2026-02-19 | 2026-02-19
Distribution | April | READY | ED-14740 | 12.81 | 2026-02-19 | 2026-02-19
Distribution | April | SAN ANDREAS | ED-15710 | 0.12 | 2026-02-18 | 2026-02-19
Distribution | April | SEXTON | ED-16220 | 29.2 | 2026-02-19 | 2026-02-19
Distribution | April | TELOMA | ED-17640 | 6.04 | 2026-02-19 | 2026-02-19
Distribution | April | VINEYARD | ED-18780 | 13.52 | 2026-02-19 | 2026-02-19
Distribution | April | AIRCRAFT | ED-00170 | 1.84 | 2026-02-16 | 2026-02-17
Distribution | April | ANGELINA | ED-00550 | 7.01 | 2026-02-16 | 2026-02-17
Distribution | April | ASHLAND | ED-00800 | 2.22 | 2026-02-16 | 2026-02-17
Distribution | April | BIG ROCK | ED-01630 | 15.59 | 2026-02-16 | 2026-02-17
Distribution | April | BLIMP | ED-01808 | 23.14 | 2026-02-17 | 2026-02-17
Distribution | April | BUFFER | ED-02390 | 6.97 | 2026-02-16 | 2026-02-17
Distribution | April | BURMA | ED-02470 | 8.11 | 2026-02-17 | 2026-02-18
Distribution | April | CATALINA | ED-03150 | 8.02 | 2026-02-18 | 2026-02-18
Distribution | April | CELLO | ED-03257 | 1.61 | 2026-02-17 | 2026-02-18
Distribution | April | CHADRON | ED-03305 | 6.35 | 2026-02-17 | 2026-02-18
Distribution | April | CHELSEA | ED-03400 | 3.13 | 2026-02-16 | 2026-02-17
Distribution | April | CLIFTON | ED-03660 | 6.24 | 2026-02-17 | 2026-02-18
Distribution | April | CORAL | ED-04032 | 4.57 | 2026-02-17 | 2026-02-17
Distribution | April | COURTLAND | ED-04220 | 2.1 | 2026-02-18 | 2026-02-18
Distribution | April | DELAWARE | ED-04810 | 6.24 | 2026-02-18 | 2026-02-18
Distribution | April | FRANKLIN | ED-06730 | 0.27 | 2026-02-17 | 2026-02-18
Distribution | April | GATEWAY | ED-07110 | 3.01 | 2026-02-17 | 2026-02-17
Distribution | April | GRANDVIEW | ED-07470 | 7.33 | 2026-02-18 | 2026-02-18
Distribution | April | GRAVEYARD | ED-07560 | 5.26 | 2026-02-18 | 2026-02-18
Distribution | April | GRIZZLEY | ED-07660 | 14.84 | 2026-02-18 | 2026-02-18
Distribution | April | HELIUM | ED-08301 | 3.24 | 2026-02-18 | 2026-02-18
Distribution | April | HOSS | ED-08707 | 3.09 | 2026-02-18 | 2026-02-18
Distribution | April | JUNEAU | ED-09410 | 5.22 | 2026-02-17 | 2026-02-17
Distribution | April | KANSAS | ED-09460 | 5.75 | 2026-02-17 | 2026-02-18
Distribution | April | MEADOWS | ED-11540 | 0.05 | 2026-02-16 | 2026-02-17
Distribution | April | MORELAND | ED-12175 | 8.47 | 2026-02-18 | 2026-02-18
Distribution | April | NELSON | ED-12590 | 8.11 | 2026-02-18 | 2026-02-18
Distribution | April | NEON | ED-12615 | 5.88 | 2026-02-17 | 2026-02-18
Distribution | April | NOMAD | ED-12776 | 0.91 | 2026-02-16 | 2026-02-17
Distribution | April | PARMAN | ED-13728 | 10.46 | 2026-02-18 | 2026-02-18
Distribution | April | PISTON | ED-14158 | 11.47 | 2026-02-18 | 2026-02-18
Distribution | April | PURDUE | ED-14496 | 6.79 | 2026-02-18 | 2026-02-18
Distribution | April | REGENT | ED-14870 | 0.87 | 2026-02-16 | 2026-02-17
Distribution | April | SALMON | ED-15670 | 11.97 | 2026-02-18 | 2026-02-18
Distribution | April | SHOWCASE | ED-16381 | 4.83 | 2026-02-18 | 2026-02-18
Distribution | April | SORRENTO | ED-16695 | 0.55 | 2026-02-18 | 2026-02-18
Distribution | April | STRAWBERRY | ED-17110 | 3.03 | 2026-02-17 | 2026-02-18
Distribution | April | TENOR | ED-17664 | 8.6 | 2026-02-18 | 2026-02-18
Distribution | April | TORSON | ED-18010 | 0.95 | 2026-02-18 | 2026-02-18
Distribution | April | TRUMPET | ED-18234 | 30.82 | 2026-02-17 | 2026-02-18
Distribution | April | TWENTY THREE ST | ED-18323 | 0.22 | 2026-02-17 | 2026-02-17
Distribution | April | TWENTY TWO ST | ED-18322 | 0.21 | 2026-02-16 | 2026-02-17
Distribution | April | WALGROVE | ED-18930 | 3.59 | 2026-02-17 | 2026-02-18
Distribution | April | YALE | ED-19720 | 1.03 | 2026-02-17 | 2026-02-18
Distribution | April | ZEPPELIN | ED-19827 | 5.41 | 2026-02-17 | 2026-02-17
Distribution | April | AMOS | ED-00470 | 5.27 | 2026-02-16 | 2026-02-24
Distribution | April | ANTWERP | ED-00590 | 4.46 | 2026-02-24 | 2026-02-25
Distribution | April | ATHERTON | ED-00820 | 5.55 | 2026-02-24 | 2026-02-25
Distribution | April | ATLANTIC | ED-00830 | 16.02 | 2026-02-16 | 2026-02-24
Distribution | April | BENNETT | ED-01500 | 8.94 | 2026-02-25 | 2026-02-25
Distribution | April | BENTREE | ED-01530 | 5.95 | 2026-02-24 | 2026-02-25
Distribution | April | BERNARD | ED-01560 | 1.54 | 2026-02-24 | 2026-02-25
Distribution | April | BORT | ED-01980 | 5.83 | 2026-02-24 | 2026-02-25
Distribution | April | BOULEVARD | ED-02030 | 4.03 | 2026-02-24 | 2026-02-25
Distribution | April | BOYLE | ED-02080 | 0.48 | 2026-02-26 | 2026-02-26
Distribution | April | CANEHILL | ED-02857 | 5.88 | 2026-02-24 | 2026-02-25
Distribution | April | CARFAX | ED-02920 | 5.62 | 2026-02-24 | 2026-02-24
Distribution | April | CODY | ED-03731 | 2.42 | 2026-02-24 | 2026-02-25
Distribution | April | CONANT | ED-03880 | 7.58 | 2026-02-25 | 2026-02-25
Distribution | April | CONCOURSE | ED-03903 | 11.8 | 2026-02-24 | 2026-02-25
Distribution | April | COYOTE | ED-04250 | 7.42 | 2026-02-25 | 2026-02-26
Distribution | April | CRUSADE | ED-04450 | 7.72 | 2026-02-24 | 2026-02-25
Distribution | April | DEVON | ED-05021 | 12.92 | 2026-02-24 | 2026-02-25
Distribution | April | DICKERSON | ED-05071 | 13.74 | 2026-02-25 | 2026-02-25
Distribution | April | DOLLAR | ED-05180 | 4.49 | 2026-02-25 | 2026-02-26
Distribution | April | FAIRMAN | ED-06230 | 7.6 | 2026-02-25 | 2026-02-25
Distribution | April | FREELAND | ED-06750 | 2.29 | 2026-02-25 | 2026-02-25
Distribution | April | GARFORD | ED-06995 | 4.52 | 2026-02-24 | 2026-02-24
Distribution | April | HEREFORD | ED-08344 | 3.87 | 2026-02-24 | 2026-02-25
Distribution | April | JESSUP | ED-09240 | 4.08 | 2026-02-24 | 2026-02-25
Distribution | April | KOBE | ED-09850 | 3.16 | 2026-02-24 | 2026-02-25
Distribution | April | LATCHFORD | ED-10180 | 3.62 | 2026-02-24 | 2026-02-26
Distribution | April | LEFFINGWELL | ED-10310 | 19.46 | 2026-02-24 | 2026-02-25
Distribution | April | MILES | ED-11890 | 2.46 | 2026-02-24 | 2026-02-25
Distribution | April | MILLERGROVE | ED-11911 | 14.16 | 2026-02-24 | 2026-02-25
Distribution | April | MOORE | ED-12165 | 4.63 | 2026-02-24 | 2026-02-24
Distribution | April | NESTLE | ED-12618 | 0.32 | 2026-02-23 | 2026-02-24
Distribution | April | NORWALK | ED-12886 | 2.18 | 2026-02-24 | 2026-02-25
Distribution | April | OAK | ED-12940 | 0.22 | 2026-02-24 | 2026-02-24
Distribution | April | PEABODY | ED-13840 | 5.22 | 2026-02-24 | 2026-02-25
Distribution | April | PLATT | ED-14180 | 6.31 | 2026-02-24 | 2026-02-25
Distribution | April | RELIEF | ED-14893 | 13.11 | 2026-02-24 | 2026-02-25
Distribution | April | ROCKET | ED-15310 | 3.95 | 2026-02-24 | 2026-02-25
Distribution | April | SATURN | ED-15910 | 2.13 | 2026-02-24 | 2026-02-24
Distribution | April | SCHOOL | ED-15990 | 2.53 | 2026-02-24 | 2026-02-25
Distribution | April | SHIPWAY | ED-16355 | 6.17 | 2026-02-25 | 2026-02-26
Distribution | April | SOPER | ED-16672 | 3.95 | 2026-02-24 | 2026-02-25
Distribution | April | SPAULDING | ED-16750 | 2.41 | 2026-02-25 | 2026-02-26
Distribution | April | STUDEBAKER | ED-17120 | 10.77 | 2026-02-24 | 2026-02-25
Distribution | April | TATTOO | ED-17570 | 8.04 | 2026-02-24 | 2026-02-26
Distribution | April | TEXAS | ED-17710 | 11.1 | 2026-02-24 | 2026-02-25
Distribution | April | TUCKER | ED-18250 | 3.95 | 2026-02-24 | 2026-02-25
Distribution | April | UNION | ED-18410 | 2.49 | 2026-02-24 | 2026-02-25
Distribution | April | WATUSI | ED-19065 | 4.54 | 2026-02-24 | 2026-02-25
Distribution | April | ZEBU | ED-19812 | 3.99 | 2026-02-24 | 2026-02-25
Distribution | April | ALSTOT | ED-00405 | 0.59 | 2026-02-23 | 2026-02-23
Distribution | April | AMBRUS | ED-05275 | 6.16 | 2026-02-23 | 2026-02-24
Distribution | April | ARBORETUM | ED-00671 | 12.66 | 2026-02-23 | 2026-02-23
Distribution | April | BEECHWOOD | ED-01385 | 2.91 | 2026-02-22 | 2026-02-23
Distribution | April | BIANCO | ED-01604 | 10.38 | 2026-02-23 | 2026-02-23
Distribution | April | BOLOR | ED-01894 | 0.3 | 2026-02-22 | 2026-02-23
Distribution | April | CABOOSE | ED-02584 | 4.52 | 2026-02-22 | 2026-02-23
Distribution | April | CHUCKER | ED-03491 | 5.03 | 2026-02-23 | 2026-02-24
Distribution | April | COLGATE | ED-03782 | 10.3 | 2026-02-24 | 2026-02-24
Distribution | April | DANES | ED-04637 | 3.84 | 2026-02-23 | 2026-02-24
Distribution | April | DEANNA | ED-04725 | 15.26 | 2026-02-23 | 2026-02-24
Distribution | April | DEERFIELD | ED-04772 | 17.06 | 2026-02-24 | 2026-02-24
Distribution | April | DINER | ED-05086 | 7.01 | 2026-02-22 | 2026-02-23
Distribution | April | DOBBINS | ED-05135 | 5.1 | 2026-02-23 | 2026-02-24
Distribution | April | ELEMENTARY | ED-05683 | 1.56 | 2026-02-23 | 2026-02-23
Distribution | April | FERON | ED-06354 | 1.51 | 2026-02-23 | 2026-02-24
Distribution | April | FINCH | ED-06429 | 6.04 | 2026-02-23 | 2026-02-23
Distribution | April | FOXDALE | ED-06700 | 0.41 | 2026-02-23 | 2026-02-23
Distribution | April | FRISBIE | ED-06833 | 7.26 | 2026-02-23 | 2026-02-24
Distribution | April | FURY | ED-06886 | 0.21 | 2026-02-23 | 2026-02-23
Distribution | April | GLORIA | ED-07375 | 5.06 | 2026-02-23 | 2026-02-23
Distribution | April | GREY | ED-07654 | 1.52 | 2026-02-23 | 2026-02-23
Distribution | April | GUEST | ED-07720 | 5.23 | 2026-02-23 | 2026-02-23
Distribution | April | GURNEY | ED-07795 | 2.17 | 2026-02-23 | 2026-02-24
Distribution | April | HONEYWELL | ED-08662 | 8.79 | 2026-02-23 | 2026-02-24
Distribution | April | JAYBIRD | ED-09189 | 3.39 | 2026-02-23 | 2026-02-23
Distribution | April | LIMA | ED-10470 | 3.02 | 2026-02-23 | 2026-02-23
Distribution | April | LOWELL | ED-10730 | 5.08 | 2026-02-23 | 2026-02-23
Distribution | April | LYTLE | ED-10855 | 3.62 | 2026-02-23 | 2026-02-24
Distribution | April | MALLET | ED-11012 | 8.83 | 2026-02-23 | 2026-02-24
Distribution | April | MARENGO | ED-11190 | 1.15 | 2026-02-23 | 2026-02-23
Distribution | April | MEDAL | ED-11563 | 14.67 | 2026-02-23 | 2026-02-23
Distribution | April | MELARA | ED-11613 | 0.99 | 2026-02-23 | 2026-02-23
Distribution | April | MOHAWK | ED-12050 | 5.36 | 2026-02-23 | 2026-02-23
Distribution | April | NOMEX | ED-12781 | 9.45 | 2026-02-23 | 2026-02-24
Distribution | April | OMEGA | ED-13164 | 25.68 | 2026-02-23 | 2026-02-24
Distribution | April | REDBALL | ED-14754 | 0.79 | 2026-02-23 | 2026-02-24
Distribution | April | ROSWELL | ED-15460 | 5.72 | 2026-02-23 | 2026-02-24
Distribution | April | SILO | ED-16436 | 1.23 | 2026-02-23 | 2026-02-24
Distribution | April | TERRA | ED-17673 | 3.25 | 2026-02-23 | 2026-02-24
Distribution | April | TEST | ED-17690 | 11.87 | 2026-02-23 | 2026-02-23
Distribution | April | TIMES | ED-17890 | 2.66 | 2026-02-23 | 2026-02-23
Distribution | April | TOMMY | ED-17965 | 15.34 | 2026-02-23 | 2026-02-23
Distribution | April | TRESTLE | ED-18126 | 12.54 | 2026-02-23 | 2026-02-24
Distribution | April | TRI CITY | ED-18140 | 12.64 | 2026-02-22 | 2026-02-23
Distribution | April | WEEKS | ED-19133 | 5.67 | 2026-02-23 | 2026-02-23
Distribution | April | ZINSER | ED-19897 | 0.19 | 2026-02-23 | 2026-02-23
Distribution | April | CANCUN | ED-02848 | 3.4 | 2026-02-26 | 2026-03-01
Distribution | April | MAZATLAN | ED-11425 | 3 | 2026-02-26 | 2026-03-01
Distribution | May | BOBSLED | ED-01855 | 2.2 | 2026-03-04 | 2026-03-04
Distribution | May | CHATEAU | ED-03382 | 1.31 | 2026-03-04 | 2026-03-04
Distribution | May | CRAWFORD | ED-04284 | 0.63 | 2026-03-04 | 2026-03-04
Distribution | May | CROWLEY | ED-04433 | 14.73 | 2026-03-04 | 2026-03-04
Distribution | May | PICKLE MEADOWS | ED-14038 | 25.65 | 2026-03-04 | 2026-03-04
Distribution | May | SITZMARK | ED-16465 | 3.29 | 2026-03-04 | 2026-03-04
Distribution | May | SLALOM | ED-16515 | 0.95 | 2026-03-04 | 2026-03-04
Distribution | May | SLOPE | ED-16545 | 2.42 | 2026-03-04 | 2026-03-04
Distribution | May | SNOWDRIFT | ED-16592 | 1.87 | 2026-03-04 | 2026-03-04
Distribution | May | STROSNIDER | ED-17122 | 12.64 | 2026-03-04 | 2026-03-04
Distribution | May | TROUT | ED-18227 | 4.21 | 2026-03-04 | 2026-03-04
Distribution | May | AMY | ED-00475 | 0.64 | 2026-03-11 | 2026-03-12
Distribution | May | AZORES | ED-00905 | 13.18 | 2026-03-10 | 2026-03-11
Distribution | May | BARTLETT | ED-01180 | 1.69 | 2026-03-11 | 2026-03-11
Distribution | May | BAYSE | ED-01260 | 4.3 | 2026-03-11 | 2026-03-11
Distribution | May | BLACKGOLD | ED-01752 | 2.99 | 2026-03-09 | 2026-03-11
Distribution | May | CHELLA | ED-03388 | 16.34 | 2026-03-10 | 2026-03-11
Distribution | May | CLAYTON | ED-03610 | 16.33 | 2026-03-11 | 2026-03-12
Distribution | May | DENISE | ED-04925 | 11.62 | 2026-03-09 | 2026-03-11
Distribution | May | DUNKIRK | ED-05413 | 9.37 | 2026-03-09 | 2026-03-11
Distribution | May | ESTATES | ED-06070 | 4.52 | 2026-03-11 | 2026-03-11
Distribution | May | GERTRUDE | ED-07185 | 5.61 | 2026-03-09 | 2026-03-09
Distribution | May | GREGG | ED-07630 | 14.76 | 2026-03-10 | 2026-03-11
Distribution | May | IRENE | ED-08985 | 9.87 | 2026-03-09 | 2026-03-11
Distribution | May | JACMAR | ED-09100 | 0.03 | 2026-03-11 | 2026-03-11
Distribution | May | KENBO | ED-09570 | 3.77 | 2026-03-09 | 2026-03-11
Distribution | May | LAKE | ED-09980 | 1.17 | 2026-03-11 | 2026-03-11
Distribution | May | LAMANDA | ED-10020 | 16.02 | 2026-03-11 | 2026-03-11
Distribution | May | LAMBDA | ED-10027 | 18.84 | 2026-03-09 | 2026-03-11
Distribution | May | LYNNE | ED-10845 | 11.66 | 2026-03-09 | 2026-03-09
Distribution | May | MAYBELL | ED-11380 | 19.64 | 2026-03-10 | 2026-03-11
Distribution | May | MERVIN | ED-11750 | 2.67 | 2026-03-11 | 2026-03-11
Distribution | May | MOONBEAM | ED-12160 | 4.73 | 2026-03-11 | 2026-03-11
Distribution | May | MULBERRY | ED-12320 | 0.02 | 2026-03-11 | 2026-03-11
Distribution | May | MYRTLE | ED-12450 | 3.34 | 2026-03-09 | 2026-03-11
Distribution | May | NOEL | ED-12770 | 0.35 | 2026-03-11 | 2026-03-11
Distribution | May | OLDS | ED-13085 | 13.71 | 2026-03-09 | 2026-03-09
Distribution | May | PAT | ED-13776 | 10.39 | 2026-03-08 | 2026-03-09
Distribution | May | PECK | ED-13877 | 3.2 | 2026-03-10 | 2026-03-11
Distribution | May | POWDER | ED-14375 | 9.87 | 2026-03-09 | 2026-03-11
Distribution | May | PRIMROSE | ED-14410 | 18.09 | 2026-03-05 | 2026-03-09
Distribution | May | ROSEGLEN | ED-15423 | 11.72 | 2026-03-11 | 2026-03-11
Distribution | May | SACRAMENTO | ED-15610 | 0.02 | 2026-03-11 | 2026-03-11
Distribution | May | SAXON | ED-15970 | 3.99 | 2026-03-11 | 2026-03-11
Distribution | May | SHAMROCK | ED-16250 | 2.54 | 2026-03-10 | 2026-03-11
Distribution | May | TANGERINE | ED-17527 | 11.75 | 2026-03-10 | 2026-03-11
Distribution | May | WASH | ED-19033 | 15.45 | 2026-03-09 | 2026-03-09
Distribution | May | WEAVER | ED-19090 | 0.08 | 2026-03-10 | 2026-03-11
Distribution | May | WOODSIDE | ED-19640 | 0.26 | 2026-03-11 | 2026-03-11
Distribution | May | AIR | ED-00169 | 0.01 | 2026-03-15 | 2026-03-16
Distribution | May | AVERY | ED-00875 | 16.13 | 2026-03-11 | 2026-03-16
Distribution | May | BABCOCK | ED-00918 | 0 | 2026-03-15 | 2026-03-16
Distribution | May | BALLZAK | ED-01510 | 6.19 | 2026-03-12 | 2026-03-16
Distribution | May | BARILLA | ED-11041 | 6.07 | 2026-03-15 | 2026-03-16
Distribution | May | BLOWER | ED-01821 | 0.01 | 2026-03-12 | 2026-03-16
Distribution | May | CABRILLO | ED-02580 | 2.81 | 2026-03-16 | 2026-03-16
Distribution | May | CALVO | ED-02762 | 9.38 | 2026-03-15 | 2026-03-16
Distribution | May | CAMPUS | ED-02840 | 12.9 | 2026-03-11 | 2026-03-16
Distribution | May | COKER 1 | ED-03756 | 0 | 2026-03-15 | 2026-03-16
Distribution | May | COKER 2 | ED-03757 | 0 | 2026-03-15 | 2026-03-16
Distribution | May | COKER 3 | ED-03758 | 0 | 2026-03-16 | 2026-03-17
Distribution | May | COKER 4 | ED-03759 | 0.01 | 2026-03-15 | 2026-03-16
Distribution | May | COKER 5 | ED-03761 | 0 | 2026-03-15 | 2026-03-16
Distribution | May | CORDON | ED-04041 | 4.46 | 2026-03-16 | 2026-03-16
Distribution | May | CRENSHAW | ED-04320 | 6.69 | 2026-03-18 | 2026-03-18
Distribution | May | CRESCENT | ED-04330 | 0.01 | 2026-03-16 | 2026-03-16
Distribution | May | DARBY | ED-04660 | 5.11 | 2026-03-17 | 2026-03-18
Distribution | May | DESSAU | ED-05010 | 10.05 | 2026-03-12 | 2026-03-16
Distribution | May | DIGNAN | ED-05081 | 0 | 2026-03-17 | 2026-03-17
Distribution | May | DOANE | ED-05132 | 12.34 | 2026-03-15 | 2026-03-16
Distribution | May | EISENMANN | ED-05635 | 0.05 | 2026-03-17 | 2026-03-17
Distribution | May | ELLENWOOD | ED-05750 | 4.62 | 2026-03-15 | 2026-03-16
Distribution | May | FALLIS | ED-06270 | 0.82 | 2026-03-17 | 2026-03-17
Distribution | May | FELON | ED-06318 | 0.01 | 2026-03-15 | 2026-03-17
Distribution | May | FIRETHORN | ED-06455 | 7.72 | 2026-03-15 | 2026-03-16
Distribution | May | FORMOSA | ED-06665 | 4.62 | 2026-03-12 | 2026-03-16
Distribution | May | GELLENBECK | ED-07143 | 0.01 | 2026-03-15 | 2026-03-17
Distribution | May | GENERAL PETROLEUM | ED-07150 | 2.19 | 2026-03-12 | 2026-03-17
Distribution | May | GILMORE | ED-07260 | 2.62 | 2026-03-17 | 2026-03-18
Distribution | May | GIRDER | ED-07268 | 7.89 | 2026-03-18 | 2026-03-18
Distribution | May | GRAYSON | ED-07530 | 4.92 | 2026-03-17 | 2026-03-18
Distribution | May | HALLDALE | ED-07868 | 12.49 | 2026-03-12 | 2026-03-16
Distribution | May | HAYDEN | ED-08230 | 0.08 | 2026-03-17 | 2026-03-18
Distribution | May | HYDROCRACKER 1 | ED-21028 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | HYDROCRACKER 2 | ED-21029 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | JAVA | ED-09180 | 2.22 | 2026-03-17 | 2026-03-18
Distribution | May | KIRSOP | ED-09806 | 0.01 | 2026-03-15 | 2026-03-17
Distribution | May | LA BREA | ED-09900 | 1.81 | 2026-03-17 | 2026-03-18
Distribution | May | LARABEE | ED-10098 | 3.64 | 2026-03-16 | 2026-03-17
Distribution | May | LISA | ED-10515 | 0.01 | 2026-03-15 | 2026-03-17
Distribution | May | LOMITA | ED-10680 | 0.69 | 2026-03-12 | 2026-03-17
Distribution | May | MARCELLINA | ED-11180 | 2.52 | 2026-03-17 | 2026-03-18
Distribution | May | MATTHEWS | ED-11347 | 0 | 2026-03-17 | 2026-03-17
Distribution | May | MERCANTILE | ED-11670 | 0.12 | 2026-03-17 | 2026-03-18
Distribution | May | NESTOR | ED-15705 | 9.6 | 2026-03-12 | 2026-03-16
Distribution | May | NORWICH | ED-12890 | 3.81 | 2026-03-12 | 2026-03-16
Distribution | May | ORCHID | ED-13235 | 7.4 | 2026-03-17 | 2026-03-18
Distribution | May | OSTRAN | ED-13320 | 5.75 | 2026-03-17 | 2026-03-18
Distribution | May | PARINA | ED-13695 | 3.47 | 2026-03-16 | 2026-03-17
Distribution | May | PENICK | ED-13908 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | PENROSE | ED-13927 | 15.24 | 2026-03-11 | 2026-03-16
Distribution | May | PUEBLO | ED-14480 | 6.34 | 2026-03-12 | 2026-03-16
Distribution | May | REPUBLIC | ED-14906 | 5.64 | 2026-03-15 | 2026-03-16
Distribution | May | RO FEED WATER | ED-21060 | 0.02 | 2026-03-15 | 2026-03-17
Distribution | May | ROSEMARY | ED-15440 | 8.9 | 2026-03-17 | 2026-03-18
Distribution | May | SANDMAN | ED-15744 | 0.08 | 2026-03-15 | 2026-03-17
Distribution | May | SHERMAN | ED-16340 | 1.58 | 2026-03-18 | 2026-03-18
Distribution | May | SNOVER | ED-16589 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | STRINGER | ED-17117 | 7.41 | 2026-03-17 | 2026-03-18
Distribution | May | SWEETZER | ED-17410 | 0.57 | 2026-03-18 | 2026-03-18
Distribution | May | TANK FARM 1 | ED-17531 | 0.97 | 2026-03-12 | 2026-03-17
Distribution | May | TANK FARM 2 | ED-17532 | 1.08 | 2026-03-12 | 2026-03-17
Distribution | May | THEES | ED-17742 | 0 | 2026-03-17 | 2026-03-17
Distribution | May | TOUR | ED-18016 | 0 | 2026-03-17 | 2026-03-17
Distribution | May | TREATER 1 | ED-21035 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | TREATER 2 | ED-21036 | 0 | 2026-03-15 | 2026-03-17
Distribution | May | TRUSS | ED-18235 | 11.02 | 2026-03-15 | 2026-03-16
Distribution | May | VULTEE | ED-18871 | 6.9 | 2026-03-15 | 2026-03-16
Distribution | May | WINLOCK | ED-19540 | 3.02 | 2026-03-12 | 2026-03-17
Distribution | May | AGRA | ED-00160 | 4.76 | 2026-03-15 | 2026-03-19
Distribution | May | ALBURY | ED-00271 | 1.69 | 2026-03-15 | 2026-03-20
Distribution | May | ANZAC | ED-00610 | 6.78 | 2026-03-17 | 2026-03-19
Distribution | May | BRADSHAW | ED-02125 | 12.84 | 2026-03-15 | 2026-03-19
Distribution | May | BRAKEBILL | ED-02135 | 8.19 | 2026-03-15 | 2026-03-19
Distribution | May | DASHWOOD | ED-04700 | 4.89 | 2026-03-18 | 2026-03-19
Distribution | May | DEEBLE | ED-04760 | 2.54 | 2026-03-17 | 2026-03-20
Distribution | May | DERRICK | ED-04990 | 3.25 | 2026-03-17 | 2026-03-20
Distribution | May | DOYLE | ED-05290 | 2.72 | 2026-03-17 | 2026-03-20
Distribution | May | DUNCAN | ED-05390 | 4.38 | 2026-03-17 | 2026-03-19
Distribution | May | ELKPORT | ED-05740 | 2.19 | 2026-03-15 | 2026-03-20
Distribution | May | FIDLER | ED-06365 | 5.1 | 2026-03-18 | 2026-03-19
Distribution | May | GALLUP | ED-06970 | 5.89 | 2026-03-18 | 2026-03-19
Distribution | May | GERATHS | ED-10000 | 1.8 | 2026-03-15 | 2026-03-20
Distribution | May | GOTHAM | ED-07450 | 5.23 | 2026-03-15 | 2026-03-19
Distribution | May | GUNDRY | ED-07770 | 3.56 | 2026-03-17 | 2026-03-22
Distribution | May | HALTER | ED-07886 | 6.02 | 2026-03-16 | 2026-03-19
Distribution | May | IRA | ED-08970 | 5.96 | 2026-03-15 | 2026-03-19
Distribution | May | KIT KAT | ED-09787 | 14.18 | 2026-03-15 | 2026-03-18
Distribution | May | KLISS | ED-09809 | 1.22 | 2026-03-16 | 2026-03-20
Distribution | May | KNEELAND | ED-09812 | 2.03 | 2026-03-16 | 2026-03-20
Distribution | May | KORDELL | ED-09851 | 8.47 | 2026-03-15 | 2026-03-19
Distribution | May | LONG | ED-10688 | 1.65 | 2026-03-16 | 2026-03-20
Distribution | May | MCNAB | ED-11520 | 3.52 | 2026-03-18 | 2026-03-20
Distribution | May | MICHIGAN | ED-11820 | 3.63 | 2026-03-17 | 2026-03-22
Distribution | May | MISSOURI | ED-11990 | 4.48 | 2026-03-17 | 2026-03-22
Distribution | May | NEBRASKA | ED-12565 | 5.19 | 2026-03-15 | 2026-03-19
Distribution | May | PARAFINE | ED-13660 | 14.16 | 2026-03-15 | 2026-03-19
Distribution | May | PRIORY | ED-14425 | 2.84 | 2026-03-17 | 2026-03-19
Distribution | May | RED FLAG | ED-14770 | 7.53 | 2026-03-15 | 2026-03-19
Distribution | May | RIVES | ED-15180 | 6.54 | 2026-03-16 | 2026-03-19
Distribution | May | SAMAR | ED-15703 | 1.28 | 2026-03-17 | 2026-03-19
Distribution | May | SHOTGUN | ED-16400 | 8.1 | 2026-03-15 | 2026-03-19
Distribution | May | TIDE | ED-17830 | 4.1 | 2026-03-16 | 2026-03-19
Distribution | May | TULANE | ED-18260 | 4.18 | 2026-03-16 | 2026-03-19
Distribution | May | VOGAN | ED-18833 | 1.66 | 2026-03-15 | 2026-03-19
Distribution | May | WARDLOW | ED-19010 | 2.8 | 2026-03-15 | 2026-03-19
Distribution | May | ABBOT | ED-00018 | 2.28 | 2026-03-10 | 2026-03-12
Distribution | May | ALLOY | ED-00331 | 10.49 | 2026-03-11 | 2026-03-12
Distribution | May | BERLIN | ED-01550 | 3.74 | 2026-03-09 | 2026-03-12
Distribution | May | BINGO | ED-01691 | 2.93 | 2026-03-10 | 2026-03-12
Distribution | May | BISON | ED-01736 | 8.27 | 2026-03-09 | 2026-03-12
Distribution | May | BOBBIT | ED-01849 | 10.13 | 2026-03-11 | 2026-03-12
Distribution | May | BRASHEARS | ED-02145 | 4.45 | 2026-03-11 | 2026-03-12
Distribution | May | BROTHERTON | ED-02313 | 0.79 | 2026-03-11 | 2026-03-12
Distribution | May | CERRITO | ED-03298 | 2.91 | 2026-03-09 | 2026-03-12
Distribution | May | CLEAT | ED-03615 | 6.15 | 2026-03-11 | 2026-03-12
Distribution | May | COCAMO | ED-03726 | 5.12 | 2026-03-10 | 2026-03-15
Distribution | May | CRIBBAGE | ED-04376 | 1.86 | 2026-03-09 | 2026-03-12
Distribution | May | CRONIN | ED-04400 | 15.92 | 2026-03-12 | 2026-03-12
Distribution | May | ELEPHANT | ED-05686 | 4.71 | 2026-03-10 | 2026-03-12
Distribution | May | FERREE | ED-07386 | 5.05 | 2026-03-10 | 2026-03-12
Distribution | May | FLOWER | ED-06580 | 1.69 | 2026-03-12 | 2026-03-15
Distribution | May | GILLIS | ED-07241 | 10.52 | 2026-03-11 | 2026-03-12
Distribution | May | GRIFFIN | ED-07661 | 2.34 | 2026-03-10 | 2026-03-12
Distribution | May | HALLSWORTH | ED-07871 | 13.33 | 2026-03-12 | 2026-03-12
Distribution | May | HIRSCH | ED-08503 | 2.78 | 2026-03-11 | 2026-03-12
Distribution | May | HOLLOWAY | ED-08580 | 2.77 | 2026-03-12 | 2026-03-12
Distribution | May | HOOK | ED-08666 | 8.08 | 2026-03-10 | 2026-03-12
Distribution | May | HUNT | ED-08840 | 12.84 | 2026-03-11 | 2026-03-12
Distribution | May | LANGLEY | ED-10046 | 9.24 | 2026-03-12 | 2026-03-12
Distribution | May | MADRONE | ED-10901 | 3.45 | 2026-03-12 | 2026-03-12
Distribution | May | MIAMI | ED-11803 | 0.37 | 2026-03-12 | 2026-03-12
Distribution | May | MONOPOLY | ED-12087 | 1.3 | 2026-03-10 | 2026-03-12
Distribution | May | MORRISON | ED-12199 | 9.91 | 2026-03-11 | 2026-03-12
Distribution | May | MORSE | ED-12205 | 0.3 | 2026-03-10 | 2026-03-12
Distribution | May | ORVIL | ED-13280 | 3.41 | 2026-03-11 | 2026-03-12
Distribution | May | PASEO | ED-13765 | 4.04 | 2026-03-10 | 2026-03-12
Distribution | May | PENINSULA | ED-13910 | 1.73 | 2026-03-11 | 2026-03-12
Distribution | May | PINOCHLE | ED-14141 | 0.17 | 2026-03-10 | 2026-03-12
Distribution | May | PORCELAIN | ED-14341 | 5.4 | 2026-03-10 | 2026-03-12
Distribution | May | PUNT | ED-14493 | 2.51 | 2026-03-10 | 2026-03-12
Distribution | May | RICHMAN | ED-15020 | 3.94 | 2026-03-11 | 2026-03-12
Distribution | May | SHADOW | ED-16230 | 12.47 | 2026-03-09 | 2026-03-12
Distribution | May | VIPER | ED-18796 | 0.95 | 2026-03-10 | 2026-03-12
Distribution | May | YAHTZEE | ED-19703 | 1.89 | 2026-03-10 | 2026-03-12
Distribution | May | RAVENNA | ED-14716 | 4.57 | 2026-03-09 | 2026-03-22
Distribution | May | CANBY | ED-02845 | 14.99 | 2026-03-05 | 2026-03-09
Distribution | May | CORDIAL | ED-04045 | 7.95 | 2026-03-08 | 2026-03-08
Distribution | May | DINKEY CREEK | ED-05085 | 5.79 | 2026-03-05 | 2026-03-08
Distribution | May | IONA | ED-08949 | 30.1 | 2026-03-08 | 2026-03-08
Distribution | May | LEMOORE | ED-10360 | 12.3 | 2026-03-08 | 2026-03-08
Distribution | May | LINDER | ED-10500 | 48.05 | 2026-03-05 | 2026-03-08
Distribution | May | MANZANILLO | ED-11140 | 34.93 | 2026-03-05 | 2026-03-08
Distribution | May | MUSSEL | ED-12420 | 10.13 | 2026-03-08 | 2026-03-09
Distribution | May | PAIGE | ED-13520 | 9.9 | 2026-03-08 | 2026-03-09
Distribution | May | RIO GRANDE | ED-15122 | 3.94 | 2026-03-05 | 2026-03-08
Distribution | May | ROSEBUD | ED-15415 | 19.49 | 2026-03-08 | 2026-03-08
Distribution | May | SABER | ED-15605 | 19.74 | 2026-03-08 | 2026-03-09
Distribution | May | SNO CAT | ED-16587 | 4.56 | 2026-03-05 | 2026-03-05
Distribution | May | SQUADRON | ED-16833 | 34.36 | 2026-03-05 | 2026-03-08
Distribution | May | ST. JOHNS | ED-17030 | 45.87 | 2026-03-05 | 2026-03-08
Distribution | May | WILBUR | ED-19360 | 33.64 | 2026-03-08 | 2026-03-08
Distribution | May | WINDT | ED-19520 | 26.14 | 2026-03-08 | 2026-03-08
Distribution | May | BOOSTER | ED-01960 | 29.96 | 2026-03-15 | 2026-03-15
Distribution | May | CAMPBELL | ED-02828 | 28.66 | 2026-03-15 | 2026-03-15
Distribution | May | CLAMPETT | ED-03583 | 3.09 | 2026-03-15 | 2026-03-15
Distribution | May | FLORY | ED-06570 | 19.84 | 2026-03-14 | 2026-03-15
Distribution | May | LEWIS | ED-10420 | 19.96 | 2026-03-11 | 2026-03-15
Distribution | May | MONACHE | ED-12083 | 14.29 | 2026-03-12 | 2026-03-15
Distribution | May | PLANO | ED-14181 | 3.84 | 2026-03-12 | 2026-03-15
Distribution | May | PRAIRIE | ED-14380 | 13.55 | 2026-03-11 | 2026-03-15
Distribution | May | ROSEDALE | ED-15420 | 11.44 | 2026-03-12 | 2026-03-15
Distribution | May | SIERRA TALC | ED-16422 | 1.09 | 2026-03-11 | 2026-03-15
Distribution | May | TOWNSITE | ED-18046 | 7.43 | 2026-03-15 | 2026-03-15
Distribution | May | ZANTE | ED-19800 | 46 | 2026-03-11 | 2026-03-15
Distribution | May | ASHLEY | ED-00801 | 2.81 | 2026-03-03 | 2026-03-03
Distribution | May | PASCOE | ED-13760 | 8.18 | 2026-03-02 | 2026-03-03
Distribution | May | RIVA | ED-15150 | 28.83 | 2026-03-02 | 2026-03-03
Distribution | May | SURFSIDE | ED-17354 | 12.29 | 2026-03-03 | 2026-03-03
Distribution | May | SWIFT | ED-17420 | 2.82 | 2026-03-03 | 2026-03-03
Distribution | May | TATANKA | ED-02031 | 3.89 | 2026-03-03 | 2026-03-03
Distribution | May | TREMAINE | ED-18122 | 5.77 | 2026-03-03 | 2026-03-03
Distribution | May | DAVENPORT | ED-04706 | 70.79 | 2026-03-02 | 2026-03-02
Distribution | May | ESCONDIDO | ED-06044 | 0.02 | 2026-03-02 | 2026-03-02
Distribution | May | LOUCKS | ED-10729 | 6.62 | 2026-03-02 | 2026-03-02
Distribution | May | SAND CANYON | ED-15737 | 28.45 | 2026-03-02 | 2026-03-02
Distribution | May | CLOUD | ED-03684 | 0.03 | 2026-03-03 | 2026-03-03
Distribution | May | CRESCENTA | ED-10313 | 24.17 | 2026-03-03 | 2026-03-03
Distribution | May | PICKENS | ED-14050 | 7.81 | 2026-03-03 | 2026-03-03
Distribution | May | DORSEY | ED-05225 | 2.89 | 2026-03-03 | 2026-03-03
Distribution | May | ENERGY | ED-05930 | 32.38 | 2026-03-03 | 2026-03-03
Distribution | May | GLASSCOCK | ED-07310 | 14.7 | 2026-03-03 | 2026-03-03
Distribution | May | HORIZON | ED-08695 | 14.97 | 2026-03-03 | 2026-03-03
Distribution | May | MCBEAN | ED-11432 | 5.67 | 2026-03-03 | 2026-03-03
Distribution | May | SIENNA | ED-16418 | 7.27 | 2026-03-03 | 2026-03-03
Distribution | May | TAMARIND | ED-17520 | 13.58 | 2026-03-03 | 2026-03-03
Distribution | June | GULL LAKE | ED-07763 | 5.3 | 2026-03-30 | 2026-03-30
Distribution | June | RHINEDOLLAR | ED-14955 | 1.65 | 2026-03-29 | 2026-03-30
Distribution | June | ROBINSON CREEK | ED-15282 | 16.19 | 2026-03-30 | 2026-03-30
Distribution | June | ALMA | ED-00340 | 6.09 | 2026-04-07 | 2026-04-08
Distribution | June | ARTISANO | ED-00780 | 6.77 | 2026-04-07 | 2026-04-08
Distribution | June | AZALIA | ED-00900 | 7.02 | 2026-04-07 | 2026-04-08
Distribution | June | BOMBAY | ED-01897 | 7.71 | 2026-04-06 | 2026-04-08
Distribution | June | BURLESON | ED-02463 | 4.25 | 2026-04-06 | 2026-04-08
Distribution | June | COOLEY | ED-03990 | 7.59 | 2026-04-07 | 2026-04-08
Distribution | June | CYANIDE | ED-04550 | 6.77 | 2026-04-07 | 2026-04-08
Distribution | June | DOMIC | ED-05190 | 24.97 | 2026-04-06 | 2026-04-07
Distribution | June | ENCHANTED | ED-05918 | 6.58 | 2026-04-06 | 2026-04-08
Distribution | June | EXCELSIOR | ED-06170 | 7.26 | 2026-04-07 | 2026-04-08
Distribution | June | GLOBE MILLS | ED-07370 | 12.74 | 2026-04-06 | 2026-04-07
Distribution | June | GULF | ED-07750 | 8.62 | 2026-04-07 | 2026-04-08
Distribution | June | HUB CITY | ED-08785 | 9.53 | 2026-04-06 | 2026-04-07
Distribution | June | LEIA | ED-10316 | 5.12 | 2026-04-07 | 2026-04-08
Distribution | June | MIDDLE ROAD | ED-11840 | 30.84 | 2026-04-06 | 2026-04-07
Distribution | June | MONTY | ED-12143 | 0.26 | 2026-04-06 | 2026-04-08
Distribution | June | MOONGLOW | ED-12159 | 10.42 | 2026-04-06 | 2026-04-07
Distribution | June | MUSKET | ED-12406 | 15.04 | 2026-04-06 | 2026-04-07
Distribution | June | PHILLIPS | ED-14030 | 9.37 | 2026-04-06 | 2026-04-08
Distribution | June | PRESTON | ED-14401 | 8.67 | 2026-04-06 | 2026-04-08
Distribution | June | RALSTON | ED-14650 | 8.03 | 2026-04-06 | 2026-04-08
Distribution | June | ROSEMONT | ED-15441 | 13.65 | 2026-04-07 | 2026-04-07
Distribution | June | SEAFORTH | ED-16043 | 30.98 | 2026-04-06 | 2026-04-07
Distribution | June | SQUALL | ED-16835 | 9.28 | 2026-04-06 | 2026-04-08
Distribution | June | SUPREME | ED-17340 | 12.6 | 2026-04-07 | 2026-04-07
Distribution | June | THUNDERBOLT | ED-17815 | 10.25 | 2026-04-06 | 2026-04-07
Distribution | June | CONESTOGA | ED-03928 | 12.52 | 2026-04-05 | 2026-04-09
Distribution | June | GRADUATE | ED-07459 | 6.03 | 2026-04-05 | 2026-04-09
Distribution | June | MERCEDES | ED-11675 | 15.56 | 2026-04-05 | 2026-04-09
Distribution | June | PUTTER | ED-14535 | 11.09 | 2026-04-05 | 2026-04-09
Distribution | June | EL MIRADOR | ED-05810 | 68.53 | 2026-04-13 | 2026-04-13
Distribution | June | FERINA | ED-06330 | 7.9 | 2026-04-12 | 2026-04-12
Distribution | June | REGAL | ED-14860 | 12.29 | 2026-04-09 | 2026-04-12
Distribution | June | COTTONMOUTH | ED-04162 | 0.08 | 2026-04-23 | 2026-04-27
Distribution | June | GARTEL | ED-07075 | 4.66 | 2026-04-23 | 2026-04-27
Distribution | June | MOCKINGBIRD | ED-12027 | 6.7 | 2026-04-23 | 2026-04-28
Distribution | June | DELHI | ED-04840 | 0.45 | 2026-04-23 | 2026-04-27
Distribution | June | DIPLOMAT | ED-05088 | 0.64 | 2026-04-23 | 2026-04-27
Distribution | June | DORCHESTER | ED-05213 | 2.87 | 2026-04-23 | 2026-04-27
Distribution | June | IDAHO | ED-08890 | 10.83 | 2026-04-23 | 2026-04-26
Distribution | June | CINDER | ED-03517 | 17.57 | 2026-03-24 | 2026-03-25
Distribution | June | GILL | ED-07240 | 45 | 2026-03-24 | 2026-03-25
Distribution | June | GILLETTE | ED-07250 | 30.23 | 2026-03-24 | 2026-03-25
Distribution | June | GROUSE | ED-07670 | 2.02 | 2026-03-24 | 2026-03-25
Distribution | June | HACK | ED-07820 | 30.29 | 2026-03-24 | 2026-03-25
Distribution | June | PERIMETER | ED-13959 | 20.39 | 2026-03-24 | 2026-03-25
Distribution | June | SEVILLE | ED-16200 | 23.47 | 2026-03-24 | 2026-03-25
Distribution | June | SUCCESS | ED-17165 | 70.98 | 2026-03-24 | 2026-03-25
Distribution | June | SUGARLOAF | ED-17190 | 5.59 | 2026-03-25 | 2026-03-25
Distribution | June | BRYN MAWR | ED-02350 | 10.19 | 2026-03-22 | 2026-03-24
Distribution | June | BURGUNDY | ED-02435 | 15.79 | 2026-03-23 | 2026-03-24
Distribution | June | CARDINAL | ED-02955 | 5.67 | 2026-03-23 | 2026-03-24
Distribution | June | CHINOOK | ED-03478 | 0.01 | 2026-03-23 | 2026-03-24
Distribution | June | CHOLLA | ED-03489 | 13.92 | 2026-03-22 | 2026-03-24
Distribution | June | DOBLE | ED-05123 | 15.57 | 2026-03-23 | 2026-03-24
Distribution | June | DOMELAND | ED-05195 | 18.69 | 2026-03-23 | 2026-03-23
Distribution | June | HARVEY FIELD | ED-08132 | 0.44 | 2026-03-23 | 2026-03-24
Distribution | June | HASTINGS | ED-08151 | 3.91 | 2026-03-23 | 2026-03-24
Distribution | June | JASPER | ED-09170 | 11.99 | 2026-03-23 | 2026-03-24
Distribution | June | KEENE | ED-09530 | 43.43 | 2026-03-22 | 2026-03-23
Distribution | June | KICKAPOO TRAIL | ED-09673 | 63.89 | 2026-03-19 | 2026-03-23
Distribution | June | KINSEY | ED-09777 | 38.45 | 2026-03-22 | 2026-03-24
Distribution | June | LARK | ED-10119 | 6.97 | 2026-03-22 | 2026-03-24
Distribution | June | MEADOWLARK | ED-11535 | 0.18 | 2026-03-23 | 2026-03-24
Distribution | June | MORONGO | ED-12178 | 35.01 | 2026-03-23 | 2026-03-23
Distribution | June | ORMAN | ED-13265 | 0.21 | 2026-03-23 | 2026-03-24
Distribution | June | POWER | ED-14377 | 3.49 | 2026-03-23 | 2026-03-24
Distribution | June | PUFF | ED-14482 | 7.32 | 2026-03-23 | 2026-03-24
Distribution | June | RIDGE | ED-15050 | 18.12 | 2026-03-23 | 2026-03-23
Distribution | June | SIROCCO | ED-16463 | 0.01 | 2026-03-23 | 2026-03-24
Distribution | June | SPARLING | ED-16736 | 17.57 | 2026-03-23 | 2026-03-23
Distribution | June | STONEWOOD | ED-17059 | 9.49 | 2026-03-23 | 2026-03-24
Distribution | June | TAGGERT | ED-17475 | 10.57 | 2026-03-23 | 2026-03-24
Distribution | June | TEJON PEAK | ED-17631 | 0 | 2026-03-23 | 2026-03-24
Distribution | June | UTE | ED-18493 | 1.98 | 2026-03-23 | 2026-03-24
Distribution | June | BREAKWATER | ED-02182 | 0.01 | 2026-03-29 | 2026-03-29
Distribution | June | CALIMESA | ED-02710 | 11.38 | 2026-03-29 | 2026-03-29
Distribution | June | CONINE | ED-03934 | 12.17 | 2026-03-29 | 2026-03-29
Distribution | June | DARTMOUTH | ED-04693 | 18.35 | 2026-03-26 | 2026-03-29
Distribution | June | EBERT | ED-05588 | 1.5 | 2026-03-29 | 2026-03-29
Distribution | June | GILMAN | ED-07258 | 1.93 | 2026-03-29 | 2026-03-29
Distribution | June | HULSTEIN | ED-08816 | 0.07 | 2026-03-29 | 2026-03-29
Distribution | June | KERRY | ED-09651 | 5.91 | 2026-03-29 | 2026-03-29
Distribution | June | KONA | ED-09815 | 27.4 | 2026-03-26 | 2026-03-29
Distribution | June | MARTIAN | ED-11299 | 1.24 | 2026-03-29 | 2026-03-29
Distribution | June | MAXIM | ED-11362 | 33.11 | 2026-03-26 | 2026-03-29
Distribution | June | MOTA | ED-12248 | 6.35 | 2026-03-29 | 2026-03-29
Distribution | June | PALMVIEW | ED-13587 | 12.25 | 2026-03-26 | 2026-03-29
Distribution | June | RUEDA | ED-15518 | 8.6 | 2026-03-29 | 2026-03-29
Distribution | June | RUIZ | ED-15533 | 8.98 | 2026-03-29 | 2026-03-29
Distribution | June | SAN RAFAEL | ED-15835 | 7.18 | 2026-03-29 | 2026-03-29
Distribution | June | STILLWATER | ED-17026 | 0.01 | 2026-03-29 | 2026-03-29
Distribution | June | SWIFTWATER | ED-17421 | 0.01 | 2026-03-29 | 2026-03-29
Distribution | June | TERRA COTTA | ED-17674 | 14.18 | 2026-03-29 | 2026-03-29
Distribution | June | THORNTON | ED-17795 | 8.32 | 2026-03-29 | 2026-03-29
Distribution | June | ABRAHAM | ED-00024 | 0.82 | 2026-03-25 | 2026-03-26
Distribution | June | ALVARADO | ED-00406 | 0.5 | 2026-03-25 | 2026-03-26
Distribution | June | AMANDA | ED-00412 | 10.37 | 2026-03-25 | 2026-03-26
Distribution | June | ARLENE | ED-00705 | 6.9 | 2026-03-26 | 2026-03-26
Distribution | June | ATMORE | ED-00840 | 12.49 | 2026-03-25 | 2026-03-26
Distribution | June | BOXCAR | ED-02048 | 34.4 | 2026-03-25 | 2026-03-26
Distribution | June | BRAEMER | ED-02185 | 8.33 | 2026-03-26 | 2026-03-26
Distribution | June | BUCKAROO | ED-02355 | 17.27 | 2026-03-26 | 2026-03-26
Distribution | June | CASTRO | ED-04632 | 41.94 | 2026-03-26 | 2026-03-26
Distribution | June | CORSICA | ED-04111 | 14.09 | 2026-03-25 | 2026-03-26
Distribution | June | DRINKWATER | ED-05324 | 1.96 | 2026-03-26 | 2026-03-26
Distribution | June | DWP DRINKWATER | ED-05323 | 0.25 | 2026-03-25 | 2026-03-26
Distribution | June | FAIR ACRES | ED-06190 | 1.8 | 2026-03-26 | 2026-03-26
Distribution | June | JAMESON | ED-09122 | 8.66 | 2026-03-26 | 2026-03-26
Distribution | June | SHEFFIELD | ED-16310 | 42.28 | 2026-03-25 | 2026-03-26
Distribution | June | THACHER | ED-17731 | 78.96 | 2026-03-25 | 2026-03-26
Distribution | June | BELUSHI | ED-01437 | 1.56 | 2026-03-29 | 2026-03-29
Distribution | June | BUTTERFIELD | ED-02562 | 4.26 | 2026-03-29 | 2026-03-29
Distribution | June | CABERNET | ED-02578 | 13.39 | 2026-03-29 | 2026-03-29
Distribution | June | CAGLI | ED-02626 | 4.89 | 2026-03-29 | 2026-03-30
Distribution | June | CHARLIE | ED-03370 | 8.05 | 2026-03-29 | 2026-03-29
Distribution | June | CUSHENBURY | ED-04516 | 6.37 | 2026-03-29 | 2026-03-29
Distribution | June | DIGBY | ED-05079 | 0.04 | 2026-03-29 | 2026-03-29
Distribution | June | DRONE | ED-05336 | 1.31 | 2026-03-29 | 2026-03-29
Distribution | June | HUFF | ED-08807 | 5.18 | 2026-03-29 | 2026-03-29
Distribution | June | JOB | ED-09275 | 5.93 | 2026-03-29 | 2026-03-29
Distribution | June | OAK KNOLL | ED-12971 | 4.4 | 2026-03-29 | 2026-03-29
Distribution | June | POULTRY | ED-14372 | 25.25 | 2026-03-29 | 2026-03-29
Distribution | June | SCOUT | ED-16013 | 0 | 2026-03-29 | 2026-03-30
Distribution | June | SQUINT | ED-16839 | 10.44 | 2026-03-29 | 2026-03-30
Distribution | June | WILSON CREEK | ED-19482 | 12.78 | 2026-03-29 | 2026-03-30
Distribution | June | AMAR | ED-00425 | 1.93 | 2026-04-01 | 2026-04-01
Distribution | June | AMTRAK | ED-00472 | 1.61 | 2026-03-30 | 2026-03-31
Distribution | June | APPLE | ED-00644 | 11.98 | 2026-03-30 | 2026-03-31
Distribution | June | BANANA | ED-01058 | 10.97 | 2026-03-30 | 2026-03-31
Distribution | June | BEAN | ED-01310 | 4.19 | 2026-03-31 | 2026-03-31
Distribution | June | BERKSHIRE | ED-01540 | 7.54 | 2026-03-30 | 2026-03-31
Distribution | June | BROOKLYN | ED-02270 | 5.3 | 2026-04-01 | 2026-04-01
Distribution | June | BRYCE | ED-02331 | 15.31 | 2026-03-31 | 2026-03-31
Distribution | June | CARR | ED-03010 | 11.06 | 2026-03-31 | 2026-03-31
Distribution | June | CHICAGO | ED-03450 | 5.35 | 2026-03-31 | 2026-04-01
Distribution | June | CORDOVA | ED-04050 | 3.25 | 2026-03-31 | 2026-03-31
Distribution | June | DAROCA | ED-04690 | 9.87 | 2026-03-31 | 2026-04-01
Distribution | June | DEL MAR | ED-04860 | 4.46 | 2026-03-31 | 2026-03-31
Distribution | June | DEUCE | ED-05017 | 13.51 | 2026-04-01 | 2026-04-01
Distribution | June | DUNDAS | ED-05411 | 2.5 | 2026-03-31 | 2026-03-31
Distribution | June | ELGIN | ED-05700 | 2.97 | 2026-03-31 | 2026-03-31
Distribution | June | ENDICOTT | ED-05926 | 5.39 | 2026-03-31 | 2026-03-31
Distribution | June | ENGINE | ED-05935 | 0.93 | 2026-04-01 | 2026-04-01
Distribution | June | FLINTRIDGE | ED-06540 | 5.11 | 2026-03-31 | 2026-04-01
Distribution | June | HAMPTON | ED-07930 | 1.9 | 2026-03-31 | 2026-04-01
Distribution | June | HERBERT | ED-08340 | 0.08 | 2026-03-31 | 2026-04-01
Distribution | June | HICKS | ED-08391 | 4.08 | 2026-03-31 | 2026-04-01
Distribution | June | HIDALGO | ED-08400 | 2.53 | 2026-03-31 | 2026-04-01
Distribution | June | JOSARD | ED-09324 | 10.62 | 2026-03-31 | 2026-03-31
Distribution | June | KEWEN | ED-09660 | 1.35 | 2026-03-31 | 2026-04-01
Distribution | June | ABLE | ED-00023 | 4.47 | 2026-03-30 | 2026-03-31
Distribution | June | ABRI | ED-00026 | 1.76 | 2026-03-30 | 2026-03-30
Distribution | June | APRICOT | ED-00660 | 3.96 | 2026-03-30 | 2026-03-31
Distribution | June | BIGELOW | ED-01650 | 8 | 2026-03-31 | 2026-03-31
Distribution | June | BRINE | ED-02243 | 6.47 | 2026-03-30 | 2026-03-31
Distribution | June | CASPIAN | ED-03110 | 14.44 | 2026-03-30 | 2026-03-30
Distribution | June | CODONA | ED-03730 | 5.1 | 2026-03-30 | 2026-03-30
Distribution | June | CYNTHIA | ED-04560 | 1.46 | 2026-03-30 | 2026-03-30
Distribution | June | DALBERG | ED-04600 | 2.24 | 2026-03-30 | 2026-03-31
Distribution | June | DENVER | ED-04950 | 6.12 | 2026-03-30 | 2026-03-30
Distribution | June | DRIFT | ED-05316 | 4.11 | 2026-03-30 | 2026-03-30
Distribution | June | EASY | ED-05580 | 0.54 | 2026-03-30 | 2026-03-31
Distribution | June | EPSILON | ED-05994 | 5.7 | 2026-03-30 | 2026-03-30
Distribution | June | EVANS | ED-06120 | 4.69 | 2026-03-30 | 2026-03-30
Distribution | June | FELDSPAR | ED-06308 | 20.92 | 2026-03-29 | 2026-03-30
Distribution | June | FIAT | ED-06362 | 5.37 | 2026-03-30 | 2026-03-31
Distribution | June | FLAGSTONE | ED-06496 | 1.49 | 2026-03-30 | 2026-03-30
Distribution | June | HANCOCK | ED-07940 | 2.62 | 2026-03-30 | 2026-03-30
Distribution | June | HARCO | ED-07990 | 4.6 | 2026-03-30 | 2026-03-30
Distribution | June | KEYSTONE | ED-09670 | 9.25 | 2026-03-30 | 2026-03-31
Distribution | June | ACME | ED-00044 | 5.58 | 2026-04-02 | 2026-04-02
Distribution | June | ADELL | ED-00093 | 0.57 | 2026-04-01 | 2026-04-02
Distribution | June | ANAHURST | ED-00490 | 7.07 | 2026-04-01 | 2026-04-01
Distribution | June | ARIES | ED-00698 | 0.11 | 2026-03-31 | 2026-04-02
Distribution | June | BALBOA | ED-00980 | 0.92 | 2026-04-01 | 2026-04-02
Distribution | June | BEIGE | ED-01392 | 0.62 | 2026-04-01 | 2026-04-02
Distribution | June | BELLGRAVE | ED-01422 | 1.07 | 2026-04-01 | 2026-04-02
Distribution | June | BISMUTH | ED-01734 | 3.64 | 2026-04-02 | 2026-04-02
Distribution | June | BLUE | ED-01838 | 4.88 | 2026-04-01 | 2026-04-01
Distribution | June | BRITTAN | ED-02250 | 6.22 | 2026-04-01 | 2026-04-01
Distribution | June | BULLOCKS | ED-02420 | 4.35 | 2026-04-01 | 2026-04-01
Distribution | June | CADMIUM | ED-02617 | 9.79 | 2026-04-01 | 2026-04-02
Distribution | June | CHARTREUSE | ED-03381 | 2.87 | 2026-04-01 | 2026-04-01
Distribution | June | CHROME | ED-03494 | 1.6 | 2026-04-01 | 2026-04-02
Distribution | June | COBALT | ED-03716 | 14.17 | 2026-04-01 | 2026-04-01
Distribution | June | COLFAX | ED-03781 | 13.06 | 2026-04-02 | 2026-04-02
Distribution | June | CONNING | ED-03939 | 3.97 | 2026-04-01 | 2026-04-01
Distribution | June | CORBINA | ED-04035 | 12.07 | 2026-04-02 | 2026-04-02
Distribution | June | CORONITA | ED-04082 | 0.5 | 2026-04-01 | 2026-04-02
Distribution | June | COURSE | ED-04205 | 5.52 | 2026-04-01 | 2026-04-02
Distribution | June | DIVOT | ED-05115 | 10.77 | 2026-03-31 | 2026-04-01
Distribution | June | FINALS | ED-06435 | 6.96 | 2026-04-01 | 2026-04-01
Distribution | June | GRAF | ED-07458 | 2.39 | 2026-04-01 | 2026-04-02
Distribution | June | GUAM | ED-07690 | 13.41 | 2026-03-31 | 2026-04-01
Distribution | June | GUNTHER | ED-07790 | 3.87 | 2026-04-01 | 2026-04-01
Distribution | June | HALEY | ED-07851 | 0.84 | 2026-04-01 | 2026-04-01
Distribution | June | ISLAND | ED-09030 | 0.02 | 2026-04-01 | 2026-04-01
Distribution | June | JAGUAR | ED-09104 | 14.61 | 2026-04-01 | 2026-04-01
Distribution | July | CALIENTE | ED-02680 | 27.35 | 2026-04-19 | 2026-04-21
Distribution | July | CUYAMA | ED-04540 | 36.67 | 2026-04-19 | 2026-04-20
Distribution | July | VIENTO | ED-18734 | 83.14 | 2026-04-20 | 2026-04-21
Distribution | July | HERRING | ED-08345 | 11.48 | 2026-05-07 | 2026-05-07
Distribution | July | HOPE | ED-08682 | 0.68 | 2026-05-07 | 2026-05-11
Distribution | July | JIMMY | ED-09249 | 9.85 | 2026-05-10 | 2026-05-11
Distribution | July | JOSHUA | ED-09330 | 11.15 | 2026-05-07 | 2026-05-11
Distribution | July | KILKENNY | ED-09693 | 16.01 | 2026-05-07 | 2026-05-10
Distribution | July | LA RICA | ED-10110 | 2.21 | 2026-05-10 | 2026-05-11
Distribution | July | LOBBY | ED-10577 | 11.31 | 2026-05-07 | 2026-05-10
Distribution | July | MACHINE | ED-10868 | 6.42 | 2026-05-10 | 2026-05-11
Distribution | July | MARS | ED-11260 | 4.93 | 2026-05-10 | 2026-05-11
Distribution | July | MONTANA | ED-12110 | 3.21 | 2026-05-10 | 2026-05-11
Distribution | July | NORWOOD | ED-12900 | 11.09 | 2026-05-10 | 2026-05-11
Distribution | July | OBAN | ED-13000 | 17.08 | 2026-05-10 | 2026-05-11
Distribution | July | ORIZABA | ED-13256 | 8.4 | 2026-05-10 | 2026-05-11
Distribution | July | SHAFFER | ED-16240 | 0.98 | 2026-05-10 | 2026-05-11
Distribution | July | SPARKS | ED-16730 | 11.28 | 2026-05-07 | 2026-05-10
Distribution | July | STORAGE | ED-17064 | 0.44 | 2026-05-07 | 2026-05-11
Distribution | July | SUPERIOR | ED-17330 | 8.41 | 2026-05-10 | 2026-05-11
Distribution | July | SUZY | ED-17385 | 0.75 | 2026-05-10 | 2026-05-11
Distribution | July | TIERRA BONITA | ED-17850 | 12.5 | 2026-05-06 | 2026-05-07
Distribution | July | VULTAIR | ED-18870 | 7.94 | 2026-05-10 | 2026-05-11
Distribution | July | WANDA | ED-18980 | 1.64 | 2026-05-07 | 2026-05-07
Distribution | July | ZANE | ED-19798 | 9.96 | 2026-05-07 | 2026-05-11
Distribution | July | INTERPACE | ED-08938 | 15.19 | 2026-05-06 | 2026-05-07
Distribution | July | KICK | ED-09672 | 7.1 | 2026-05-06 | 2026-05-07
Distribution | July | KRAFT | ED-09865 | 21.42 | 2026-05-06 | 2026-05-06
Distribution | July | LATTE | ED-10199 | 10.96 | 2026-05-06 | 2026-05-07
Distribution | July | LOLA | ED-10655 | 1.48 | 2026-05-06 | 2026-05-07
Distribution | July | MABLE | ED-10865 | 3.84 | 2026-05-07 | 2026-05-07
Distribution | July | MEATS | ED-11560 | 6.64 | 2026-05-06 | 2026-05-07
Distribution | July | MICHAEL | ED-11817 | 4.13 | 2026-05-07 | 2026-05-07
Distribution | July | PALACE | ED-13543 | 1.96 | 2026-05-06 | 2026-05-07
Distribution | July | RACINE | ED-14601 | 7.53 | 2026-05-07 | 2026-05-07
Distribution | July | RADEC | ED-14608 | 4.17 | 2026-05-07 | 2026-05-07
Distribution | July | RUSTIC | ED-15586 | 17.56 | 2026-05-06 | 2026-05-06
Distribution | July | STAGHORN | ED-16884 | 13.3 | 2026-05-06 | 2026-05-07
Distribution | July | STROH | ED-17121 | 2.47 | 2026-05-06 | 2026-05-07
Distribution | July | TEXFI | ED-17717 | 8.94 | 2026-05-07 | 2026-05-07
Distribution | July | THELMA | ED-17754 | 9.21 | 2026-05-06 | 2026-05-07
Distribution | July | TOUCHDOWN | ED-18013 | 4.5 | 2026-05-07 | 2026-05-07
Distribution | July | WYLE | ED-19697 | 5.57 | 2026-05-07 | 2026-05-07
Distribution | July | YOGI | ED-19747 | 7.05 | 2026-05-06 | 2026-05-07
Distribution | July | HURSTVIEW | ED-08850 | 9.41 | 2026-05-12 | 2026-05-13
Distribution | July | KEIM | ED-09539 | 4.52 | 2026-05-12 | 2026-05-14
Distribution | July | LOMAS | ED-10665 | 11.85 | 2026-05-11 | 2026-05-13
Distribution | July | LURAY | ED-10810 | 4.46 | 2026-05-12 | 2026-05-13
Distribution | July | LYNDORA | ED-10840 | 5.23 | 2026-05-12 | 2026-05-14
Distribution | July | MARKET | ED-11220 | 6.05 | 2026-05-12 | 2026-05-13
Distribution | July | MATNEY | ED-11345 | 4.61 | 2026-05-13 | 2026-05-13
Distribution | July | MC CLARY | ED-11446 | 13.87 | 2026-05-10 | 2026-05-13
Distribution | July | MEDNICK | ED-11600 | 1.42 | 2026-05-11 | 2026-05-13
Distribution | July | NEGEL | ED-12580 | 5.81 | 2026-05-12 | 2026-05-14
Distribution | July | NEMAHA | ED-12610 | 4.58 | 2026-05-13 | 2026-05-13
Distribution | July | NOCTA | ED-12760 | 5.07 | 2026-05-12 | 2026-05-14
Distribution | July | OSGOOD | ED-13300 | 7.02 | 2026-05-11 | 2026-05-13
Distribution | July | OWL | ED-13390 | 4.98 | 2026-05-13 | 2026-05-14
Distribution | July | OXLEY | ED-12120 | 4.36 | 2026-05-13 | 2026-05-13
Distribution | July | PETRI | ED-13990 | 13.67 | 2026-05-10 | 2026-05-13
Distribution | July | PHANTOM | ED-14003 | 1.88 | 2026-05-09 | 2026-05-13
Distribution | July | ROYCROFT | ED-15510 | 3.68 | 2026-05-12 | 2026-05-13
Distribution | July | SANITARIUM | ED-15790 | 5.49 | 2026-05-12 | 2026-05-13
Distribution | July | SEGOVIA | ED-16110 | 8.68 | 2026-05-10 | 2026-05-13
Distribution | July | SHAKE | ED-16244 | 5.85 | 2026-05-11 | 2026-05-13
Distribution | July | SHAW | ED-16300 | 5.78 | 2026-05-12 | 2026-05-13
Distribution | July | SPILLWAY | ED-16775 | 9.08 | 2026-05-10 | 2026-05-13
Distribution | July | STANDISH | ED-16910 | 5.53 | 2026-05-13 | 2026-05-14
Distribution | July | SUNNYSLOPE | ED-17280 | 5.88 | 2026-05-11 | 2026-05-13
Distribution | July | TRIUMPH | ED-18163 | 2.17 | 2026-05-10 | 2026-05-13
Distribution | July | VERDUGO | ED-18660 | 38.55 | 2026-05-14 | 2026-05-14
Distribution | July | VIDEO | ED-18730 | 12.44 | 2026-05-11 | 2026-05-13
Distribution | July | WEBER | ED-19120 | 5.77 | 2026-05-12 | 2026-05-13
Distribution | July | HILL | ED-08430 | 6.53 | 2026-05-11 | 2026-05-12
Distribution | July | HILTON | ED-08495 | 3.91 | 2026-05-11 | 2026-05-12
Distribution | July | JANICE | ED-09130 | 2.46 | 2026-05-11 | 2026-05-12
Distribution | July | KEATS | ED-09500 | 0.83 | 2026-05-11 | 2026-05-12
Distribution | July | LANTANA | ED-10059 | 5.72 | 2026-05-11 | 2026-05-12
Distribution | July | MAJOR | ED-10980 | 6.46 | 2026-05-11 | 2026-05-12
Distribution | July | MALAGA COVE | ED-11000 | 1.18 | 2026-05-11 | 2026-05-12
Distribution | July | MAMBA | ED-11022 | 13.54 | 2026-05-11 | 2026-05-11
Distribution | July | MCKINLEY | ED-11510 | 8.5 | 2026-05-11 | 2026-05-11
Distribution | July | NORMANDIE | ED-12811 | 7.38 | 2026-05-10 | 2026-05-11
Distribution | July | NORTH BEACH | ED-12830 | 2.85 | 2026-05-11 | 2026-05-12
Distribution | July | OVERHILL | ED-13370 | 6.97 | 2026-05-10 | 2026-05-14
Distribution | July | PADRE | ED-13510 | 2.42 | 2026-05-12 | 2026-05-13
Distribution | July | PARADISE | ED-13658 | 14.95 | 2026-05-11 | 2026-05-13
Distribution | July | PINZON | ED-14150 | 4.88 | 2026-05-11 | 2026-05-12
Distribution | July | PLATEAU | ED-14190 | 18.56 | 2026-05-11 | 2026-05-13
Distribution | July | PYTHON | ED-14547 | 24.08 | 2026-05-11 | 2026-05-12
Distribution | July | QUICKSILVER | ED-14586 | 14.69 | 2026-05-11 | 2026-05-13
Distribution | July | RIPTIDE | ED-15118 | 3.39 | 2026-05-11 | 2026-05-11
Distribution | July | ROCHA | ED-15290 | 9.73 | 2026-05-10 | 2026-05-11
Distribution | July | ROXBURY | ED-15490 | 1.52 | 2026-05-11 | 2026-05-12
Distribution | July | RYAN | ED-15603 | 19.63 | 2026-05-11 | 2026-05-12
Distribution | July | SHERBOURNE | ED-16334 | 16.88 | 2026-05-13 | 2026-05-13
Distribution | July | SOUTH STRAND | ED-16710 | 2.51 | 2026-05-11 | 2026-05-12
Distribution | July | TAPER | ED-17530 | 4.42 | 2026-05-11 | 2026-05-12
Distribution | July | TAPO | ED-17548 | 14.69 | 2026-05-11 | 2026-05-11
Distribution | July | TARTAR | ED-17558 | 2.31 | 2026-05-12 | 2026-05-12
Distribution | July | TRANSPLANT | ED-18100 | 7.94 | 2026-05-10 | 2026-05-13
Distribution | July | TWINING | ED-18350 | 5.29 | 2026-05-11 | 2026-05-12
Distribution | July | VALLECITO | ED-18525 | 22.29 | 2026-05-12 | 2026-05-12
Distribution | July | VALMONTE | ED-18550 | 5.03 | 2026-05-11 | 2026-05-12
Distribution | July | VIOLET | ED-18790 | 4.94 | 2026-05-11 | 2026-05-12
Distribution | July | WAGNER | ED-18910 | 5.94 | 2026-05-11 | 2026-05-12
Distribution | July | WETHERLY | ED-19220 | 0.26 | 2026-05-11 | 2026-05-12
Distribution | July | PORPHYRY | ED-14346 | 3.67 | 2026-04-26 | 2026-05-12
Distribution | July | PROFIT | ED-14441 | 13.78 | 2026-04-27 | 2026-05-12
Distribution | July | ROVER | ED-15474 | 26.3 | 2026-04-27 | 2026-05-12
Distribution | July | CLANCY | ED-03584 | 32.82 | 2026-05-06 | 2026-05-10
Distribution | July | SERENITY | ED-16153 | 31.97 | 2026-05-06 | 2026-05-10
Distribution | July | STURGEON | ED-17140 | 42.84 | 2026-05-06 | 2026-05-10
Distribution | July | GREVELIA | ED-07650 | 3.61 | 2026-05-12 | 2026-05-14
Distribution | July | HAMMELL | ED-07910 | 4.8 | 2026-05-12 | 2026-05-14
Distribution | July | HARDY | ED-08020 | 3.35 | 2026-05-13 | 2026-05-13
Distribution | July | HORNTOAD | ED-08698 | 20.23 | 2026-05-12 | 2026-05-13
Distribution | July | NIDEVER | ED-12705 | 1.26 | 2026-05-12 | 2026-05-12
Distribution | July | TWIN PEAKS | ED-18375 | 8.37 | 2026-05-13 | 2026-05-13
Distribution | July | NADINE | ED-12474 | 4.69 | 2026-05-07 | 2026-05-10
Distribution | July | AKRON | ED-00190 | 10.25 | 2026-05-10 | 2026-05-14
Distribution | July | CHIPPEWA | ED-03487 | 9.95 | 2026-05-10 | 2026-05-13
Distribution | July | COMANCHE | ED-03848 | 5.26 | 2026-05-11 | 2026-05-13
Distribution | July | HALIBUT | ED-07860 | 1.62 | 2026-05-11 | 2026-05-13
Distribution | July | KATELLA | ED-09471 | 5.37 | 2026-05-11 | 2026-05-13
Distribution | July | MIDWAY | ED-11850 | 2.69 | 2026-05-11 | 2026-05-13
Distribution | July | ROSSMOOR | ED-15451 | 4.58 | 2026-05-11 | 2026-05-13
Distribution | July | ALFALFA | ED-00300 | 25.57 | 2026-04-20 | 2026-04-22
Distribution | July | BUTTE | ED-02560 | 21.76 | 2026-04-21 | 2026-04-22
Distribution | July | DIVISION | ED-05110 | 7.68 | 2026-04-21 | 2026-04-21
Distribution | July | DUNTLEY | ED-05420 | 24.11 | 2026-04-20 | 2026-04-21
Distribution | July | FORAGE | ED-06630 | 26.46 | 2026-04-20 | 2026-04-21
Distribution | July | GRUBSTAKE | ED-07680 | 42.41 | 2026-04-20 | 2026-04-21
Distribution | July | HOVEY | ED-08760 | 13.63 | 2026-04-20 | 2026-04-21
Distribution | July | HURON | ED-08849 | 19.45 | 2026-04-20 | 2026-04-21
Distribution | July | LLOYD | ED-10570 | 47.07 | 2026-04-19 | 2026-04-21
Distribution | July | WILLOW SPRINGS | ED-19430 | 52.25 | 2026-04-21 | 2026-04-21
Distribution | July | ALPINE | ED-00390 | 9.03 | 2026-04-21 | 2026-04-22
Distribution | July | ARMIJO | ED-00727 | 38.81 | 2026-04-22 | 2026-04-22
Distribution | July | BASE | ED-01191 | 5.89 | 2026-04-21 | 2026-04-22
Distribution | July | CITY CREEK | ED-03560 | 9.26 | 2026-04-21 | 2026-04-22
Distribution | July | DOOLEY | ED-05211 | 11.74 | 2026-04-22 | 2026-04-22
Distribution | July | FREIGHTLINER | ED-06796 | 11.29 | 2026-04-21 | 2026-04-22
Distribution | July | GAMBLER | ED-06987 | 63.17 | 2026-04-21 | 2026-04-22
Distribution | July | GUTHRIE | ED-07798 | 8.04 | 2026-04-22 | 2026-04-22
Distribution | July | HARLEM SPRINGS | ED-08045 | 14.1 | 2026-04-22 | 2026-04-22
Distribution | July | HOOK CREEK | ED-08670 | 3.39 | 2026-04-21 | 2026-04-21
Distribution | July | INTERNATIONAL | ED-08939 | 4 | 2026-04-21 | 2026-04-22
Distribution | July | KENWORTH | ED-09643 | 76.82 | 2026-04-22 | 2026-04-22
Distribution | July | TALPA | ED-03155 | 16 | 2026-04-22 | 2026-04-22
Distribution | July | VOLVO | ED-18841 | 1.42 | 2026-04-21 | 2026-04-21
Distribution | July | ALCALDE | ED-00274 | 0.35 | 2026-04-19 | 2026-04-20
Distribution | July | AVENTURA | ED-00885 | 16.1 | 2026-04-20 | 2026-04-21
Distribution | July | BLEND | ED-01807 | 18.44 | 2026-04-20 | 2026-04-20
Distribution | July | BUCKBOARD | ED-02361 | 6.23 | 2026-04-20 | 2026-04-20
Distribution | July | CAFE | ED-02633 | 27.93 | 2026-04-19 | 2026-04-20
Distribution | July | CARISO | ED-02944 | 3.77 | 2026-04-20 | 2026-05-14
Distribution | July | COACHELLA | ED-03715 | 18.14 | 2026-04-20 | 2026-04-20
Distribution | July | CRUZ | ED-04457 | 4.1 | 2026-04-20 | 2026-04-21
Distribution | July | DILLON | ED-05082 | 1.02 | 2026-04-20 | 2026-04-21
Distribution | July | DONNER | ED-05208 | 3.9 | 2026-04-20 | 2026-04-21
Distribution | July | DORMAN | ED-05216 | 3.26 | 2026-04-20 | 2026-04-21
Distribution | July | ESPRESSO | ED-06053 | 5.75 | 2026-04-20 | 2026-04-21
Distribution | July | FRONTIER | ED-06841 | 1.35 | 2026-04-20 | 2026-04-21
Distribution | July | GILSTRAP | ED-00634 | 15.89 | 2026-04-20 | 2026-04-20
Distribution | July | GRANNY SMITH | ED-07495 | 27.85 | 2026-04-20 | 2026-04-20
Distribution | July | HILLS | ED-08454 | 0.27 | 2026-04-20 | 2026-04-21
Distribution | July | HITCH | ED-08501 | 0.25 | 2026-04-19 | 2026-04-21
Distribution | July | HUBBLE | ED-00651 | 13.66 | 2026-04-20 | 2026-04-20
Distribution | July | INVADER | ED-08946 | 24.87 | 2026-04-19 | 2026-04-20
Distribution | July | SABINO | ED-15608 | 0.31 | 2026-04-19 | 2026-04-21
Distribution | July | SPUTNIK | ED-16831 | 1.43 | 2026-04-20 | 2026-04-21
Distribution | July | ABBEY | ED-00020 | 45.45 | 2026-05-05 | 2026-05-13
Distribution | July | BOWEN | ED-02040 | 43.48 | 2026-05-10 | 2026-05-13
Distribution | July | GREEN | ED-07570 | 23.8 | 2026-05-05 | 2026-05-13
Distribution | July | HART | ED-08110 | 30.17 | 2026-05-10 | 2026-05-13
Distribution | July | ALAMOSA | ED-00233 | 11.92 | 2026-05-04 | 2026-05-05
Distribution | July | CAL POLY | ED-02745 | 6.77 | 2026-05-04 | 2026-05-05
Distribution | July | CALSPAR | ED-02755 | 7.41 | 2026-05-04 | 2026-05-05
Distribution | July | CREEKSIDE | ED-04314 | 10.03 | 2026-05-04 | 2026-05-05
Distribution | July | DONOHUE | ED-05212 | 2.93 | 2026-05-04 | 2026-05-05
Distribution | July | FAIRMONT | ED-06240 | 28.89 | 2026-05-04 | 2026-05-05
Distribution | July | FOOTHILL | ED-06620 | 7.62 | 2026-05-04 | 2026-05-05
Distribution | July | FORBES | ED-06634 | 9.8 | 2026-05-04 | 2026-05-05
Distribution | July | FOYT | ED-06717 | 3.53 | 2026-05-04 | 2026-05-05
Distribution | July | HARDROCK | ED-08016 | 10.68 | 2026-05-05 | 2026-05-05
Distribution | July | MESQUITE | ED-11744 | 27.15 | 2026-05-04 | 2026-05-05
Distribution | July | MOUNTAIN | ED-12270 | 2.88 | 2026-05-04 | 2026-05-05
Distribution | July | PENCIL | ED-13902 | 10.52 | 2026-05-04 | 2026-05-05
Distribution | July | PERSHING | ED-13970 | 4.69 | 2026-05-04 | 2026-05-05
Distribution | July | PLACID | ED-14178 | 31.86 | 2026-05-03 | 2026-05-05
Distribution | July | POCO | ED-14262 | 21.1 | 2026-05-05 | 2026-05-05
Distribution | July | ROOSEVELT | ED-15390 | 36.39 | 2026-05-03 | 2026-05-05
Distribution | July | SEALS | ED-16049 | 29.36 | 2026-05-04 | 2026-05-05
Distribution | July | SKIP | ED-16479 | 22.99 | 2026-05-04 | 2026-05-05
Distribution | July | SNOWDEN | ED-16590 | 14.06 | 2026-05-04 | 2026-05-05
Distribution | July | STERLING | ED-16980 | 4.62 | 2026-05-05 | 2026-05-05
Distribution | July | WEISS | ED-19136 | 19.57 | 2026-05-05 | 2026-05-06
Distribution | July | ACKLEY | ED-00043 | 6.16 | 2026-04-29 | 2026-05-04
Distribution | July | ADOBE | ED-00095 | 8.88 | 2026-04-28 | 2026-05-04
Distribution | July | ALMANSOR | ED-00350 | 3.78 | 2026-05-03 | 2026-05-04
Distribution | July | ANCHOR | ED-00514 | 5.3 | 2026-04-29 | 2026-05-04
Distribution | July | ANN | ED-00565 | 15.13 | 2026-04-27 | 2026-05-03
Distribution | July | ARDIS | ED-00690 | 6.33 | 2026-04-29 | 2026-05-04
Distribution | July | ARGONNE | ED-00695 | 3.15 | 2026-05-03 | 2026-05-04
Distribution | July | ASTEROID | ED-00813 | 12.8 | 2026-04-28 | 2026-05-03
Distribution | July | AVON | ED-00881 | 4.44 | 2026-05-03 | 2026-05-04
Distribution | July | BACON | ED-00930 | 6.69 | 2026-04-29 | 2026-05-04
Distribution | July | BARLEY FLATS | ED-01100 | 10.66 | 2026-04-28 | 2026-05-03
Distribution | July | BATEMAN | ED-01210 | 8.3 | 2026-04-28 | 2026-05-03
Distribution | July | BENEDICT | ED-01490 | 0.87 | 2026-04-28 | 2026-05-04
Distribution | July | BILTON | ED-01680 | 13.2 | 2026-04-27 | 2026-05-03
Distribution | July | BLANKET | ED-01800 | 6.5 | 2026-04-29 | 2026-05-04
Distribution | July | BOGART | ED-01869 | 2.2 | 2026-04-28 | 2026-05-04
Distribution | July | BORDEN | ED-01975 | 4.64 | 2026-04-29 | 2026-05-04
Distribution | July | BOXER | ED-02050 | 5.6 | 2026-04-29 | 2026-05-04
Distribution | July | BOYER | ED-02060 | 1.55 | 2026-04-28 | 2026-05-04
Distribution | July | BRAYTON | ED-02170 | 5.5 | 2026-05-03 | 2026-05-04
Distribution | July | BRENT | ED-02190 | 3.3 | 2026-05-03 | 2026-05-04
Distribution | July | BRETHREN | ED-02192 | 4.04 | 2026-04-29 | 2026-05-04
Distribution | July | BUDLONG | ED-02380 | 3.89 | 2026-05-03 | 2026-05-04
Distribution | July | CALYPSO | ED-02763 | 15.5 | 2026-04-27 | 2026-05-03
Distribution | July | CAWSTON | ED-03190 | 0.65 | 2026-04-29 | 2026-05-04
Distribution | July | CHRIS | ED-01070 | 9.95 | 2026-04-28 | 2026-05-03
Distribution | July | CLIFFORD | ED-03655 | 6.69 | 2026-04-29 | 2026-05-04
Distribution | July | CLOVERLY | ED-03700 | 3.82 | 2026-04-29 | 2026-05-04
Distribution | July | COGSWELL | ED-03750 | 5.47 | 2026-05-03 | 2026-05-04
Distribution | July | COLDWATER | ED-03770 | 1.26 | 2026-04-28 | 2026-05-04
Distribution | July | COLYER | ED-03840 | 13.66 | 2026-04-27 | 2026-05-03
Distribution | July | COMMONWEALTH | ED-03860 | 2.75 | 2026-05-03 | 2026-05-04
Distribution | July | CORRINE | ED-04103 | 4.27 | 2026-04-29 | 2026-05-04
Distribution | July | CYCLOPS | ED-04553 | 2.28 | 2026-05-03 | 2026-05-04
Distribution | July | CYLINDER | ED-04554 | 5.93 | 2026-04-29 | 2026-05-04
Distribution | July | DAELEY | ED-04626 | 1.3 | 2026-04-29 | 2026-05-04
Distribution | July | DAHLIA | ED-04590 | 7.49 | 2026-04-29 | 2026-05-04
Distribution | July | DIE | ED-05075 | 8.12 | 2026-04-28 | 2026-05-04
Distribution | July | DUNROBIN | ED-05430 | 5.77 | 2026-04-29 | 2026-05-04
Distribution | July | EL CENTRO | ED-05650 | 2.74 | 2026-05-03 | 2026-05-04
Distribution | July | ELDRIDGE | ED-05676 | 5.82 | 2026-04-29 | 2026-05-04
Distribution | July | FACTORY | ED-06177 | 1.95 | 2026-04-28 | 2026-05-04
Distribution | July | FLANDERS | ED-06500 | 4.48 | 2026-04-29 | 2026-05-04
Distribution | July | FLORENCE | ED-06551 | 14.27 | 2026-04-27 | 2026-05-03
Distribution | July | FOREST | ED-06660 | 8.78 | 2026-04-28 | 2026-05-03
Distribution | July | GATLIN | ED-07112 | 0.64 | 2026-04-28 | 2026-05-04
Distribution | July | GERONA | ED-07180 | 8.83 | 2026-04-29 | 2026-05-03
Distribution | July | GREENWELL | ED-07618 | 0.8 | 2026-04-28 | 2026-05-04
Distribution | July | HARBOR | ED-07980 | 9.15 | 2026-04-28 | 2026-05-03
Distribution | July | HARDHAT | ED-08010 | 0.57 | 2026-04-28 | 2026-05-04
Distribution | July | HARKNESS | ED-08040 | 6.1 | 2026-04-29 | 2026-05-04
Distribution | July | ASTORIA | ED-00815 | 5.16 | 2026-05-06 | 2026-05-06
Distribution | July | AUSTIN | ED-00873 | 7.52 | 2026-05-05 | 2026-05-06
Distribution | July | BAYLOR | ED-01255 | 14.23 | 2026-05-06 | 2026-05-06
Distribution | July | BEN NEVIS | ED-01497 | 14.03 | 2026-05-05 | 2026-05-06
Distribution | July | BOLLERO | ED-01891 | 4.72 | 2026-05-05 | 2026-05-06
Distribution | July | CAMEO | ED-02773 | 6.89 | 2026-05-06 | 2026-05-06
Distribution | July | CERAMIC | ED-03296 | 5.99 | 2026-05-05 | 2026-05-06
Distribution | July | COMPLEX | ED-03873 | 6.41 | 2026-05-05 | 2026-05-06
Distribution | July | DORIS | ED-05215 | 5.23 | 2026-05-05 | 2026-05-06
Distribution | July | DRIFTWOOD | ED-05317 | 9.83 | 2026-05-05 | 2026-05-06
Distribution | July | FAIRWAY | ED-06250 | 5.81 | 2026-05-05 | 2026-05-06
Distribution | July | FLABOB | ED-06497 | 3.27 | 2026-05-06 | 2026-05-06
Distribution | July | GASTON | ED-07100 | 15.9 | 2026-05-06 | 2026-05-06
Distribution | July | GLACIER | ED-07276 | 9.37 | 2026-05-06 | 2026-05-06
Distribution | July | MATERA | ED-11335 | 0.54 | 2026-05-05 | 2026-05-06
Distribution | July | NAPOLEON | ED-12485 | 8.23 | 2026-05-05 | 2026-05-06
Distribution | July | OZARK | ED-13409 | 2.05 | 2026-05-05 | 2026-05-06
Distribution | July | PALA | ED-13542 | 4.09 | 2026-05-06 | 2026-05-07
Distribution | July | PIERSON | ED-14082 | 2.17 | 2026-05-05 | 2026-05-06
Distribution | July | PINE COVE | ED-14097 | 22.73 | 2026-05-05 | 2026-05-06
Distribution | July | POTTERY | ED-14378 | 9.95 | 2026-05-05 | 2026-05-06
Distribution | July | RANIER | ED-14705 | 4.01 | 2026-05-05 | 2026-05-06
Distribution | July | SERNA | ED-16147 | 4.02 |  | 2026-05-06
Distribution | July | STAGELINE | ED-16882 | 12.12 | 2026-05-05 | 2026-05-06
Distribution | July | TOWNHALL | ED-18043 | 16.88 | 2026-05-05 | 2026-05-06
Distribution | July | WINERY | ED-19528 | 51.84 | 2026-05-05 | 2026-05-06
Distribution | July | YUBAN | ED-19787 | 8.08 | 2026-05-05 | 2026-05-06
Distribution | July | HAYS | ED-08240 | 16.06 | 2026-04-26 | 2026-04-27
Distribution | July | HOMER | ED-08640 | 20.74 | 2026-04-26 | 2026-04-27
Distribution | July | REDBANKS | ED-14750 | 39.42 | 2026-04-26 | 2026-04-27
Distribution | July | SHIRK | ED-16359 | 9.02 | 2026-04-26 | 2026-04-28
Distribution | July | TERMINUS | ED-17672 | 28.73 | 2026-04-26 | 2026-04-27
Distribution | July | WHEY | ED-19239 | 14.72 | 2026-04-26 | 2026-04-28
Distribution | August | HURLEY | ED-08847 | 9.13
Distribution | August | LATHE | ED-10184 | 5.58
Distribution | August | SKI | ED-16477 | 6.41
Distribution | August | STEELMAN | ED-16974 | 18.49
Distribution | August | STOCKTON | ED-17006 | 6.05
Distribution | August | FURNACE CREEK | ED-06885 | 49.7 | 2026-05-18 | 2026-05-20
Distribution | August | GRAPEVINE | ED-07513 | 7.48 | 2026-05-18 | 2026-05-20
Distribution | August | HOMEWOOD | ED-08645 | 6.55 | 2026-05-18 | 2026-05-20
Distribution | August | ALICIA | ED-00307 | 4.11
Distribution | August | ANAWALT | ED-00510 | 14
Distribution | August | ANDRIA | ED-00535 | 10.47
Distribution | August | ARMSTRONG | ED-00740 | 4.71
Distribution | August | BEASLEY | ED-01340 | 7.76
Distribution | August | BENSON | ED-01518 | 1.95
Distribution | August | CACTUS | ED-02600 | 3.94
Distribution | August | CHIME | ED-03472 | 4
Distribution | August | CURRAN | ED-04505 | 4.28
Distribution | August | DALMATIAN | ED-04628 | 4.91
Distribution | August | EAST END | ED-05502 | 0.96
Distribution | August | FERNSTROM | ED-06340 | 4.62
Distribution | August | GAREY | ED-07040 | 5.78
Distribution | August | HAMBONE | ED-07900 | 1.11
Distribution | August | HEDBERG | ED-08274 | 1.81
Distribution | August | JURUPA | ED-09420 | 10.19
Distribution | August | KINGSLEY | ED-09760 | 12.02
Distribution | August | LOBET | ED-10580 | 6.57
Distribution | August | MAITLAND | ED-10970 | 4.04
Distribution | August | MARBUCK | ED-11175 | 7.75
Distribution | August | PANHANDLE | ED-13731 | 0.33
Distribution | August | PATE | ED-13778 | 10.11
Distribution | August | PINEAPPLE | ED-14095 | 13.74
Distribution | August | PLATOON | ED-14189 | 3.97
Distribution | August | PRODUCTS | ED-14436 | 6.26
Distribution | August | ROCK | ED-15300 | 4.03
Distribution | August | SAPPHIRE | ED-15880 | 7.38
Distribution | August | SIREN | ED-16461 | 1.36
Distribution | August | SKYLAND | ED-16480 | 7.21
Distribution | August | SPANADA | ED-16726 | 13.26
Distribution | August | SPECTRUM | ED-16763 | 2.59
Distribution | August | THOR | ED-17785 | 12.73
Distribution | August | TITUS | ED-17912 | 1.91
Distribution | August | WILLIS | ED-19417 | 9.13
Distribution | August | YOUNKIN | ED-19785 | 2.54
Distribution | August | ADAK | ED-00070 | 6.1
Distribution | August | ALBACORE | ED-00245 | 8.24
Distribution | August | ANZA | ED-00600 | 2.95
Distribution | August | BARGE | ED-01097 | 7.64
Distribution | August | BUTANE | ED-02540 | 15.86
Distribution | August | CALM | ED-02735 | 6.14
Distribution | August | CARTER | ED-03030 | 8.35
Distribution | August | CORY | ED-04138 | 3.35
Distribution | August | ELEVADO | ED-05690 | 2.13
Distribution | August | FACTOR | ED-06175 | 2.07
Distribution | August | FAIRBANKS | ED-06200 | 4.52
Distribution | August | GEM | ED-07145 | 2.37
Distribution | August | HAWTHORNE | ED-08180 | 10.73
Distribution | August | INTERSTATE | ED-08940 | 4.59
Distribution | August | KELVINATOR | ED-09580 | 12.6
Distribution | August | LADERA | ED-09970 | 4.05
Distribution | August | LIBERATOR | ED-10435 | 0.82
Distribution | August | LLEWELLYN | ED-10560 | 5.25
Distribution | August | LOCK | ED-10620 | 4.3
Distribution | August | LOQUAT | ED-10708 | 5.74
Distribution | August | MCDONNELL | ED-11479 | 8.07
Distribution | August | MENLO | ED-11640 | 2.28
Distribution | August | NARBONNE | ED-12490 | 5.3
Distribution | August | OCTANE | ED-13040 | 10.05
Distribution | August | PACOMA | ED-13470 | 8.87
Distribution | August | PANSY | ED-13650 | 7.35
Distribution | August | PATTIE | ED-13810 | 4.59
Distribution | August | SPINEL | ED-16777 | 2.24
Distribution | August | SPINNING | ED-16790 | 6.67
Distribution | August | STORM | ED-17065 | 16.69
Distribution | August | SUNDALE | ED-17250 | 4.38
Distribution | August | TYBURN | ED-18385 | 0.18
Distribution | August | VAN WICK | ED-18620 | 8.52
Distribution | August | WINONA | ED-19550 | 5.7
Distribution | August | YORK | ED-19770 | 2
Distribution | August | ZEBRA | ED-19810 | 7.36
Distribution | August | ABERDEEN | ED-00021 | 4.83
Distribution | August | ALLRED | ED-00333 | 5.72
Distribution | August | ALONDRA | ED-00360 | 4.12
Distribution | August | BABER | ED-00919 | 11.56
Distribution | August | CANDLE | ED-02850 | 8.26
Distribution | August | CAPETOWN | ED-02900 | 2.45
Distribution | August | CAR WASH | ED-03065 | 1.59
Distribution | August | CARO | ED-03001 | 9.49
Distribution | August | COLDBROOK | ED-03766 | 1.62
Distribution | August | CONGRESS | ED-03935 | 3.03
Distribution | August | DOHN | ED-05150 | 6.77
Distribution | August | DORNES | ED-05218 | 8.57
Distribution | August | DUNBAR | ED-05380 | 5.87
Distribution | August | DURHAM | ED-05462 | 0.49
Distribution | August | EMORY | ED-05895 | 0.94
Distribution | August | HACKBERRY | ED-07825 | 17.5
Distribution | August | HARTLE | ED-08112 | 2.37
Distribution | August | HEARTWELL | ED-08269 | 1.72
Distribution | August | JAMES | ED-09120 | 4.34
Distribution | August | JAYBLUE | ED-09188 | 5.25
Distribution | August | JUDGE | ED-09375 | 4.26
Distribution | August | LEMONT | ED-10350 | 2.95
Distribution | August | LONGHORN | ED-10689 | 1.3
Distribution | August | MAPES | ED-11156 | 12.41
Distribution | August | MAPLEWOOD | ED-11160 | 7.85
Distribution | August | MARTY | ED-11301 | 3.78
Distribution | August | NELLES | ED-12600 | 4.19
Distribution | August | ORA | ED-13200 | 5.16
Distribution | August | POPPY | ED-14340 | 10.03
Distribution | August | PRESIDENT | ED-14398 | 14.43
Distribution | August | PRIDA | ED-12779 | 7.71
Distribution | August | PRIVET | ED-14432 | 11.17
Distribution | August | RATON | ED-14713 | 5.33
Distribution | August | REDSKIN | ED-14813 | 13.47
Distribution | August | REX | ED-14930 | 4.12
Distribution | August | RODNEY | ED-15335 | 1.24
Distribution | August | SENATE | ED-16122 | 2.28
Distribution | August | SHARP | ED-16270 | 3.88
Distribution | August | STAMPER | ED-16920 | 4.25
Distribution | August | TRIMBLE | ED-18150 | 5.39
Distribution | August | WILCOX | ED-19370 | 4.42
Distribution | August | WOLF | ED-19590 | 6.84
Distribution | August | BRAZIL | ED-02180 | 10.6
Distribution | August | BRIDE | ED-02204 | 1.79
Distribution | August | CABANA | ED-02577 | 2.79
Distribution | August | CATFISH | ED-03166 | 12.51
Distribution | August | CATHY | ED-03168 | 10.59
Distribution | August | CORTESE | ED-04117 | 2.23
Distribution | August | GRACE | ED-07457 | 9.93
Distribution | August | HALSEY | ED-07876 | 0.6
Distribution | August | HANDY | ED-07950 | 8.61
Distribution | August | HARVARD | ED-08130 | 3.02
Distribution | August | HAWK | ED-08193 | 7.87
Distribution | August | IRAN | ED-08955 | 11.91
Distribution | August | KENTUCKY | ED-09635 | 0.83
Distribution | August | LAWRENCE | ED-10240 | 1.68
Distribution | August | LISBON | ED-10520 | 6.54
Distribution | August | MARIGOLD | ED-11212 | 10.41
Distribution | August | MEMORY | ED-11635 | 9.23
Distribution | August | MOONWALK | ED-12164 | 10.37
Distribution | August | NIMBUS | ED-12715 | 4.44
Distribution | August | PAUL | ED-13817 | 8.75
Distribution | August | PERSIA | ED-13971 | 11.13
Distribution | August | PONTIAC | ED-14323 | 8.79
Distribution | August | RAYBESTOS | ED-14719 | 4.79
Distribution | August | ROYER | ED-15515 | 4.18
Distribution | August | RUBIN | ED-15517 | 5.58
Distribution | August | SCIENCE | ED-16004 | 0.98
Distribution | August | TARPON | ED-17551 | 8.19
Distribution | August | VERBENA | ED-18654 | 9.44
Distribution | August | WATERFIELD | ED-19044 | 3.44
Distribution | August | ALEXANDER | ED-00298 | 4.58 | 2026-05-21 | 2026-05-21
Distribution | August | ANAKIN | ED-00494 | 2.17 | 2026-05-20
Distribution | August | ASTOR | ED-00814 | 3.83 | 2026-05-21
Distribution | August | BEELINE | ED-01515 | 12.39
Distribution | August | BOX SPRING | ED-02054 | 0.45
Distribution | August | BURWOOD | ED-02525 | 7.9 | 2026-05-21 | 2026-05-21
Distribution | August | CAREY | ED-02937 | 6.72 | 2026-05-21 | 2026-05-21
Distribution | August | CHATTANOOGA | ED-03383 | 5.92 | 2026-05-21 | 2026-05-21
Distribution | August | ELLIOT | ED-05710 | 3.08 | 2026-05-21
Distribution | August | FAMOUS | ED-06272 | 2.84 | 2026-05-21
Distribution | August | FONRI | ED-06607 | 7.75 | 2026-05-21 | 2026-05-21
Distribution | August | GARNER | ED-07060 | 4.55
Distribution | August | HANGER | ED-07960 | 22.15 | 2026-05-21 | 2026-05-21
Distribution | August | HASS | ED-08145 | 33.83 | 2026-05-18 | 2026-05-21
Distribution | August | HERZ | ED-08360 | 14.24
Distribution | August | LEONA | ED-10370 | 4.01 | 2026-05-22
Distribution | August | LORENE | ED-10714 | 10.22
Distribution | August | MANZER | ED-11142 | 9.35 | 2026-05-21
Distribution | August | MONTREAL | ED-12136 | 16.3 | 2026-05-21 | 2026-05-21
Distribution | August | NEVCAL | ED-12635 | 2.45 | 2026-05-21
Distribution | August | OAK CREEK | ED-12950 | 31.66 | 2026-05-19 | 2026-05-21
Distribution | August | PARKDALE | ED-13705 | 8.06
Distribution | August | PENDLETON | ED-13900 | 9.31
Distribution | August | PETAN | ED-13980 | 32.26 | 2026-05-19 | 2026-05-21
Distribution | August | PETTIS | ED-13999 | 6.94 | 2026-05-21 | 2026-05-21
Distribution | August | POINT OF ROCKS | ED-14275 | 13.51 | 2026-05-20 | 2026-05-21
Distribution | August | PUMALO | ED-14511 | 13.68 | 2026-05-21
Distribution | August | SAD | ED-15615 | 3.27 | 2026-05-21
Distribution | August | SAWPIT | ED-15954 | 6.58 | 2026-05-21 | 2026-05-21
Distribution | August | SEYMOUR | ED-16222 | 9.98
Distribution | August | SHOPS | ED-16370 | 6.56
Distribution | August | STEALTH | ED-16963 | 14.83 | 2026-05-21 | 2026-05-21
Distribution | August | TOMCAT | ED-17963 | 1.44 | 2026-05-20
Distribution | August | TWAIN | ED-18338 | 9.14 | 2026-05-21 | 2026-05-21
Distribution | August | VIADUCT | ED-18720 | 4.12
Distribution | August | BUNDY | ED-02422 | 7.9 | 2026-05-19 | 2026-05-20
Distribution | August | BURNS | ED-02480 | 7.79 | 2026-05-19 | 2026-05-20
Distribution | August | CANAL | ED-02841 | 21.94 | 2026-05-19 | 2026-05-19
Distribution | August | CITY OF BANNING #1 | ED-20905 | 2.43 | 2026-05-19 | 2026-05-21
Distribution | August | CITY OF BANNING #2 | ED-17119 | 1.13 | 2026-05-19 | 2026-05-20
Distribution | August | DELUZ | ED-04793 | 9.96 | 2026-05-19 | 2026-05-20
Distribution | August | EAGLE CREST | ED-05487 | 8.65 | 2026-05-19 | 2026-05-20
Distribution | August | FLAGSTAFF | ED-06498 | 0.82 | 2026-05-19 | 2026-05-20
Distribution | August | GREENER | ED-07574 | 6.96 | 2026-05-19 | 2026-05-20
Distribution | August | HARNAGE | ED-08055 | 10.81 | 2026-05-19 | 2026-05-20
Distribution | August | LUISENO | ED-10785 | 37.61 | 2026-05-18 | 2026-05-19
Distribution | August | MESA GRANDE | ED-11732 | 11.51 | 2026-05-19 | 2026-05-20
Distribution | August | MUDDY | ED-12304 | 14.33 | 2026-05-19 | 2026-05-20
Distribution | August | PICONI | ED-14043 | 17.25 | 2026-05-19 | 2026-05-20
Distribution | August | RECTIFIER | ED-21048 | 0.26 | 2026-05-19 | 2026-05-20
Distribution | August | RESORT | ED-14923 | 29.99 | 2026-05-18 | 2026-05-20
Distribution | August | ROMERO | ED-15376 | 1.21 | 2026-05-19 | 2026-05-20
Distribution | August | ROUNDEL | ED-15468 | 5.78 | 2026-05-19 | 2026-05-20
Distribution | August | SDGE 520 | ED-30520 | 2.11 | 2026-05-19 | 2026-05-20
Distribution | August | SDGE 521 | ED-30521 | 0.86 | 2026-05-19 | 2026-05-20
Distribution | August | SEAWOLF | ED-16075 | 3.37 | 2026-05-19 | 2026-05-20
Distribution | August | SHETLAND | ED-16349 | 2.82 | 2026-05-19 | 2026-05-20
Distribution | August | SKINNER | ED-16492 | 10.63 | 2026-05-19 | 2026-05-20
Distribution | August | SOPHIE | ED-16673 | 30.8 | 2026-05-18 | 2026-05-20
Distribution | August | SPRAGUE | ED-16795 | 39.74 | 2026-05-18 | 2026-05-19
Distribution | August | TEMECK | ED-17653 | 0.1 | 2026-05-19 | 2026-05-20
Distribution | August | HACKMAN | ED-07822 | 41.49
Distribution | August | KENO | ED-09625 | 122.07 | 2026-05-21
Distribution | August | OLANCHA | ED-13082 | 13.45
Distribution | August | POTATO | ED-14371 | 15.36
Distribution | August | ROBIN | ED-15275 | 13.85
Distribution | August | RYE | ED-15604 | 9.67
Distribution | August | STEGMAN | ED-16978 | 4.89
Distribution | August | TUSSING | ED-18335 | 76.96
Distribution | August | VALLEY OF THE MOON | ED-18540 | 6.74
Distribution | August | WESTEND | ED-19184 | 1.3
Distribution | August | ZAPPA | ED-19807 | 9.77
Distribution | August | STRIPER | ED-17112 | 0.95 | 2026-05-21
Distribution | August | TAHQUITZ | ED-17546 | 11.13 | 2026-05-21
Distribution | August | CATTLE | ED-03170 | 28.15
Distribution | August | LATON | ED-10200 | 5.25
Distribution | August | MERRYMAN | ED-11730 | 48.01
Distribution | August | NICKERSON | ED-12690 | 60.86
Distribution | August | ROEDING | ED-15340 | 59.27
Distribution | August | WELLS | ED-19150 | 39.9
Distribution | August | CALGROVE | ED-02674 | 19.16
Distribution | August | CANALINO | ED-02842 | 0.02
Distribution | August | CARPOIL | ED-03003 | 13.33
Distribution | August | CHAPALA | ED-03350 | 0.53
Distribution | August | CHUMASH | ED-03501 | 0.5
Distribution | August | CONEJO | ED-03930 | 1.38
Distribution | August | CRUMNER | ED-04445 | 10.37
Distribution | August | EMPIRE | ED-05897 | 6.98
Distribution | August | FAYE | ED-06305 | 30.76
Distribution | August | FLYING D | ED-06585 | 58.04
Distribution | August | KANAN | ED-09455 | 0.61
Distribution | August | LAURO | ED-10210 | 0.22
Distribution | August | LINDERO | ED-10502 | 0.65
Distribution | August | MATILIJA | ED-11341 | 19.72
Distribution | August | MENTRY | ED-11644 | 2.04
Distribution | August | MULHOLLAND | ED-12350 | 20.88
Distribution | August | NEEDHAM | ED-12572 | 9.12
Distribution | August | NICHOLAS | ED-12700 | 4.5
Distribution | August | PATRICIA | ED-13791 | 40.32
Distribution | August | REJADA | ED-14892 | 3.91
Distribution | August | RHODA | ED-14960 | 3.66
Distribution | August | RIVIERA | ED-15200 | 6.33
Distribution | August | SERRA | ED-16150 | 17.37
Distribution | August | STRATHERN | ED-17090 | 9.91
Distribution | August | TRIUNFO | ED-18164 | 3.21
Distribution | August | TURNPIKE | ED-18330 | 16.21
Distribution | August | WHIZZIN | ED-19345 | 2.15
Distribution | August | ACORN | ED-00047 | 4.86
Distribution | August | ALTA | ED-00410 | 5.48
Distribution | August | ANGELES | ED-19694 | 9.39
Distribution | August | ASHMONT | ED-00802 | 2.74
Distribution | August | BRICKYARD | ED-02200 | 16.07
Distribution | August | BRONCO | ED-02280 | 15.98
Distribution | August | BRUNNER | ED-02320 | 3.89
Distribution | August | CHAPMAN | ED-03340 | 4.29
Distribution | August | CONVEYOR | ED-03951 | 12.26
Distribution | August | DELARRO | ED-04800 | 2.27
Distribution | August | DEVILS GATE | ED-05030 | 20.98
Distribution | August | GABRIELINO | ED-06891 | 1.23
Distribution | August | GARIBALDI | ED-07050 | 12.8
Distribution | August | HOLLY | ED-08590 | 4.55
Distribution | August | JOSLYN | ED-09350 | 9.56
Distribution | August | KENMORE | ED-09610 | 4.01
Distribution | August | MALDEN | ED-11010 | 13.39
Distribution | August | MARENDALE | ED-11185 | 1.44
Distribution | August | MERCER | ED-11680 | 9.82
Distribution | August | OLNEY | ED-13150 | 9.48
Distribution | August | PILGRIM | ED-14088 | 0.09
Distribution | August | PUTNEY | ED-14530 | 6.21
Distribution | August | RAVINE | ED-14726 | 12.71
Distribution | August | ROBBIE | ED-15235 | 7.53
Distribution | August | SHOEMAKER | ED-16364 | 2.9
Distribution | August | TELSTAR | ED-17645 | 7.49
Distribution | August | TORPEDO | ED-18000 | 12.93
Distribution | August | TURF | ED-18310 | 1.84
Transmission | March | ELDORADO-LUGO | ET-00106 | 176.9
Transmission | March | SPRINGVILLE-ANODE NO.1 | ET-02129 | 0.12
Transmission | March | SPRINGVILLE-ANODE NO.2 | ET-02130 | 0.14
Transmission | March | COOLWATER-SANDLOT | ET-00262 | 29.95
Transmission | March | LA CIENEGA-LA FRESA | ET-00982 | 11.95
Transmission | March | LA CIENEGA-STANHILL-WINDSOR HILLS | ET-00984 | 1.45
Transmission | March | MAGUNDEN-SPRINGVILLE NO. 1 | ET-07239 | 52.09 | 2026-09-01 | 2026-09-01
Transmission | March | MAGUNDEN-SPRINGVILLE NO. 2 | ET-07240 | 52.09 | 2026-09-01 | 2026-09-01
Transmission | March | RECTOR-RIVERWAY | ET-06602 | 7.41 | 2026-01-31 | 2026-02-01
Transmission | March | EAGLE ROCK-ALHAMBRA NO. 1 | ET-01553 | 6.02 | 2026-01-31 | 2026-02-01
Transmission | March | EAGLE ROCK-ALHAMBRA NO. 2 | ET-00819 | 6.97 | 2026-01-31 | 2026-02-01
Transmission | March | EAGLE ROCK-BEVERLY | ET-00368 | 16.09 | 2026-01-31 | 2026-02-04
Transmission | March | EAGLE ROCK-MACNEIL NO. 1 | ET-01637 | 15.26 | 2026-01-31 | 2026-02-01
Transmission | March | EAGLE ROCK-MACNEIL NO.2 | ET-00440 | 15.5 | 2026-01-31 | 2026-02-01
Transmission | March | IDLE LA FRESA-AMCO-NATIONAL SUPPLY | ET-01032 | 1.27 | 2026-01-31 | 2026-02-01
Transmission | March | IDLE LAGUNA BELL-GOODRICH-WEST | ET-02086 | 0.39 | 2026-01-31 | 2026-02-01
Transmission | March | IDLE LIGHTHIPE-IMPERIAL B | ET-02082 | 0.56 | 2026-01-31 | 2026-02-01
Transmission | March | MESA-RUSH NO. 3 | ET-00656 | 1.71 | 2026-01-31 | 2026-02-01
Transmission | March | RAVENDALE-ROSEMEAD | ET-06906 | 2.09 | 2026-01-31 | 2026-02-01
Transmission | March | RIO HONDO-AMADOR | ET-06802 | 3.58 | 2026-01-31 | 2026-02-01
Transmission | March | RIO HONDO-ANITA NO. 1 | ET-06801 | 3.21 | 2026-01-31 | 2026-02-01
Transmission | March | RIO HONDO-ANITA NO.2 | ET-00371 | 6.51 | 2026-01-31 | 2026-02-01
Transmission | March | RIO HONDO-ARCADIA | ET-06811 | 6.62 | 2026-01-31 | 2026-02-01
Transmission | March | RIO HONDO-BRADBURY | ET-06821 | 3.65 | 2026-01-31 | 2026-02-01
Transmission | March | WINDHUB-MONOLITH-WINDFARMS | ET-00158 | 11.78 | 2026-01-31 | 2026-02-01
Transmission | March | ETIWANDA-ALDER-RANDALL | ET-01573 | 9.98 | 2026-01-16 | 2026-01-31
Transmission | March | ETIWANDA-FALCON RIDGE | ET-00089 | 7.76 | 2026-01-15 | 2026-01-19
Transmission | March | IDLE CHINO-LA HABRA NO. 1 | ET-00005 | 8.68 | 2026-01-15 | 2026-01-15
Transmission | March | IDLE CHINO-LA HABRA NO. 2 | ET-00006 | 8.68 | 2026-01-15 | 2026-01-15
Transmission | March | IDLE CRATER-POTRERO-THOUSAND OAKS | ET-00536 | 0.4 | 2026-01-17 | 2026-01-19
Transmission | March | IDLE GOLETA-GAVIOTA | ET-02492 | 0.93 | 2026-01-18 | 2026-01-19
Transmission | March | IDLE ROYAL-SHELLINE-VALDEZ | ET-00750 | 0.44 | 2026-01-17 | 2026-01-19
Transmission | March | IDLE SANTA BARBARA-SAN MARCOS-VEGAS | ET-06969 | 2.05 | 2026-01-18 | 2026-01-19
Transmission | March | IDLE SANTA CLARA-P.S. 11 | ET-07052 | 25.02 | 2026-01-15 | 2026-01-18
Transmission | March | MOORPARK-NEWBURY | ET-00177 | 8.54 | 2026-01-19 | 2026-01-19
Transmission | March | SAN MARCOS-VEGAS | ET-06985 | 3.18 | 2026-01-17 | 2026-01-18
Transmission | March | VISTA-ALUMAX-HUNTER | ET-01185 | 2.61 | 2026-01-17 | 2026-01-19
Transmission | March | CAPSULE-CARDIFF | ET-00823 | 1.08 | 2026-01-15 | 2026-01-19
Transmission | March | CARDIFF-DEL ROSA | ET-00722 | 4.16 | 2026-01-15 | 2026-01-18
Transmission | March | CARMENITA-MURPHY-PIONEER-TELEGRAPH | ET-00765 | 11.33 | 2026-01-14 | 2026-01-15
Transmission | March | CENTER-DOWNEYMED-STEWART | ET-00924 | 3.22 | 2026-01-15 | 2026-01-15
Transmission | March | CENTER-GALLATIN | ET-00848 | 4.55 | 2026-01-15 | 2026-01-15
Transmission | March | CHANNEL ISLAND-LEHMAN-LEVY-OXGEN | ET-01645 | 7.34 | 2026-01-15 | 2026-01-15
Transmission | March | CHINO-FIREHOUSE NO. 1 | ET-01767 | 7.13 | 2026-01-14 | 2026-01-14
Transmission | March | CHINO-FIREHOUSE NO. 2 | ET-01771 | 7.17 | 2026-01-14 | 2026-01-15
Transmission | March | CHINO-FRANCIS | ET-01693 | 5.36 | 2026-01-12 | 2026-01-13
Transmission | March | CHINO-NAROD NO.1 | ET-01057 | 4.4 | 2026-01-12 | 2026-01-13
Transmission | March | CHINO-NAROD NO.2 | ET-00736 | 3.5 | 2026-01-14 | 2026-01-14
Transmission | March | COLTON-CENTURY | ET-01439 | 0.02 | 2026-01-15 | 2026-01-19
Transmission | March | COLTON-HUB | ET-01438 | 0.04 | 2026-01-15 | 2026-01-19
Transmission | March | DECLEZ-NIAGARA-THRIVE | ET-01959 | 8.8 | 2026-01-14 | 2026-01-15
Transmission | March | DEL AMO-SOMERSET | ET-01445 | 4.05 | 2026-01-15 | 2026-01-15
Transmission | March | EL NIDO-FELTON | ET-01366 | 2.2 | 2026-01-17 | 2026-01-19
Transmission | March | ESTERO-LEVY-ORMOND BEACH-WASTEWATER-WILL | ET-01374 | 12.69 | 2026-01-12 | 2026-01-13
Transmission | March | ESTERO-MISSILE | ET-01686 | 1.33 | 2026-01-17 | 2026-01-19
Transmission | March | ETIWANDA-FURNACE-ROLLING | ET-01127 | 3.4 | 2026-01-15 | 2026-01-18
Transmission | March | HINSON-LONG BEACH-STATE STREET | ET-01007 | 5.83 | 2026-01-15 | 2026-01-27
Transmission | March | HINSON-LOS CERRITOS | ET-00809 | 1.5 | 2026-01-17 | 2026-01-19
Transmission | March | HINSON-PICO | ET-00583 | 4.73 | 2026-01-14 | 2026-01-14
Transmission | March | HUGHSAIRE-SEPULVEDA | ET-01288 | 0.65 | 2026-01-15 | 2026-01-19
Transmission | March | HUGHTRON-TORRANCE-WALTERIA | ET-01302 | 2.13 | 2026-01-17 | 2026-01-19
Transmission | March | IDLE ALDER-DECLEZ | ET-00918 | 0.2 | 2026-01-26 | 2026-01-26
Transmission | March | IDLE CENTER-DEL AMO | ET-02023 | 0.13 | 2026-01-25 | 2026-01-26
Transmission | March | IDLE CHINO-BROCKWAY-GLASS-FRANCIS | ET-01228 | 0.82 | 2026-01-15 | 2026-01-15
Transmission | March | IDLE CHINO-CORONA | ET-00572 | 2.23 | 2026-01-14 | 2026-01-14
Transmission | March | IDLE CHINO-GANESHA-PEYTON NO. 2 | ET-01159 | 2.38 | 2026-01-17 | 2026-01-19
Transmission | March | IDLE CHINO-LAYFAIR | ET-00302 | 1.23 | 2026-01-15 | 2026-01-18
Transmission | March | IDLE CHINO-LIGHTHIPE | ET-01938 | 0.55 | 2026-01-15 | 2026-01-19
Transmission | March | IDLE CORONA-FIREHOUSE | ET-01425 | 0.7 | 2026-01-15 | 2026-01-19
Transmission | March | IDLE ETIWANDA-AMERON-GRAPELAND-PIPE | ET-01037 | 0.35 | 2026-01-15 | 2026-01-19
Transmission | March | IDLE LIGHTHIPE-CLEANSTEEL-NEPTUNE | ET-00335 | 0.48 | 2026-01-08 | 2026-01-18
Transmission | March | LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO1 | ET-01250 | 8.9 | 2026-01-14 | 2026-02-01
Transmission | March | LA FRESA-VICTORIA NO. 1 | ET-04308 | 3.13 | 2026-01-18 | 2026-01-18
Transmission | March | LAGUNA BELL-FEDERALGEN-FRUITLAND | ET-01289 | 6.02 | 2026-01-15 | 2026-01-19
Transmission | March | LAGUNA BELL-YBARRA | ET-01787 | 2.68 | 2026-01-15 | 2026-01-19
Transmission | March | LIGHTHIPE-CALDEN-FERNWOOD-SHRED | ET-01886 | 14.38 | 2026-01-15 | 2026-01-15
Transmission | March | WALNUT-BASSETT-MERCED | ET-00305 | 7.67 | 2026-01-14 | 2026-01-15
Transmission | March | WALNUT-PUENTE-RAILROAD-SANTEE | ET-00681 | 4.29 | 2026-01-15 | 2026-02-01
Transmission | March | MIRA LOMA-CORONA-PEDLEY | ET-01740 | 12.96 | 2026-01-07 | 2026-01-11
Transmission | March | OLINDA-CAROLINA | ET-01450 | 5.99 | 2026-01-07 | 2026-01-14
Transmission | March | OLINDA-LA HABRA NO. 1 | ET-01605 | 2.23 | 2026-01-07 | 2026-01-31
Transmission | March | OLINDA-LA HABRA NO. 2 | ET-01608 | 2.33 | 2026-01-17 | 2026-01-14
Transmission | March | VISTA-BLOOMINGTON-GLEN AVON | ET-02063 | 16.82 | 2026-01-07 | 2026-01-15
Transmission | March | BRYAN-IRVINE-LAS LOMAS | ET-00101 | 1.41 | 2026-01-18 | 2026-01-19
Transmission | March | BRYAN-MODENA | ET-01349 | 4.94 | 2026-01-18 | 2026-01-18
Transmission | March | CAMDEN-CHESTNUT-TALBERT | ET-01513 | 4.87 | 2026-01-18 | 2026-01-22
Transmission | March | DEL AMO-LA MIRADA | ET-00817 | 4.56 | 2026-01-18 | 2026-01-19
Transmission | March | ELLIS-FAIRVIEW-GISLER | ET-00801 | 2.32 | 2026-01-18 | 2026-01-19
Transmission | March | ELLIS-GISLER-ORCOSAN | ET-00790 | 1.83 | 2026-01-18 | 2026-01-19
Transmission | March | IDLE BRYAN-MODENA-TUSTIN | ET-01441 | 1.58 | 2026-01-18 | 2026-01-19
Transmission | March | IDLE ELLIS-OCEANVIEW | ET-01733 | 0.61 | 2026-01-18 | 2026-01-19
Transmission | March | JOHANNA-CAMDEN-THADDEUS | ET-02007 | 1.86 | 2026-01-19 | 2026-01-19
Transmission | March | LA HABRA-MWD-TELEGRAPH | ET-01327 | 4.53 | 2026-01-18 | 2026-01-19
Transmission | March | VILLA PARK-ORANGE NO. 1 | ET-01283 | 3.33 | 2026-01-18 | 2026-01-19
Transmission | March | VILLA PARK-ORANGE NO. 2 | ET-01284 | 3.32 | 2026-01-18 | 2026-01-19
Transmission | March | BIG CREEK 2-BIG CREEK 8 | ET-00545 | 1.72 | 2026-01-29 | 2026-02-01
Transmission | March | BIG CREEK 3-BIG CREEK 4 | ET-00577 | 5.63 | 2026-01-31 | 2026-02-01
Transmission | March | BIG CREEK 3-BIG CREEK 8 | ET-00609 | 7.1 | 2026-01-31 | 2026-02-01
Transmission | March | RECTOR-VESTAL NO. 1 | ET-01083 | 33.37 | 2026-09-01 | 2026-09-01
Transmission | March | RECTOR-VESTAL NO. 2 | ET-06644 | 33.38 | 2026-09-01 | 2026-09-01
Transmission | March | ARCOGEN-HINSON NO. 1 | ET-01433 | 1.49 | 2026-01-08 | 2026-01-13
Transmission | March | ARCOGEN-HINSON NO. 2 | ET-01434 | 1.48 | 2026-01-08 | 2026-01-14
Transmission | March | CENTER-DEL AMO | ET-00490 | 6.07 | 2026-01-08 | 2026-01-13
Transmission | March | CHINO-MIRA LOMA NO.3 | ET-00592 | 6.75 | 2026-01-11 | 2026-01-15
Transmission | March | DEL AMO-LAGUNA BELL | ET-01062 | 18.99 | 2026-01-12 | 2026-01-27
Transmission | March | EL NIDO-EL SEGUNDO | ET-01618 | 2.91 | 2026-01-26 | 2026-01-27
Transmission | March | HINSON-LA FRESA | ET-01038 | 14.08 | 2026-01-13 | 2026-01-22
Transmission | March | HINSON-LIGHTHIPE | ET-01050 | 6.34 | 2026-01-07 | 2026-01-11
Transmission | March | LIGHTHIPE-MESA | ET-04540 | 12.24 | 2026-01-11 | 2026-01-27
Transmission | March | MOUNTAINVIEW-SAN BERNARDINO NO.3 | ET-01013 | 0.23 | 2026-01-08 | 2026-01-13
Transmission | March | MOUNTAINVIEW-SAN BERNARDINO NO.4 | ET-01018 | 0.25 | 2026-01-07 | 2026-01-14
Transmission | March | PARDEE-SANTA CLARA | ET-00776 | 39.78 | 2026-01-14 | 2026-01-14
Transmission | March | PARDEE-VINCENT NO. 1 | ET-01925 | 31.78 | 2026-01-11 | 2026-01-14
Transmission | March | PARDEE-VINCENT NO. 2 | ET-00669 | 31.94 | 2026-01-11 | 2026-01-14
Transmission | March | SAN BERNARDINO-VISTA | ET-00785 | 8.14 | 2026-01-07 | 2026-02-01
Transmission | March | SANTA CLARA-VINCENT | ET-00770 | 69.89 | 2026-01-17 | 2026-01-26
Transmission | March | CIMA-ELDORADO-PISGAH NO.1 | ET-00096 | 109.14 | 2026-02-02 | 2026-02-03
Transmission | March | GOODRICH-MESA | ET-00637 | 8.85 | 2026-02-02 | 2026-02-04
Transmission | March | IVANPAH-PRIMM | ET-00188 | 9.64 | 2026-02-02 | 2026-02-04
Transmission | March | LUGO-VINCENT NO.1 | ET-00112 | 46.9 | 2026-02-02 | 2026-02-04
Transmission | March | LUGO-VINCENT NO.2 | ET-00104 | 46.93 | 2026-02-02 | 2026-02-04
Transmission | March | MAGUNDEN-OMAR | ET-00491 | 9.4 | 2026-02-02 | 2026-02-04
Transmission | March | MIDWAY-VINCENT NO.1 | ET-00126 | 112.49 | 2026-02-02 | 2026-02-04
Transmission | March | CIMA-ELDORADO-PISGAH NO.2 | ET-00465 | 109.47 | 2026-02-02 | 2026-02-03
Transmission | March | MESA-VINCENT NO. 1 | ET-01091 | 35.98 | 2026-02-02 | 2026-02-03
Transmission | March | MESA-VINCENT NO. 2 | ET-01093 | 36.36 | 2026-02-02 | 2026-02-03
Transmission | March | MESA-WALNUT | ET-00689 | 13.91 | 2026-02-02 | 2026-02-03
Transmission | March | MIDWAY-VINCENT NO.2 | ET-00127 | 112.72 | 2026-02-02 | 2026-02-03
Transmission | March | PARDEE-PASTORIA-WARNE | ET-00624 | 41.58 | 2026-02-02 | 2026-02-03
Transmission | March | RATTLESNAKE-WHIRLWIND | ET-01927 | 0.63 | 2026-02-02 | 2026-02-03
Transmission | March | VICTOR-RIVERTEX | ET-01001 | 8.67 | 2026-02-02 | 2026-02-03
Transmission | March | VICTOR-SAVAGE NO.3 | ET-00193 | 7.05 | 2026-02-02 | 2026-02-03
Transmission | March | BAILEY-PARDEE | ET-00665 | 26.83 | 2026-02-03 | 2026-02-04
Transmission | March | BAILEY-PASTORIA | ET-00655 | 12.44 | 2026-02-03 | 2026-02-04
Transmission | March | CALDWELL-COLUSA-VICTOR | ET-02028 | 7.63 | 2026-02-03 | 2026-02-04
Transmission | March | COOLWATER-SEGS 2-TORTILLA | ET-01363 | 13.31 | 2026-02-03 | 2026-02-04
Transmission | March | COOLWATER-SILVER SPRINGS | ET-02033 | 0.07 | 2026-02-03 | 2026-02-04
Transmission | March | IDLE MIRA LOMA-VINCENT | ET-00390 | 0.05 | 2026-02-03 | 2026-02-04
Transmission | March | LA FRESA-LAGUNA BELL | ET-04320 | 16.69 | 2026-02-03 | 2026-02-04
Transmission | March | MAGUNDEN-VESTAL NO. 1 | ET-08214 | 35.8 | 2026-02-03 | 2026-02-04
Transmission | March | MAGUNDEN-VESTAL NO. 2 | ET-08342 | 35.8 | 2026-02-03 | 2026-02-04
Transmission | March | MESA-RIO HONDO NO.1 | ET-01968 | 10.99 | 2026-02-03 | 2026-02-04
Transmission | March | PARDEE-PASTORIA | ET-00667 | 38.74 | 2026-02-03 | 2026-02-04
Transmission | March | EDMONSTON-PASTORIA | ET-00684 | 0.99 | 2026-09-01 | 2026-09-01
Transmission | March | CRAFTON HILLS-MENTONE-ZANJA | ET-01832 | 5.28 | 2026-01-07 | 2026-01-12
Transmission | March | LA FRESA-REDONDO NO.1 | ET-00216 | 4.51 | 2026-01-15 | 2026-01-18
Transmission | March | LA FRESA-REDONDO NO.2 | ET-00217 | 4.51 | 2026-01-15 | 2026-01-15
Transmission | March | MESA-REDONDO | ET-00213 | 26.19 | 2026-01-15 | 2026-01-25
Transmission | March | CENTIPEDE-COLORADO RIVER | ET-01947 | 0.1 | 2026-01-12 | 2026-01-14
Transmission | March | COACHELLA VALLEY-MIRAGE | ET-01483 | 0.84 | 2026-01-08 | 2026-01-13
Transmission | March | COLORADO RIVER-RED BLUFF NO.1 | ET-00943 | 31.56 | 2026-01-09 | 2026-01-14
Transmission | March | COLORADO RIVER-RED BLUFF NO.2 | ET-00959 | 31.55 | 2026-01-10 | 2026-01-14
Transmission | March | DESERT SUNLIGHT-RED BLUFF | ET-00123 | 0.16 | 2026-01-07 | 2026-01-14
Transmission | March | EL CASCO-SAN BERNARDINO | ET-00515 | 13.75 | 2026-01-26 | 2026-01-28
Transmission | March | ELLIS-HUNTINGTON BEACH NO.1 | ET-02994 | 4.19 | 2026-01-07 | 2026-01-12
Transmission | March | ELLIS-HUNTINGTON BEACH NO.3 | ET-01074 | 4.19 | 2026-01-08 | 2026-01-12
Transmission | March | ELLIS-JOHANNA | ET-00972 | 6.35 | 2026-01-06 | 2026-01-11
Transmission | March | ELLIS-SANTIAGO | ET-00974 | 14.68 | 2026-01-08 | 2026-01-11
Transmission | March | JOHANNA-SANTIAGO | ET-00973 | 8.32 | 2026-01-08 | 2026-01-13
Transmission | March | JULIAN HINDS-MIRAGE | ET-00226 | 46.21 | 2026-01-08 | 2026-01-08
Transmission | March | OBERON-RED BLUFF | ET-02091 | 0.16 | 2026-01-08 | 2026-01-14
Transmission | March | SERRANO-VILLA PARK NO.2 | ET-00475 | 3.2 | 2026-01-07 | 2026-01-13
Transmission | March | STADLER-TENAJA | ET-00543 | 4.61 | 2026-01-07 | 2026-01-07
Transmission | March | VALLEY-ALESSANDRO-BUNKER | ET-01621 | 15.5 | 2026-01-06 | 2026-01-07
Transmission | March | ELDORADO-IVANPAH | ET-00185 | 34.39 | 2026-02-05 | 2026-02-06
Transmission | March | ELDORADO-MCCULLOUGH | ET-00116 | 0.12 | 2026-02-05 | 2026-02-06
Transmission | March | ELDORADO-PRIMM | ET-00187 | 24.91 | 2026-02-05 | 2026-02-06
Transmission | March | PRIMM-SILVER STATE | ET-00186 | 0.07 | 2026-02-05 | 2026-02-06
Transmission | March | ELDORADO-MAGNOLIA | ET-00178 | 0.05 | 2026-09-01 | 2026-09-01
Transmission | March | SAN ONOFRE-SANTIAGO NO.1 | ET-01188 | 28.41 | 2026-05-18
Transmission | March | SAN ONOFRE-SANTIAGO NO.2 | ET-01189 | 28.41 | 2026-05-18
Transmission | April | KRAMER-VICTOR | ET-01118 | 34.84
Transmission | April | ARROYO-EAGLE ROCK | ET-01601 | 4.76 | 2026-02-27 | 2026-03-01
Transmission | April | CENTER-MESA | ET-00926 | 12.63 | 2026-02-27 | 2026-03-01
Transmission | April | ELDORADO-HARRY ALLEN | ET-01983 | 0.52 | 2026-03-01 | 2026-03-01
Transmission | April | EL NIDO-FELTON-LA CIENEGA | ET-01961 | 9.75 | 2026-03-23 | 2026-03-23
Transmission | April | MIRA LOMA-BAIN-PEDLEY | ET-01809 | 17.64 | 2026-03-26 | 2026-03-29
Transmission | April | SUNWARD-WINDHUB NO.2 | ET-02128 | 0.19 | 2026-03-29 | 2026-03-19
Transmission | April | SAN ONOFRE-SERRANO | ET-00471 | 40.06 | 2026-05-14
Transmission | April | SAN ONOFRE-VIEJO | ET-00881 | 23.31 | 2026-05-14
Transmission | April | KRAMER-TORTILLA | ET-00560 | 31.88
Transmission | April | ANTELOPE-VINCENT NO. 1 | ET-01905 | 17.44 | 2026-02-12 | 2026-02-12
Transmission | April | ANTELOPE-VINCENT NO. 2 | ET-01906 | 17.44 | 2026-02-12 | 2026-02-12
Transmission | April | CALECTRIC-HIGHGROVE NO. 2 | ET-00622 | 8.1 | 2026-02-15 | 2026-02-16
Transmission | April | CALECTRIC-SHANDIN | ET-01715 | 11.02 | 2026-02-13 | 2026-02-16
Transmission | April | CLEMENTINE-MENTONE-PUREWATER | ET-00023 | 5.05 | 2026-02-12 | 2026-02-12
Transmission | April | IDLE LUGO-MIRA LOMA (TEMP TAP LINE) | ET-01964 | 0.25 | 2026-02-15 | 2026-02-16
Transmission | April | IDLE VICTOR-APPLE VALLEY-HESPERIA | ET-02148 | 7.69 | 2026-02-12 | 2026-02-12
Transmission | April | IDLE VICTOR-AQUEDUCT-PHELAN | ET-02100 | 7.28 | 2026-02-12 | 2026-02-12
Transmission | April | LIGHTHIPE-REDONDO | ET-00219 | 14.12 | 2026-02-12 | 2026-02-12
Transmission | April | RIO HONDO-VINCENT NO.2 | ET-00707 | 32.21 | 2026-02-12 | 2026-02-17
Transmission | April | VICTOR-APPLE VALLEY-HESPERIA | ET-01430 | 17.54 | 2026-02-12 | 2026-02-16
Transmission | April | VICTOR-AQUEDUCT-HESPERIA | ET-01629 | 11.63 | 2026-02-15 | 2026-02-17
Transmission | April | VICTOR-AQUEDUCT-PHELAN | ET-01630 | 19.11 | 2026-02-12 | 2026-02-12
Transmission | April | VICTOR-PHELAN | ET-01729 | 15.28 | 2026-02-12 | 2026-02-12
Transmission | April | VICTOR-ROADWAY | ET-00200 | 5.2 | 2026-02-12 | 2026-02-12
Transmission | April | ALESSANDRO-HIGHGROVE-MAXWELL | ET-01281 | 13.25 | 2026-02-11 | 2026-02-11
Transmission | April | ELSINORE-SKYLARK | ET-01582 | 4.61 | 2026-02-11 | 2026-02-11
Transmission | April | IDLE ALESSANDRO-AULD-CAJALCO-SKYLARK | ET-01321 | 0.47 | 2026-02-11 | 2026-02-11
Transmission | April | IDLE VALLEY-AULD-SKYLARK | ET-01379 | 0.54 | 2026-02-12 | 2026-02-12
Transmission | April | LAKEVIEW-MOVAL | ET-00069 | 10.95 | 2026-02-11 | 2026-02-11
Transmission | April | NELSON-STETSON | ET-01141 | 3.83 | 2026-02-11 | 2026-02-11
Transmission | April | VALLEY-BUNKER-CAJALCO | ET-01622 | 18.38 | 2026-02-11 | 2026-02-12
Transmission | April | VALLEY-IVYGLEN | ET-01946 | 19.33 | 2026-02-11 | 2026-02-11
Transmission | April | VALLEY-MAYBERRY-MORENO-VISTA | ET-01471 | 51.65 | 2026-02-11 | 2026-02-12
Transmission | April | VALLEY-MWD-STETSON | ET-01784 | 13.11 | 2026-02-11 | 2026-02-11
Transmission | April | VALLEY-NEWCOMB | ET-01852 | 6.4 | 2026-02-11 | 2026-02-11
Transmission | April | VALLEY-NEWCOMB-SKYLARK | ET-01856 | 19.3 | 2026-02-11 | 2026-02-11
Transmission | April | VALLEY-TRITON | ET-02035 | 13.98 | 2026-02-12 | 2026-02-12
Transmission | April | BIG CREEK 3-MAMMOTH | ET-04870 | 6.67 | 2026-02-08 | 2026-02-10
Transmission | April | ARRO-CARDIFF-STODDARD | ET-00849 | 2.77 | 2026-02-17 | 2026-02-18
Transmission | April | ASTRO-CERTIFIED-SIGNAL HILL-SUNNYSIDE | ET-01156 | 4.16 | 2026-02-17 | 2026-02-18
Transmission | April | BAILEY-NEENACH-WESTPAC | ET-00827 | 21.52 | 2026-02-15 | 2026-02-18
Transmission | April | BANDUCCI-CORRECTION-CUMMINGS | ET-02156 | 6.56 | 2026-02-16 | 2026-02-17
Transmission | April | BEVERLY-STUDIO-UNIVERSAL | ET-01587 | 5.58 | 2026-02-16 | 2026-02-19
Transmission | April | BOWL-LOS CERRITOS-SIGNAL HILL | ET-01233 | 2.73 | 2026-02-17 | 2026-02-19
Transmission | April | CAL CEMENT-WINDPARKS | ET-00058 | 8.21 | 2026-02-17 | 2026-02-17
Transmission | April | CARMENITA-LA MIRADA | ET-01748 | 3.82 | 2026-02-16 | 2026-02-18
Transmission | April | CARSON-DOMHILL-NOLA-RALPHS | ET-01624 | 3.84 | 2026-02-17 | 2026-02-18
Transmission | April | CENTER-SANTA FE SPRINGS-SIGGEN | ET-00028 | 3.96 | 2026-02-16 | 2026-02-17
Transmission | April | CHATSWORTH-NATURAL | ET-00149 | 10.41 | 2026-02-16 | 2026-02-17
Transmission | April | CHATSWORTH-THRUST | ET-02045 | 0.74 | 2026-02-15 | 2026-02-17
Transmission | April | CYBER-SEPULVEDA-SERVER | ET-00628 | 1.4 | 2026-02-15 | 2026-02-17
Transmission | April | DEL AMO-ERIC NO. 1 | ET-00796 | 1.62 | 2026-02-15 | 2026-02-18
Transmission | April | DOUGLAS-SERVER | ET-00612 | 0.25 | 2026-02-17 | 2026-02-18
Transmission | April | EL NIDO-GALAXY-SPACE | ET-01293 | 1.24 | 2026-02-15 | 2026-02-18
Transmission | April | EL NIDO-SEPULVEDA-SPACE-WESBASIN | ET-01663 | 5.08 | 2026-02-20 | 2026-02-24
Transmission | April | ETIWANDA-GALVANIZING-STRIP | ET-01106 | 3.82 | 2026-02-17 | 2026-02-19
Transmission | April | ETIWANDA-ROLLING-STRIP | ET-01172 | 2.66 | 2026-02-17 | 2026-02-19
Transmission | April | GALAXY-ROSECRANS | ET-01948 | 0.52 | 2026-02-15 | 2026-02-17
Transmission | April | GOLETA-CAPITAN | ET-01576 | 7.03 | 2026-02-16 | 2026-02-18
Transmission | April | GOLETA-CAPITAN-GAVIOTA | ET-01575 | 16.34 | 2026-02-16 | 2026-02-18
Transmission | April | GOLETA-COLEGIO-ISLA VISTA-VEGAS | ET-01800 | 7.83 | 2026-02-15 | 2026-02-18
Transmission | April | GOULD-LA CANADA | ET-00381 | 2.03 | 2026-02-16 | 2026-02-17
Transmission | April | IDLE ANTELOPE-CAL CEMENT | ET-01795 | 3.53 | 2026-02-16 | 2026-02-18
Transmission | April | IDLE CARMENITA-LA MIRADA | ET-00730 | 0.45 | 2026-02-15 | 2026-02-17
Transmission | April | IDLE DEL AMO-LIGHTHIPE-CARMENITA | ET-02017 | 0.43 | 2026-02-15 | 2026-02-17
Transmission | April | IDLE ETIWANDA-BAIN-DECLEZ-REBAR | ET-01177 | 0.35 | 2026-02-13 | 2026-02-17
Transmission | April | IDLE KERN RIVER 1-MACNEIL | ET-02042 | 7.75 | 2026-02-16 | 2026-02-19
Transmission | April | IDLE LA FRESA - VICTORIA | ET-01924 | 0.7 | 2026-02-15 | 2026-02-18
Transmission | April | IDLE LIGHTHIPE-ALON-STAUFFER | ET-00752 | 0.3 | 2026-02-13 | 2026-02-17
Transmission | April | IDLE SANTA CLARA-GETTY | ET-00723 | 10.39 | 2026-02-16 | 2026-02-17
Transmission | April | IDLE SAUGUS-FILLMORE-SNTA CLRA-WAKEFIELD | ET-01098 | 18.87 | 2026-02-17 | 2026-02-19
Transmission | April | IDLE U.S. RUBBER-WHITEWALL | ET-00640 | 0.66 | 2026-02-15 | 2026-02-17
Transmission | April | LA CIENEGA-BEVERLY | ET-00996 | 4.79 | 2026-02-16 | 2026-02-19
Transmission | April | LA CIENEGA-BEVERLY-CULVER | ET-00987 | 3.88 | 2026-02-17 | 2026-02-19
Transmission | April | LA FRESA-TORRANCE-VAPOR | ET-01713 | 2.26 | 2026-02-17 | 2026-02-19
Transmission | April | LAGUNA BELL-BANDINI | ET-01557 | 3.6 | 2026-02-17 | 2026-02-18
Transmission | April | LAGUNA BELL-LEONIS-VERNON | ET-01373 | 3.65 | 2026-02-19 | 2026-02-19
Transmission | April | LIGHTHIPE-FREMONT-JERSEY | ET-00443 | 5.67 | 2026-02-16 | 2026-02-17
Transmission | April | LONG BEACH-PICO | ET-01060 | 3.58 | 2026-02-17 | 2026-02-18
Transmission | April | MESA-RAVENDALE-RUSH | ET-00843 | 12.23 | 2026-02-18 | 2026-02-19
Transmission | April | MOORPARK-VALDEZ | ET-01971 | 24.86 | 2026-02-16 | 2026-02-18
Transmission | April | NAROD-SAN ANTONIO-UPLAND | ET-00744 | 6.69 | 2026-02-17 | 2026-02-18
Transmission | April | NORTH OAKS-SOLEMINT | ET-00688 | 3.12 | 2026-02-16 | 2026-02-17
Transmission | April | PASSONS-PROCAL-SANTA FE SPRINGS | ET-01659 | 2.29 | 2026-02-16 | 2026-02-17
Transmission | April | PICO-PIER-SEABRIGHT | ET-00774 | 1.96 | 2026-02-15 | 2026-02-18
Transmission | April | SANTA CLARA-CARPINTERIA-CASITAS | ET-01949 | 23.82 | 2026-02-16 | 2026-02-18
Transmission | April | SANTA CLARA-CARPINTERIA-GETTY | ET-01950 | 24.15 | 2026-02-16 | 2026-02-19
Transmission | April | SAUGUS-ELIZABETH LAKE-MWD FOOTHILL | ET-01570 | 8.99 | 2026-02-16 | 2026-02-18
Transmission | April | WALNUT-CORTEZ-MERCED NO. 1 | ET-00898 | 8.63 | 2026-02-17 | 2026-02-18
Transmission | April | WALNUT-CORTEZ-MERCED NO. 2 | ET-00897 | 8.67 | 2026-02-17 | 2026-02-18
Transmission | April | BARRE-ELY-GILBERT | ET-00855 | 9.37 | 2026-02-10 | 2026-02-11
Transmission | April | BOLSA-OCEANVIEW-TRASK | ET-00457 | 4.59 | 2026-02-10 | 2026-02-10
Transmission | April | ELLIS-TALBERT NO. 1 | ET-00448 | 1.96 | 2026-02-10 | 2026-02-10
Transmission | April | ELLIS-TALBERT NO.2 | ET-01760 | 2.47 | 2026-02-10 | 2026-02-10
Transmission | April | IDLE BARRE-FULLERTON NO.2 | ET-00877 | 0.36 | 2026-02-10 | 2026-02-11
Transmission | April | IDLE BARRE-LAMPSON NO.2 | ET-00878 | 1.25 | 2026-02-10 | 2026-02-10
Transmission | April | IDLE VILLA PARK-CANYON-YORBA LINDA | ET-01147 | 1 | 2026-02-10 | 2026-02-11
Transmission | April | IDLE VILLA PARK-ORANGE NO. 1 | ET-01146 | 0.12 | 2026-02-10 | 2026-02-11
Transmission | April | JOHANNA-CABRILLO | ET-01516 | 2.22 | 2026-02-10 | 2026-02-11
Transmission | April | JOHANNA-CABRILLO-ESTRELLA | ET-01514 | 1.33 | 2026-02-10 | 2026-02-11
Transmission | April | OLINDA-ATWOOD-BREA-CAROLINA | ET-01689 | 9.92 | 2026-02-10 | 2026-02-10
Transmission | April | OLINDA-TELEGRAPH | ET-01611 | 5.23 | 2026-02-10 | 2026-02-11
Transmission | April | ORANGE-WASHINGTON | ET-00524 | 2.56 | 2026-02-10 | 2026-02-10
Transmission | April | SANTIAGO-CABRILLO-CHIP-MACARTHUR | ET-01644 | 7.21 | 2026-02-10 | 2026-02-10
Transmission | April | IDLE SPRINGVILLE-TULE RIVER | ET-02165 | 7.24 | 2026-02-09 | 2026-02-10
Transmission | April | VALLEY-LAKEVIEW | ET-00070 | 7.67 | 2026-02-17 | 2026-02-18
Transmission | April | ALBA-SANDLOT | ET-00284 | 0.05 | 2026-02-13 | 2026-02-17
Transmission | April | IDLE CAL CEMENT-MONOLITH-RSMOND-WNDFRMS | ET-01796 | 0.92 | 2026-02-14 | 2026-02-17
Transmission | April | KRAMER-COOLWATER | ET-00561 | 44.02 | 2026-02-13 | 2026-02-17
Transmission | April | KRAMER-SANDLOT | ET-00276 | 14.24 | 2026-02-13 | 2026-02-17
Transmission | April | LUGO-PISGAH NO.1 | ET-00290 | 65.2 | 2026-02-13 | 2026-02-17
Transmission | April | EL NIDO-LA CIENEGA | ET-00981 | 8.95 | 2026-02-25 | 2026-02-25
Transmission | April | LA CIENEGA-EL NIDO-SANTA MONICA | ET-01045 | 13.09 | 2026-02-26 | 2026-02-26
Transmission | April | LUGO-VICTOR NO. 3 | ET-00038 | 10.77 | 2026-02-25 | 2026-02-25
Transmission | April | LUGO-VICTOR NO. 4 | ET-00039 | 10.78 | 2026-02-25 | 2026-02-25
Transmission | April | LUGO-VICTOR NO.1 | ET-00299 | 10.91 | 2026-02-25 | 2026-02-25
Transmission | April | LUGO-VICTOR NO.2 | ET-00306 | 10.92 | 2026-02-25 | 2026-02-25
Transmission | April | LUGO-VICTORVILLE | ET-00117 | 7.63 | 2026-02-25 | 2026-02-25
Transmission | April | VINCENT-WINDSTAR 1 | ET-00153 | 1.35 | 2026-02-25 | 2026-02-25
Transmission | April | EL NIDO-DOUGLAS-ROSECRANS | ET-00584 | 4.28 | 2026-03-29 | 2026-03-09
Transmission | April | ELDORADO-SLOAN CANYON | ET-01984 | 0.23 | 2026-03-22 | 2026-03-22
Transmission | May | COOLWATER-TIEFORT | ET-00257 | 29.56
Transmission | May | CORUM-GOLDTOWN | ET-02503 | 18.77
Transmission | May | PADUA-MWD-SAN DIMAS | ET-01236 | 13.69
Transmission | May | BIG CREEK 1-BIG CREEK 2 | ET-00449 | 4.44 | 2026-03-02 | 2026-03-04
Transmission | May | RECTOR-GOSHEN-LIBERTY | ET-01942 | 14.07 | 2026-03-02 | 2026-03-04
Transmission | May | OCASO-SANDLOT | ET-00322 | 0.05
Transmission | May | ELDORADO-MEAD NO.1 | ET-00517 | 15.25 | 2026-03-01 | 2026-03-01
Transmission | May | ELDORADO-MEAD NO.2 | ET-00521 | 15.24 | 2026-03-01 | 2026-03-01
Transmission | May | ELDORADO-MERCHANT NO.1 | ET-00369 | 1.07 | 2026-03-01 | 2026-03-01
Transmission | May | ELDORADO-MOENKOPI | ET-00121 | 28.08 | 2026-03-01
Transmission | May | ELDORADO-MOHAVE | ET-00079 | 59.56 | 2026-03-01 | 2026-03-01
Transmission | May | ANTELOPE-DEL SUR-GLOW | ET-00155 | 2.74 | 2026-03-01 | 2026-03-01
Transmission | May | ANTELOPE-NEENACH | ET-00285 | 16.63 | 2026-03-01 | 2026-03-01
Transmission | May | DAWN-ROSAMOND-TWILIGHT | ET-00169 | 0.05 | 2026-03-01 | 2026-03-01
Transmission | May | GOLETA-CARPINTERIA-DESAL-SANTA BARBARA | ET-01597 | 30.24 | 2026-03-01 | 2026-03-02
Transmission | May | GOLETA-SANTA CLARA NO.1 | ET-00337 | 49.16 | 2026-03-01 | 2026-03-02
Transmission | May | GOLETA-SANTA CLARA NO.2 | ET-00338 | 49.16 | 2026-03-01 | 2026-03-01
Transmission | May | IDLE SAUGUS-ELIZABETH LAKE-FILLMORE | ET-00630 | 12.17 | 2026-03-01 | 2026-03-01
Transmission | May | KINGBIRD-WHIRLWIND | ET-00107 | 0.53 | 2026-03-01 | 2026-03-01
Transmission | May | MOORPARK-ROYAL NO. 2 | ET-00444 | 9.76 | 2026-03-01 | 2026-03-02
Transmission | May | SANTA CLARA-CAMARILLO | ET-01561 | 21.63 | 2026-03-01 | 2026-03-01
Transmission | May | TEDDY-WHIRLWIND | ET-00021 | 0.53 | 2026-03-01 | 2026-03-01
Transmission | May | BRIGHTON-HOWARD | ET-03193 | 1.94 | 2026-03-05 | 2026-03-05
Transmission | May | CALECTRIC-HIGHGROVE NO. 1 | ET-00623 | 7.9 | 2026-03-05 | 2026-03-06
Transmission | May | CALECTRIC-PEPPER | ET-00291 | 3.12 | 2026-03-03 | 2026-03-04
Transmission | May | CARODEAN-HI DESERT | ET-00046 | 3.92 | 2026-03-03 | 2026-03-04
Transmission | May | CARODEAN-LEATHERNECK | ET-00047 | 8.99 | 2026-03-03 | 2026-03-04
Transmission | May | CHEVMAIN-EL NIDO | ET-01709 | 1.25 | 2026-03-04 | 2026-03-05
Transmission | May | CHEVMAIN-EL SEGUNDO | ET-01710 | 1.77 | 2026-03-04 | 2026-03-05
Transmission | May | CHINO-FRANCIS-SAN ANTONIO | ET-00861 | 10.64 | 2026-03-04 | 2026-03-04
Transmission | May | CHINO-PEYTON-SOQUEL | ET-01300 | 5.8 | 2026-03-04 | 2026-03-05
Transmission | May | COTTONWOOD-SAVAGE | ET-00316 | 30.15 | 2026-03-03 | 2026-03-04
Transmission | May | DEL AMO-CORNUTA | ET-01307 | 3.26 | 2026-03-05 | 2026-03-06
Transmission | May | DEL AMO-CYPRESS NO. 1 | ET-01276 | 4.33 | 2026-03-04 | 2026-03-05
Transmission | May | DEL AMO-GREENING | ET-01955 | 4.04 | 2026-03-04 | 2026-03-04
Transmission | May | DEL AMO-HINSON | ET-00464 | 12.5 | 2026-03-07 | 2026-03-08
Transmission | May | GANESHA-SIMPSON | ET-01355 | 0.99 | 2026-03-04 | 2026-03-09
Transmission | May | GANESHA-TROPHY | ET-01209 | 3.06 | 2026-03-04 | 2026-03-08
Transmission | May | HI DESERT-LEATHERNECK-YUCCA | ET-01934 | 25.15 | 2026-03-04 | 2026-03-08
Transmission | May | HINSON-CARBONIC-NEPTUNE | ET-01704 | 3.08 | 2026-03-05 | 2026-03-08
Transmission | May | ICEGEN-JERSEY-NOLA | ET-01537 | 2.41 | 2026-03-04 | 2026-03-05
Transmission | May | IDLE DEL AMO-LAKEWOOD-TURBO | ET-01347 | 0.04 | 2026-03-04 | 2026-03-08
Transmission | May | IDLE DEL AMO-LUCAS NO. 1 | ET-02018 | 0.02 | 2026-03-03 | 2026-03-04
Transmission | May | IDLE DEL AMO-LUCAS NO. 2 | ET-02019 | 0.08 | 2026-03-03 | 2026-03-05
Transmission | May | IDLE GALLATIN-LAGUNA BELL-MERCURY-SPONGE | ET-00418 | 0.12 | 2026-03-03 | 2026-03-08
Transmission | May | IDLE INYOKERN-MCGEN-SEARLES | ET-02052 | 5.08 | 2026-04-06 | 2026-04-06
Transmission | May | IDLE WALNUT-JOHNSTON-SAN DIMAS | ET-00691 | 2 | 2026-03-03 | 2026-03-04
Transmission | May | IDLE WESTFLOR-YUKON | ET-08741 | 0.32 | 2026-03-03 | 2026-03-05
Transmission | May | KRAMER-LSP | ET-01538 | 0.2 | 2026-03-04 | 2026-03-05
Transmission | May | LA CIENEGA-EL NIDO-TAHITI | ET-01171 | 11.1 | 2026-03-04 | 2026-03-06
Transmission | May | LA CIENEGA-MOVIE | ET-01420 | 1.52 | 2026-03-04 | 2026-03-05
Transmission | May | LA FRESA-CREST | ET-01237 | 7.95 | 2026-03-05 | 2026-03-08
Transmission | May | LA FRESA-WALTERIA | ET-01234 | 5.79 | 2026-03-04 | 2026-03-05
Transmission | May | LAGUNA BELL-LEONIS | ET-04354 | 2.68 | 2026-03-08 | 2026-03-09
Transmission | May | LAGUNA BELL-LEONIS-TRIGAS | ET-04353 | 3.94 | 2026-03-08 | 2026-03-09
Transmission | May | LAGUNA BELL-NEWMARK-VAIL | ET-01558 | 9.45 | 2026-03-06 | 2026-03-08
Transmission | May | LAGUNA BELL-VAIL | ET-01218 | 3.1 | 2026-03-05 | 2026-03-08
Transmission | May | LIGHTHIPE-BULLIS-IMPERIAL-RINGMILL-WEBME | ET-01957 | 7.44 | 2026-03-04 | 2026-03-08
Transmission | May | LIGHTHIPE-CARSON NO. 1 | ET-01024 | 3.69 | 2026-03-05 | 2026-03-09
Transmission | May | LIGHTHIPE-CARSON NO. 2 | ET-01324 | 3.04 | 2026-03-05 | 2026-03-08
Transmission | May | LIGHTHIPE-SIGNAL HILL-WESTEX | ET-01061 | 8.79 | 2026-03-07 | 2026-03-10
Transmission | May | MESA-NEWMARK NO. 1 | ET-04876 | 1.2 | 2026-03-03 | 2026-03-04
Transmission | May | MESA-NEWMARK NO. 2 | ET-04877 | 1.2 | 2026-03-03 | 2026-03-04
Transmission | May | MURPHY-SANTA FE SPRINGS | ET-07098 | 1.61 | 2026-03-03 | 2026-03-04
Transmission | May | ROSECRANS-SEPULVEDA | ET-07191 | 0.37 | 2026-03-03 | 2026-03-05
Transmission | May | VICTOR-SAVAGE NO.1 | ET-00309 | 7.05 | 2026-03-03 | 2026-03-04
Transmission | May | WALNUT-NOGALES-RAILROAD NO. 2 | ET-00680 | 7.48 | 2026-03-05 | 2026-03-05
Transmission | May | ATHOS-RED BLUFF | ET-02038 | 0.16 | 2026-03-02 | 2026-03-02
Transmission | May | AULD-SUN CITY | ET-00902 | 7.69 | 2026-03-02 | 2026-03-02
Transmission | May | BARRE-CYPRESS-MARION | ET-00242 | 6.45 | 2026-03-02 | 2026-03-02
Transmission | May | BARRE-LA PALMA NO. 2 | ET-00541 | 2.7 | 2026-03-02 | 2026-03-02
Transmission | May | BARRE-SHAWNEE-TRASK | ET-01641 | 6.23 | 2026-03-03 | 2026-03-08
Transmission | May | BOVINE-LA MIRADA | ET-00334 | 5.85 | 2026-03-02 | 2026-03-02
Transmission | May | CHASE-JEFFERSON | ET-01469 | 4.72 | 2026-03-02 | 2026-03-02
Transmission | May | COLORADO RIVER-SUNCATCHER | ET-01985 | 0.02 | 2026-03-02 | 2026-03-02
Transmission | May | ELLIS-SULLIVAN NO.2 | ET-01745 | 6.08 | 2026-03-02 | 2026-03-02
Transmission | May | ELLIS-WAVE NO. 2 | ET-00501 | 4.63 | 2026-03-02 | 2026-03-02
Transmission | May | IDLE OCEANVIEW-TALBERT | ET-05584 | 1 | 2026-03-02 | 2026-03-02
Transmission | May | IDLE SANTIAGO-BRYAN-CABRLLO-IRVNE-JOHNNA | ET-01305 | 0.37 | 2026-03-02 | 2026-03-02
Transmission | May | IDLE VALLEY-AULD-TRITON | ET-00067 | 1.55 | 2026-03-02 | 2026-03-02
Transmission | May | IDLE VILLA PARK-PAPER-PLACENTIA | ET-01295 | 0.75 | 2026-03-02 | 2026-03-02
Transmission | May | JOHANNA-CABRILLO-FAIRVIEW | ET-01891 | 2.09 | 2026-03-02 | 2026-03-03
Transmission | May | JOHANNA-CHESTNUT | ET-01518 | 3.25 | 2026-03-02 | 2026-03-02
Transmission | May | OCEANVIEW-SLATER | ET-00746 | 4.38 | 2026-03-02 | 2026-03-03
Transmission | May | SANTIAGO-BORREGO | ET-00551 | 5.4 | 2026-03-02 | 2026-03-02
Transmission | May | SANTIAGO-ESTRELLA NO. 2 | ET-01521 | 4.94 | 2026-03-02 | 2026-03-02
Transmission | May | SANTIAGO-IRVINE NO. 1 | ET-01801 | 2.42 | 2026-03-02 | 2026-03-03
Transmission | May | SANTIAGO-IRVINE NO. 2 | ET-01356 | 0.88 | 2026-03-02 | 2026-03-02
Transmission | May | VALLEY-AULD NO.1 | ET-02072 | 10.88 | 2026-03-02 | 2026-03-02
Transmission | May | VALLEY-AULD NO.2 | ET-02135 | 10.39 | 2026-03-02 | 2026-03-02
Transmission | May | VIEJO-CHIQUITA NO.1 | ET-01991 | 2.98 | 2026-03-02 | 2026-03-07
Transmission | May | VIEJO-CHIQUITA NO.2 | ET-01992 | 2.98 | 2026-03-02 | 2026-03-03
Transmission | May | VIEJO-CHIQUITA-O'NEILL | ET-00732 | 3.87 | 2026-03-02 | 2026-03-02
Transmission | May | PADUA-MWD-SAN DIMAS | ET-01236 | 13.69
Transmission | May | POLYPRO-WATSON | ET-01750 | 4.22
Transmission | May | ELDORADO-MERCHANT NO.2 | ET-00378 | 1.11
Transmission | May | ELDORADO-NSO | ET-00179 | 0.05
Transmission | May | IDLE O LINE-SEAL BEACH | ET-76554 | 9.89
Transmission | June | CPC EAST-WINDHUB | ET-00585 | 0.23 | 2026-03-18 | 2026-03-19
Transmission | June | CPC WEST-WINDHUB | ET-00587 | 0.23 | 2026-03-18 | 2026-03-19
Transmission | June | DESERT STAR - WHIRLWIND | ET-00041 | 0.63 | 2026-03-18 | 2026-03-19
Transmission | June | EAGLE ROCK-MESA | ET-00771 | 24.56 | 2026-03-17 | 2026-03-19
Transmission | June | GOULD-SYLMAR | ET-00701 | 27.36 | 2026-03-17 | 2026-03-19
Transmission | June | HARBORGEN-HINSON | ET-01495 | 3.08 | 2026-03-18 | 2026-03-19
Transmission | June | HARBORGEN-LIGHTHIPE | ET-01951 | 8.48 | 2026-03-18 | 2026-03-19
Transmission | June | HIGHWIND-MANDIBLE | ET-01260 | 0.42 | 2026-03-18 | 2026-03-19
Transmission | June | MOORPARK-ORMOND BEACH NO. 1 | ET-00662 | 21.95 | 2026-04-15 | 2026-04-15
Transmission | June | MOORPARK-ORMOND BEACH NO. 2 | ET-00653 | 21.95 | 2026-04-15 | 2026-04-15
Transmission | June | MOORPARK-ORMOND BEACH NO. 3 | ET-00838 | 21.71 | 2026-03-19 | 2026-04-15
Transmission | June | MOORPARK-ORMOND BEACH NO. 4 | ET-00839 | 22 | 2026-03-19 | 2026-04-15
Transmission | June | RISING TREE-WINDHUB | ET-00399 | 0.17 | 2026-03-18 | 2026-03-19
Transmission | June | ROSE MEADOW-WHIRLWIND | ET-00840 | 0.31 | 2026-03-18 | 2026-03-19
Transmission | June | ROY-SOLAR RANCH-WHIRLWIND | ET-00013 | 0.47 | 2026-03-18 | 2026-03-19
Transmission | June | SUNCREEK-WINDHUB | ET-00910 | 0.36 | 2026-03-18 | 2026-03-19
Transmission | June | BREEZE-MONOLITH NO. 1 | ET-01436 | 0.32
Transmission | June | BREEZE-MONOLITH NO. 2 | ET-01437 | 0.3
Transmission | June | MOORPARK-PARDEE NO.4 | ET-01989 | 25.72 | 2026-04-06 | 2026-04-07
Transmission | June | VESTAL-BROWNING-QUINN | ET-01990 | 18.02 | 2026-04-20 | 2026-04-20
Transmission | June | LUGO-MOHAVE | ET-00081 | 174.99 | 2026-03-22 | 2026-03-23
Transmission | June | BARRE-APOLLO-SHAWNEE | ET-01642 | 8.59 | 2026-03-22 | 2026-03-22
Transmission | June | BARRE-ELY | ET-00466 | 5.6 | 2026-03-25 | 2026-03-25
Transmission | June | BARRE-ELY-MARION | ET-00260 | 8.27 | 2026-03-21 | 2026-03-22
Transmission | June | BREA-BROADROCK | ET-01904 | 0.87 | 2026-03-21 | 2026-03-22
Transmission | June | DIEMER-MWD | ET-01158 | 0.52 | 2026-03-18 | 2026-03-21
Transmission | June | DIEMER-YORBA LINDA | ET-01152 | 1.52 | 2026-03-19 | 2026-03-21
Transmission | June | FOGARTY-IVYGLEN | ET-00152 | 9.32 | 2026-03-19 | 2026-03-22
Transmission | June | FULLERTON-GILBERT-SUNNYHILLS | ET-01707 | 4.75 | 2026-03-21 | 2026-03-22
Transmission | June | IDLE CHINO-ARCHIBALD-BAIN-JEFFERSON | ET-00921 | 0.1 | 2026-03-22 | 2026-03-22
Transmission | June | IDLE FOGARTY-IVYGLEN | ET-02149 | 0.11 | 2026-03-19 | 2026-03-22
Transmission | June | LA VETA-WASHINGTON | ET-00909 | 2.7 | 2026-03-21 | 2026-03-22
Transmission | June | VILLA PARK-BRYAN | ET-01510 | 9.67 | 2026-03-19 | 2026-03-21
Transmission | June | SANTA CLARA-CASITAS | ET-01862 | 11.59 | 2026-03-22 | 2026-03-22
Transmission | June | SANTA CLARA-COLONIA-PROCGEN | ET-01572 | 15.78 | 2026-03-22 | 2026-03-22
Transmission | June | SANTA CLARA-OJAI | ET-00297 | 12.64 | 2026-03-22 | 2026-03-22
Transmission | June | SANTA CLARA-OJAI-SANTA BARBARA | ET-00436 | 50.8 | 2026-03-19 | 2026-03-22
Transmission | June | SANTA CLARA-TAYSHELL | ET-00423 | 10.03 | 2026-03-19 | 2026-03-22
Transmission | June | ANAVERDE-RITTER RANCH | ET-00666 | 5.49 | 2026-03-22 | 2026-03-24
Transmission | June | APL-DOCK-LONG BEACH | ET-01826 | 2.41 | 2026-03-23 | 2026-03-24
Transmission | June | BAILEY-GORMAN | ET-00237 | 3.37 | 2026-03-22 | 2026-03-23
Transmission | June | BOOST-LUCAS | ET-01874 | 6.1 | 2026-03-24 | 2026-03-24
Transmission | June | CARBOGEN-HANJIN-LONG BEACH | ET-01735 | 1.32 | 2026-03-23 | 2026-03-25
Transmission | June | CHANNEL ISLAND-MANDALAY-UNIOIL | ET-01466 | 3.51 | 2026-03-23 | 2026-03-24
Transmission | June | CHARMIN-PROCGEN | ET-01531 | 0.05 | 2026-03-23 | 2026-03-24
Transmission | June | CHINO-DIAMOND BAR-GANESHA | ET-01497 | 14.28 | 2026-03-22 | 2026-03-23
Transmission | June | CRATER-RECLAIM-TAPIA | ET-01596 | 6.04 | 2026-03-23 | 2026-03-25
Transmission | June | CREST-MARYMOUNT | ET-00757 | 2.22 | 2026-03-23 | 2026-03-24
Transmission | June | CUMMINGS-MONOLITH | ET-02157 | 7.48 | 2026-03-23 | 2026-03-23
Transmission | June | DEL AMO-CARMENITA | ET-01031 | 4.61 | 2026-03-23 | 2026-03-24
Transmission | June | DEL AMO-CORNUTA-SOMERSET | ET-01308 | 5.98 | 2026-03-24 | 2026-03-24
Transmission | June | DEL AMO-LUCAS NO. 1 | ET-01426 | 2.14 | 2026-03-24 | 2026-03-24
Transmission | June | DEL AMO-LUCAS NO. 3 | ET-01428 | 2.38 | 2026-03-23 | 2026-03-24
Transmission | June | DEL ROSA-SAN MANUEL | ET-02036 | 1.02 | 2026-03-23 | 2026-03-25
Transmission | June | DOCK-FUEL-LONG BEACH | ET-01827 | 1.06 | 2026-03-23 | 2026-03-24
Transmission | June | DOCK-NAVY MOLE | ET-01830 | 2.65 | 2026-03-23 | 2026-03-23
Transmission | June | EL NIDO-HUGHESAIR-LA FRESA | ET-01287 | 5.85 | 2026-03-26 | 2026-03-26
Transmission | June | ETIWANDA-ARBORS-FORGE-REDUCTION | ET-01065 | 2.85 | 2026-03-24 | 2026-03-24
Transmission | June | ETIWANDA-DECLEZ-LINDE | ET-01893 | 10.17 | 2026-03-23 | 2026-03-23
Transmission | June | ETIWANDA-INLAND-WIMBLEDON | ET-01336 | 5.2 | 2026-03-23 | 2026-03-26
Transmission | June | FELTON-LENNOX | ET-01367 | 2.81 | 2026-03-23 | 2026-03-24
Transmission | June | FURNACE-GALVANIZING | ET-01598 | 0.29 | 2026-03-22 | 2026-03-24
Transmission | June | GONZALES-MANDALAY-MCGRATH | ET-01039 | 5.37 | 2026-03-24 | 2026-02-25
Transmission | June | GREAT LAKES-LANCASTER-ROSAMOND | ET-00157 | 18.72 | 2026-03-24 | 2026-03-24
Transmission | June | HATHAWAY-INJECTION | ET-01824 | 2.23 | 2026-03-23 | 2026-03-25
Transmission | June | HINSON-CATHODE NO.2 | ET-02133 | 0.21 | 2026-03-23 | 2026-03-24
Transmission | June | HINSON-LIGHTHIPE-POLYPRO | ET-01752 | 6.99 | 2026-03-23 | 2026-03-26
Transmission | June | HINSON-LONG BEACH | ET-01004 | 3.79 | 2026-03-24 | 2026-03-25
Transmission | June | HOLLYWOOD PARK-INGLEWOOD | ET-02000 | 1.14 | 2026-03-24 | 2026-03-24
Transmission | June | HOLLYWOOD PARK-LENNOX | ET-01999 | 0.23 | 2026-03-24 | 2026-03-24
Transmission | June | IDLE CHINO-LIVE OAK-SAN ANTONIO-UPLAND | ET-00516 | 3.7 | 2026-03-23 | 2026-03-23
Transmission | June | IDLE CORTEZ-GARDEN STATE-LAYFAIR-SAN DMS | ET-00742 | 3.64 | 2026-03-24 | 2026-03-24
Transmission | June | IDLE GORMAN-OSITO | ET-00259 | 8.64 | 2026-03-22 | 2026-02-25
Transmission | June | IDLE LAGUNA BELL-LEONIS SOUTH | ET-02085 | 0.38 | 2026-03-25 | 2026-03-26
Transmission | June | IDLE SANTA CLARA-SAN MARCOS | ET-07083 | 8.32 | 2026-03-24 | 2026-03-25
Transmission | June | LA FRESA-VICTORIA NO. 2 | ET-04309 | 3.12 | 2026-03-24 | 2026-03-24
Transmission | June | LAGUNA BELL-CUDAHY-SHULTZ | ET-01662 | 4.32 | 2026-03-24 | 2026-03-25
Transmission | June | LIGHTHIPE-ALON-PACLINE-REFINERY | ET-01681 | 7.39 | 2026-03-26 | 2026-03-26
Transmission | June | LINDE-WIMBLEDON | ET-01869 | 2.42 | 2026-03-23 | 2026-03-23
Transmission | June | LONG BEACH-SEABRIGHT | ET-00995 | 3.91 | 2026-03-24 | 2026-03-25
Transmission | June | MARYMOUNT-ROLLING HILLS | ET-00758 | 6.53 | 2026-03-24 | 2026-02-25
Transmission | June | MESA-LAGUNA BELL-NARROWS | ET-01559 | 9.61 | 2026-03-26 | 2026-03-26
Transmission | June | MOORPARK-OAK PARK | ET-01339 | 12.76 | 2026-03-22 | 2026-03-24
Transmission | June | MOORPARK-ROYAL NO. 1 | ET-04985 | 8.65 | 2026-03-23 | 2026-03-24
Transmission | June | PADUA-LAYFAIR | ET-00860 | 13.45 | 2026-03-24 | 2026-03-24
Transmission | June | PICO-SHIP-TIDELANDS | ET-00700 | 0.49 | 2026-03-22 | 2026-03-24
Transmission | June | PICO-THUMSGEN | ET-01861 | 0.87 | 2026-03-23 | 2026-03-23
Transmission | June | PIER-PROCESS | ET-00049 | 1.95 | 2026-03-22 | 2026-03-24
Transmission | June | PROCESS-WHARF | ET-00050 | 0.37 | 2026-03-22 | 2026-03-23
Transmission | June | SAUGUS-HASKELL | ET-01571 | 2.98 | 2026-03-24 | 2026-03-24
Transmission | June | SAUGUS-HASKELL-LOCKHEED | ET-00073 | 3.36 | 2026-03-22 | 2026-03-24
Transmission | June | SAUGUS-NEWHALL-NORTH OAKS | ET-02075 | 13.47 | 2026-03-22 | 2026-03-23
Transmission | June | SAUGUS-NORTH OAKS-TENGEN | ET-01653 | 8.8 | 2026-03-23 | 2026-03-24
Transmission | June | STEVEDORE-WHARF | ET-00866 | 0.13 | 2026-03-23 | 2026-03-23
Transmission | June | WINDHUB-BROOKFIELD DESERT-CAMERON RIDGE | ET-00229 | 0.07 | 2026-03-22 | 2026-03-23
Transmission | June | WINDHUB-KALAMA | ET-00027 | 0.01 | 2026-03-22 | 2026-03-23
Transmission | June | WINDHUB-SUNSPOT | ET-00031 | 0.02 | 2026-03-22 | 2026-03-23
Transmission | June | BIG CREEK 1-EASTWOOD | ET-01081 | 4.77 | 2026-03-17 | 2026-03-19
Transmission | June | EARLIMART-PIXLEY | ET-01690 | 9.19 | 2026-03-17 | 2026-03-19
Transmission | June | HAAGEN-PROTEIN-TULARE | ET-01838 | 4.33 | 2026-03-17 | 2026-03-19
Transmission | June | RECTOR-OAKGROVE | ET-06601 | 9.26 | 2026-03-17 | 2026-03-19
Transmission | June | CAPTIVE-WELLGEN | ET-00136 | 1.83 | 2026-03-29 | 2026-03-29
Transmission | June | CENTER-IMPERIAL | ET-00871 | 3.64 | 2026-03-29 | 2026-03-29
Transmission | June | COTTONWOOD-PERMANENTE | ET-01669 | 1.9 | 2026-03-29 | 2026-03-29
Transmission | June | IDLE DEVERS-CARODEAN-HI DESERT-YUCCA | ET-01738 | 0.6 | 2026-03-29 | 2026-03-29
Transmission | June | IDLE LIGHTHIPE-SIGNAL HILL NO.2 | ET-01926 | 4.15 | 2026-03-29 | 2026-03-29
Transmission | June | IDLE SAUGUS-APPGEN-THATCHER GLASS | ET-01463 | 0.24 | 2026-03-29 | 2026-03-29
Transmission | June | RIO HONDO-DALTON-FINANCE-LARK ELLEN | ET-01711 | 5.61 | 2026-03-29 | 2026-03-29
Transmission | June | SERRANO-VALLEY | ET-00132 | 40.19 | 2026-03-26
Transmission | July | VESTAL-WHEATLAND | ET-08427 | 8.13
Transmission | July | ACTON-RITTER RANCH | ET-00904 | 5.92 | 2026-04-26 | 2026-04-26
Transmission | July | IDLE SAUGUS-LOCKHEED-THATCHER GLASS | ET-00607 | 0.16 | 2026-04-23 | 2026-04-26
Transmission | July | IDLE SAUGUS-P.S. 128 | ET-00614 | 13 | 2026-04-26 | 2026-04-27
Transmission | July | NATURAL-SUNSHINE | ET-00148 | 3.86 | 2026-04-26 | 2026-04-26
Transmission | July | NEWHALL-SAN FERNANDO-SUNSHINE | ET-00147 | 11.39 | 2026-04-26 | 2026-04-27
Transmission | July | SAUGUS-NEWHALL NO. 2 | ET-00494 | 1.6 | 2026-04-23 | 2026-04-26
Transmission | July | SAUGUS-NEWHALL NO.1 | ET-00495 | 1.6 | 2026-04-23 | 2026-04-26
Transmission | July | CASA DIABLO-RUSH CREEK | ET-00886 | 19.64 | 2026-05-06 | 2026-05-10
Transmission | July | ARBORS-ARCHLINE | ET-01880 | 2.92 | 2026-04-27 | 2026-04-29
Transmission | July | ARCHIBALD-CHINO-CORONA | ET-01029 | 14.55 | 2026-04-29 | 2026-04-29
Transmission | July | ARROWHEAD-CALECTRIC-DEVIL CANYON-SHANDIN | ET-00833 | 29.71 | 2026-05-05 | 2026-05-05
Transmission | July | CALECTRIC-HOMART-MENTONE | ET-01998 | 16.03 | 2026-04-27 | 2026-04-29
Transmission | July | CARBOGEN-WATSON | ET-01892 | 4.43 | 2026-04-27 | 2026-04-29
Transmission | July | CARDIFF-GREENSPOT-SANTA ANA RIVER 3 | ET-01834 | 13.7 | 2026-04-29 | 2026-04-30
Transmission | July | CARMENITA-ERIC | ET-00841 | 4.19 | 2026-04-29 | 2026-04-29
Transmission | July | CHERRY-STATE STREET | ET-01418 | 0.54 | 2026-04-28 | 2026-04-28
Transmission | July | CHINO-SOQUEL | ET-01548 | 2.37 | 2026-04-27 | 2026-04-29
Transmission | July | CITRUS-DALTON-KIRKWALL | ET-01883 | 4.89 | 2026-04-27 | 2026-05-05
Transmission | July | CLARK-COLLEGE-DEL AMO-HATHAWAY | ET-01562 | 7.8 | 2026-04-29 | 2026-04-29
Transmission | July | IDLE DEL AMO-CARMENITA | ET-00003 | 0.53 | 2026-04-27 | 2026-04-28
Transmission | July | IDLE ETIWANDA-DECLEZ-LINDE | ET-00009 | 3.32 | 2026-04-29 | 2026-04-29
Transmission | July | ALESSANDRO-HIGHGROVE-MAXWELL-TANKER | ET-01643 | 16.44 | 2026-04-27 | 2026-04-29
Transmission | July | APOLLO-BOLSA-TEAM | ET-01563 | 4.54 | 2026-04-27 | 2026-04-28
Transmission | July | BANNING-ZANJA | ET-01912 | 18.19 | 2026-04-27 | 2026-04-28
Transmission | July | BARRE-FULLERTON-VILLA PARK | ET-01868 | 11.95 | 2026-04-28 | 2026-04-29
Transmission | July | BARRE-KINDER-LAMPSON | ET-01636 | 8.17 | 2026-04-28 | 2026-04-29
Transmission | July | BARRE-LAMPSON | ET-01635 | 5.94 | 2026-04-27 | 2026-04-28
Transmission | July | BORREGO-MOULTON-NIGUEL | ET-00497 | 6.69 | 2026-04-28 | 2026-04-28
Transmission | July | IDLE BARRE-LA HABRA | ET-00467 | 0.06 | 2026-04-27 | 2026-04-28
Transmission | July | IDLE VILLA PARK-PAPER-ORANGE | ET-00231 | 0.46 | 2026-04-27 | 2026-04-28
Transmission | July | MORENO-MOVAL-VISTA | ET-00505 | 13.63 | 2026-04-27 | 2026-04-29
Transmission | July | SANTIAGO-ESTRELLA NO. 1 | ET-00865 | 6.28 | 2026-04-27 | 2026-04-29
Transmission | July | ANTELOPE-ANAVERDE-HELIJET | ET-01671 | 20.22 | 2026-05-04 | 2026-05-04
Transmission | July | ANTELOPE-QUARTZ HILL NO. 1 | ET-00648 | 5.24 | 2026-05-03 | 2026-05-04
Transmission | July | ANTELOPE-QUARTZ HILL NO. 2 | ET-00649 | 5.61 | 2026-05-03 | 2026-05-04
Transmission | July | BOREL-HAVILAH-LORAINE-MONOLITH-WALKER BA | ET-01119 | 38.66 | 2026-05-03 | 2026-05-04
Transmission | July | IDLE BURRO FLATS-CHATSWORTH-THRUST | ET-01780 | 0.4 | 2026-05-04 | 2026-05-04
Transmission | July | IDLE CHATSWORTH-SUNSHINE | ET-01105 | 0.38 | 2026-05-05 | 2026-05-05
Transmission | July | IDLE SANTA SUSANA-TIGE | ET-01488 | 1.27 | 2026-05-03 | 2026-05-04
Transmission | July | IDLE SAUGUS-ELZBTH LKE-HSKELL-MWD FTHILL | ET-01229 | 0.8 | 2026-05-03 | 2026-05-04
Transmission | July | MOORPARK-NEWBURY-PHARMACY | ET-01873 | 9.36 | 2026-05-03 | 2026-05-04
Transmission | July | MOORPARK-POTRERO | ET-01407 | 11.88 | 2026-05-04 | 2026-05-04
Transmission | July | MOORPARK-THOUSAND OAKS NO. 1 | ET-04990 | 7.77 | 2026-05-04 | 2026-05-04
Transmission | July | MOORPARK-THOUSAND OAKS NO. 2 | ET-04991 | 10.08 | 2026-05-04 | 2026-05-04
Transmission | July | SAUGUS-CHATSWORTH-ROYAL-SANTA SUSANA | ET-01489 | 23.4 | 2026-05-04 | 2026-05-04
Transmission | July | SAUGUS-COLOSSUS-LOCKHEED-PITCHGEN | ET-01772 | 6.72 | 2026-05-04 | 2026-05-04
Transmission | July | SAUGUS-FILLMORE NO. 2 | ET-01822 | 22.6 | 2026-05-03 | 2026-05-04
Transmission | July | SAUGUS-FILLMORE NO.1 | ET-01821 | 22.89 | 2026-05-03 | 2026-05-04
Transmission | July | APPLE VALLEY-COTTONWOOD-PLUESS-SAVAGE | ET-01720 | 31.81 | 2026-05-05 | 2026-05-05
Transmission | July | ARCHIBALD-FIREHOUSE-MILLIKEN | ET-01759 | 11.58 | 2026-05-04 | 2026-05-05
Transmission | July | ARROYO-EAGLE ROCK-LA CANADA | ET-00564 | 5.96 | 2026-05-04 | 2026-05-05
Transmission | July | AZUSA-KIRKWALL | ET-01882 | 2.69 | 2026-05-05 | 2026-05-05
Transmission | July | DEL AMO-HATHAWAY-LAKEWOOD | ET-01875 | 4.69 | 2026-05-04 | 2026-05-07
Transmission | July | DEL AMO-LAKEWOOD | ET-01876 | 2.93 | 2026-05-05 | 2026-05-05
Transmission | July | DEL AMO-LUCAS NO. 2 | ET-01427 | 2.11 | 2026-05-05 | 2026-05-05
Transmission | July | EAGLE ROCK-ALHAMBRA NO. 3 | ET-01793 | 8.24 | 2026-05-05 | 2026-05-06
Transmission | July | EAGLE ROCK-GARFIELD-WABASH | ET-01792 | 13.98 | 2026-05-05 | 2026-05-05
Transmission | July | ETIWANDA-DECLEZ NO.1 | ET-01857 | 4.09 | 2026-05-05 | 2026-05-05
Transmission | July | ETIWANDA-DECLEZ NO.2 | ET-01858 | 2.88 | 2026-05-05 | 2026-05-05
Transmission | July | ETIWANDA-RANDALL | ET-01860 | 5.95 | 2026-05-05 | 2026-05-06
Transmission | July | GALLATIN-LAGUNA BELL-SPONGE | ET-01806 | 4.06 | 2026-05-06 | 2026-05-06
Transmission | July | IDLE CARDIFF-CAPSULE-STODDARD | ET-01005 | 0.57 | 2026-05-04 | 2026-05-05
Transmission | July | IDLE DEL AMO-CORNUTA | ET-02016 | 0.97 | 2026-05-04 | 2026-05-05
Transmission | July | IDLE ETIWANDA-DECLEZ-RANDALL | ET-01802 | 0.11 | 2026-05-04 | 2026-05-04
Transmission | July | IDLE LAGUNA BELL-P.S.33 | ET-04333 | 3.34 | 2026-05-05 | 2026-05-05
Transmission | July | LA FRESA-AMCO-MOOG | ET-01736 | 4.78 | 2026-05-05 | 2026-05-06
Transmission | July | LA FRESA-BRIDGE-NORTHROP-YUKON NO. 1 | ET-01699 | 5.56 | 2026-05-06 | 2026-05-06
Transmission | July | LA FRESA-BRIDGE-NORTHROP-YUKON NO. 2 | ET-01700 | 3.81 | 2026-05-06 | 2026-05-07
Transmission | July | LA FRESA-REDONDO-ROLLING HILLS-TOPAZ NO2 | ET-01251 | 7.53 | 2026-05-05 | 2026-05-06
Transmission | July | LAGUNA BELL-CALDEN-CUDAHY | ET-02002 | 9.43 | 2026-05-06 | 2026-05-06
Transmission | July | LAGUNA BELL-CUDAHY | ET-04339 | 4 | 2026-05-06 | 2026-05-06
Transmission | July | LIGHTHIPE-BULLIS-FERNWOOD | ET-04466 | 6.66 | 2026-05-06 | 2026-05-07
Transmission | July | LIGHTHIPE-CORNERS-SUNNYSIDE-TOYOTA | ET-01592 | 4.27 | 2026-05-05 | 2026-05-06
Transmission | July | M.W.D.-REDUCTION | ET-01069 | 0.03 | 2026-05-04 | 2026-05-04
Transmission | July | MESA-NARROWS | ET-04863 | 8.5 | 2026-05-06 | 2026-05-07
Transmission | July | MIRA LOMA-ARCHIBALD | ET-01803 | 2.23 | 2026-05-05 | 2026-05-05
Transmission | July | SANTA ANA RIVER NO. 1-NO. 3 | ET-07216 | 3.98 | 2026-05-05 | 2026-05-05
Transmission | July | CLEARGEN-JEFFERSON | ET-01888 | 2.78 | 2026-05-03 | 2026-05-03
Transmission | July | ELLIS-BAYSIDE | ET-01691 | 5.89 | 2026-05-03 | 2026-05-04
Transmission | July | JOHANNA-CHESTNUT-WASHINGTON | ET-01519 | 3.46 | 2026-05-03 | 2026-05-04
Transmission | July | JOHANNA-ELLIS-FAIRVIEW | ET-01394 | 7.17 | 2026-05-03 | 2026-05-04
Transmission | July | MORAGA-PECHANGA | ET-01677 | 5.55 | 2026-05-03 | 2026-05-04
Transmission | July | PAUBA-PECHANGA | ET-01678 | 7.48 | 2026-05-03 | 2026-05-03
Transmission | July | SANTIAGO-CROWN | ET-02150 | 3.38 | 2026-05-03 | 2026-05-03
Transmission | July | SULLIVAN-VERA | ET-07315 | 3.6 | 2026-05-03 | 2026-05-03
Transmission | July | VILLA PARK-BURPIT-CANYON-YORBA LINDA | ET-01520 | 16.55 | 2026-05-04 | 2026-05-04
Transmission | July | VILLA PARK-CANYON-DIEMER | ET-01144 | 12.37 | 2026-05-03 | 2026-05-04
Transmission | July | VILLA PARK-CAROLINA-PLACENTIA-TITANS | ET-01694 | 11.57 | 2026-05-03 | 2026-05-04
Transmission | July | VILLA PARK-PLACENTIA | ET-02093 | 11.75 | 2026-05-03 | 2026-05-04
Transmission | July | MESA-NEWMARK-RAMONA | ET-01794 | 2.79 | 2026-04-22 | 2026-04-22
Transmission | July | MESA-REPETTO-WABASH | ET-04906 | 4.83 | 2026-04-22 | 2026-04-22
Transmission | July | OASIS-SOLARIS | ET-00030 | 0.11 | 2026-04-22 | 2026-04-22
Transmission | July | OASIS-TORTOISE | ET-01359 | 2.02 | 2026-04-22 | 2026-04-22
Transmission | July | IDLE VICTOR-CALECTRIC NO. 2 | ET-76847 | 17.66 | 2026-04-29 | 2026-04-30
Transmission | July | VICTOR-BLACK MOUNTAIN-SOPORT-SOUTHCAP-SO | ET-01661 | 21.62 | 2026-04-29 | 2026-04-29
Transmission | July | VICTOR-SAVAGE NO.2 | ET-00311 | 7.45 | 2026-04-29 | 2026-04-29
Transmission | July | VILLA PARK-ATWOOD | ET-08440 | 5.35 | 2026-05-03 | 2026-05-03
Transmission | August | CHASE-CORONA-DATABANK | ET-01631 | 7.21
Transmission | August | LIGHTHIPE-SIGNAL HILL | ET-04515 | 4.72
Transmission | August | LIMESTONE-SANTIAGO | ET-01273 | 4.01
Transmission | August | MALIBU-OAK PARK | ET-01338 | 3.46
Transmission | August | MESA-RIO HONDO NO.2 | ET-01969 | 11.01
Transmission | August | MIRA LOMA-ARCHIBALD-BAIN-METALCAN | ET-01808 | 11.4
Transmission | August | MIRA LOMA-CLEARGEN | ET-02006 | 10.46
Transmission | August | MOORPARK-CRATER-MALIBU | ET-01408 | 22.45
Transmission | August | NEWBURY-THOUSAND OAKS | ET-01020 | 12.37
Transmission | August | SANTIAGO-BORREGO-MORRO | ET-01056 | 9.35
Transmission | August | SANTIAGO-LIMESTONE-MOULTON | ET-01652 | 6.44
Transmission | August | VILLA PARK-MODENA NO. 1 | ET-08477 | 3.33
Transmission | August | BIG CREEK 1-RECTOR | ET-01082 | 74.45 | 2026-05-18 | 2026-05-18
Transmission | August | BIG CREEK 3-RECTOR NO.1 | ET-01046 | 64.7 | 2026-05-18 | 2026-05-18
Transmission | August | RECTOR-SPRINGVILLE | ET-01073 | 47.7 | 2026-05-18 | 2026-05-18
Transmission | August | BORREGO-CHIQUITA | ET-01275 | 13.14
Transmission | August | DEVERS-MIRAGE NO 2 | ET-01125 | 15.08
Transmission | August | DEVERS-VENWIND | ET-00091 | 2.62
Transmission | August | IDLE DEVERS-EISENHOWER-IID | ET-01078 | 0.21
Transmission | August | ACTON-PALMDALE-SHUTTLE | ET-00905 | 20.27 | 2026-05-18 | 2026-05-19
Transmission | August | ANTELOPE-MAGUNDEN NO.1 | ET-04676 | 59.39 | 2026-05-19 | 2026-05-20
Transmission | August | ANTELOPE-MAGUNDEN NO.2 | ET-04677 | 59.44 | 2026-05-19 | 2026-05-20
Transmission | August | BAILEY-ALAMO-OSO | ET-01388 | 7.09 | 2026-05-18 | 2026-05-19
Transmission | August | EAGLE ROCK-FAIRFAX-WABASH | ET-01651 | 19.83 | 2026-05-19 | 2026-05-20
Transmission | August | EATON-RAVENDALE | ET-06594 | 2.97 | 2026-05-19 | 2026-05-20
Transmission | August | HELIJET-LITTLE ROCK-PALMDALE-ROCKAIR | ET-01402 | 15.22 | 2026-05-18 | 2026-05-19
Transmission | August | IDLE ANTELOPE-ANAVRDE-LTTLE ROCK-PALMDLE | ET-00150 | 1.97 | 2026-05-19 | 2026-05-19
Transmission | August | LAGUNA BELL-MESA NO.2 | ET-04489 | 5.06 | 2026-05-18 | 2026-05-19
Transmission | August | LANCASTER-PURIFY-REDMAN | ET-04436 | 16.93 | 2026-05-18 | 2026-05-19
Transmission | August | LITTLE ROCK-SPARKLE-WILSONA | ET-00032 | 16.68 | 2026-05-18 | 2026-05-19
Transmission | August | MACNEIL-STUDIO-UNIVERSAL | ET-01588 | 3.64 | 2026-05-18 | 2026-05-19
Transmission | August | MESA-ROSEMEAD NO. 1 | ET-04921 | 4.89 | 2026-05-19 | 2026-05-20
Transmission | August | MESA-ROSEMEAD NO. 2 | ET-04922 | 8.59 | 2026-05-18 | 2026-05-19
Transmission | August | MESA-RUSH NO. 2 | ET-04926 | 2.87 | 2026-05-18 | 2026-05-19
Transmission | August | MESA-SAN GABRIEL | ET-04930 | 4.52 | 2026-05-19 | 2026-05-19
Transmission | August | PIUTE-REDMAN | ET-06762 | 5.09 | 2026-05-19 | 2026-05-20
Transmission | August | RAVENDALE-SAN GABRIEL | ET-06595 | 2.64 | 2026-05-19 | 2026-05-19
Transmission | August | CASA DIABLO-CONTROL | ET-00951 | 53.04
Transmission | August | ALAMITOS-BARRE NO. 2 | ET-01063 | 15.47 | 2026-05-21 | 2026-05-21
Transmission | August | CHINO-GANESHA-PLASTIC | ET-01728 | 7.03 | 2026-05-21 | 2026-05-21
Transmission | August | DEVERS-HI DESERT-YUCCA | ET-02068 | 38.36 | 2026-05-20 | 2026-05-21
Transmission | August | DEVERS-YUCCA | ET-01933 | 19.89 | 2026-05-20 | 2026-05-21
Transmission | August | AGUA MANZA-COLTON-DREWS | ET-03031 | 0.02
Transmission | August | ALAMITOS-UNIT 2 | ET-02009 | 0.04
Transmission | August | BLOOMINGTON-COLTON-GLEN AVON | ET-01312 | 14.12
Transmission | August | CARMENITA-GREENING | ET-01268 | 1.63
Transmission | August | CHINO-GANESHA-PEYTON | ET-01200 | 9.06
Transmission | August | CREST-WALTERIA | ET-08710 | 2.99
Transmission | August | ETIWANDA-ARCHLINE-CUCAMONGA-GENAMIC | ET-01688 | 12.54
Transmission | August | ETIWANDA-GRAPELAND-PIPE | ET-01965 | 0.59
Transmission | August | GOLETA-ELLWOOD-ISLAVISTA-ONSHORE | ET-01683 | 5.08
Transmission | August | HINSON-SEABRIGHT | ET-03180 | 4.75
Transmission | August | LA FRESA-BRIGHTON NO. 1 | ET-04242 | 4.8
Transmission | August | LA FRESA-BRIGHTON NO. 2 | ET-04243 | 3.73
Transmission | August | EAGLE MOUNTAIN-BLYTHE | ET-75165 | 52.43
Transmission | August | ALAMITOS-BARRE NO. 1 | ET-00483 | 15.37
Transmission | August | ALAMITOS-CENTER | ET-00488 | 11.56
Transmission | August | ALAMITOS-HATHAWAY | ET-00433 | 7.39
Transmission | August | BOWL-LONG BEACH | ET-01009 | 2.4
Transmission | August | CRATER-LATIGO | ET-00343 | 8.92
Transmission | August | DIKE-LONG BEACH | ET-01016 | 2.19
Transmission | August | GOLETA-SAN MARCOS | ET-00330 | 10.33
Transmission | August | GOLETA-VEGAS | ET-00324 | 7.45
Transmission | August | HINSON-STATE STREET | ET-03184 | 3.55
Transmission | August | HYGEN-LINDE | ET-04549 | 0.68
Transmission | August | IDLE CHINO-GANESHA-LA HABRA-SOUTH- WALNT | ET-00976 | 1.23
Transmission | August | IDLE CRATER-MALIBU | ET-00345 | 3.7
Transmission | August | LA FRESA-MOBILOIL NO. 1 | ET-04272 | 0.78
Transmission | August | LA FRESA-MOBILOIL NO. 2 | ET-04273 | 0.77
Transmission | August | LAYFAIR-SAN ANTONIO | ET-00725 | 5.8
Transmission | August | LIVE OAK-WEYMOUTH | ET-00907 | 3.61
Transmission | August | MALIBU-POTRERO | ET-00645 | 4.06
Transmission | August | PARDEE-SAUGUS NO.1 | ET-00670 | 1.47
Transmission | August | PARDEE-SAUGUS NO.2 | ET-00679 | 1.48
Transmission | August | PARDEE-SAUGUS NO.3 | ET-00674 | 1.45
Transmission | August | SAUGUS-NEWHALL NO.3 | ET-00858 | 5.02
Transmission | August | ALMASOL-RED BLUFF | ET-00128 | 0.11
Transmission | August | ATWOOD-PLACENTIA | ET-05780 | 4.13
Transmission | August | BLACK CREEK-COLORADO RIVER | ET-00978 | 0.1
Transmission | August | BLACK RANCH-RED BLUFF | ET-01930 | 0.12
Transmission | August | BUCK BLVD.-JULIAN HINDS | ET-00245 | 0.12
Transmission | August | COLORADO RIVER-DRACKER | ET-00908 | 0.1
Transmission | August | COLORADO RIVER-GENESIS | ET-00935 | 0.1
Transmission | August | DEVERS-MIRAGE NO 1 | ET-01124 | 15.09 | 2026-05-21
Transmission | August | DEVERS-SENTINEL | ET-00204 | 0.4 | 2026-05-21
Transmission | August | ELLIS-HAMILTON NO. 2 | ET-00570 | 2.84 | 2026-05-21
Transmission | August | FULLERTON-LA PALMA | ET-04440 | 5.22
Transmission | August | HUNTINGTON BEACH-WAVE | ET-00446 | 1.19 | 2026-05-21
Transmission | August | IDLE BARRE-GILBERT | ET-02060 | 0.45 | 2026-05-21
Transmission | August | JOHANNA-CAMDEN-FAIRVIEW | ET-01517 | 2.75 | 2026-05-21
Transmission | August | ALAMITOS-CLARK-DEL AMO | ET-00430 | 7.95
Transmission | August | ALAMITOS-LIGHTHIPE | ET-00461 | 11.88
Transmission | August | CARPINTERIA-ORTEGA-SANTA BARBARA | ET-00756 | 15.8
Transmission | August | CRATER-MALIBU-VALDEZ | ET-01406 | 13.86
Transmission | August | DEL AMO-CYPRESS NO.3 | ET-00432 | 6.5
Transmission | August | GOLETA-SANTA BARBARA | ET-00339 | 17.09
Transmission | August | IDLE CHATSWORTH-ROCKETDYNE | ET-01361 | 0.85
Transmission | August | IDLE CHINO-DELGEN-JEFFERSON | ET-01454 | 4.56
Transmission | August | IDLE LA FRESA-CARBIDE | ET-04247 | 1.28
Transmission | August | IDLE LA FRESA-INGLEWOOD NO.2 | ET-02118 | 3.18
Transmission | August | LA FRESA-REDONDO | ET-04392 | 4.57
Transmission | August | LAGUNA BELL-RANDOLPH NO. 1 | ET-04364 | 2.96
Transmission | August | LAGUNA BELL-RANDOLPH NO. 4 | ET-04366 | 3.46
Transmission | August | LATIGO-POTRERO | ET-01019 | 17.27
Transmission | August | LIGHTHIPE-BULLIS | ET-04467 | 3.29
Transmission | August | LIGHTHIPE-FREMONT | ET-04480 | 6.33
Transmission | August | LIGHTHIPE-JERSEY | ET-00347 | 3.57
Transmission | August | LIGHTHIPE-REVITAL-SUNNYSIDE | ET-01623 | 3.81
Transmission | August | MOORPARK-POTRERO-THOUSAND OAKS | ET-00636 | 12
Transmission | August | MOORPARK-RTS 48 | ET-00993 | 16.04
Transmission | August | PARDEE-SAUGUS NO.4 | ET-00603 | 1.45
Transmission | August | RIO HONDO-CITRUS | ET-06827 | 9.06
Transmission | August | RIO HONDO-DALTON-LIQUID | ET-01457 | 3.03
Transmission | August | RIO HONDO-LARK ELLEN-WALNUT | ET-01493 | 13.88
Transmission | August | SANTA BARBARA-SAN MARCOS | ET-00336 | 10.67
Transmission | August | SAUGUS-MOORPARK-SANTA SUSANA-TORREY | ET-00900 | 36.61
Transmission | September | ANTELOPE-BERRENDO | ET-00074 | 0.03
Transmission | September | ANTELOPE-LANCASTER-LANPRI-SHUTTLE | ET-01590 | 13.23
Transmission | September | ANTELOPE-LANCASTER-OASIS | ET-00741 | 16.78
Transmission | September | ANTELOPE-QUARTZ HILL-SHUTTLE | ET-00739 | 13.16
Transmission | September | BIG CREEK 3-RECTOR NO.2 | ET-01058 | 74.78
Transmission | September | CASA DIABLO-CONTROL-SHERWIN | ET-01449 | 35.53
Transmission | September | CONTROL-OXBOW | ET-01446 | 0.08
Transmission | September | DEL SUR-GOLDFINGER | ET-00029 | 0.02
Transmission | September | DEL SUR-LANCASTER-RITEAID | ET-04424 | 9.51
Transmission | September | IDLE MESA-SYLMAR | ET-00429 | 5.8
Transmission | September | IDLE RIO HONDO-AMADOR | ET-02176 | 1.46
Transmission | September | KAWEAH 1 2 3-KAWGEN-LEMON COVE-THREE RIV | ET-01503 | 28.33
Transmission | September | LAGUNA BELL-MESA NO.1 | ET-04488 | 4.91
Transmission | September | LANCASTER-LITTLE ROCK-PIUTE | ET-01403 | 15.42
Transmission | September | OASIS-PALMDALE-QUARTZ HILL | ET-00747 | 19.4
Transmission | September | BIG CREEK 4-SPRINGVILLE | ET-07241 | 81.61 | 2026-05-05
Transmission | October | BOREL-ISABELLA | ET-01939 | 4.49
Transmission | October | CONTROL-PLANT 5-PLANT 6 | ET-75435 | 1.84
Transmission | October | ISABELLA-KERN RIVER 3-LAKEGEN-WELDON | ET-01941 | 27.1
Transmission | October | KERN RIVER 3-KERNVILLE | ET-04204 | 0.4