## Cumulative Progress Summary
Type | Scope Month | Total circuits | Ready circuits | GIS 100% circuits | PC QA circuits | Scope Month miles (MB) | Actionable miles | Ready miles | GIS 100% miles | PC QA miles | Actionable % of Scope | % Ready (of Actionable) | % GIS 100% (of Actionable) | % PC QA (of Actionable)
Distribution | August | 293 | 81 | 72 | 3 | 2775.427 | 2775.46 | 1220.48 | 978.58 | 63.73 | 100% | 43.97% | 35.26% | 2.296%
Transmission | August | 118 | 56 | 54 | 19 | 1229.994 | 1202.54 | 740.74 | 683.23 | 325.11 | 97.77% | 61.6% | 56.82% | 27.04%
Combined | August | 411 | 137 | 126 | 22 | 4005.421 | 3978 | 1961.22 | 1661.81 | 388.84 | 99.32% | 49.3% | 41.78% | 9.775%

## Daily Rate
Date | Type | Scope Month | Bucket | Miles | Circuits | Cumulative Miles
2026-05-18 | Distribution | August | MB Check done | 235.7 | 8 | 235.7
2026-05-18 | Transmission | August | Final review done | 186.85 | 3 | 186.85
2026-05-18 | Transmission | August | MB Check done | 283.2 | 12 | 283.2
2026-05-19 | Distribution | August | Final review done | 99.29 | 3 | 99.29
2026-05-19 | Distribution | August | MB Check done | 212.54 | 24 | 448.24
2026-05-19 | Transmission | August | Final review done | 105.48 | 12 | 292.33
2026-05-19 | Transmission | August | MB Check done | 160.74 | 9 | 443.94
2026-05-20 | Distribution | August | Final review done | 248.77 | 25 | 348.06
2026-05-20 | Distribution | August | MB Check done | 17.12 | 3 | 465.36
2026-05-20 | Transmission | August | Final review done | 151.61 | 6 | 443.94
2026-05-20 | Transmission | August | MB Check done | 58.25 | 2 | 502.19
2026-05-21 | Distribution | August | Final review done | 222.5 | 16 | 570.56
2026-05-21 | Distribution | August | MB Check done | 281.46 | 21 | 746.82
2026-05-21 | Transmission | August | Final review done | 80.75 | 4 | 524.69
2026-05-21 | Transmission | August | MB Check done | 45.22 | 8 | 547.41
2026-05-22 | Distribution | August | Final review done | 60.36 | 9 | 630.92
2026-05-22 | Distribution | August | MB Check done | 69.28 | 6 | 816.1
2026-05-22 | Transmission | August | Final review done | 57.76 | 7 | 582.45
2026-05-22 | Transmission | August | MB Check done | 93.66 | 14 | 641.07
2026-05-22 | Transmission | August | PC QA | 122.15 | 2 | 122.15
2026-05-23 | Distribution | August | MB Check done | 9.77 | 1 | 825.87
2026-05-23 | Transmission | August | MB Check done | 8.94 | 4 | 650.01
2026-05-23 | Transmission | August | PC QA | 64.7 | 1 | 186.85
2026-05-25 | Distribution | August | Final review done | 282.43 | 13 | 913.35
2026-05-25 | Distribution | August | MB Check done | 145.6 | 7 | 971.47
2026-05-25 | Distribution | August | PC QA | 63.73 | 3 | 63.73
2026-05-25 | Transmission | August | Final review done | 68.03 | 17 | 650.48
2026-05-25 | Transmission | August | MB Check done | 33.2 | 4 | 683.21
2026-05-26 | Distribution | August | Final review done | 65.23 | 6 | 978.58
2026-05-26 | Distribution | August | MB Check done | 249.01 | 11 | 1220.48
2026-05-26 | Transmission | August | Final review done | 32.75 | 5 | 683.23
2026-05-26 | Transmission | August | MB Check done | 57.53 | 3 | 740.74
2026-05-26 | Transmission | August | PC QA | 138.26 | 16 | 325.11

## Per Circuit
Type | Scope Month | Circuit Name | Circuit ID | Mileage | MB Check done date | Final review done date | PC QA done date
Distribution | August | FURNACE CREEK | ED-06885 | 49.7 | 2026-05-18 | 2026-05-20 | 2026-05-25
Distribution | August | GRAPEVINE | ED-07513 | 7.48 | 2026-05-18 | 2026-05-20 | 2026-05-25
Distribution | August | HOMEWOOD | ED-08645 | 6.55 | 2026-05-18 | 2026-05-20 | 2026-05-25
Distribution | August | ALICIA | ED-00307 | 4.11
Distribution | August | ANAWALT | ED-00510 | 14
Distribution | August | ANDRIA | ED-00535 | 10.47
Distribution | August | ARMSTRONG | ED-00740 | 4.71
Distribution | August | BEASLEY | ED-01340 | 7.76
Distribution | August | BENSON | ED-01518 | 1.95
Distribution | August | CACTUS | ED-02600 | 3.94
Distribution | August | CHIME | ED-03472 | 4
Distribution | August | CURRAN | ED-04505 | 4.28
Distribution | August | DALMATIAN | ED-04628 | 4.91
Distribution | August | EAST END | ED-05502 | 0.96
Distribution | August | FERNSTROM | ED-06340 | 4.62
Distribution | August | GAREY | ED-07040 | 5.78
Distribution | August | HAMBONE | ED-07900 | 1.11
Distribution | August | HEDBERG | ED-08274 | 1.81
Distribution | August | JURUPA | ED-09420 | 10.19
Distribution | August | KINGSLEY | ED-09760 | 12.02
Distribution | August | LOBET | ED-10580 | 6.57
Distribution | August | MAITLAND | ED-10970 | 4.04
Distribution | August | MARBUCK | ED-11175 | 7.75
Distribution | August | PANHANDLE | ED-13731 | 0.33
Distribution | August | PATE | ED-13778 | 10.11
Distribution | August | PINEAPPLE | ED-14095 | 13.74
Distribution | August | PLATOON | ED-14189 | 3.97
Distribution | August | PRODUCTS | ED-14436 | 6.26
Distribution | August | ROCK | ED-15300 | 4.03
Distribution | August | SAPPHIRE | ED-15880 | 7.38
Distribution | August | SIREN | ED-16461 | 1.36
Distribution | August | SKYLAND | ED-16480 | 7.21
Distribution | August | SPANADA | ED-16726 | 13.26
Distribution | August | SPECTRUM | ED-16763 | 2.59
Distribution | August | THOR | ED-17785 | 12.73
Distribution | August | TITUS | ED-17912 | 1.91
Distribution | August | WILLIS | ED-19417 | 9.13
Distribution | August | YOUNKIN | ED-19785 | 2.54
Distribution | August | ADAK | ED-00070 | 6.1
Distribution | August | ALBACORE | ED-00245 | 8.24
Distribution | August | ANZA | ED-00600 | 2.95
Distribution | August | BARGE | ED-01097 | 7.64
Distribution | August | BUTANE | ED-02540 | 15.86
Distribution | August | CALM | ED-02735 | 6.14
Distribution | August | CARTER | ED-03030 | 8.35
Distribution | August | CORY | ED-04138 | 3.35
Distribution | August | ELEVADO | ED-05690 | 2.13
Distribution | August | FACTOR | ED-06175 | 2.07
Distribution | August | FAIRBANKS | ED-06200 | 4.52
Distribution | August | GEM | ED-07145 | 2.37
Distribution | August | HAWTHORNE | ED-08180 | 10.73
Distribution | August | INTERSTATE | ED-08940 | 4.59
Distribution | August | KELVINATOR | ED-09580 | 12.6
Distribution | August | LADERA | ED-09970 | 4.05
Distribution | August | LIBERATOR | ED-10435 | 0.82
Distribution | August | LLEWELLYN | ED-10560 | 5.25
Distribution | August | LOCK | ED-10620 | 4.3
Distribution | August | LOQUAT | ED-10708 | 5.74
Distribution | August | MCDONNELL | ED-11479 | 8.07
Distribution | August | MENLO | ED-11640 | 2.28
Distribution | August | NARBONNE | ED-12490 | 5.3
Distribution | August | OCTANE | ED-13040 | 10.05
Distribution | August | PACOMA | ED-13470 | 8.87
Distribution | August | PANSY | ED-13650 | 7.35
Distribution | August | PATTIE | ED-13810 | 4.59
Distribution | August | SPINEL | ED-16777 | 2.24
Distribution | August | SPINNING | ED-16790 | 6.67
Distribution | August | STORM | ED-17065 | 16.69
Distribution | August | SUNDALE | ED-17250 | 4.38
Distribution | August | TYBURN | ED-18385 | 0.18
Distribution | August | VAN WICK | ED-18620 | 8.52
Distribution | August | WINONA | ED-19550 | 5.7
Distribution | August | YORK | ED-19770 | 2
Distribution | August | ZEBRA | ED-19810 | 7.36
Distribution | August | ABERDEEN | ED-00021 | 4.83
Distribution | August | ALLRED | ED-00333 | 5.72
Distribution | August | ALONDRA | ED-00360 | 4.12
Distribution | August | BABER | ED-00919 | 11.56
Distribution | August | CANDLE | ED-02850 | 8.26
Distribution | August | CAPETOWN | ED-02900 | 2.45
Distribution | August | CAR WASH | ED-03065 | 1.59
Distribution | August | CARO | ED-03001 | 9.49
Distribution | August | COLDBROOK | ED-03766 | 1.62
Distribution | August | CONGRESS | ED-03935 | 3.03
Distribution | August | DOHN | ED-05150 | 6.77
Distribution | August | DORNES | ED-05218 | 8.57
Distribution | August | DUNBAR | ED-05380 | 5.87
Distribution | August | DURHAM | ED-05462 | 0.49
Distribution | August | EMORY | ED-05895 | 0.94
Distribution | August | HACKBERRY | ED-07825 | 17.5
Distribution | August | HARTLE | ED-08112 | 2.37
Distribution | August | HEARTWELL | ED-08269 | 1.72
Distribution | August | JAMES | ED-09120 | 4.34
Distribution | August | JAYBLUE | ED-09188 | 5.25
Distribution | August | JUDGE | ED-09375 | 4.26
Distribution | August | LEMONT | ED-10350 | 2.95
Distribution | August | LONGHORN | ED-10689 | 1.3
Distribution | August | MAPES | ED-11156 | 12.41
Distribution | August | MAPLEWOOD | ED-11160 | 7.85
Distribution | August | MARTY | ED-11301 | 3.78
Distribution | August | NELLES | ED-12600 | 4.19
Distribution | August | ORA | ED-13200 | 5.16
Distribution | August | POPPY | ED-14340 | 10.03
Distribution | August | PRESIDENT | ED-14398 | 14.43
Distribution | August | PRIDA | ED-12779 | 7.71
Distribution | August | PRIVET | ED-14432 | 11.17
Distribution | August | RATON | ED-14713 | 5.33
Distribution | August | REDSKIN | ED-14813 | 13.47
Distribution | August | REX | ED-14930 | 4.12
Distribution | August | RODNEY | ED-15335 | 1.24
Distribution | August | SENATE | ED-16122 | 2.28
Distribution | August | SHARP | ED-16270 | 3.88
Distribution | August | STAMPER | ED-16920 | 4.25
Distribution | August | TRIMBLE | ED-18150 | 5.39
Distribution | August | WILCOX | ED-19370 | 4.42
Distribution | August | WOLF | ED-19590 | 6.84
Distribution | August | BRAZIL | ED-02180 | 10.6
Distribution | August | BRIDE | ED-02204 | 1.79
Distribution | August | CABANA | ED-02577 | 2.79
Distribution | August | CATFISH | ED-03166 | 12.51
Distribution | August | CATHY | ED-03168 | 10.59
Distribution | August | CORTESE | ED-04117 | 2.23
Distribution | August | GRACE | ED-07457 | 9.93
Distribution | August | HALSEY | ED-07876 | 0.6
Distribution | August | HANDY | ED-07950 | 8.61
Distribution | August | HARVARD | ED-08130 | 3.02
Distribution | August | HAWK | ED-08193 | 7.87
Distribution | August | IRAN | ED-08955 | 11.91
Distribution | August | KENTUCKY | ED-09635 | 0.83
Distribution | August | LAWRENCE | ED-10240 | 1.68
Distribution | August | LISBON | ED-10520 | 6.54
Distribution | August | MARIGOLD | ED-11212 | 10.41
Distribution | August | MEMORY | ED-11635 | 9.23
Distribution | August | MOONWALK | ED-12164 | 10.37
Distribution | August | NIMBUS | ED-12715 | 4.44
Distribution | August | PAUL | ED-13817 | 8.75
Distribution | August | PERSIA | ED-13971 | 11.13
Distribution | August | PONTIAC | ED-14323 | 8.79
Distribution | August | RAYBESTOS | ED-14719 | 4.79
Distribution | August | ROYER | ED-15515 | 4.18
Distribution | August | RUBIN | ED-15517 | 5.58
Distribution | August | SCIENCE | ED-16004 | 0.98
Distribution | August | TARPON | ED-17551 | 8.19
Distribution | August | VERBENA | ED-18654 | 9.44
Distribution | August | WATERFIELD | ED-19044 | 3.44
Distribution | August | HURLEY | ED-08847 | 9.13
Distribution | August | SKI | ED-16477 | 6.41
Distribution | August | MOFFITT | ED-12040 | 23.39
Distribution | August | NAVIGATOR | ED-12551 | 6.6
Distribution | August | PEOPLES | ED-13933 | 0.75
Distribution | August | STEELMAN | ED-16974 | 18.49
Distribution | August | STOCKTON | ED-17006 | 6.05
Distribution | August | SWATZKE | ED-17401 | 7.05
Distribution | August | TRAILBLAZER | ED-18081 | 7.69
Distribution | August | LATHE | ED-10184 | 5.58
Distribution | August | LEVEL | ED-10417 | 17.47
Distribution | August | RANKIN | ED-14700 | 14.22
Distribution | August | TEE VEE | ED-17607 | 5.18
Distribution | August | ALEXANDER | ED-00298 | 4.58 | 2026-05-21 | 2026-05-21
Distribution | August | ANAKIN | ED-00494 | 2.17 | 2026-05-20 | 2026-05-22
Distribution | August | ASTOR | ED-00814 | 3.83 | 2026-05-21 | 2026-05-22
Distribution | August | BEELINE | ED-01515 | 12.39 | 2026-05-22 | 2026-05-22
Distribution | August | BOX SPRING | ED-02054 | 0.45 | 2026-05-26 | 2026-05-26
Distribution | August | BURWOOD | ED-02525 | 7.9 | 2026-05-21 | 2026-05-21
Distribution | August | CAREY | ED-02937 | 6.72 | 2026-05-21 | 2026-05-21
Distribution | August | CHATTANOOGA | ED-03383 | 5.92 | 2026-05-21 | 2026-05-21
Distribution | August | ELLIOT | ED-05710 | 3.08 | 2026-05-21 | 2026-05-25
Distribution | August | FAMOUS | ED-06272 | 2.84 | 2026-05-21 | 2026-05-25
Distribution | August | FONRI | ED-06607 | 7.75 | 2026-05-21 | 2026-05-21
Distribution | August | GARNER | ED-07060 | 4.55 | 2026-05-25 | 2026-05-26
Distribution | August | HANGER | ED-07960 | 22.15 | 2026-05-21 | 2026-05-21
Distribution | August | HASS | ED-08145 | 33.83 | 2026-05-18 | 2026-05-21
Distribution | August | HERZ | ED-08360 | 14.24 | 2026-05-26
Distribution | August | LEONA | ED-10370 | 4.01 | 2026-05-22 | 2026-05-22
Distribution | August | LORENE | ED-10714 | 10.22 | 2026-05-22 | 2026-05-22
Distribution | August | MANZER | ED-11142 | 9.35 | 2026-05-21 | 2026-05-22
Distribution | August | MONTREAL | ED-12136 | 16.3 | 2026-05-21 | 2026-05-21
Distribution | August | NEVCAL | ED-12635 | 2.45 | 2026-05-21 | 2026-05-25
Distribution | August | OAK CREEK | ED-12950 | 31.66 | 2026-05-19 | 2026-05-21
Distribution | August | PARKDALE | ED-13705 | 8.06 | 2026-05-26 | 2026-05-26
Distribution | August | PENDLETON | ED-13900 | 9.31 | 2026-05-26
Distribution | August | PETAN | ED-13980 | 32.26 | 2026-05-19 | 2026-05-21
Distribution | August | PETTIS | ED-13999 | 6.94 | 2026-05-21 | 2026-05-21
Distribution | August | POINT OF ROCKS | ED-14275 | 13.51 | 2026-05-20 | 2026-05-21
Distribution | August | PUMALO | ED-14511 | 13.68 | 2026-05-21 | 2026-05-22
Distribution | August | SAD | ED-15615 | 3.27 | 2026-05-21 | 2026-05-22
Distribution | August | SAWPIT | ED-15954 | 6.58 | 2026-05-21 | 2026-05-21
Distribution | August | SEYMOUR | ED-16222 | 9.98 | 2026-05-26
Distribution | August | SHOPS | ED-16370 | 6.56 | 2026-05-26 | 2026-05-26
Distribution | August | STEALTH | ED-16963 | 14.83 | 2026-05-21 | 2026-05-21
Distribution | August | TOMCAT | ED-17963 | 1.44 | 2026-05-20 | 2026-05-22
Distribution | August | TWAIN | ED-18338 | 9.14 | 2026-05-21 | 2026-05-21
Distribution | August | VIADUCT | ED-18720 | 4.12 | 2026-05-26 | 2026-05-26
Distribution | August | BUNDY | ED-02422 | 7.9 | 2026-05-19 | 2026-05-20
Distribution | August | BURNS | ED-02480 | 7.79 | 2026-05-19 | 2026-05-20
Distribution | August | CANAL | ED-02841 | 21.94 | 2026-05-19 | 2026-05-19
Distribution | August | CITY OF BANNING #1 | ED-20905 | 2.43 | 2026-05-19 | 2026-05-21
Distribution | August | CITY OF BANNING #2 | ED-17119 | 1.13 | 2026-05-19 | 2026-05-20
Distribution | August | DELUZ | ED-04793 | 9.96 | 2026-05-19 | 2026-05-20
Distribution | August | EAGLE CREST | ED-05487 | 8.65 | 2026-05-19 | 2026-05-20
Distribution | August | FLAGSTAFF | ED-06498 | 0.82 | 2026-05-19 | 2026-05-20
Distribution | August | GREENER | ED-07574 | 6.96 | 2026-05-19 | 2026-05-20
Distribution | August | HARNAGE | ED-08055 | 10.81 | 2026-05-19 | 2026-05-20
Distribution | August | LUISENO | ED-10785 | 37.61 | 2026-05-18 | 2026-05-19
Distribution | August | MESA GRANDE | ED-11732 | 11.51 | 2026-05-19 | 2026-05-20
Distribution | August | MUDDY | ED-12304 | 14.33 | 2026-05-19 | 2026-05-20
Distribution | August | PICONI | ED-14043 | 17.25 | 2026-05-19 | 2026-05-20
Distribution | August | RECTIFIER | ED-21048 | 0.26 | 2026-05-19 | 2026-05-20
Distribution | August | RESORT | ED-14923 | 29.99 | 2026-05-18 | 2026-05-20
Distribution | August | ROMERO | ED-15376 | 1.21 | 2026-05-19 | 2026-05-20
Distribution | August | ROUNDEL | ED-15468 | 5.78 | 2026-05-19 | 2026-05-20
Distribution | August | SDGE 520 | ED-30520 | 2.11 | 2026-05-19 | 2026-05-20
Distribution | August | SDGE 521 | ED-30521 | 0.86 | 2026-05-19 | 2026-05-20
Distribution | August | SEAWOLF | ED-16075 | 3.37 | 2026-05-19 | 2026-05-20
Distribution | August | SHETLAND | ED-16349 | 2.82 | 2026-05-19 | 2026-05-20
Distribution | August | SKINNER | ED-16492 | 10.63 | 2026-05-19 | 2026-05-20
Distribution | August | SOPHIE | ED-16673 | 30.8 | 2026-05-18 | 2026-05-20
Distribution | August | SPRAGUE | ED-16795 | 39.74 | 2026-05-18 | 2026-05-19
Distribution | August | TEMECK | ED-17653 | 0.1 | 2026-05-19 | 2026-05-20
Distribution | August | HACKMAN | ED-07822 | 41.49 | 2026-05-25 | 2026-05-26
Distribution | August | KENO | ED-09625 | 122.07 | 2026-05-21 | 2026-05-25
Distribution | August | OLANCHA | ED-13082 | 13.45 | 2026-05-22 | 2026-05-25
Distribution | August | POTATO | ED-14371 | 15.36 | 2026-05-22 | 2026-05-25
Distribution | August | ROBIN | ED-15275 | 13.85 | 2026-05-22 | 2026-05-25
Distribution | August | RYE | ED-15604 | 9.67 | 2026-05-25 | 2026-05-25
Distribution | August | STEGMAN | ED-16978 | 4.89 | 2026-05-25 | 2026-05-25
Distribution | August | TUSSING | ED-18335 | 76.96 | 2026-05-25 | 2026-05-25
Distribution | August | VALLEY OF THE MOON | ED-18540 | 6.74 | 2026-05-25 | 2026-05-25
Distribution | August | WESTEND | ED-19184 | 1.3 | 2026-05-25 | 2026-05-25
Distribution | August | ZAPPA | ED-19807 | 9.77 | 2026-05-23 | 2026-05-25
Distribution | August | STRIPER | ED-17112 | 0.95 | 2026-05-21
Distribution | August | TAHQUITZ | ED-17546 | 11.13 | 2026-05-21
Distribution | August | CATTLE | ED-03170 | 28.15 | 2026-05-26
Distribution | August | LATON | ED-10200 | 5.25
Distribution | August | MERRYMAN | ED-11730 | 48.01 | 2026-05-26
Distribution | August | NICKERSON | ED-12690 | 60.86 | 2026-05-26
Distribution | August | ROEDING | ED-15340 | 59.27 | 2026-05-26
Distribution | August | WELLS | ED-19150 | 39.9
Distribution | August | CALGROVE | ED-02674 | 19.16
Distribution | August | CANALINO | ED-02842 | 0.02
Distribution | August | CARPOIL | ED-03003 | 13.33
Distribution | August | CHAPALA | ED-03350 | 0.53
Distribution | August | CHUMASH | ED-03501 | 0.5
Distribution | August | CONEJO | ED-03930 | 1.38
Distribution | August | CRUMNER | ED-04445 | 10.37
Distribution | August | EMPIRE | ED-05897 | 6.98
Distribution | August | FAYE | ED-06305 | 30.76
Distribution | August | FLYING D | ED-06585 | 58.04
Distribution | August | KANAN | ED-09455 | 0.61
Distribution | August | LAURO | ED-10210 | 0.22
Distribution | August | LINDERO | ED-10502 | 0.65
Distribution | August | MATILIJA | ED-11341 | 19.72
Distribution | August | MENTRY | ED-11644 | 2.04
Distribution | August | MULHOLLAND | ED-12350 | 20.88
Distribution | August | NEEDHAM | ED-12572 | 9.12
Distribution | August | NICHOLAS | ED-12700 | 4.5
Distribution | August | PATRICIA | ED-13791 | 40.32
Distribution | August | REJADA | ED-14892 | 3.91
Distribution | August | RHODA | ED-14960 | 3.66
Distribution | August | RIVIERA | ED-15200 | 6.33
Distribution | August | SERRA | ED-16150 | 17.37
Distribution | August | STRATHERN | ED-17090 | 9.91
Distribution | August | TRIUNFO | ED-18164 | 3.21
Distribution | August | TURNPIKE | ED-18330 | 16.21
Distribution | August | WHIZZIN | ED-19345 | 2.15
Distribution | August | ACORN | ED-00047 | 4.86
Distribution | August | ALTA | ED-00410 | 5.48
Distribution | August | ANGELES | ED-19694 | 9.39
Distribution | August | ASHMONT | ED-00802 | 2.74
Distribution | August | BRICKYARD | ED-02200 | 16.07
Distribution | August | BRONCO | ED-02280 | 15.98
Distribution | August | BRUNNER | ED-02320 | 3.89
Distribution | August | CHAPMAN | ED-03340 | 4.29
Distribution | August | CONVEYOR | ED-03951 | 12.26
Distribution | August | DELARRO | ED-04800 | 2.27
Distribution | August | DEVILS GATE | ED-05030 | 20.98
Distribution | August | GABRIELINO | ED-06891 | 1.23
Distribution | August | GARIBALDI | ED-07050 | 12.8
Distribution | August | HOLLY | ED-08590 | 4.55
Distribution | August | JOSLYN | ED-09350 | 9.56
Distribution | August | KENMORE | ED-09610 | 4.01
Distribution | August | MALDEN | ED-11010 | 13.39
Distribution | August | MARENDALE | ED-11185 | 1.44
Distribution | August | MERCER | ED-11680 | 9.82
Distribution | August | OLNEY | ED-13150 | 9.48
Distribution | August | PILGRIM | ED-14088 | 0.09
Distribution | August | PUTNEY | ED-14530 | 6.21
Distribution | August | RAVINE | ED-14726 | 12.71
Distribution | August | ROBBIE | ED-15235 | 7.53
Distribution | August | SHOEMAKER | ED-16364 | 2.9
Distribution | August | TELSTAR | ED-17645 | 7.49
Distribution | August | TORPEDO | ED-18000 | 12.93
Distribution | August | TURF | ED-18310 | 1.84
Transmission | August | CHASE-CORONA-DATABANK | ET-01631 | 7.21
Transmission | August | RED BLUFF-VICTORY PASS | ET-02105 | 0.14
Transmission | August | RIO HONDO-AMADOR-JOSE-MESA | ET-01604 | 12.75
Transmission | August | BIG CREEK 1-RECTOR | ET-01082 | 74.45 | 2026-05-18 | 2026-05-18 | 2026-05-22
Transmission | August | BIG CREEK 3-RECTOR NO.1 | ET-01046 | 64.7 | 2026-05-18 | 2026-05-18 | 2026-05-23
Transmission | August | RECTOR-SPRINGVILLE | ET-01073 | 47.7 | 2026-05-18 | 2026-05-18 | 2026-05-22
Transmission | August | BORREGO-CHIQUITA | ET-01275 | 13.14 | 2026-05-22 | 2026-05-25
Transmission | August | DEVERS-MIRAGE NO 2 | ET-01125 | 15.08 | 2026-05-22 | 2026-05-25
Transmission | August | DEVERS-VENWIND | ET-00091 | 2.62 | 2026-05-22 | 2026-05-25
Transmission | August | IDLE DEVERS-EISENHOWER-IID | ET-01078 | 0.21 | 2026-05-22 | 2026-05-25
Transmission | August | LIGHTHIPE-SIGNAL HILL | ET-04515 | 4.72
Transmission | August | MALIBU-OAK PARK | ET-01338 | 3.46
Transmission | August | MESA-RIO HONDO NO.2 | ET-01969 | 11.01
Transmission | August | MIRA LOMA-ARCHIBALD-BAIN-METALCAN | ET-01808 | 11.4
Transmission | August | MOORPARK-CRATER-MALIBU | ET-01408 | 22.45
Transmission | August | NEWBURY-THOUSAND OAKS | ET-01020 | 12.37
Transmission | August | LIMESTONE-SANTIAGO | ET-01273 | 4.01
Transmission | August | MIRA LOMA-CLEARGEN | ET-02006 | 10.46
Transmission | August | SANTIAGO-BORREGO-MORRO | ET-01056 | 9.35
Transmission | August | SANTIAGO-LIMESTONE-MOULTON | ET-01652 | 6.44
Transmission | August | VILLA PARK-MODENA NO. 1 | ET-08477 | 3.33
Transmission | August | ACTON-PALMDALE-SHUTTLE | ET-00905 | 20.27 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | ANTELOPE-MAGUNDEN NO.1 | ET-04676 | 59.39 | 2026-05-19 | 2026-05-20
Transmission | August | ANTELOPE-MAGUNDEN NO.2 | ET-04677 | 59.44 | 2026-05-19 | 2026-05-20
Transmission | August | BAILEY-ALAMO-OSO | ET-01388 | 7.09 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | EAGLE ROCK-FAIRFAX-WABASH | ET-01651 | 19.83 | 2026-05-19 | 2026-05-20 | 2026-05-26
Transmission | August | EATON-RAVENDALE | ET-06594 | 2.97 | 2026-05-19 | 2026-05-20 | 2026-05-26
Transmission | August | HELIJET-LITTLE ROCK-PALMDALE-ROCKAIR | ET-01402 | 15.22 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | IDLE ANTELOPE-ANAVRDE-LTTLE ROCK-PALMDLE | ET-00150 | 1.97 | 2026-05-19 | 2026-05-19 | 2026-05-26
Transmission | August | LAGUNA BELL-MESA NO.2 | ET-04489 | 5.06 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | LANCASTER-PURIFY-REDMAN | ET-04436 | 16.93 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | LITTLE ROCK-SPARKLE-WILSONA | ET-00032 | 16.68 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | MACNEIL-STUDIO-UNIVERSAL | ET-01588 | 3.64 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | MESA-ROSEMEAD NO. 1 | ET-04921 | 4.89 | 2026-05-19 | 2026-05-20 | 2026-05-26
Transmission | August | MESA-ROSEMEAD NO. 2 | ET-04922 | 8.59 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | MESA-RUSH NO. 2 | ET-04926 | 2.87 | 2026-05-18 | 2026-05-19 | 2026-05-26
Transmission | August | MESA-SAN GABRIEL | ET-04930 | 4.52 | 2026-05-19 | 2026-05-19 | 2026-05-26
Transmission | August | PIUTE-REDMAN | ET-06762 | 5.09 | 2026-05-19 | 2026-05-20 | 2026-05-26
Transmission | August | RAVENDALE-SAN GABRIEL | ET-06595 | 2.64 | 2026-05-19 | 2026-05-19 | 2026-05-26
Transmission | August | CASA DIABLO-CONTROL | ET-00951 | 53.04 | 2026-05-22 | 2026-05-22
Transmission | August | ALAMITOS-BARRE NO. 2 | ET-01063 | 15.47 | 2026-05-21 | 2026-05-21
Transmission | August | CHINO-GANESHA-PLASTIC | ET-01728 | 7.03 | 2026-05-21 | 2026-05-21
Transmission | August | DEVERS-HI DESERT-YUCCA | ET-02068 | 38.36 | 2026-05-20 | 2026-05-21
Transmission | August | DEVERS-YUCCA | ET-01933 | 19.89 | 2026-05-20 | 2026-05-21
Transmission | August | AGUA MANZA-COLTON-DREWS | ET-03031 | 0.02 | 2026-05-26 | 2026-05-26
Transmission | August | ALAMITOS-UNIT 2 | ET-02009 | 0.04 | 2026-05-22 | 2026-05-25
Transmission | August | BLOOMINGTON-COLTON-GLEN AVON | ET-01312 | 14.12 | 2026-05-25 | 2026-05-26
Transmission | August | CARMENITA-GREENING | ET-01268 | 1.63 | 2026-05-23 | 2026-05-25
Transmission | August | CHINO-GANESHA-PEYTON | ET-01200 | 9.06 | 2026-05-25 | 2026-05-26
Transmission | August | CREST-WALTERIA | ET-08710 | 2.99 | 2026-05-23 | 2026-05-25
Transmission | August | ETIWANDA-ARCHLINE-CUCAMONGA-GENAMIC | ET-01688 | 12.54
Transmission | August | ETIWANDA-GRAPELAND-PIPE | ET-01965 | 0.59 | 2026-05-23 | 2026-05-25
Transmission | August | GOLETA-ELLWOOD-ISLAVISTA-ONSHORE | ET-01683 | 5.08 | 2026-05-26
Transmission | August | HINSON-SEABRIGHT | ET-03180 | 4.75 | 2026-05-22 | 2026-05-26
Transmission | August | LA FRESA-BRIGHTON NO. 1 | ET-04242 | 4.8 | 2026-05-25 | 2026-05-26
Transmission | August | LA FRESA-BRIGHTON NO. 2 | ET-04243 | 3.73 | 2026-05-23 | 2026-05-25
Transmission | August | EAGLE MOUNTAIN-BLYTHE | ET-75165 | 52.43 | 2026-05-26
Transmission | August | ALAMITOS-BARRE NO. 1 | ET-00483 | 15.37
Transmission | August | ALAMITOS-CENTER | ET-00488 | 11.56
Transmission | August | ALAMITOS-HATHAWAY | ET-00433 | 7.39
Transmission | August | BOWL-LONG BEACH | ET-01009 | 2.4
Transmission | August | CRATER-LATIGO | ET-00343 | 8.92
Transmission | August | DIKE-LONG BEACH | ET-01016 | 2.19
Transmission | August | GOLETA-SAN MARCOS | ET-00330 | 10.33
Transmission | August | GOLETA-VEGAS | ET-00324 | 7.45
Transmission | August | HINSON-STATE STREET | ET-03184 | 3.55
Transmission | August | HYGEN-LINDE | ET-04549 | 0.68
Transmission | August | IDLE CHINO-GANESHA-LA HABRA-SOUTH- WALNT | ET-00976 | 1.23
Transmission | August | IDLE CRATER-MALIBU | ET-00345 | 3.7
Transmission | August | LA FRESA-MOBILOIL NO. 1 | ET-04272 | 0.78
Transmission | August | LA FRESA-MOBILOIL NO. 2 | ET-04273 | 0.77
Transmission | August | LAYFAIR-SAN ANTONIO | ET-00725 | 5.8
Transmission | August | LIVE OAK-WEYMOUTH | ET-00907 | 3.61
Transmission | August | MALIBU-POTRERO | ET-00645 | 4.06
Transmission | August | PARDEE-SAUGUS NO.1 | ET-00670 | 1.47
Transmission | August | PARDEE-SAUGUS NO.2 | ET-00679 | 1.48
Transmission | August | PARDEE-SAUGUS NO.3 | ET-00674 | 1.45
Transmission | August | SAUGUS-NEWHALL NO.3 | ET-00858 | 5.02
Transmission | August | ALMASOL-RED BLUFF | ET-00128 | 0.11 | 2026-05-22 | 2026-05-22
Transmission | August | ATWOOD-PLACENTIA | ET-05780 | 4.13 | 2026-05-22 | 2026-05-25
Transmission | August | BLACK CREEK-COLORADO RIVER | ET-00978 | 0.1 | 2026-05-22 | 2026-05-25
Transmission | August | BLACK RANCH-RED BLUFF | ET-01930 | 0.12 | 2026-05-22 | 2026-05-22
Transmission | August | BUCK BLVD.-JULIAN HINDS | ET-00245 | 0.12 | 2026-05-22 | 2026-05-25
Transmission | August | COLORADO RIVER-DRACKER | ET-00908 | 0.1 | 2026-05-22 | 2026-05-22
Transmission | August | COLORADO RIVER-GENESIS | ET-00935 | 0.1 | 2026-05-22 | 2026-05-25
Transmission | August | DEVERS-MIRAGE NO 1 | ET-01124 | 15.09 | 2026-05-21 | 2026-05-25
Transmission | August | DEVERS-SENTINEL | ET-00204 | 0.4 | 2026-05-21 | 2026-05-25
Transmission | August | ELLIS-HAMILTON NO. 2 | ET-00570 | 2.84 | 2026-05-21 | 2026-05-25
Transmission | August | FULLERTON-LA PALMA | ET-04440 | 5.22 | 2026-05-25 | 2026-05-25
Transmission | August | HUNTINGTON BEACH-WAVE | ET-00446 | 1.19 | 2026-05-21 | 2026-05-22
Transmission | August | IDLE BARRE-GILBERT | ET-02060 | 0.45 | 2026-05-21 | 2026-05-22
Transmission | August | JOHANNA-CAMDEN-FAIRVIEW | ET-01517 | 2.75 | 2026-05-21 | 2026-05-22
Transmission | August | ALAMITOS-CLARK-DEL AMO | ET-00430 | 7.95
Transmission | August | ALAMITOS-LIGHTHIPE | ET-00461 | 11.88
Transmission | August | CARPINTERIA-ORTEGA-SANTA BARBARA | ET-00756 | 15.8
Transmission | August | CRATER-MALIBU-VALDEZ | ET-01406 | 13.86
Transmission | August | DEL AMO-CYPRESS NO.3 | ET-00432 | 6.5
Transmission | August | GOLETA-SANTA BARBARA | ET-00339 | 17.09
Transmission | August | IDLE CHATSWORTH-ROCKETDYNE | ET-01361 | 0.85
Transmission | August | IDLE CHINO-DELGEN-JEFFERSON | ET-01454 | 4.56
Transmission | August | IDLE LA FRESA-CARBIDE | ET-04247 | 1.28
Transmission | August | IDLE LA FRESA-INGLEWOOD NO.2 | ET-02118 | 3.18
Transmission | August | LA FRESA-REDONDO | ET-04392 | 4.57
Transmission | August | LAGUNA BELL-RANDOLPH NO. 1 | ET-04364 | 2.96
Transmission | August | LAGUNA BELL-RANDOLPH NO. 4 | ET-04366 | 3.46
Transmission | August | LATIGO-POTRERO | ET-01019 | 17.27
Transmission | August | LIGHTHIPE-BULLIS | ET-04467 | 3.29
Transmission | August | LIGHTHIPE-FREMONT | ET-04480 | 6.33
Transmission | August | LIGHTHIPE-JERSEY | ET-00347 | 3.57
Transmission | August | LIGHTHIPE-REVITAL-SUNNYSIDE | ET-01623 | 3.81
Transmission | August | MOORPARK-POTRERO-THOUSAND OAKS | ET-00636 | 12
Transmission | August | MOORPARK-RTS 48 | ET-00993 | 16.04
Transmission | August | PARDEE-SAUGUS NO.4 | ET-00603 | 1.45
Transmission | August | RIO HONDO-CITRUS | ET-06827 | 9.06
Transmission | August | RIO HONDO-DALTON-LIQUID | ET-01457 | 3.03
Transmission | August | RIO HONDO-LARK ELLEN-WALNUT | ET-01493 | 13.88
Transmission | August | SANTA BARBARA-SAN MARCOS | ET-00336 | 10.67
Transmission | August | SAUGUS-MOORPARK-SANTA SUSANA-TORREY | ET-00900 | 36.61